## ALL
COMMERCIAL SUBMISSION PLAN
Task Name | Date for Submission | Forms, information and supporting evidence to be submitted | Fees and charges
Building Approval | Early works - 17/06/2024 Final documents and approvals - 03/02/2025 | • Plans and specifications (Architectural, Structural, Electrical, Basement Sprinklers, Hydraulics ) • Site Plan • Specialist reports • Completed Engagement Agreement • DA Form 2 • Locations plans with sewer, water etc • QBCC Builder License • Fire sprinkler layout schematic & details | Building Approval - Cert & Inspection Included - $18,590.00
Performance Bond | 2024-06-17 | • Completed Bond assessment • Landscape Bond calculation sheet • Uncompleted works bond: Bill of Quantities & Landscape bond calculation sheet | Landscape Performance Bond - $5,000.00
Infrastructure Charges | 2024-06-17 | • Infrastructure charge proposal summary form • Owner's consent • Plans • Specialist reports • Supporting documents | Infrastructure Charges - $891,325.84
Construction Management Plan | 2024-06-17 | • Application for Construction Management Plan form • Plans and details of the following: - any gantried or overhead protective awnings proposed over the road or footpath - The type and height of perimeter security fencing and lockable gates to be used by vehicular or and pedestrian traffic - Parking of site workers vehicles - location of street lights, fire hydrants, sewer and stormwater pipes and manholes and footpaths acround/across the perimeter of the site. Include details of any proposed service protection measured to be installed during works. - Location and size of work zones for the loading and unloading of materials and deliveries. - Location and details of public information signs with contact name/s and phone numbers - Proposed sediment and erosion control measures including any rubble grids or shakers. - Proposed temporary vehicle crossing points - Any construction zones or occupied space on the external verge or pavement within the road reserve - Location of buildings and structures of adjacent properties • Details of measures for the collection and control of building rubbish • Specific details or the storage of any hazardous or dangerous material on site and the particulars location of any required signage as applicable. • Details of how the general public and the surrounding residents will be informed of changes in traffic flows during construction. • Details of any proposed staging of works and the timing of deliveries inclusive of concrete pours. • Details of how pedestrian movement around the site is to be managed during works and outside normal working hours. • Details of traffic controllers required to coordinate traffic flow around surrounding roads and any specific controls for concrete pours or mobile crane lifting movements during building and construction works. | Assessment of Construction Management Plan - $889.00
Notice of Works | 2024-06-17 | • Notice of Works Timetable
Development Permit - Operational works application - Civils | 2024-06-17 | • Cover sheet, locality plan, schedule of drawings and general notes • Civil works Plans • Driveways 1 & 2 longitudinal sections • Erosion and sediment control plan • Erosion and sediment control details • Water connection plan • City of Gold Coast Online Form | Operational Works - Major works - $3,193.00
Temporary Road Closure Category 2 | 2024-06-24 | • Site plan outlining the location of the works and available pedestrian access. • Traffic Management Plan • Construction Management Plan • Copies of other approvals that relate to this permit • City of Gold Coast online form | Temporary Road Closure Category 2 & Work Zone Permit - $234.00
Temporary Road Closure Category 1 Temporary Road Closure Verge / footpath >1 month (8mx3m) Temporary Road Closure Verge / footpath >1 month (15mx2mm) | 2024-06-24 | • Site plan outlining the location of the works and available pedestrian access. • Traffic Management Plan • Construction Management Plan • Copies of other approvals that relate to this permit • City of Gold Coast online form | Temporary Road closure 1 - $182.00 Temporary road closure verge / footpath fee - $775.00 Temporary road closure verge / footpath fee - $972.00
Temporary Road Closure and Work Zone Permit (Work Zone = 50 metres) | 2024-06-24 | • Site plan outlining the location of the works. • Traffic Management Plan • Construction Management Plan • Copies of other approvals that relate to this permit • City of Gold Coast online form | Work zone signing/marking installation / removal - $954.00
Temporary plumbing approval | 2024-06-24 | • Cover sheet & Site Plan Hydraulics Services - Temporary Site Services • Scope of Works - Temporary Hydraulic Services • Local authority submission application • City of Gold Coast online form | Inspection fees for fictures @ $126.00 ea x 12 = $1,512.00
Material Change of Use - Food and drink outlet | 2024-06-24 | • Cover page / Title Page • Ground Floor Plans • Completed State Government DA Form 1 • Owners Consent •City of Gold Coast Online Form | Development permit for a Material Change of Use for a Food and Drink Outlet (Café) - $8,901.00
QFES Building Assessment | 2024-07-01 | • QFES Assessment form • Electrical Drawings / Plans | QFES Building Assessment - $31,989.79
Notice of Works
Operation Works - Infrastructure (Electrical Works) | 2024-08-12 | • Pre-assessment certificate • Application form for operation works • Cover sheet • Electrical Plans | Operation Works - Inrastructure (Electrical Works) - $1,038.00
Operational works submission - Stormwater & Flood Management | 2024-08-19 | • Water meter details spreadsheet • Contractor's SWMS for each activity • Developer connection methodology clearly detailing each connection • Stamped approved plans • Public Liability insurance certificate (minimum $20,000,000 and must include Council of the City of Gold Coast ABN 84 858 458 460 as an interested party) • Workers compensation insurance CoC • Signed Water and Waste inductions for all personnel • City of Gold Coast Online Form | Operational Works - Connection to Council Stormwater drainage, sewer or water system - $866.00
Operational works application - Water Connection - Non-standard connection | 2024-09-06 | • Water meter details spreadsheet • Contractor's SWMS for each activity • Developer connection methodology clearly detailing each connection • Stamped approved plans • Public Liability insurance certificate (minimum $20,000,000 and must include Council of the City of Gold Coast ABN 84 858 458 460 as an interested party) • Workers compensation insurance CoC • Signed Water and Waste inductions for all personnel • City of Gold Coast online form | Water Connection - $1,846.20
Operational works application - Sewerage Connection | 2024-09-06 | • Water meter details spreadsheet • Contractor's SWMS for each activity • Developer connection methodology clearly detailing each connection • Stamped approved plans • Public Liability insurance certificate (minimum $20,000,000 and must include Council of the City of Gold Coast ABN 84 858 458 460 as an interested party) • Workers compensation insurance CoC • Signed Water and Waste inductions for all personnel • City of Gold Coast Online Form | Sewerage Connection - $1,846.20
Plumbing & Drainage Permit Application and Inspection | 2024-09-06 | • Cover page / Title Page • Plans (Basement floor drainage, ground floor drainage, L1 floor drainage, L2 floor drainage, Roof plan, basement water, L1 & L2 Water, Basement Fire plans) • Hydraulic Schematics • Hydraulic Details • Completed Form 1 - Compliance assessment application for plumbing, drainage • Soil Classification Report | • Inspection fees for fixtures x 81 @ $126.00 ea - $10,206.00 • Testable backflow prevention device x5 (Inc Fire) @ $126.00 ea - $630.00 • Fire Sprinklers installation inspection fee per floor x 1 basement - $202.00 • AMR sub-meter assessment minimum fee x 1 - $447.00 • Fire hydrant x 10 @ $58.00 ea - $580.00 • Perusal of plans per stage - $1487.20
Development Permit - Operational works application - Landscaping (Includes final Inspection) | 2024-10-07 | • Cover page / Title Page • Layout Plan • Planting Plan and Deails • City of Gold Coast online form | Operational Works - Landscaping on Private Land - $1092.00
QLeave (QLD) and Long Service Leave Levy | Prepaired and Paid Quarterly | • Complete Qleave Online form | QLeave (QLD) and Long Service Leave Levy - $72,168.73
Certificate of Occupancy (Form 11) | 2024-12-12 | The building Certifier will apply for this after the final inspection. | Commercial - Certificate of Occupancy - Offices / shops >500m2 = $1480.00