CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Alex Butler |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 9/10/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 30 |  | Yes | No |

Assessor Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Concrete material | Concreters |  |
|  | Timber | Formworkers |  |
|  | Steel | Steelfixers |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | An employee works in and part of a business, where as a contractor is someone who runs their own business. Both are influenced by scheduling – it is important to schedule tasks, as builders will not always have employees on hand who have the specialist skills required to complete a project. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Local council ABCC |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | Colour selections are one of the most common areas that can result in a variation to the contract. Quite often this occurs because it has not been confirmed in writing. This is one reason why it is important to include colour selection on schedules. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | The Brisbane City Council has noise restrictions in place from 6.30 pm to 6.30 am, Monday to Saturday. On Sunday, there is a total restriction. This affects schedules for obvious reasons – schedules must revolve around these restrictions unless an exemption from the council is given. Sometimes nightwork will need to occur for any number of reasons, in this case permission must be requested from the council. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Material specifications | Includes the details of the type, strength and size of material to be used |  |
|  | Colour specifications | Include the colour selection for internal and external areas. If the project is in a heritage protected area, the colour specifications would come from the council stating the colours that should be used. |  |
|  | Floor and wall covering specifications | Includes details of the type and colour of material used for floors and walls. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | Remind home owners that It is their responsibility to put in variations in writing to you as early as possible. Variations should not be made verbally as they are difficult to prove if there are disputes so make sure they are on paper or provided and agreed to in an email. As with any contract, changes to any terms, including the cost, must be dated and signed by all the parties to the contract and added to the contract documentation – you should also give copies to the client for their own records |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Changes to colour schemes | It could cause a delay whilst waiting for the order to arrive. It could cause an even longer delay if some of the original plan had been begun. |  |
|  | Redesigning kitchens and kitchen layouts | Builder would need to rearrange the order and then additional time would be needed whilst waiting for kitchen material. |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Variation raised due to weather | Wet weather can cause delays |  |
|  | Additional time needed for excavation because rocks are found | More time needed |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | Overlay drawings are drawings that show further detail on top of any existing plans and specifications. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | Work Time period Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | Order date and delivery date Purchase order number Supplier details Delivery details Supplier contact information Project manager details Project description Terms and conditions Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is a sheet used to track when materials are needed and when they should be ordered. This tool allows site personnel to schedule and coordinate activities that are to be undertaken on site. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Architecual plans, land survey |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - D | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - A | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Bricks | 3 days | 29/10/19 | 26/10/19 | It is recommended to order 10% extra to allow for site wasteage and breakage |  |
|  | Concrete | 7 days | 15/10/19 | 8/10/19 | Please ensure concrete is delivered at a steady pace in order to avoid cold joints. |  |
|  | Prefabricated roof trusses | 7 days | 18/10/19 | 11/10/19 | Please ensure trusses are stored within range of mobile crane |  |
|  | Powder coated aluminium windows | 5 days | 28/10/19 | 23//1019 | Please take care not to damage frames |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | The bricks were ordered as per the date listed on the call forward sheet. It was ensured that the bricks were the same as the bricks the clients had selected. The call forward sheet included information found on the purchase order. | The contractor chose from several different suppliers. Contributing factors to the decision were the suppliers reputations for affordability and the quality of the material they sold. |  |
|  | Wall frame | The wall frames will be built on site so individual components will be ordered at the best price possible from a supplier. | The contractor chose from different suppliers and as per above, chose a supplier with a good reputation for affordability and quality.. |  |
|  | Windows | The particular window frames that the client have requested aren’t stocked my most suppliers so it was a challenge in itself to find a supplier. | The contractor had few suppliers to choose from and went for the cheapest price. |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer |  |  |
| --- | --- | --- |