BSBPMG407A

Apply risk management techniques

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Debbie Cremer |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 11/11/2018 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 16 |  | Yes | No |

Assessor Comments

Describe a project below. Conduct a SWOT analysis for the project. Identify at least two (2) points per area.

| Project description | Extension of existing water pipeline in far north Queensland. Clear land, dig trench, lay pipe, connect to existing pipeline, backfill, landscape area. To be completed within 8 months – prior to the beginning of the wet season. |
| --- | --- |

| Answer | Area | Detail |  |
| --- | --- | --- | --- |
|  | S | Experienced team who have done similar projects together Access to records from existing pipeline installation Excellent long-term relationship with pipe supplier providing lowest prices possible |  |
|  | W | Have not worked for this particular client before so their expectations are somewhat unknown Our head office is in the city so we do not have a base near the location |  |
|  | O | Utilising existing vegetation for landscaping reducing cost Local knowledge – have managed projects in the area before so have contacts for suppliers etc Have not worked for this particular client before so opportunity for more work in the future |  |
|  | T | Remote location – heat, lack of facilities, difficulties in sourcing and materials, logistics. Weather Limited timeframe Damage to materials during transportation |  |

Consider the project you identified in Q1. For each of the areas identified in the table below, identify one (1) risk that may arise.

| Answer | Area | Project risk |  |
| --- | --- | --- | --- |
|  | Environmental | Clearing protected vegetation |  |
|  | Finance | Price increase of materials and plant/labour hire |  |
|  | Human resources | High attrition rate due to remote area |  |
|  | Legal | Encroaching onto private land |  |
|  | Technology | Plant/Machinery breakdown |  |

Using ticks, identify whether each of the risk analysis methods listed below is either ‘qualitative’ or ‘quantitative’.

| Answer | Qualitative | Quantitative | Method |  |
| --- | --- | --- | --- | --- |
|  |  |  | Analyses expected monetary value |  |
|  |  |  | Considers likelihood of occurrence and impact on projective objectives |  |
|  |  |  | Ranks risks |  |

Refer to the Risk Matrix below when responding to Q4.

| Matrix | A: Catastrophic | B: Major | C: Moderate | D: Minor | E: Insignificant |
| --- | --- | --- | --- | --- | --- |
| 1: Almost certain | E | E | H | H | M |
| 2: Likely | E | H | H | M | M |
| 3: Occasionally | H | H | M | M | L |
| 4: Unlikely | H | M | M | L | L |
| 5: Rare | M | M | L | L | L |

| E: Extreme | H: High | M: Medium | L: Low |
| --- | --- | --- | --- |

Referring to your responses in Q2. rate each of the risks you identified using the Risk Matrix shown above. Identify the Likelihood and Impact you have determined, plus the overall risk rating. 

Prioritise each risk from 1 to 5 (1 = highest priority, 5 = lowest priority).

| Answer | Area | Risk rating | Priority |  |
| --- | --- | --- | --- | --- |
|  | Environmental | Likelihood: 3 Impact: B Risk rating: H | 1 |  |
|  | Finance | Likelihood: 3 Impact: B Risk rating: H | 2 |  |
|  | Human resources | Likelihood: 1 Impact: C Risk rating: H | 4 |  |
|  | Legal | Likelihood: 4 Impact: B Risk rating: M | 5 |  |
|  | Technology | Likelihood: 3 Impact: B Risk rating: H | 3 |  |

Order the elements of the hierarchy of control, from 1 to 6 (i.e. most effective to least effective).

| Answer | Label (1 – 6) | Element |  |
| --- | --- | --- | --- |
|  | 3 | Isolate the hazard |  |
|  | 6 | Provide and use Personal Protective Equipment (PPE) |  |
|  | 1 | Eliminate the hazard |  |
|  | 4 | Control the hazard by engineering means |  |
|  | 5 | Control the hazard by administrative means |  |
|  | 2 | Substitute the hazard |  |

Referring to your responses in Q2. propose one (1) risk control for the risk identified in each of the areas listed below.

| Answer | Area | Risk control |  |
| --- | --- | --- | --- |
|  | Environmental | Engage qualified environmental advisors to survey land and report on any protected vegetation prior to clearing. |  |
|  | Finance | Have a clause in subcontracts stating prices are to remain the same for the life of the project i.e. no rise and fall |  |
|  | Human resources | Training and education on the location/facilities available and how to manage heat, isolation, fatigue. |  |
|  | Legal | Survey land and erect barriers around the perimeter of the project i.e. flagging. |  |
|  | Technology | Mechanical checks to be carried out on all plant and machinery with records/reports to be submitted and reviewed/signed-off prior to mobilising to site |  |

Which of the following parties should be consulted and agree to proposed risk managed strategies, plans and reporting mechanisms? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Project manager |  |
|  |  | Project specialist |  |
|  |  | Team members |  |

True or False (Tick your response): Organisations all use the same risk analysis methods, techniques and tools.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify the four (4) options that may be followed once you have established the revised risk level.

| Answer | Do nothing Implement risk controls Reassess risk Accept the risk |  |
| --- | --- | --- |

What is the name of the risk level measured after risk controls have been implemented? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Initial risk |  |
|  |  | Revised risk |  |
|  |  | Residual risk |  |
|  |  | Updated risk |  |

On what document should incidents be recorded?

| Answer | Issue Register |  |
| --- | --- | --- |

What is to be completed when a variation is to be made to the project?

| Answer | Change Request |  |
| --- | --- | --- |

True or False (Tick your response): You should report opportunities for action in the same way as risks.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify two (2) types of documents that may be referred to when conducting a review of a risk management plan.

| Answer | Incident logs Project files |  |
| --- | --- | --- |

Explain the relevance of evaluating project outcomes (e.g. agreed major milestones) as part of reviewing risk management activities.

| Answer | Lessons learned from prior incidents/occurrences can be used to help reduce/eliminate future risk. New risks can be identified and added to the risk management plan/register. Effectiveness of current risk management procedures can be reviewed and changed if ineffective or eliminated if irrelevant or redundant. Any changes in the project can be risk assessed and added to the plan. |  |
| --- | --- | --- |

True or False (Tick your response): You may refer to past projects for lessons learned regarding risk management, even when the past projects are not identical to the current one.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |