## Summary
02 PRELIMINARIES
Code | Description | Total
PRELIMINARIES
01.1 | SUPERVISION / LABOUR COSTS | 802844
01.2 | AUTHORITY FEES & INSURANCES | 221112.536
01.3 | CONSUMABLES & DOCUMENT CONTROL | 11823.6
01.4 | HOARDINGS, GANTRIES AND FENCING | 41219.58
01.5 | SITE ACCOMODATION | 24500.4
01.6 | TEMPORARY SERVICES | 12238.4
01.7 | CLEANING AND BINS | 24215
01.8 | SURVEYING & TRAFFIC MANAGEMENT | 41252.8
01.9 | SITE SECURITY | 495
01.10 | SMALL TOOLS, EQUIPMENT & PLANT | 5210
01.11 | CRANAGE, HOISTS & SCAFFOLD | 3200
| TOTAL | 1188111.316

## 5-SUPERVISION LABOUR COSTS
SUPERVISION / LABOUR COSTS
Code | Description | Quantity | Unit | Rate | Total
## DESIGN DEVELOPMENT ##
| Design Manager | 10 | week | 4500 | 27000
| Project Manager | 10 | week | 5500 | 0
| Contracts Administrator 1 | 10 | week | 4000 | 0
| Contracts Administrator 2 | 10 | week | 4000 | 0
| Team Leader | 10 | week | 6500 | 0
| xxxxxx | 10 | week | 0 | 0
| xxxxxx | 10 | week | 0 | 0
## PROCUREMENT ¦ LETTING ##
| Design Manager | 9 | week | 4500 | 0
| Project Manager | 9 | week | 5500 | 24750
| Contracts Administrator 1 | 9 | week | 4000 | 36000
| Contracts Administrator 2 | 9 | week | 4000 | 0
| Team Leader | 9 | week | 6500 | 0
| xxxxxx | 9 | week | 0 | 0
| xxxxxx | 9 | week | 0 | 0
## CONSTRUCTION ##
| Design Manager | 33.4 | week | 4500 | 0
| Project Manager | 33.4 | week | 5500 | 91850
| Contracts Administrator 1 | 33.4 | week | 4000 | 133600
| Contracts Administrator 2 | 33.4 | week | 3000 | 50100
| Team Leader | 33.4 | week | 6500 | 0
| Site Manager 1 | 33.4 | week | 5000 | 167000
| Site Manager 2 | 33.4 | week | 5000 | 0
| Structural Foreman 1 | 33.4 | week | 4500 | 150300
| Structural Foreman 2 | 33.4 | week | 4500 | 0
| Finishes Foreman 1 | 33.4 | week | 4500 | 0
| Finishes Foreman 2 | 33.4 | week | 4500 | 0
| Structural Leading Hand 1 | 33.4 | week | 4100 | 0
| Structural Leading Hand 2 | 33.4 | week | 4100 | 0
| Site HSEQ Officer | 33.4 | week | 4800 | 32064
| Site Official - Bananas | 33.4 | week | 5700 | 0
| Labourer 1 - Skilled | 33.4 | week | 4500 | 90180
| Labourer 2 - Skilled | 33.4 | week | 4500 | 0
| Peggy | 33.4 | week | 5000 | 0
| Total |  |  |  | 802844

## 6-AUTHORITY FEES & INSURANCES
AUTHORITY FEES & INSURANCES
Code | Description | Quantity | Unit | Rate | Total
## FEES & INSURANCES ##
| Contract works, third party liability and professional indemnity insurance (Gross project value) | 1 | item | 104943.75 | 104943.75
| Portable long service levy ¦ Q Leave | 1 | item | 104060.786 | 104060.786
| Legal fee's | 1 | item | 2500 | 0
## INSURANCE BONDS / BANK GUARANTEES ##
| Insurance bonds | 1 | item | 0 | 0
| Bank guarantees | 1 | item | 12108 | 12108
| Total |  |  |  | 221112.536

## 7-CONSUMABLES & DOCUMENT CONTRO
CONSUMABLES & DOCUMENT CONTROL
Code | Description | Quantity | Unit | Rate | Total
## SITE PURCHASES ##
| First Aid Box | 1 | item | 250 | 250
| First Aid Supplies | 33.4 | week | 10 | 334
| Office equipment and maintenance | 33.4 | week | 30 | 1002
| Office stationary and supplies | 33.4 | week | 30 | 1002
| Site Consumables | 33.4 | week | 40 | 1336
| Safety Consumables | 33.4 | week | 40 | 1336
| Carparking | 1 | item | 10000 | 0
## TELEPHONES ¦ COMMUNICATIONS ##
| 2 Ways radios | 1 | item | 2500 | 0
| Temporary mobile; telephones and intercom | 33.4 | week | 100 | 0
| Time Lapse Camera | 1 | item | 6563.6 | 6563.6
## ACONEX ¦ DOCUMENT CONTROL & ISSUING ##
| Document reproduction / distribution | 33.4 | week | 20 | 0
| Couriers and mail expenses | 33.4 | week | 30 | 0
| Total |  |  |  | 11823.6

## 8-HOARDINGS, GANTRIES AND FENCI
HOARDINGS, GANTRIES AND FENCING
Code | Description | Quantity | Unit | Rate | Total
## HARDSTAND (CRUSH ROCK BASES) ##
| Office Compound | 500 | m2 | 12 | 6000
| Temporary Roads | 0 | m2 | 60 | 0
## HOARDINGS ¦ SITE WORKS ##
| Plywood Hoardings (including framing, plywood and painting (black)) - Supply & Install | 0 | m | 200 | 0
| Gates | 0 | item | 500 | 0
## GANTRIES ##
| Gantry allowance (30 weeks) | 150 | m | 1750 | 0
| Additional hire | 3.4 | week | 765 | 0
## TEMPORARY FENCE HIRE ##
| Temp Fencing (0-3 Months) | 0 | m | 8.5 | 0
| Temp Fencing (0-6 Months) | 0 | m | 9 | 0
| Temp Fencing (0-9 Months) | 1223.39 | m | 12 | 14680.68
| Temp Fencing (0-12 Months) | 0 | m | 15 | 0
| Temp Fencing (0-18 Months) | 0 | m | 21 | 0
| Un-Branded Shade Cloth | 0 | m | 4 | 0
| Branded Shade Cloth | 1223.39 | m | 10.0409 | 12283.9
## TEMPORARY HOARDING HIRE ##
| Hoarding Panels (0-3 Months) | 0 | m | 13 | 0
| Hoarding Panels (0-6 Months) | 0 | m | 14 | 0
| Hoarding Panels (0-9 Months) | 0 | m | 17 | 0
| Hoarding Panels (0-12 Months) | 0 | m | 20 | 0
| Hoarding Panels (0-18 Months) | 0 | m | 27.5 | 0
## SIGNAGE ##
| Site Signage | 6 | item | 40 | 240
| Safety Signage | 6 | item | 40 | 240
| Project Signboard | 2 | item | 250 | 500
## MISCELLANEOUS ##
| Make Good Pavements | 80 | m2 | 80 | 6400
| Temporary Crossovers | 0 | m2 | 80 | 0
## PROTECTION ##
| Floor protection - black plastic | 0 | m2 | 1 | 0
| Floor protection - woven plastic | 500 | m2 | 1.75 | 875
| Floor protection - coreflute | 0 | m2 | 2.5 | 0
| Floor protection - hardboard | 0 | m2 | 8 | 0
| Lift protection (Plywood Fitout) | 0 | item | 1280.4 | 0
| Bathroom protection | 0 | item | 1750 | 0
| Aircon - return air filters - 2 to 4 per floor | 0 | item | 45 | 0
| Total |  |  |  | 41219.58

## 9-SITE ACCOMODATION
SITE ACCOMODATION
Code | Description | Quantity | Unit | Rate | Total
## HUTS, SHEDS & OFFICES ##
First Aid Room
| First Aid Room 4.8m x 3.0m | 33.4 | week | 84 | 2805.6
| First Aid Room 6.0m x 3.0m | 33.4 | week | 105 | 0
| Change Room Delivery/Collection | 1 | drop | 530 | 530
Meals/Mess Rooms
| Meal Room 6.0m x 3.0 m | 33.4 | week | 70 | 0
| Meal Room 9.6m x 3.0m | 33.4 | week | 98 | 0
| Meal Room 12.0m x 3.0m | 33.4 | week | 105 | 3507
| Meal/Mess 6.0m/9.6m Delivery/Collection | 0 | drop | 530 | 0
| Meal/Mess 12.0m Delivery/Collection | 1 | drop | 840 | 840
Offices
| Office 3.6m x 2.4m | 33.4 | week | 63 | 0
| Office 3.6m x 3.0m | 33.4 | week | 63 | 0
| Office 4.8m x 2.4m | 33.4 | week | 63 | 0
| Office 6.0m x 3.0m | 33.4 | week | 70 | 0
| Office 9.6m x 3.0m | 33.4 | week | 98 | 0
| Office 12.0m x 3.0m | 33.4 | week | 105 | 3507
| Office 3.6m/4.8m/6.0m Delivery/Collection | 0 | drop | 530 | 0
| Office 9.0m Delivery/Collection | 0 | drop | 750 | 0
| Office 12.0m Delivery/Collection | 1 | drop | 840 | 840
Site Storage Containers
| Container 3.0m x 2.4m | 33.4 | week | 24.5 | 0
| Container 6.0m x 2.4m | 33.4 | week | 24.5 | 0
| Container Delivery/Pickup | 0 | drop | 530 | 0
Toilets ¦ Abulution Blocks
| Abulution Block 2.4 x 2.4m - 2 Pan | 33.4 | week | 91 | 0
| Abulution Block 3.6 x 2.4m - 3 Pan | 33.4 | week | 105 | 0
| Abulution Block 4.8 x 3.0m - 4 Pan | 33.4 | week | 105 | 0
| Abulution Block 6.0 x 3.0m - 5 Pan | 33.4 | week | 112 | 3740.8
| Abulution Block 7.2 x 3.0m - 6 Pan | 33.4 | week | 175 | 0
| Abulution Block 12.0 x 3.0m - 10 Pan | 33.4 | week | 182 | 0
| Waste Tank. 3600 - 4800mm x 2400mm | 33.4 | week | 63 | 0
| Waste Tank. 6000mm x 2400mm | 33.4 | week | 70 | 0
| Abulution Servicing - Fortnightly | 16.7 | fort | 250 | 0
| Abulution Block Delivery/Collection | 1 | drop | 530 | 530
| Portaloo incl weekly service | 33.4 | week | 70 | 0
Purpose Built
| Roofway over portable sheds | 40 | m2 | 80 | 3200
| Walkway between portable sheds | 0 | m2 | 80 | 0
| Toilets in tower | 0 | item | 6240 | 0
| Site Setup in Basement | 0 | item | 50000 | 0
## CYCLONE TIE DOWN ALLOWANCES ##
| Alowance for Cyclone Tie Downs | 1 | week | 5000 | 5000
| Total |  |  |  | 24500.4

## 10-TEMPORARY SERVICES
TEMPORARY SERVICES
Code | Description | Quantity | Unit | Rate | Total
## ELECTRICAL ##
| Power Usage - Low Usage Site | 33.4 | week | 50 | 0
| Power Usage - Medium Usage Site | 33.4 | week | 125 | 4175
| Power Usage - High Usage Site | 33.4 | week | 250 | 0
| Temp Power Boards | 0 | item | 1000 | 0
| Temp Power Pole. Including Pole, O/H 80Amp, install/remove and minium 12 weeks period. | 1 | item | 850 | 850
| Temp Power Pole. Additional weekly hire after 12 weeks | 21.4 | week | 41 | 877.4
## HYDRAULICS ##
| Water Usage - Low Usage Site | 33.4 | week | 40 | 1336
| Water Usage - Medium Usage Site | 33.4 | week | 120 | 0
| Water Usage - High Usage Site | 33.4 | week | 240 | 0
## SEWER ##
| Sewer line to connect into existing | 100 | m | 50 | 5000
| Allowance for authorities, design and connections | 1 | item | 10000 | 0
| Total |  |  |  | 12238.4

## 11-CLEANING AND BINS
CLEANING AND BINS
Code | Description | Quantity | Unit | Rate | Total
## FINAL CLEAN ##
| Building Common Areas | 0 | m2 | 1.5 | 0
| Façade - Residential | 0 | m2 | 5.33 | 0
| Apartments / Hotel Rooms | 0 | room | 399 | 0
| Road cleaning | 0 | m2 | 8 | 0
## PROGRESSIVE CLEAN ##
| Cleaner to clean / tidy up general amentities & work site - 4 Hours per week | 33.4 | hour/week | 60 | 4008
## BIN HIRE ##
| 3m3 | 33.4 | no/week | 200 | 0
| 4m3 | 33.4 | no/week | 270 | 0
| 6m3 | 33.4 | no/week | 375 | 0
| 8m3 | 33.4 | no/week | 520 | 0
| 12m3 | 33.4 | no/week | 605 | 20207
| 15m3 | 33.4 | no/week | 705 | 0
## 660 LITRE BIN HIRE ##
| 660 Litre Bin Hire | 33.4 | no/week | 5 | 0
| 660 Litre Bin Empty | 33.4 | no/week | 50 | 0
## RUBBISH CHUTE ##
| Hire - per m section | 33.4 | m/week | 50 | 0
| Erect & Dismantle | 1 | item | 3000 | 0
| Transport | 1 | item | 600 | 0
| Total |  |  |  | 24215

## 12-SURVEYING & TRAFFIC MANAGEME
SURVEYING & TRAFFIC MANAGEMENT
Code | Description | Quantity | Unit | Rate | Total
## SURVEYING ##
Identification Survey of Boundaries
| Field Work | 8 | hour | 150 | 1200
| Office Work | 4 | hour | 150 | 600
Initial Site Establishment inclusive of survey control and RLs
| Field Work | 8 | hour | 150 | 1200
| Office Work | 4 | hour | 150 | 600
Setout of Piles/Bored Piers/Ground Improvements
| Field Work | 8 | hour | 150 | 1200
| Office Work | 4 | hour | 150 | 600
Calculations of Building Elements from Architectural, Structural, Services and Civil Drawings
Architechural
| Field Work | 16 | hour | 150 | 2400
| Office Work | 8 | hour | 150 | 1200
Structural
| Field Work | 32 | hour | 150 | 4800
| Office Work | 16 | hour | 150 | 2400
Services
| Field Work | 8 | hour | 150 | 1200
| Office Work | 4 | hour | 150 | 600
Civil
| Field Work | 40 | hour | 150 | 6000
| Office Work | 20 | hour | 150 | 3000
As Constructed Survey (BAC AS CON SURVEY)
| Field Work | 20 | hour | 150 | 3000
| Office Work | 20 | hour | 150 | 3000
## TRAFFIC MANAGEMENT ##
| Days per week | 5 | day
| Hours per day | 8 | hour
| No of Controllers | 2 | each
| Weeks | 1 | week
Traffic Controllers
| Day Rate - Non Bananas | 80 | hour | 61.91 | 4952.8
| Night Rate - Non Bananas | 80 | hour | 88.58 | 0
| Day Rate - Bananas | 80 | hour | 110.4 | 0
| Night Rate - Bananas | 80 | hour | 169.48 | 0
Vechicles and Equipment
| Traffic Control Vehicle – Fully Equipped | 40 | hour | 20 | 800
| Truck Mounted Attenuator (TMA) with Driver (6 hour minimum) | 40 | hour | 140 | 0
| Variable Message Signs (VMS) Vehicle without signs | 40 | hour | 30 | 0
| Variable Message Board (VMS) per 24hr day (plus delivery & pick-up) | 40 | hour | 90 | 0
| TLight (Trailer mounted lighting tower) per shift (plus delivery & pick-up) | 40 | hour | 120 | 0
| Sign hire (per sign per day) | 5 | day | 6 | 0
Permits & Plans
| Traffic Guidance Schemes | 1 | item | 750 | 750
| Traffic Management Plans | 1 | item | 1000 | 1000
| Council Road Permit. Brisbane City Council | 1 | item | 750 | 750
| Council Road Permit. Gold Coast City Council | 1 | item | 750 | 0
| Council Road Permit. Other Council Permits | 1 | item | 750 | 0
| Department of Main Roads Permit | 1 | item | 1000 | 0
| Total |  |  |  | 41252.8

## 13-SITE SECURITY
SITE SECURITY
Code | Description | Quantity | Unit | Rate | Total
## SITE SECURITY ##
| Security System | 1 | item | 3000 | 0
| Monitoring | 33.4 | week | 12 | 0
| Call outs to last | 16.7 | no/weeks | 120 | 0
| Watchman | 16.7 | no/weeks | 1000 | 0
| Security Guard | 16.7 | no/weeks | 2737 | 0
## CHAINS & PADLOCKS ##
| Delivery | 1 | drop | 25 | 25
| Abus Square Chain. 8mm x 400mm L | 5 | item | 22 | 110
| Gen 6 Padlock | 5 | item | 55 | 275
| Gen 6 Keys | 5 | item | 17 | 85
## SITE SECURITY CAMERA ##
| Camera | 1 | item | 3935 | 0
| Total |  |  |  | 495

## 14-SMALL TOOLS, EQUIPMENT & PLA
SMALL TOOLS, EQUIPMENT & PLANT
Code | Description | Quantity | Unit | Rate | Total
## SMALL TOOLS AND EQUIPMENT ##
| Small tools and equipment - Small Site | 33.4 | week | 150 | 5010
| Small tools and equipment - Medium Site | 33.4 | week | 250 | 0
| Small tools and equipment - Large Site | 33.4 | week | 400 | 0
## JOB BOX ##
| Allowance to re-stock existing Job Box with Provisions | 1 | item | 200 | 200
| Allowance for new Job Box & Provisions | 1 | item | 750 | 0
## MOBILE SCAFFOLD ##
| Scaffold Tower: 2.0m H | 4 | week | 81.2 | 0
| Scaffold Tower: 2.0m - 3.0m H | 4 | week | 122.5 | 0
| Scaffold Tower: 3.0m - 4.0m H | 4 | week | 163.1 | 0
| Scaffold Tower: 4.0m - 5.0m H | 4 | week | 209.3 | 0
| Scaffold Tower: 5.0m - 6.0m H | 4 | week | 245 | 0
| Scaffold Tower: 6.0m - 7.0m H | 4 | week | 280 | 0
| Scaffold Tower: 7.0m - 8.0m H | 4 | week | 315 | 0
| Scaffold Tower: 8.0m - 9.0m H | 4 | week | 364 | 0
## ACCESS EQUIPMENT ##
Manlift
| 2.7m - 4.5m Electric | 0 | week | 350 | 0
| 4.6m - 6.6m Electric | 0 | week | 385 | 0
| 6.7m - 7.9m Electric | 0 | week | 546 | 0
| Delivery/Pickup allowance | 0 | drop | 310 | 0
Knuckle Booms
| 9.1m - 10.6m Electric | 0 | week | 735 | 0
| 9.1m - 10.6m Diesel | 0 | week | 735 | 0
| 12.1m - 15.0m Diesel | 0 | week | 770 | 0
| 18.0m Diesel | 0 | week | 1120 | 0
| 24.3m Diesel | 0 | week | 1365 | 0
| 41.1m Diesel | 0 | week | 2240 | 0
| Fuel allowance | 0 | week | 200 | 0
| Delivery/Pickup allowance | 0 | drop | 480 | 0
Straight Booms
| 12.1m - 14.0m Diesel | 0 | week | 770 | 0
| 18.0m - 20.1m Diesel | 0 | week | 1120 | 0
| 24.3m - 26.8m Diesel | 0 | week | 1379 | 0
| Fuel allowance | 0 | week | 200 | 0
| Delivery/Pickup allowance | 0 | drop | 480 | 0
Scissor Lifts
| 5.7m - 6.1m Electric | 0 | week | 175 | 0
| 7.6m - 9.4m Electric | 0 | week | 266 | 0
| 7.6m - 9.4m Diesel | 0 | week | 399 | 0
| 9.7m - 10.0m Electric | 0 | week | 315 | 0
| 9.7m - 10.0m Diesel | 0 | week | 399 | 0
| 11.8m - 12.1m Electric | 0 | week | 455 | 0
| 12.1m - 13.1m Diesel | 0 | week | 504 | 0
| 15.2m - 16.1m Diesel | 0 | week | 560 | 0
| Fuel allowance | 0 | week | 200 | 0
| Delivery/Pickup allowance | 0 | drop | 480 | 0
## MATERIALS HANDLING ##
Fork Lifts
| 2.5 Tonne | 0 | week | 437.5 | 0
| 3.5 Tonne | 0 | week | 612.5 | 0
| Fuel allowance | 0 | week | 150 | 0
| Delivery/Pickup allowance | 0 | drop | 480 | 0
Telehandler
| 2.5 Tonne with 5.0m reach | 0 | week | 1085 | 0
| 3.0 Tonne with 7.0m reach | 0 | week | 1365 | 0
| Fuel allowance | 0 | week | 200 | 0
| Delivery/Pickup allowance | 0 | drop | 660 | 0
## GENERATORS ##
| 5Kva - Diesel | 0 | week | 318 | 0
| 6 - 8Kva - Diesel | 0 | week | 318 | 0
| 11 - 14Kva - Diesel | 0 | week | 494 | 0
| 15 - 18Kva - Diesel | 0 | week | 599 | 0
| 20 - 25Kva - Diesel | 0 | week | 599 | 0
| 26 - 36Kva - Diesel | 0 | week | 816 | 0
| 40 - 45Kva - Diesel | 0 | week | 858 | 0
| 56 - 60Kva - Diesel | 0 | week | 1006 | 0
| 76 - 80Kva - Diesel | 0 | week | 1076 | 0
| 96 - 100Kva - Diesel | 0 | week | 1565 | 0
| 150 - 160Kva - Diesel | 0 | week | 2045 | 0
| 180 - 185Kva - Diesel | 0 | week | 3003 | 0
| 200 - 230Kva - Diesel | 0 | week | 3158 | 0
| 250 - 275Kva - Diesel | 0 | week | 3391 | 0
| 300 - 330Kva - Diesel | 0 | week | 4745 | 0
| 500 - 550Kva - Diesel | 0 | week | 7010 | 0
| Cabling - Set of Five (5) to suit up to 35Kva | 0 | week | 140 | 0
| Cabling - Set of Five (5) to suit up to 70Kva | 0 | week | 175 | 0
| Cabling - Set of Five (5) to suit up to 300Kva | 0 | week | 350 | 0
| Cable Protector Yellow Jacket - 5 Slot | 0 | week | 28 | 0
| Distribution Boards | 0 | week | 154 | 0
| Fuel Cell 950L (Double Bunded) | 0 | week | 175 | 0
| Fuel Cell 2000L (Double Bunded) | 0 | week | 259 | 0
| Delivery/Pickup allowance | 0 | drop | 530 | 0
## PORTABLE LIGHTING ##
| Lighting Tower: 4000W | 4 | week | 360 | 0
| Lighting Tower: 6000W Mine Spec | 0 | week | 390 | 0
| Lighting Tower LED 170 - 240k Lumens Mine Spec | 0 | week | 390 | 0
| Lighting Tower LED Cube 125 - 160k Lumens | 0 | week | 360 | 0
| Delivery/Pickup allowance | 1 | drop | 250 | 0
## PUMPS & FLUID MANAGEMENT ##
Pumps
| 100mm Submersible (3 Phase) | 4 | week | 595 | 0
| 100mm Submersible High Head | 0 | week | 651 | 0
| 150mm Submersible (3 Phase) | 0 | week | 651 | 0
| 150mm Diesel Self Primed | 0 | week | 1120 | 0
Hoses
| Layflat - 100mm Dia x 20m | 4 | week | 119 | 0
| Layflat - 150mm Dia x 20m | 0 | week | 147 | 0
| Layflat - 200mm Dia x 20m | 0 | week | 224 | 0
| Suction Hose - 100mm Dia x 6m | 0 | week | 105 | 0
| Suction Hose - 150mm Dia x 3m | 0 | week | 133 | 0
| Suction Hose - 200mm Dia x 3m | 0 | week | 203 | 0
Tanks
| Liqiud Storage Tank - 1000L | 0 | week | 133 | 0
| Liqiud Storage Tank - 1500L | 0 | week | 161 | 0
| Trailer Mounted Water Cart - 1000L | 0 | week | 525 | 0
| Trailer Mounted Water Cart - 1500L | 0 | week | 560 | 0
| Delivery/Pickup allowance | 0 | drop | 240 | 0
## HANDRAILS ##
Temp Handrails
| Hire | 0 | m | 15 | 0
| Strip | 0 | m | 15 | 0
| Total |  |  |  | 5210

## 15-CRANAGE, HOISTS & SCAFFOLD
CRANAGE, HOISTS & SCAFFOLD
Code | Description | Quantity | Unit | Rate | Total
## MOBILE CRANES ##
Site Establishment
| Site Mobilisation (Site Sheds etc) - 25 Tonne Franna + 1 Dogman | 8 | hour | 200 | 1600
| Site De-mobilisation (Site Sheds etc) - 25 Tonne Franna + 1 Dogman | 8 | hour | 200 | 1600
Structural Lifts
Basement Lifts
| Basement Lifts - 25 Tonne Franna + 1 Dogman | 8 | hour | 200 | 0
Ground Lifts
| In-Ground Bored Piers/Pad Footings etc - 25 Tonne Franna + 1 Dogman | 6 | hour | 200 | 0
| Ground Floor Formwork - 25 Tonne Franna + 1 Dogman | 4 | hour | 200 | 0
| Ground Floor Reinforcement - 25 Tonne Franna + 1 Dogman | 4 | hour | 200 | 0
| Ground Floor Column Formwork/Reinforcement - 25 Tonne Franna + 1 Dogman | 4 | hour | 200 | 0
First Floor Lifts
| Formwork Deck Lift Up - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Reinforcement Bottom Layer - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| PTs Lift Up - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Reinforcement Top Layer - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Concrete Gear Lift Up - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Concrete Gear Lift Down - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Scaffold/Formwork Lift Down - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| Columns/RC Walls Formwork/Reinforcement Lift Up - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
| PT Machine Lift Up - 60 tonne slew + 2 dogman | 4 | hour | 425 | 0
Second Floor Lifts
| Formwork Deck Lift Up - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Reinforcement Bottom Layer - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| PTs Lift Up - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Reinforcement Top Layer - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Concrete Gear Lift Up - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Concrete Gear Lift Down - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Scaffold/Formwork Lift Down - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| Columns/RC Walls Formwork/Reinforcement Lift Up - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
| PT Machine Lift Up - 80 tonne slew + 2 dogman | 4 | hour | 470 | 0
## TOWER CRANE ##
Crane 1 - M220DX - Luffing max 55m Boom length, max load 18t @ 17.5m
Signage
| Engineered sign to tower crane machine deck with mounting brackets | 2 | item | 10000 | 0
Crane Hire
| Tower section to accommodate erection free standing height | 42 | week | 4000 | 0
Insurance/Maintenance/Commissioning
| Maintenance as per Manufacturers recommendation | 42 | week | 625 | 0
| Radio base station and 2 handheld radios | 42 | week | 150 | 0
General Ancillary Equipment
| Chains, Brick Cage, Kibble, Conc. Collection Tray, Manbox, Rescue Cage | 42 | week | 150 | 0
Climbing Frame
| Supply, transport, hire of climbing frame from point of first climb above erection height | 42 | week | 200 | 0
Additional Tower Sections
| Hire of additional tower sections above inital errection height (16 x 6 m sections) | 42 | week | 800 | 0
Safety Documents
| Pre erection and dismantle, work procedures, job safety and environmental analysis, site inspection and coordination | 1 | item | 4000 | 0
Tower Crane Base
| Allowance to design crane base | 1 | item | 7500 | 0
| WH&S approvals | 1 | item | 5000 | 0
| Allowance for crane base | 1 | item | 48256.0625 | 0
| Extra over for bored piers | 1 | item | 10980.824 | 0
Tower Crane Base Starter System
| Supply tower crane section starter system to free stand initial engineered erection free stand height | 1 | item | 10000 | 0
| Transport and install tower crane tower section starter system | 1 | item | 15000 | 0
| Transport and remove tower crane tower section starter system | 1 | item | 15000 | 0
| Load test crane to Australian Standard | 1 | item | 3000 | 0
General Items
| Safety Access Security Hoarding around Base Tower | 1 | item | 2250 | 0
| Traffic Management - Road closure erection / dismantle & climbing | 1 | item | 30000 | 0
| Aviation light | 1 | item | 2750 | 0
| Crane Lights | 1 | item | 12500 | 0
Crane Crew
| Drive | 42 | week | 5072 | 0
| Rigger - x 2 | 42 | week | 11412 | 0
Erection and Transport
| Erect tower crane to designed free stand height including mobile cranage | 1 | item | 40000 | 0
Climb Tower Crane Up/Down
| Load and Transport tower sections | 16 | item | 200 | 0
| Climb tower crane - per tower section (approx 16 x 6 m tower sections) | 16 | item | 3500 | 0
| Climb tower crane down to erection height for dismantle | 16 | item | 3500 | 0
| Climbing staging elevations and building tie design | 1 | item | 7500 | 0
Building Tie Tower Section Yoke
| Supply, fabricate and install building ties | 8 | item | 2500 | 0
| Remove building ties | 8 | item | 5000 | 0
Dismantle and Transport
| Tower crane dismantled from erected height including mobile cranage | 1 | item | 40000 | 0
## LOADING BAYS ##
SuperDeck Range
| SuperDeck 3.2 | 44 | week | 295 | 0
| SuperDeck 4.2 | 44 | week | 380 | 0
SuperDeck Accessories
| Bolt Down Assemblies | 0 | deck | 75 | 0
| Corporate Signage Stencil per deck | 0 | deck | 600 | 0
| Corporate Painting per deck | 0 | deck | 995 | 0
| SuperProps 350 | 44 | week | 25 | 0
| SuperProps 480 | 44 | week | 25 | 0
| SuperProps 625 | 44 | week | 35 | 0
Miscellaneous
| Delivery/Pickup | 0 | drop | 540 | 0
| Install (2 x 4 Hours per deck install) | 0 | deck | 1620 | 0
## HOIST HIRE ##
Hoist 1 - Twin GJJ 20/32
| Hire of hoist including gates, poles | 44 | week | 3750 | 0
| Maintenance & Insurance | 1 | item | 250 | 0
| Erect hoist using site tower crane | 1 | item | 14905 | 0
| Commissioning, load test and supply documentation | 1 | item | 5000 | 0
| Dismantle Hoist from full height | 1 | item | 20000 | 0
| Transport | 1 | item | 15000 | 0
| Extend Hoist including building floor ties | 40 | floor | 2000 | 0
| Allowance for safety documentation for erection and dismantle including all work procedures, job safety, environmental analysis and site inspections | 1 | item | 3500 | 0
| Hoist base engineering | 1 | item | 5000 | 0
| Penetration mesh panels | 1 | item | 10000 | 0
| Full meshing floor to floor | 1 | item | 10000 | 0
| Pad Footing, pit, etc | 0 | item | 7581.4115 | 0
Hoist Driver
| Driver | 44 | week | 5840 | 0
## BUILDER'S LIFTS ##
Maintenance - Lift No. 1
| Lift Hire | 33.4 | week | 350 | 0
| Reg. Cleandown & Rebalance | 1 | item | 5500 | 0
| Protect Lift Car & doors | 1 | item | 850 | 0
| Lift Driver | 33.4 | week | 5840 | 0
Maintenance - Lift No. 2
| Lift Hire | 33.4 | week | 350 | 0
| Reg. Cleandown & Rebalance | 1 | item | 5500 | 0
| Protect Lift Car & doors | 1 | item | 850 | 0
| Lift Driver | 33.4 | week | 5840 | 0
## SCAFFOLD ##
Scaffold
| Hire |  | m2 | 16.8 | 0
| Labour | 0 | m2 | 46 | 0
| Transport | 0 | m2 | 3.71 | 0
| Sale Materials | 0 | m2 | 1.25 | 0
| Design | 1 | item | 3000 | 0
| Engineering | 1 | item | 3000 | 0
| Allowance for hop up movement to all decks | 1 | item | 5000 | 0
## SWINGING STAGE AND MAST CLIMBERS ##
Swing Stage
| Swinging Stages | 4 | item | 10000 | 0
| Relocations | 4 | item | 3000 | 0
| Hire (1200 / week) - allow 2 weeks | 8 | item | 2400 | 0
Mast Climber
| Single mast climber | 2 | item | 25000 | 0
| Hire (1650 / week) - allow 6 weeks | 2 | item | 9900 | 0
| Total |  |  |  | 3200