## Program
Varsity Lakes to Burleigh - 4 WKLA Program
Work Area : Zone 1 - Mainline
2022-02-23
[17 empty] | Week Starting → |  | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10 | [6 empty] | 2020-08-17 | [6 empty] | 2020-08-24 | [6 empty] | 2020-08-31 | [6 empty] | 2020-09-07 | [6 empty] | 2020-09-14 | [6 empty] | 2020-09-21 | [6 empty] | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | Comments
|  |  | Activity |  |  | Qty | UoM | AP / PO Req | Wet Delays | Work crew | Material | Col | Super | eng | Days | D/N | Start Date | Finish Date | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  |  | HR | Risk | time axis 2020-05-11 to 2022-04-24
Project Works | [13 empty] | AB
Zone 1 - Mainline
|  | 1 | SOUTHBOUND CARRIAGEWAY - GATE SB1
|  | 2 | Fill Area
|  | 3 | Set Scuppers CH67,560 - 68,000 |  |  | 285 | m |  |  | SWC Slipform |  | P |  |  | 1 | Day | 2021-08-31 | 2021-08-31
|  | 4 | Pave Barrier with Scuppers CH67,560 - 68,000 |  |  | 285 | m |  |  | SWC Slipform |  | P |  |  | 2 | Day | #REF! | #REF!
|  | 5 | Barrier Voids |  |  | 4 | each |  |  | SWC Slipform |  | P |  |  | 1 | Day | #REF! | #REF!
|  | 3 | Lightpole Footings | Bob Walker |  | 1 | each |  |  | DM Roads |  | O |  |  | 1 | Day | 2021-10-08 | 2021-10-08
|  | 4 | Koala Fencing on Barrier | Bob Walker |  | 500 | m |  |  | Origin Fencing |  | O |  |  | 5 | Day | 2021-10-05 | 2021-10-11
5
|  | 6 | Cut Area
|  | 5.9286 | Prime - K2 |  |  | 5500 | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-06 | 2021-09-06
|  | 6.3929 | Seal - C170 |  |  | 5500 | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-06 | 2021-09-06
|  | 6.8571 | EME2 Base 1 |  |  | 1200 | tonne |  |  | Boral |  | R |  |  | 1 | Night | 2021-09-06 | 2021-09-06
|  | 7.3214 | EME2 Base 2 |  |  | 1200 | tonne |  |  | Boral |  | R |  |  | 1 | Night | 2021-09-07 | 2021-09-07
|  | 7.7857 | V drain Excavation |  |  | 105 |  |  |  | SWC |  | G |  |  | 3 | Day | 2021-09-14 | 2021-09-16
|  | 7 | Install COGC Fence over Cut | Bob Walker |  | 300 | m |  |  | Origin Fencing |  | O |  |  | 3 | Day | 2021-10-14 | 2021-10-18
8
|  | 9 | Culvert 1AB Area
|  | 10 | FRP Barrier Footing Ch68,270 to Ch68,580 | Reon Knowler | Plant on Plant | 205 | m |  |  | SWC Slipform |  | P |  |  | 1 | Day | 2021-09-28 | 2021-09-28
|  | 11 | Install Verge against barrier footing | Reon Knowler | Plant on Person | 400 | m |  |  | SWC |  | B |  |  | 5 | Day | 2021-09-29 | 2021-10-06
|  | 12 | Set Scuppers | Reon Knowler | Electrocution | 400 | m |  |  | SWC Slipform |  | P |  |  | 2 | Day | 2021-09-29 | 2021-09-30
|  | 13 | Pave Barrier TL-6 - Ch68.270 to Ch68,420 - 1.1m hgh | Reon Knowler | Plant on Plant | 150 | m |  |  | SWC Slipform |  | P |  |  | 1 | Day | 2021-10-07 | 2021-10-07
|  | 14 | Pave Barrier TL-5 - Ch68.420 to Ch68,580 - 1.1m high | Reon Knowler | Plant on Plant | 160 | m |  |  | SWC Slipform |  | P |  |  | 2 | Day | 2021-10-08 | 2021-10-11
|  | 11.6137 | Prime - K2 | Reon Knowler |  |  | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-06 | 2021-09-06
|  | 12.0572 | Seal - C170 | Reon Knowler |  |  | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-06 | 2021-09-06
|  | 12.5006 | EME2 Base 1 inclu Geofabric | Reon Knowler |  |  | tonne |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-06 | 2021-09-06
|  | 12.9441 | EME2 Base 2 | Reon Knowler |  |  | tonne |  |  | Boral |  | R |  |  | 1 | Day | 2021-09-07 | 2021-09-07
|  | 15 | Barrier Voids | Reon Knowler | Manual Handling, Using Small Cutting Tools |  |  |  |  | SWC Slipform |  | P |  |  | 2 | Day | 2021-10-12 | 2021-10-13
|  | 16 | Lightpole Footings | Reon Knowler | Underground Services - Electrocution, Sewer or Water Bursts (Enviro Issue) | 5 | each |  |  | DM Roads |  | O |  |  | 2 | Day | 2021-10-14 | 2021-10-15
|  | 17 | Koala Fencing on Barrier | Reon Knowler | PPE, Hand and eye protection |  |  |  |  | Origin Fencing |  | O |  |  | 7 | Day | 2021-10-18 | 2021-10-26
|  | 18 | CTB/Subsoil 87 Offramp Wedge | Reon Knowler | Plant on Plant |  |  |  |  | SWC |  | G |  |  | 2 | Day | 2021-10-05 | 2021-10-06
|  | 19 | Asphalt 87 Offramp | Reon Knowler | Plant on Plant |  |  |  |  | Boral |  | R |  |  | 1 | Night | 2021-10-07 | 2021-10-07
|  | 20 | Lean Mix Barrier Footing | Reon Knowler | Plant on Person |  |  |  |  | SWC Slipform |  | P |  |  | 1 | Day | 2021-10-14 | 2021-10-14
|  | 21 | Pave 87 Offramp Barrier footing | Reon Knowler | Plant on Person | 90 | m |  |  | SWC Slipform |  | P |  |  | 1 | Night | 2021-10-17 | 2021-10-17
|  | 22 | Pave 87 Offramp Barrier | Reon Knowler |  | 90 | m |  |  | SWC Slipform |  | P |  |  | 3 | Night | 2021-10-18 | 2021-10-20
|  | 23 | **Zone 2 Barrier | Reon Knowler | [5 empty] | SWC Slipform |  | P |  |  | 1 | Night | 2021-10-21 | 2021-10-21
24
|  | 31 | V2A CULVERT CONSTRUCTION
|  | 32 | Excavation
|  | 33 | Profile down AC/CTB - Ch66,870 to Ch67,000 | Kieran West |  | 910 | m2 |  |  | Bitumill |  | Y |  |  | 1 | Day | 2021-09-22 | 2021-09-22
|  | 34 | Locate Services | Kieran West | [7 empty] | B |  |  | 3 | Day | 2021-09-22 | 2021-09-24
|  | 35 | Enviro Controls/Site Set Up | Kieran West | [5 empty] | SWC |  | B |  |  | 3 | Day | 2021-09-22 | 2021-09-24
|  | 36 | Excavate around RCBC & removal of sandbag wall/soil nails | Kieran West | [5 empty] | SWC |  | B |  |  | 7 | Day | 2021-09-27 | 2021-10-06
|  | 38 | Hammer/Remove RCBC units/Headwalls inclu. Load out | Kieran West | [5 empty] | SWC |  | B |  |  | 8 | Day | 2021-10-07 | 2021-10-18
|  | 39 | Stablise Excavation Batter | Kieran West | [5 empty] | SWC |  | B |  |  | 2 | Day | 2021-10-19 | 2021-10-20
|  | 40 | Saw Cut and remove apron | Kieran West |  | 21 | m |  |  | SWC Slipform |  | P |  |  | 4 | Day | 2021-10-19 | 2021-10-22
|  | 41 | Clean off base slab/apron | Kieran West | [5 empty] | Greystone |  | B |  |  | 2 | Day | 2021-10-25 | 2021-10-26
|  |  | Base Slab/Apron Stitch Pour Foundation Treatments + blinding | Kieran West | [5 empty] | SWC |  | B |  |  | 4 | Day | 2021-10-27 | 2021-11-01
|  | 42 | Install SSD's | Kieran West | [5 empty] | Greystone |  | B |  |  | 2 | Day | 2021-11-02 | 2021-11-03
|  | 43 | Apply Fosroc ConBextra GP to fill Recess | Kieran West | [5 empty] | Greystone |  | B |  |  | 1 | Day | 2021-11-04 | 2021-11-04
|  | 44 | Apply Prime & Fosroc Cemtop HD30 to cover slab | Kieran West | [5 empty] | Greystone |  | B |  |  | 2 | Day | 2021-11-05 | 2021-11-08
|  | 45 | FRP Base Slab Extensions (include Sth Nibs) + curing | Kieran West | [5 empty] | Greystone |  | B |  |  | 7 | Day | 2021-11-09 | 2021-11-17
|  | 46 | FRP Apron Slab | Kieran West | [5 empty] | Greystone |  | B |  | B | 6 | Day | 2021-11-09 | 2021-11-16
|  | 47 | Install Nibs on Northern side existing slab | Kieran West | [5 empty] | Greystone |  | B |  |  | 1 | Day | 2021-11-09 | 2021-11-09
|  | 48 | Cure & Strip Nib Formwork | Kieran West | [5 empty] | Greystone |  | B |  |  | 2 | Day | 2021-11-10 | 2021-11-11
|  | 49 | Install Culvert Units & link slabs | Kieran West |  | 36 | ea |  |  | Greystone |  | B |  |  | 4 | Day | 2021-11-12 | 2021-11-17
|  | 50 | FRP Apron Wingwall & Headwall + curing | Kieran West | [5 empty] | Greystone |  | B |  |  | 9 | Day | 2021-11-18 | 2021-11-30
|  | 51 | No fines block behind wingwalls | Kieran West |  | 0.3 | m3 |  |  | SWC |  | B |  |  | 1 | Day | 2021-12-01 | 2021-12-01
|  | 52 | Backfill RCBC & Wingwall | Kieran West | [5 empty] | SWC |  | B |  |  | 7 | Day | 2021-12-01 | 2021-12-09
|  | 53 | Lean Mix Backfill between link slabs inclu. Curing | Kieran West |  | 35 | m3 |  |  | SWC |  | B |  |  | 3 | Day | 2021-12-10 | 2021-12-14
|  | 54 | Scour Protection Excavation & load out + Reon Mattress | Kieran West | [5 empty] | SWC |  | G |  |  | 6 | Day | 2021-12-15 | 2021-12-22
|  | 56 | General Fill - Ch66,880 to Ch66,940 | Kieran West |  | 95 | m3 |  |  | Grader |  | G |  |  | 2 | Day | 2021-12-23 | 2022-01-10
|  | 57 | Select Fill 170mm - Ch66,880 to Ch66,940 | Kieran West |  | 60 | t |  |  | Grader |  | G |  |  | 1 | Day | 2022-01-11 | 2022-01-11
|  | 58 | CTB - Improved Layer 150mm - Ch66,880 to Ch66,940 | Kieran West |  | 60 | t |  |  | Grader |  | G |  |  | 1 | Day | 2022-01-12 | 2022-01-12
|  |  | Profile down AC/CTB - Ch66,870 to Ch67,000 | Kieran West
|  | 59 | Prime | Kieran West |  |  | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2022-01-13 | 2022-01-13
|  | 60 | Seal | Kieran West |  |  | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2022-01-14 | 2022-01-14
|  | 61 | EME Base 1 - AC - Ch66,880 to Ch66,940 | Kieran West |  | 32 | t |  |  | Boral |  | R |  |  | 1 | Night | 2022-01-13 | 2022-01-13
|  | 62 | EME Base 2 - AC - Ch66,880 to Ch66,940 | Kieran West |  | 32 | t |  |  | Boral |  | R |  |  | 1 | Night | 2022-01-14 | 2022-01-14
|  | 63 | Landscape | Kieran West | [5 empty] | Topgun |  | O |  |  | 3 | Day | 2022-01-17 | 2022-01-19
|  |  | SB-V14 Barrier Ch69,960 to Ch67,300 | Kieran West | [5 empty] | SWC Slipform |  | P |  |  | 3 | Day | 2022-01-20 | 2022-01-24
|  |  | AC14 Binder | Kieran West | [5 empty] | Boral |  | R |  |  |  |  | 2022-01-25 | 2022-01-24
|  | 69 | SB3 MEDIAN CARRIAGEWAY
|  | 84 | Median Works CH67,240 - 67,700
|  | 94 | Prime - AMCO | Luke Wadham |  | 3500 | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-10-09 | 2021-10-09
|  | 95 | Seal - C170 | Luke Wadham |  | 3500 | m2 |  |  | Boral |  | R |  |  | 1 | Day | 2021-10-11 | 2021-10-11
|  | 96 | EME2 Base 1 - 190mm | Luke Wadham |  | 1450 | tonne |  |  | Boral |  | R |  |  | 1 | Night | 2021-10-10 | 2021-10-10
|  | 97 | EME2 Base 1 - 175mm Sth Bound | Luke Wadham |  | 800 | tonne |  |  | Boral |  | R |  |  | 1 | Night | 2021-10-11 | 2021-10-11
|  | 98 | EME2 Base 2 - 190mm | Luke Wadham |  |  | tonne |  |  | Boral |  | R |  |  | 2 | Night | 2021-10-12 | 2021-10-13
|  | 99 | EME2 Base 2 - 175mm Sth Bound | Luke Wadham | [5 empty] | Boral |  | R |  |  | 2 | Night | 2021-10-14 | 2021-10-15
|  | 100 | AC14 Binder including current NB Ch68,090 to Ch67,550 | Luke Wadham |  | 380 | tonne |  |  | Boral |  | R |  |  | 1 | Day | 2021-10-18 | 2021-10-18
|  | 101 | Place Barriers + Linemarking | Luke Wadham | [5 empty] | SWC |  | G |  |  | 2 | Night | 2021-10-19 | 2021-10-20
|  |  | Defects | Luke Wadham | [5 empty] | SWC |  | Y |  |  | 5 | Day | 2021-10-21 | 2021-10-27
Median TTM Crossover
|  |  | Lean Mix infill | Rychelle Whitney | [5 empty] | SWC |  | B |  |  | 1 | Day | 2021-10-07 | 2021-10-07
|  |  | High Perm | Rychelle Whitney | [5 empty] | SWC |  | B |  |  | 1 | Day | 2021-10-08 | 2021-10-08
|  | 102 | Switch to Full Contraflow - Contraflow Stage 2 |  |  | 1 | each |  |  | Milestone |  | R |  |  | 1 | Night | 2021-10-28 | 2021-10-28
103
|  | 104 | SB Highway - Post Contraflow
105
|  | 106 | Testing for Rubbilisation + Approval by GHD | [6 empty] | CS + QuickCore |  | O |  |  | 14 | Day | 2021-10-29 | 2021-11-17
|  | 107 | Sawcut for Drainage & ITS Trenches + Remove Concrete |  |  | 13 | ea |  |  | SWC + Quickcore |  | O |  |  | 4 | Day | 2021-10-29 | 2021-11-03
|  | 108 | Rubbilisation Ch67,420 to Ch68,270 |  |  | 850 | m |  |  | RPQ |  | Y |  |  | 3 | Day | 2021-11-19 | 2021-11-23
|  |  | Rubbilisation Ch68,320 to Ch68,620 |  |  | 300 | m |  |  | RPQ |  | Y |  |  | 1 | Day | 2021-11-24 | 2021-11-24
|  |  | Rubbilisation Ch67,260 to Ch67,350 |  |  | 90 | m |  |  | RPQ |  | Y |  |  | 1 | Day | 2021-11-25 | 2021-11-25
|  |  | Remove & Replace AC patch Ch67,240 to Ch67,350 |  |  | 110 | m |  |  | SWC |  | Y |  |  | 2 | Day | 2021-11-26 | 2021-11-29
|  |  | Fill Lean Mix AC Patch Ch67,240 to Ch67,350 (500mm thick) |  |  | 175 | m3 |  |  | SWC |  | G |  |  | 1 | Day | 2021-11-30 | 2021-11-30
|  | 110 | Place Improved Layer Ch67,415 to Ch68,270 |  |  | 3700 | tonne |  |  | Grader |  | G |  |  | 3 | Day | 2021-11-24 | 2021-11-26
|  | 111 | Place Improved Layer Ch68,320 to Ch68,640 |  |  | 1400 | tonne |  |  | Grader |  | G |  |  | 2 | Day | 2021-11-25 | 2021-11-26
|  | 112 | Place Improved Layer Ch67,260 to Ch67,350 |  |  |  | tonne |  |  | Grader |  | G |  |  | 1 | Day | 2021-11-26 | 2021-11-26
|  | 113 | ITS Crossings |  |  | 6 | ea |  |  | DM Roads |  | O |  |  | 6 | Day | 2021-11-30 | 2021-12-07
|  | 114 | Prime | [6 empty] | Boral |  | R |  |  | 3 | Day | 2021-12-01 | 2021-12-03
|  | 115 | Seal | [6 empty] | Boral |  | R |  |  | 1 | Day | 2021-11-29 | 2021-11-29
|  | 116 | EME2 Layer 1
|  | 117 | EME2 Layer 2
|  | 118 | AC14 Binder
119
120
|  | 121 | E85 Onramp
|  | 122 | Eastern Shoulder Rectification | [6 empty] | SWC |  | G |  |  | 3 | Day
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
Formulas:
Finish Date = WORKDAY.INTL([Start Date],[Days]-1,1,'Non-working'!$B3:B105)
Start Date = WORKDAY.INTL([Finish Date, row above],1,1,'Non-working'!$B3:B105)
Start Date = WORKDAY.INTL([Finish Date, row above]-1,1,1,'Non-working'!$B3:B105)
Note on M5: Andreas A. Andreou: Bar Colours : y = Yellow p = Purple r = Red b = Blue g = Green o = Orange

## Sheet1
BL
C
M

## Non-working
PH & RDO
2018-04-17 | Project Launch
2018-04-25 | Anzac Day
2018-05-06 | Sunday Before Labour Day
2018-05-07 | Labour Day
2018-08-31 | Gold Coast Show Day
2018-10-01 | Queens Birthday
2018-12-21 | x
2018-12-24 | x
2018-12-25 | Christmas Day
2018-12-26 | Boxing Day
2018-12-27 | x
2018-12-28 | x
2018-12-31 | x
2019-01-01 | x
2019-01-02 | x
2019-01-03 | x
2019-01-04 | x
2019-01-07 | x
2019-01-28 | x
2019-04-19 | Easter Firday
2019-04-22 | Easter Monday
2019-04-25 | Anzac Day
2019-05-06 | Labour Day
2019-08-30 | Gold Coast Show Day
2019-10-07 | Queens Birthday
2019-12-20
2019-12-22 | x
2019-12-23 | x
2019-12-24 | x
2019-12-25 | Christmas Day
2019-12-26 | Boxing Day
2019-12-27 | x
2019-12-30 | x
2019-12-31 | x
2020-01-01 | New years Day
2020-01-02 | x
2020-01-03 | x
2020-08-14 | Gold Coast Show Day
2020-10-05 | Queens Birthday
2020-12-18 | Last Day No Work
2020-12-19 | Christmas Shutdown
2020-12-20 | Christmas Shutdown
2020-12-21 | Christmas Shutdown
2020-12-22 | Christmas Shutdown
2020-12-23 | Christmas Shutdown
2020-12-24 | Christmas Shutdown
2020-12-25 | Christmas Shutdown
2020-12-26 | Christmas Shutdown
2020-12-27 | Christmas Shutdown
2020-12-28 | Christmas Shutdown
2020-12-29 | Christmas Shutdown
2020-12-30 | Christmas Shutdown
2020-12-31 | Christmas Shutdown
2021-01-01 | Christmas Shutdown
2021-01-02 | Christmas Shutdown
2021-01-03 | Christmas Shutdown
2021-01-04 | First Day Soft Start
2021-01-26 | Australia Day
2021-04-26 | Anzac Day
2021-05-03 | Labour Day
2021-08-27 | Gold Coast Show Day
2021-10-04 | Queens Birthday
2021-12-24 | Christmas Shutdown
2021-12-25 | Christmas Shutdown
2021-12-26 | Christmas Shutdown
2021-12-27 | Christmas Shutdown
2021-12-28 | Christmas Shutdown
2021-12-29 | Christmas Shutdown
2021-12-30 | Christmas Shutdown
2021-12-31 | Christmas Shutdown
2022-01-01 | Christmas Shutdown
2022-01-02 | Christmas Shutdown
2022-01-03 | Christmas Shutdown
2022-01-04 | Christmas Shutdown
2022-01-05 | Christmas Shutdown
2022-01-06 | Christmas Shutdown
2022-01-07 | Christmas Shutdown
2022-01-08 | Christmas Shutdown
2022-01-09 | Christmas Shutdown