Project – Construction of Large Deck

Project budget - $240,000 (3 progress payments)

Project Time Frame – 10 weeks

Project contract awarded to Decks are Us

- Decks are us have contracted all works and are consulting and managing the project.

- All Contractors had to submit application for the tender

Tender requirements

- Show ability to fulfill the contract on time and to budget

- Licenced for works and have permits, own machinery and tools.

- Provide certificate of insurance with public liability

- Supply all materials for project

Procurement of the project will cover

- Scheduling

- Performance reporting

- Human resources

All Contractors are to sign contracts for work tendered and are only contracted for this project only

Task 1

Survey the layout of the Deck

Skillset required – Qualified/Licenced Surveyor

Task 2

Excavate area

Skillset required – Qualified and licenced excavator driver with own machinery.

Task 3

Construct framework

Skillset required – Qualified and licenced carpenter with deck building experience

Task 4

Lay Decking

Skillset required - Qualified and licenced carpenter with deck building experience

Task 5

Conduct safety and quality check

Skillset required – Qualified quality inspector

Project\Organisational Structure

Project sponsor

- Sam smith (Local council)

Project Manager/Business owner

- Paul Blake (Decks are US)

- Responsible for the entire project and its delivering it on budget and time

- Review daily reports to ensure the project is running smoothly.

- Gather and access all project documentation.

Team Leader/site supervisor

- Gary White (Decks are US)

- Responsible for managing day to day tasks of the project and ensure all contractors are effectively performing all tasks to schedule. Also responsible for ongoing and final safety and quality checks.

Contractors

- Craig Becks (Tip top Excavations) – Responsible for excavating and clearing site, digging footings and removal of waste. Contract value $22,000

- Ben Spense and John Dude (Plain It Carpenters) – Responsible for construction of deck frame and deck laying. Contract Value $165,000

- Ken Burk (All Surveying) – Responsible for surveying the area and providing surveying report and authorisations for the construction of the deck. Service Cost $2,400

Inspector

- James Lewis (Local Council) – Responsible for signing off on the deck

Project cycle

Surveying and report – 5 days

Excavation works and site clearing – 8 days

Frame construction – 4 weeks

Deck laying – 3 weeks

Methods and practices for improving performance of personal

- As project manager, Paul Blake will mentor Gary the site supervisor by having regular discussions to enhance his knowledge, skills and performance. Paul will also seek feedback from Sam Smith on expectations and outcomes

- Gary as Site supervisor will give continues feedback to all contractors to ensure that they are performing and are on track with the project. He will also provide daily progress reports for Paul to review

- Site pre start and toolbox will be conducted daily to discuss daily proceedings and tasks, any concerns or conflict prior work commencing. All discussions, conflicts and resolutions will be documented and signed by each personnel present.

- Gary has organised a social event each Friday after work for those involved to help develop team bonding and moral.

Gary is employed full time by Paul Blake (decks are US) and has several contracts to manage through out the year. He has an employment agreement in place and is paid a salary with 4 weeks annual leave and superannuation. After this project is completed Gary is taking 2 weeks annual leave and will be returning to work in time to start the next project.

- Gary is completing a project management course for his personal own personal development which Decks are US is funding

- Paul is Mentoring Gary to become a project manager to grow his business. This is done by having regular discussions as well as monthly performance reviews.

Project Risks

The objective of the project is to minimise any risk to the project. By meeting with the client to discuss the project they would like completed, we ensure that there is a clear understanding of what they would like done. By providing a quote and plans for the works to be done and have the client sign off on them. we reduce any risk of not achieving their vision

- Risks that have identified that may develop and need to be managed include

- Weather

- Customer not having the finances to pay for the project

- Not having worked with any of the sub contractors

- Communication between trade

- Trades relying on the completed works of other trades to proceed

- Project quality.

Risk ratings and categories

Weather

- Environmental

- Moderate risk rating

- Controls include: Gazebos to work under, rain jackets, water management (pumps), sunscreen and tinted glasses, water for hydration. Allowances in project schedule for potential weather delays

Customer not having finances

- Finance / Legal

- Low risk rating

- Controls include: Deposit being paid before work commences, projects plan being signed by the client, progress payments for each completed stage, Contracts for all sub contractors with set prices. And fixed quotations from suppliers.

Not having worked with sub contractors in the past

- Organisational brand and Quality

- Moderate risk rating

- Controls include: Detailed contracts with scope of works for each contractor, regular communication (pre starts, tool boxes), regular site and work inspections, regular feedback

Communication between trades

- Communication

- Low risk rating

- Controls include: site pre starts each day, tool box meeting each week. Site supervisor mediating any conflict

Trades relying on the completed works of other trades to proceed

- Communication and Project process risk

- Moderate risk rating

- Controls include: Project schedule provided to all contractors, accessible gantt chart, site supervisor communicating with each contractor to ensure work is completed to schedule. Pre starts to ensure works to be completed for the day are clearly communicated. Delay notices for any project delays

Project quality

- Quality

- Moderate risk

- Controls include: Ensuring contractors and following their scope of work as per their contract, Regular site inspections to ensure the quality of work is meeting standard. Regular site walks with the client to ensure their expectations are being meet. Regular feedback in prestart meetings.

Final review of the project is to be completed at the end of the projects to analyse the impact any of these potential risks or other risks that were not identified. All Documentations to be reviewed and signed by the project manager.