PE&BA Building Pty.Ltd

Meeting minutes

15/02/2020

- Opening:

The regular meeting of the PE&BA building was called to order at 2pm on 15 FEB 2020 at 19 Premier St, Oxley

- Present:

Peter Yong, Waterproofer

Junquan Chen, Tiler

Alex Wang, Builder

Yixu Zhang, Supervisor

- WORK COMPLETED - List the work completed in the previous week:

  - Finished waterproofing of two bathrooms on second floor

  - Finished floor Bedding of two bathrooms on second floor

  - Finished floor tiling of two bathrooms on second floor

- WORK SCHEDULED - List the work scheduled for the following week:

  - Finish waterproofing of two bathrooms on ground floor

  - Finish wall tiling of  two bathrooms on ground floor

  - Finish floor Bedding of two bathrooms on ground floor

  - Finish floor tiling of two bathrooms on ground floor

- FIELD OBSERVATIONS, PROBLEMS, and/or DECISIONS:

  - Ensuite bathroom floor grout missed at vanity area

  - Silicone defect as masking tape marked

  - Fix the problem as above next week

- GENERAL DISCUSSION - List any items for general discussion:

  - Water resistant to 1800mm above finished floor level

  - Ensure coners are waterproof 40mm eachway

  - Using angle grinder cutting tiles, keep everything outside the house

Revised 7/2019