## Version history
DATE | VERSION
1st May 2023 | 1.0

## Discrepancies
PROJECT | 123 ABC Residential street, QLD
DATE COMPLETED | 2023-05-05
COMPLETED BY | 2023-05-05
| DISCREPANCY | REASONS FOR DISCREPANCY | HOW TO GET BACK ON TRACK
LABOUR COSTS
Superannuation | 0 | nil | N/A
Payroll | 0
Leaves | 0
Training | 0
Development | 0
Demolition labour | 0
Kitchen Labour | 0
Butlers Pantry Labour | 0
Laundry Labour | 0
Plumbing | 0
Electrical | 0
Tiling Labour | 0
Butlers Pantry - Fixed Glass Window Labour | 0
French Doors - Triple Slider Labour | 0
Dining Room Slider - Reverse Opening Labour | 0
Removal of Debris | 0
TOTAL | 0
0
MATERIAL COSTS | 0
Purchasing | 0
Transportation | 0
Storage | 0
Plant rental | 0
Equipment rental | 0
TOTAL | 0

## Actual
|  | MONTH 1 | MONTH 2 | TOTAL
LABOUR COSTS
Superannuation | 1575 | 945 | 630 | 1575
Payroll | 13425 | 8055 | 5370 | 13425
Leaves |  | 0 | 0 | 0
Training |  | 0 | 0 | 0
Development |  | 0 | 0 | 0
Demolition labour | 6800 | 4080 | 2720 | 6800
Kitchen Labour | 8305 | 4983 | 3322 | 8305
Butlers Pantry Labour | 1745 | 1047 | 698 | 1745
Laundry Labour | 2000 | 1200 | 800 | 2000
Plumbing | 2500 | 1500 | 1000 | 2500
Electrical | 3200 | 1920 | 1280 | 3200
Tiling Labour | 7930 | 4758 | 3172 | 7930
Butlers Pantry - Fixed Glass Window Labour | 160 | 96 | 64 | 160
French Doors - Triple Slider Labour | 240 | 144 | 96 | 240
Dining Room Slider - Reverse Opening Labour | 400 | 240 | 160 | 400
Removal of Debris | 600 | 360 | 240 | 600
TOTAL | 48880 | 29328 | 19552 | 48880
|  | 0 | 0 | 0
MATERIAL COSTS |  | 0 | 0 | 0
Purchasing | 92440 | 55464 | 36976 | 92440
Transportation | 2300 | 1380 | 920 | 2300
Storage |  | 0 | 0 | 0
Plant rental | 820 | 492 | 328 | 820
Equipment rental | 5270 | 3162 | 2108 | 5270
TOTAL | 100830 | 60498 | 40332 | 100830

## Estimated
ESTIMATED
LABOUR COSTS
Superannuation | 1575
Payroll | 13425
Leaves
Training
Development
Demolition labour | 6800
Kitchen Labour | 8305
Butlers Pantry Labour | 1745
Laundry Labour | 2000
Plumbing | 2500
Electrical | 3200
Tiling Labour | 7930
Butlers Pantry - Fixed Glass Window Labour | 160
French Doors - Triple Slider Labour | 240
Dining Room Slider - Reverse Opening Labour | 400
Removal of Debris | 600
TOTAL | 48880
MATERIAL COSTS
Purchasing | 92440
Transportation | 2300
Storage
Plant rental | 820
Equipment rental | 5270
TOTAL | 100830