Assessment Workbook 2

BSB51415 Diploma

of Project Management

Constraint Management

Version 1.11 Produced 18 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following Training Package update | 1.0 |
| 22 June 2017 | Updated Table of Contents | 1.1 |
| 18 October 2018 | Change to Practical Assessment | 1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Written Questions	5

Part 1 – Project Scope	5

Part 2 – Project Time	17

Part 3 – Project Cost	26

Part 4 – Project Quality	30

Case Study	36

Instructions to Student	36

Introduction	37

Workbook Checklist	51

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 2 |  |  |
| --- | --- | --- | --- |
| TITLE: | Constraint Management |  |  |
| FIRST AND SURNAME: | Paul Blake |  |  |
| PHONE: | 0434159033 |  |  |
| EMAIL: | paulrblake@bigpond.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name : Paul Blake |  | Signature: | Date: 29.03.20 |

# Written Questions

Part 1 – Project Scope

| - Which of the following are project initiation documentation required at the start of the project? Select all that apply. |  |
| --- | --- |
|  | - Communications log |
|  | - Project plan |
|  | - Work Breakdown Structure (WBS) |
|  | - Gantt Chart |
|  | - Project charter |
|  | - Risk management |

| - Which of the following are components of a project scope-management plan? Select all that apply. |  |
| --- | --- |
|  | - Project deliverables |
|  | - Project staff assignments |
|  | - Change request |
|  | - Project justification |
|  | - Product description |
|  | - Performance reports |
|  | - Project objectives |
|  | - Project funding requirements |
|  | - Quality metrics |
|  | - Budget forecasts |

- In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

Time and cost affect the project scope because all projects work towards a dead line and a budget. The longer a project runs for the more it will cost. It is important to determine a start and finish date and set project milestones and time frames so that project budgets and profit margins can be achieved

| - Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request? Select all that apply. |  |
| --- | --- |
|  | - The deliverables may not meet quality requirements. |
|  | - Grammatical and typo errors are found in the project initiation documents. |
|  | - The deliverables may not be what the client wanted, even though they were covered in the project plan. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - Observance of non-working holidays affecting project time. |
|  | - Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant. |
|  | - Failure of equipment needed to produce the deliverables. |
|  | - Missing documentations in the project’s information system. |
|  | - Raw materials are no longer available. |
|  | - Supplier or contractor closing business. |

| - Which of the following are procedures that typically must be followed under change control processes? Select all that apply. |  |
| --- | --- |
|  | - Project manager seeks advice from supervisor regarding changes in cost. |
|  | - Project manager assigns a project team member to recalculate for the critical path. |
|  | - Project manager provides the change request to the appropriate stakeholder for approval. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - The project manager updates the project plan and other documentation where required. |
|  | - Project manager drafts the change request. |
|  | - Project manager delegates the authority to the project team members in advising other stakeholders of the changes. |
|  | - The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes. |
|  | - Details of the proposed change to be communicated to the project manager. |
|  | - The project sponsor and owner may automatically terminate the project contract. |

| - The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Method | Description |
| c | Units completed | - Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion. |
| a | Incremental milestones | - In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements. |
| d | Start / finish | - This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled. |
| b | Weighted or equivalent units | - This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed. |

| - Which of the following are activities involved in decomposition of the total work project? Select all that apply. |  |
| --- | --- |
|  | - Summarise project tasks in the form of a written report. |
|  | - Identify and analyse the deliverables and related work. |
|  | - Structure and organise the work breakdown structure (WBS). |
|  | - Arrange the smallest project tasks to form an aggregate representation of the total project task |
|  | - Decompose the upper work breakdown structure (WBS) levels into lower level detailed components. |
|  | - Calculate duration and resource effort for each project task. |
|  | - Develop and assign identification codes to the WBS components. |
|  | - Inspect whether work and deliverables meet requirements and product acceptance criteria. |
|  | - List resources required for each project task. |
|  | - Verify that the degree of decomposition of the work is necessary and sufficient. |

- List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

- Using phases of the project lifecycle as the first level of decomposition, with the product and project deliverables inserted at the second level - Using major deliverables at the first level of decomposition - Using the subprojects that may be developed by organisations outside the project team such as the contracted work

| - The following are some problem areas in scope management. In your own words, briefly discuss each problem area. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Problem areas | Discussion |
| Scope creep | scope creep is when small, continuous requests stretch the project beyond its originally defined scope. |
| Sponsor / project owner approval | Sponsor/client is going to try to get as much as possible out of the project for a fixed price and will often ask for additional work to be done. |
| Project team accountability | Team members don’t take responsibility/accountability for their role in achieving project success and an bring the project to a halt |

- In your own words, discuss the significance of scope management. Do not exceed 150 words.

It is the process that ensures that a project includes all the relevant work to achieve the project's objectives. It controls what is in the project and enables project managers and supervisors to allocate just the right amount of work necessary to complete a project.

| - The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process. |  |
| --- | --- |
| Project Scope Management | Tool or technique |
| Collect requirements | Interviews |
| Define scope | Expert Judgement |
| Create WBS | Decomposition |
| Verify scope | Inspection |
| Control scope | Variance analysis |

| - Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles. |  |
| --- | --- |
| Roles (list five (5)) | Responsibilities (List at least one (1) for each role) |
| Understanding the project | Understand the deliverables of the project |
| Scope management | Ensure to take down all the requirements and turn them into work packages that will soon be deliverables |
| Time Management | To schedule the project |
| Cost management | To come up with the cost baseline |
| Quality management | Plan the QA and QC activities |

Part 2 – Project Time

| - The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| b | Analogous estimating | - This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration. |
| a | Parametric estimating | - This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project. |
| e | Three-point estimating | - This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them. |
| c | Expert judgement estimating | - Contingencies are accounted for into the overall project schedule to account for schedule uncertainties. |
| d | Reserve analysis | - This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:Te=To +4 x Tm + Tp6 . |

| - The following are estimation tools techniques used in determining activity resource. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| d | Expert judgment | - Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries. |
| e | Alternative analysis | - In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources. |
| a | Published estimating data | - This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates. |
| c | Bottom-Up estimating | - This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise. |
| b | Project management software | - These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource. |

| - In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Parameter | Discussion |
| ES | The earliest time at which a task can start, given that any predecessor task must be completed first |
| EF | The earliest start time for the task plus the time required to complete the task |
| LF | The latest time at which the task can be completed without delaying the project |
| LS | The latest finish time minus the time required to complete the task |

| - Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline? Select all that apply. |  |
| --- | --- |
|  | - Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule. |
|  | - The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases. |
|  | - Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline. |
|  | - Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work. |
|  | - Developing the schedule baseline starts and ends in the planning phase of the project. |

| - Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. Which of the following are processes that are involved in schedule control? Select all that apply. |  |
| --- | --- |
|  | - Determining the current status of the project schedule. |
|  | - Defining activities or specific actions to be performed to produce project deliverables |
|  | - Influencing the factors that create schedule changes |
|  | - Decomposing total project work into its lowest levels. |
|  | - Determining that the project schedule has changed |
|  | - Estimating duration and resource effort for the project. |
|  | - Managing the actual changes as they occur. |

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words. - List three (3) project data generated from the Gantt Chart. - List three (2) limitations of the Gantt Chart.

- Useful for planning and scheduling projects. They help show how long a project should take, determine the resources needed, and plan the order in which task are completed. It provides a visual display of the project. - Start and end date of the project Progress of the project Cost of each task - The format is not common so the project manager often needs to PDF the Gantt chart to distribute it The area of the Gantt chart is very large and often difficult to print The progress of each task is very subjective so a project manger can be tempted to exaggerate the progress of a task to make the Gantt chart look better.

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words. - List three (3) project data generated from the Critical Path Method. - Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

- Critical path method is an algorithm for planning, managing and analyzing the timing of a project. It helps to identify critical and non-critical tasks from start to finish and prevents temporary risks - Parameters of each task Activities on the critical path Critical elements of the project - Project mangers need to spend a lot of time to calculate the critical path correctly and it can not be used to form and control the schedules of the persons involved in the project. The allocations of resources cannot be properly monitored.

| - The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Project scheduling tools and techniques | Description |
| b | Schedule network analysis | - This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. |
| a | Critical Path Analysis | - This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts |
| d | Schedule compression | - They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations. |
| c | Automated scheduling tools | - This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. |

| - Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules? Select all that apply. |  |
| --- | --- |
|  | - Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components. |
|  | - The work breakdown structure (WBS) identifies project personnel who are responsible for each project task. |
|  | - Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work. |
|  | - The work breakdown structure (WBS) is used to represent the full project scope of the project. |
|  | - The work breakdown structure provides the relationships among all components of the project and the project deliverables. |
|  | - The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables. |
|  | - Project work at lowest levels are not included in the work breakdown structure (WBS) |

Part 3 – Project Cost

| - The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Estimating costs | The process of developing an estimation of costs based on the information that is given at a point in time |
| Determine budget | Is the process of calculating the total cost of individual activities or work packages to determine an authorized cost baseline. |
| Control cost | Is the process of monitoring the status of a project to update the project budget and managing changes to the cost baseline |

| - The following are different tools and techniques used in cost management. Match each to its correct description. Write the letters that correspond in the spaces provided. |  |  |
| --- | --- | --- |
|  | Strategy | Description |
| b | Analogous estimating | - This is used to establish both the contingency reserves and the management reserves for the project with regards to cost. |
| c | Parametric estimating | - This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters. |
| e | Cost aggregation | - This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project. |
| a | Reserve analysis | - These are used to develop mathematical models to predict total project costs. |
| d | Historical relationships | - Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project. |
| g | Earned value management | - In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline. |
| f | Variance analysis | - This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. |

- List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

- Using an effect tool for managing the projects finances - Sending invoices on a regular basis - Paying invoices promptly - Checking incoming invoices against contracts, quotes, agreements etc.

- You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123). - In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. - In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope. - In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures. Do not exceed 100 words for each discussion.

- The policy outlines principles and responsibilities associated with the management of the company. The background states that the policy is designed to specify the minimum essential elements in the management of projects to assist in articulating scope, involving stakeholders, managing risk and maximising project benefits. The purpose is to improve the way in which company projects are managed as they progress to completion. The scope outlines that the management model has been designed to accommodate project needs across the corporation. - The purpose is to define the processes that are performed throughout the life of the project to ensure the efficient and effective management of projects. The scope is to apply management procedures to projects and ensure projects have a defined start and finish that adhere to a formal project management methodology. - Pre initiate phase – builds the foundation of the project by making an initial assessment of the project size and governance structure, and completing a business case Initiate phase – is the process of determining how the project will be executed. The project initiation documents are produced in this phase. The project manager and key stake holders outline the intended approach to project governance, executing the work and managing resources and risk. Plan Phase- Provides further detail about how the project will be conducted. Detailed schedule and budget information are added to the initiation documents. Implement phase – focuses on the process of determining how the project outputs will be delivered. Close phase – is the formal closure of the delivery component of the project. Involves the hand over of the project outputs to the operational areas and the evaluation of the success of the project.

Part 4 – Project Quality

| - In your own words, discuss each of the following key concepts in Quality Management. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Key Concepts in Quality Management | Discussion |
| Customer satisfaction | It is the best measurement and indicator of the projects quality. If the customer is not happy with the process or end product of the project then the customer is most likely consider the project quality as poor. Customers expectations is a critical element you need to meet for the project to be successful. |
| Prevention over inspection | Is known as the cost of conformance and the cost of nonconformance. The cost of preventing mistakes is usually much less that fixing them |
| Continuous improvement | Is the ongoing effort to improve the product, services or processes overtime. Improvements can be big or small. |

- In your own words, discuss the difference between Quality Assurance and Quality Control. Do not exceed 100 words.

Quality assurance is the process for achieving quality requirements and quality control is the testing of the end product to ensure it meets quality requirements.

| - The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| People standards | The requirement of peoples qualifications and experience working on a project |
| Process standards | The standards for the processes in delivering the project, involving quality assurance auditing |
| Product / service standards | The standards that look at the end product. Involves quality control standards. |

| - The following are quality assurance and control methods, techniques and tools. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Methods, tools, techniques | Description |
| h | Benchmarking standards | - This is a distribution of dots comparing two variables. If the two variables are completely independent you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it. |
| g | Brainstorming sessions | - These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis. |
| d | Control charts | - It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes. |
| f | Flowcharts | - These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors. |
| b | Histograms | - It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results. |
| e | Pareto charts | - A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions. |
| c | Run charts | - It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions. |
| a | Scatter grams | - These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies. |

- List five (5) responsibilities of the project manager in quality management.

- Determine the quality standards for the project deliverables - Determine the quality standards for the project process - Conducting or coordinating project audits - Leading or at least coordinating project QA and QC activities - Recording of quality outcomes to the project sponsor

| - The following are methods used in managing continuous improvement. In your own words, discuss each method. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Six Sigma | A tool used for identifying and removing the causes of defects and reducing variability in manufacturing and business process. |
| Lean Six Sigma | A method that relies on the projects team working together to reduce the 8 kinds of waste, time, inventory, motion, waiting, overproduction, over processing, defects and skills |
| Total Quality Management | An approach to project management that seeks to improve the quality of products and services through ongoing refinements in response to ongoing feedback |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You have already provided advice to Awesome Landscapes in the previous workbook. Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off. As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario. The documents you need to complete the succeeding tasks can be accessed through the following links: Project Charter version 2 (.pdf) Project Plan version 2 (.pdf) Project Gantt Chart version 2 (.mpp) Project Gantt Chart version 2 (.pdf) Project Network Diagram version 2 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- List the three (3) project deliverables in Phase 1.

- Vegetation removal - Construct access roads - Build retaining walls

| - Discuss the project constraints in terms of scope, time, cost, and quality. |  |
| --- | --- |
| Scope | Must allow for other conditions imposed by the council. Landscaping must work in with the building construction, natural environment must be preserved as per council requirements. |
| Time | The project must be completed within a 9 month time frame. And allow for risks such as adverse weather conditions and delays |
| Cost | The project has a fixed budget $550000 + GST which needs to allow for change requests. |
| Quality | Council regulations, building regulations, licensing for operation of equipment and council audits |

| - Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. Write 1 – 12 in the spaces provided; where 1 go first and 12 go last. |  |
| --- | --- |
| 8 | Remove weeds |
| 11 | Plant additional plants |
| 2 | Move gravel to car park |
| 1 | Expand car park |
| 12 | Remove greenhouses |
| 9 | Plant plants from greenhouses |
| 3 | Seal car park |
| 6 | Soil preparation |
| 7 | Add boulders |
| 5 | Construct stone paving pathway |
| 10 | Purchase additional plants |
| 4 | Landscape over old access roads |

- Review the Project Plan. The change request has outlined one change in the scope of the project. - What is the change in scope? - How does this change in scope impact the overall duration of the project? - How does this change in scope impact the quality aspect of the project?

- Addition of 3 new retaining walls and services to additional units as per updated site plan, increase in cost of road gravel $6500. - It doesn’t phase 1 of the pre build starts 6 days earlier - Additional works need to be audited and signed off and completed within time.

- Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request? Do not exceed 100 words.

Because it is a fixed priced contract so the funds paid will be the same regardless of any project extensions, variations in scope or increases in cost of labor, procurement or purchases. So the inclusion of just the one change is merely indicated a change without the need for details because of the contract restraint.

- Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

The Project Manager – Sam Ng

- Access and review the Gantt Chart version 2. - What important tasks are not included in the project Gantt Chart? - Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

- The construction of the chalets - It is important to include the construction planned process as phase 1 needs to be completed prior to the construction of the chalets. So the Gantt chart needs to reflect the progress of the tasks being performed in relation to the build process. the building of the chalets also heavily impacts the time it takes to complete phase 2 of the program because all tasks have to work around the build stage so if it is delayed than the time to complete phase 2 will also be delayed as well as the commencement of phase 3. So its exclusion from the Gantt chart doesn’t give a true representation of the job as it doesn’t interoperate how the tasks work in with the build process.

- List the three (3) personnel who signed off on the change request.

- Susan Wills - Kim Nguyen - Stephan Lyons

- What is the total increase in cost of the project as a result of this change request?

$462195 - $444253 Total increase = $17900

- List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

- Installation of utilities. - Weather damage - Provision or delivery of pipes and tanks - Monitoring and maintaining the main Road. - Testing of utilities

- Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. Do not exceed 50 words.

The process of change has been conducted correctly as per procedure, the correct forms and templates have been filled out and the correct personal involved. However the changes don’t support the exclusions that are stated the project plan scope.

- Access and review the Gantt Chart version 2. It shows double bars for each task. - What do the coloured bars represent? - What do the grey bars represent? - Why do the grey and coloured bards do not match up in the Gantt chart?

- Progress and manual progress - External tasks - Because the grey are tasks performed by others and cannot be controlled and the colored are tasks that can be. The tasks that are colored have to be conducted around and supporting the grey.

- Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. Do not include the task ‘Project Management’.

- Delivery of granite boulders - Install road gravel

- If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely: - Construction of retaining walls. - Install and compact soil behind walls. According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

Because once one retaining wall is complete soil compacting can commence for that wall during the construction of the other walls.

- According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’, - Which tasks, if any, are immediately delayed? - Will this delay push out the completion of the project? Why or why not? - Discuss how this could affect the resourcing of the project. - List one (1) risk that could arise from this issue.

- Erection of signs and detailed landscaping - No, Because paths can still be completed without hindering other tasks of the project so will not effect the completion date of the project - Finding the extra labor to complete the paths which may effect the labor needed to complete other tasks - The extra cost of labor and a deduction of profits due to the delays.

- What is the total budget for the project expenditure?

$462153

- Sam is very concerned about the cash flow of the project. - What is the problem? - What would you suggest be done to rectify the cash flow issue?

- Two thirds into the project the cash flow is in the negative and has been inconsistent throughout the project - He could follow up with Massive eco-development to see if they can advance partial progress payment to cover for the costs to the program being extended due to the build of the extra chalets.

- Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-development Corporation to absorb some or all of these cost increases. Your discussion must be 200 – 300 words in length. Guidance: The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

No – Massive Eco Development are a new client for awesome landscaping and there is enough in profit margin that makes it not worth upsetting them considering the potential for ongoing projects with Massive Eco Development. Extra funding is not the answer however partial progress payment for phase 2 may be an option considering the impact the extra build has on the program cash flow. It is understandable that the extra cost for labor and materials need to be paid for through out the progression of the build phase resulting in a decrease in profit margins needed to pay for this phase. It would not be unreasonable for these costs to be paid for in advance from the progress payment due at the end of phase 2. They also need to consider that the contract does include a fixed budget with no allowance for variations. First thing to do is audit the program and determine if everything is being done to try and recoup some of the expense for example tighten the program schedule, renegotiate material costs etc.

- Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project. Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Paul Blake |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: | Overall Project Status: |  |  |  |  |  |  |  |
| Audit Date: | Audit Number: |  | Audit Leader: |  |  |  |  |  |
| Audit Team: |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To examine project expenses to determine if improvement can be made. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are the tasks being completed on schedule |  | Assessment: | Comment: |  |  |  |  |  |
| 2. Is the labour being used to conduct tasks within budget |  | Assessment: | Comment: |  |  |  |  |  |
| 3. Have cost of materials been re-evaluated with suppliers |  | Assessment: | Comment: |  |  |  |  |  |
| 4. Is financial reporting being conducted on time |  | Assessment: | Comment: |  |  |  |  |  |
| 5. Has the construction of chalets effected the schedule of the program occurring in delays |  | Assessment: | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes |  | no |  |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |
| Audit Report Submitted To: |  |  |  | Date: |  |  |  |  |

- Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions: - What was the cause of the unsatisfactory results? - What action would you recommend to prevent the issue coming up again in this project?

- Tasks only being communicated as per Gantt chart to the site supervisor who is having to seek clarification regularly on requirements of tasks resulting in a delayed response from the site supervisor back to the team members and contractors. - The project manager to conduct a team meeting discussing the audit with all involved to clarify the issue at hand and discuss better ways to communicate and interoperate the information be that needs to be passed forward.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng |  |  |  |  |  |  |  |  |
| Date: 17 August 2015 |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: Implementation | Overall Project Status: On schedule |  |  |  |  |  |  |  |
| Audit Date: 17 August 2011 | Audit Number: 26 |  | Audit Leader: Sam Ng |  |  |  |  |  |
| Audit Team: Sam Ng, John Cowley, Ann Deak. |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the communication and reporting processes. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are tasks being communicated to site supervisor in a reasonable amount of time? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| 2. Are tasks being communicated to site supervisor of sufficient detail? |  | Assessment: Not satisfactory. | Comment: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. |  |  |  |  |  |
| 3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time? |  | Assessment: Not satisfactory. | Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. |  |  |  |  |  |
| 4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. Project manager to prepare task briefs in enough time to add the required level of detail. 2. Task briefs are to be supplied with all relevant attachments such as detailed plans. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes | x | no |  |
| Audit Report Submitted To: Kim Nguyen |  |  |  | Date: 24/08/2015 |  |  |  |  |

- The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. Guidance: Your Cost Management Plan must cover the following quality objectives and criteria. - Meeting with contractual requirements. - Paying invoices on time. - Ensure invoices are sent out in time. - Ensuring financial reporting is done on time. - Include a calendar of when payments are likely to be due. - Comparison of actual cash flow against projected cash flow.

Awesome landscapes will meet all contractual requirements and will raise an invoice on the first working day of the month following the due date of any progress payment. To ensure accurate financial reporting, all invoices received will be paid within 7days of invoice date. As well as this all wages are payed on a 7 days basis. Financial reports are due weekly so that the project team and accurately access and manage the project costs and revise any issues in a more timely manor. These reports must relate the costs associated with each task. Weekly management meetings to be conducted with senior project team Mondays – All invoices received paid by 1pm Mondays -All wages processed and paid Tuesdays – Financial reporting due to project manager by 1pm for the previous week Wednesdays – Meeting to be conducted to discus reporting and project planning . With more timely payment of invoices and reporting. A more accurate cash flow can be constructed to compare against projected cash flows. This will allow for any issues to be addressed in a more timely approach in effort to reduce fincial risks.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Part 1 – Project Scope Part 2 – Project Time Part 3 – Project Cost Part 4 – Project Quality Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document