CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | GENEVIEVE INCLAN |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 1/06/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 45 |  | Yes | No |

Assessor Comments

Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Project Plans Specification |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | QBCC Act 1991 (Qld) | Section 33 of Schedule 1B of the QBCC Act sets out the following maximum deposits: - For contracts priced at $3301 - $19,999 (level 1 contracts) – a maximum of 10% of the total contract price - For contracts priced at $20,000 or more (level 2 contracts) – a maximum of 5% of the total contract price. - Maximum Penalty – 100 Penalty Units |  |

Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Plasterer | Install internal linings. |  |
|  | Carpenter | Installs flooring, wall frames, roof trusses, windows, external doors and frames, decking and steps; attends to joinery and mouldings. |  |
|  | Painter | Paints areas, such as walls and ceilings. |  |

Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

Explain the importance of determining subcontractor or plant availability for a job.

| Answer | - High quality workmanship of the subcontractors. Subcontractors specialise in a single trade and are generally more efficient and knowledgeable about their work than a jack-of-all-trades - Subcontractors are readily available - They can be used for small tasks, rather than paying a worker for an extended period (during which their skills may not be used the whole time) |  |
| --- | --- | --- |

Identify two (2) methods you might use to find a supplier for materials.

| Answer | - Phone around to find out who has good supplies - Liaise with known suppliers that are resourceful and reliable |  |
| --- | --- | --- |

Name two (2) factors that may impact on the availability of materials.

| Answer | - imported materials which need to be transported from interstate or overseas. - Reliable supplier |  |
| --- | --- | --- |

Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | AS/NZS 1680 |  |
| --- | --- | --- |

Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Tower Lift | Lift steel, concrete, large tools like acetylene torches and generators, and a wide variety of other building materials. |  |
|  | Excavators | Excavate and load most types of soil. |  |

Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Ladders | Use to undertakes a task at heights |  |
|  | Wheel barrows | Carry heavy loads easily and efficiently |  |

Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Invoices & Receipts |  |
| --- | --- | --- |

Name five (5) temporary services that need to be organised for a building site.

| Answer | 1. temporary electrical pole 2. water tapping 3. temporary fencing 4. barricades 5. waste bin |  |
| --- | --- | --- |

True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

Identify one (1) action you might take to facilitate site access for machinery.

| Answer | - Ensure there is adequate room for trucks to stop and use lifting equipment such as forklifts from the side of the road onto the site. |  |
| --- | --- | --- |

Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | NCC Vol. 2, Part 2.5, 3.9 | NCC Vol. 1, Section D |  |

You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | - a site-specific Construction Noise Management Plan (Word - 89.71kb); - a copy of the letter that will be provided to premises/residents who are likely to be affected, which must include: - after hours contact name and phone number for a company representative; - date and times the construction activities will take place; and - type of construction activity to take place. A minimum of 10 working days is required for Council to assess an application. |  |
| --- | --- | --- |

In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Lane or Road closure permit | Council |  |
|  | Electricity Supply permit | Energex |  |

True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What document should be developed when purchasing supplies or construction materials?

| Answer | Purchase Order |  |
| --- | --- | --- |

True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Who should be contacted if items are missing from a delivery?

| Answer | Supplier |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | Work Health and Safety Act 2011 (Qld), Section 17-18 | indicates that risks should be identified and eliminated, so far as is reasonably practicable (or otherwise minimised so far as is reasonably practicable). |  |

Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | The Work Health and Safety Regulation 2011 (Qld) provides more specific detail about the requirements of the Act and outlines types workplace risks. |  |
| --- | --- | --- |

What document should be followed when disposing of hazardous materials?

| Answer | When handling and disposing of hazardous materials, it is essential to follow any Safety Data Sheets (SDS), where applicable. |  |
| --- | --- | --- |

An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10 |  |
| --- | --- | --- |

True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | This can save a great deal of time, as the subcontractors can work on the next job while waiting for another to complete If sub-contractors move to another location it can be difficult to ensure their return for the next stage of the project. If sub-contractors move to another location it can be difficult to ensure their return for the next stage of the project. |  |
| --- | --- | --- |

Provide one (1) example to explain why construction operations must be sequenced.

| Answer | It allows for a break up of activities where trades are required on more than one occasion – such as electrical, for the initial wiring, and then later, after the internal linings and finishes have been installed, for the final fix (e.g. power points, switches, light fittings, etc). |  |
| --- | --- | --- |

Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 3 | Floor frame |  |
|  | 6 | Installing brick base |  |
|  | 5 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 4 | Wall frames |  |

Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| - Task ID | - Task | - Preceding event | - Nodes |
| --- | --- | --- | --- |
| - A | - Make enquiries and order all materials required | - Start | - 1 |
| - B | - Wait for bricks, sand and cement to arrive | - A | - 2 |
| - C | - Clear vegetation from the site | - A | - 2 |
| - D | - Order concrete to be delivered | - A | - 2 |
| - E | - Dig the trench | - C | - 4 |
| - F | - Pour the footings | - E | - 5 |
| - G | - Footings curing time | - F | - 6 |
| - H | - Load the bricks on the site | - B | - 3 |
| - I | - Mix the mortar and lay the bricks | - H | - 7 |
| - J | - Clean rubbish from the area | - I | - 8 |
|  | - Finish | - J | - 9 |

G

F

H

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | MICROSOFT PROJECT |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

Describe the critical path.

| Answer | The ‘critical path’ – the longest sequence of activities in a project (which determines the shortest possible completion time if all events are to be completed) |  |
| --- | --- | --- |

True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | - Unexpected delays: Strikes, illness, mistakes - Building inspections: Failing inspections - Weather: Can spend time waiting for weather to pass or for the site to recover |  |
| --- | --- | --- |

Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

Why should you take photographs of site boundaries with neighbouring properties?

| Answer | It will be helpful in the event of a dispute with a neighbour. |  |
| --- | --- | --- |

When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

When might a neighbouring property owner be required to refer to a condition report?

| Answer | If any damage has occurred through the construction process. |  |
| --- | --- | --- |