## Risk log
Risk Register
Project name: Common project risks |  | Caval Ridge Administration Extension
Project manager: J Black |  | C . Turner
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status
1 | 2020-04-23 | Project purpose and need is not well-defined. | Medium | High | High | BMA Engineering Team, Project Management Team | Ensure purpose is well defined on Project Charter and PID. Project objective statement is updated | Escalate to the Project Board with an assessment of the risk of runaway costs/never-ending project. | Objective statement re-written with clear deliverables and submitted to the project board for approval. | Open
2 | 2020-05-03 | Uncontrollable act of God eg: Earthquake/ fire | Low | High | High | Project Sponsor | Bma Mine manager to implement safeguards for entire mine which will include renovation project. | Document assumptions made and associated risks. Request high risk items that are ill-defined are removed from scope. | Evacuation procedure re visited | Open
3 | 2020-05-03 | Project schedule is not clearly defined or understood | Low | Medium | Medium | Project Manager | Hold scheduling workshops with the project team so they understand the plan and likelihood of missed tasks is reduced. | Share the plan and go through upcoming tasks at each weekly project progress meeting. | Workshops scheduled. | Open
4 | 2020-05-10 | No control over staff priorities | Medium | Medium | Medium | Project Manager | The Project Sponsor will brief team managers on the importance of the project. Human resource management, BBQ and beers held after shift to lift moral. Identify back ups for each human resource on the project. | Escalate to the BMA upper management and bring in back up resource. | Project Sponsor has agreed to hold briefing. Now making arrangements for a meeting room. | Open
5 | 2020-05-19 | Consultant or contractor delays | Medium | High | High | Project Manager | Include late penalties in contracts. Build in and protect lead time in the schedule. Communicate schedule early. Check in with suppliers regularly. Query '90% done'. Ask again and again if they need anything else. | Escalate to BMA Engineering management and Contracts Manager. Implement late clauses. | Lead time from each contractor built into the project schedule. Late penalties agreed to and contracts signed. | Open
6 | 2020-06-02 | Severe Weather | Medium | High | High | Project Manager | No mitigation for likelyhood but brief all contractors on Lightning and Rain site procedures and TARPS. | Document lost project time and any damage to work area and equipment due to storms. | Project Manager and site supervisor responsible for actions during and after storm. | Open
7 | 2020-07-04 | Unplanned work that must be accommodated | Low | High | Medium | Site Supervisor (Christian Turner) | Attend project scheduling workshops. Check previous projects, for actual work and costs. Check all plans and quantity surveys. Document all assumptions made in planning and communicate to the project manager before project kick off. | Escalate to the Project Manager with plan of action, including impact on time, cost and quality. | Team managers attending scheduling workshops. | Open
8 | 2020-07-04 | Lack of communication, causing lack of clarity and confusion. | Medium | Medium | Medium | Project Manager | Write a communication plan which includes frequency, goal, and audience of each communication. Identify stakeholders early and make sure they are considered I the communication plan. Use most appropriate channel of communication for audience e.g. don't send 3 paragraph email to Developers, have a call instead. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly using assistance from Project Sponsor if needed. | Communication plan in progress. | Open
9 | 2020-07-08 | Pressure to arbitrarily reduce task durations and or run tasks in parallel which would increase risk of errors. | Low | High | Medium | Project Manager | Share the schedule with key stakeholders to reduce the risk of this happening. Patiently explain that schedule was built using the expertise of subject matter experts. Explain the risks of the changes. Share the Dennis Lock quote at https://www.stakeholdermap.com/plan-project/plan-reduction-crashing.html. | Escalate to Project Board with assessment of risk and impact of the change. Hold emergency risk management call with decision makers & source of pressure and lay out risk and impact. | Awaiting completion of the schedule. | Open
10 | 2020-07-18 | JSA / Swims not complete or up to date | Medium | High | High | Project Manager/ site supervisor | Daily checks of all site safety sign on and hazard reduction documents | If failure to comply with hazard documents standards , contractors to be reprimanded and possible replacement human resources sourced . | Prestart meetings attended prior to work commencement and all safety documentation examined daily | Open

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low