# Project Schedule

Site Address: 123 ABC Residential street, QLD

| Milestones to be completed | - Kick-off meeting for Residential Project 1/3/23 - Possession of site date 5/3/23 - Start date 5/3/23 - Plumbing Rough In 7/3/23 - Electrical Rough In 7/3/23 - Building works – wet areas, walls, ceiling, doors/windows 10/3/23 - Plaster works and finish 17/3/23 - Water proofing 19/3/23 - Cabinets installation, skirting/architraves installation, benchtop , kitchen, laundry, pantry installation 28/3/23 - Tiling 28/4/23 - Electrical Fit-Off 1/5/23 - Plumbing Fit-Off 1/5/23 - Accessories Fit-Off 3/5/23 - Caulking 3/5/23 - Screen installation 4/5/23 - Practical completion date 5/5/23 - Completion: Prior to Practical Completion, submit a detailed schedule of defects and incomplete work to the Superintendent indicating that each item has been corrected or completed to the satisfaction of the Contractor. - Collect the section 40 Certificates of Compliance from the subcontractors and the Final Inspection Certificate from the Building Certifier. Submit these with the Builder’s Declaration prior to Practical Completion. Practical Completion is contingent upon receipt of the Building Certifier’s Occupancy Permit. |
| --- | --- |
| Estimated project progress | On time, scope and budget |
| Start date | 5/3/2023 |
| End date | 5/5/2023 |
| Labour start date | 5/3/2023 |
| Delivery date for materials | 5/3/2023 |

| Task | Start date | End date | Material required | Labour required |
| --- | --- | --- | --- | --- |
| Demolish existing kitchen and make good Dismantling the existing storage, slab platform including supporting walls, wall tiles, flooring, sink etc. at all levels as required carefully and disposing off and clearing away the debrisSlabs to be chased to allow for new plumbing | 5/3/23 | 6/3/23 | Jack hammer | Demolition labour Demolish existing kitchen and make good Dismantling the existing storage, slab platform including supporting walls, wall tiles, flooring, sink etc. at all levels as required carefully and disposing off and clearing away the debris Slabs to be chased to allow for new plumbing |
| Plumbing rough in | 7/3/23 | 7/3/2023 |  | Plumber |
| Electrical rough in | 7/3/23 | 7/3/2023 |  | Electrician |
| Kitchen Elevation Bench Drawers Spice rack Brushed stainless steel laminate Ducting Overheads Shelves Caesarstone bench top Island Sink cupboard Paint Cabinetry - Blum Tandembox antaro h. Fronted pull-out C - DQC5JY, D - DQC69A, DQCB6M Urbane Castella 192mmCTC handle | 5/3/23 | 24/3/2023 | Kitchen elevation 2730x2550Hx600mm diameter or expressed as 2.7mx2.55mx0.6m Bench height 1000mm with 3 sets of 3 blum tip drawers with 1 of orga line spice rack insert Brushed stainless steel laminate kick face Ducting for downdraft cooktop to run behind draws Overheads 650mm Height with 1 of adjustable shelf with doors hanging below as finger pull and LED strip lighting to underside Internal 16mm HMR with 1mm ABS PVC match edge Fronts in 18mm white sating with 2 pac satin finish 40mm Caesarstone bianco drift bench top with cutout | Carpenter Plumber Painter Installation of supply mentioned |
| Butlers Pantry Door sink cupbard Bins Dishwasher Drawers Shelves Overheads Paint | 5/3/23 | 24/3/2023 | 4480x2550 Hx620mm D pantry or expressed as 4.48m x 2.550m x 0.620m with door sink cupboard and 2x20L bins Dishwasher opening 600mm 3 sets of 3 blum tip on drawers with 885mm pantyr to RH side 2 door pantry unit with 5 blum soft close internal drawers and 4 adj shelves Overheads 3595x650 Hx400mm D with 1 adj shelf with doors hanging below as finger pull | Carpenter Plumber Painter Installation of supply mentioned |
| Laundry Laundry tub unit Shelves Bench Caesartone top 6131 Bianco Drift, 4600 Organic white Shute cupboard Overheads Drawers Tall cupboard Brushed SS laminate Single door cupboard Paint | 6/3/23 | 24/3/2023 | L shaped laundry 2450x2520x2550mm or expressed as 2.45m x 2.52m x 2.55m with 4 door laundry tub unit with 1 adj shelf with bench at 1000mm H 40mm Caesarstone organic white top running wall to wall below laundry shute cupboard and 20mm thick splashback 150mm height 4 door overhead cupboard with 2 adj shelves and dorrs hanging down as finger pull above dryer and washing machine openings with flat pull out shelves and 1 of blum soft close drawer below 2 door Tall broom storage cupboard to right side with 1 of blum soft close drawer below 1 0f internal adj shelf Brushed stainless steel laminate kick face Single door cupboard 600x600mm on opposite wall 1000mm height bench top. All internals 16mm white HMR with 1mm ABS PVCedge. All fronts in 18mm white sating with 2 pac satin finish Dryer and washing machine panels, bottoms in 32mm MDF with 2pac finish | Carpenter Plumber Painter Installation of supply mentioned |
| Island & laundry - franke ancona single bowl undermount sink – anx 110-48 Pantry - franke ancona double bowl undermount sink - anx 120 Island & pantry - mizu drift mk2 gooseneck sink mixer pull-out Laundry - mizu soothe square gooseneck sink mixer | 8/3/23 | 24/3/2023 | Island & laundry - franke ancona single bowl undermount sink – anx 110-48 Pantry - franke ancona double bowl undermount sink - anx 120 Island & pantry - mizu drift mk2 gooseneck sink mixer pull-out Laundry - mizu soothe square gooseneck sink mixer | Carpenter Plumber Installation of supply mentioned |
| Building works – wet areas, walls, ceiling, doors/windows | 10/3/23 | 28/3/2023 |  | Carpenter Labour for scopes of work described excluding the installation of above fixtures New stud plasterboard wall to be build New fixed glass window to existing opening Enclose wall above and below to match existing Window tint to be discussed with client New doors to match switch opening with screens New doors to match triple slider with screens New Laundry door location cavity slider to match existing Tambour door in kitchen New Laundry window to suit existing opening width over dishwasher |
| Plaster works and finish | 17/3/23 | 22/3/2023 |  | Plasterer Installation of supply mentioned |
| Waterproofing | 19/3/23 | 22/3/2023 |  | Waterproofer Installation of supply mentioned |
| Cabinets installation, skirting/architraves installation, benchtop , kitchen, laundry, pantry installation | 28/3/23 | 18/4/2023 |  | Carpenter Installation of supply mentioned |
| Timber look tile flooring Ceramic tile splashback – kitchen and laundry Kitchen timber look tile to match floors Brushed stainless steel laminate | 20/4/23 | 24/4/2023 | New timber look tile flooring Kitchen – timber look tiles to match floors 1200x x230mm Laundry and kitchen - ceramic tile splashback - Snow Brillo Tile Sc19 A7615, Amber Tiles To Match Cabinets. 130mmx130mm Brushed stainless steel laminate kick face 130 sqm | Tiler Carpenter Installation of supply mentioned |
| Tiling | 28/4/23 | 1/5/2023 |  | Tiler Installation of supply mentioned |
| Electrical Light LED tape | 28/4/23 | 1/5/2023 | Beacon Herman 1 light pendant 14 watt led tape and recess led profile under overhead cupboards Single phase underground power connection from existing supply point. Led light strip under island bench Cooktop isolation switch | Electrician |
| Electrical fit off | 1/5/23 | 3/5/2023 |  | Electrician Installation of supply mentioned above Electricity cap off and reconnections Electricity dis-connections to existing serviceable connection points and connections Duct work for bench mount exhaust to run through back of drawers and wall to external wall and motor Cooktop downdraft ventilation system |
| Plumbing fit off | 1/5/23 | 3/5/2023 |  | Plumber Installation of supply mentioned above Slabs to be chased to allow for new plumbing Plumbing cap off and reconnections Plumbing dis-connections to existing serviceable connection points and connections Water dis-connection and connections from pre-tapped water main |
| Butlers Pantry - Fixed Glass Window French Doors - Triple Slider Dining Room Slider - Reverse Opening | 2/5/23 | 2/5/2023 | New fixed glass window to suit existing opening width frame 1800x600mm Colour to match exiting and tinted to client requirement (customized) New Triple Slider With Screens To Match Existing Profile & Colour 2710x2100mm Slider with reversed opening with screen to match existing profile and colour 1810mmx2100mm | Carpenter Installation of supply mentioned |
| Accessories fit off | 3/5/23 | 5/5/2023 |  | Carpenter Installation of supply mentioned |
| Caulking | 3/5/23 | 5/5/2023 |  | Carpenter Installation of supply mentioned |
| Screen installation | 4/5/23 | 4/5/2023 |  | Carpenter Installation of supply mentioned |
| Removal of debris and site clean up | 5/5/2023 | 5/5/2023 | Skip bins Cleaning material | All trades |

Contingency: 1

| Summary of contingency | It shall be the responsibility of the Contractor to ascertain all information relating to the services, the works and site conditions that may affect the progress or method of performing all services and works as specified within the scope of this contract and to prepare for every contingency that may arise. It is further understood that just provision for these contingencies have been accounted for, implicitly or explicitly within the lump sum price submitted. ## Also as per our Policy - Create Contingency Plans - There are so many ways a project can get off track. Carefully review your master schedule and identify potential risks that could disrupt your schedule. Crafting contingency plans that can easily be executed will go a long way in mitigating and resolving issues before they get out of control. - You may need to assign overtime if you are running behind schedule. Weather delays might require you to bring in extra labor and equipment to get your project back on track. Brainstorm possible schedule delays with the rest of the project team and build contingency plans for each situation. Once construction starts, the goal is to make keep the project on schedule as much as possible. Typically, a project will get derailed by lots of minor issues rather than one huge problem. Carefully analyzing daily progress reports, keeping an eye on the budget and schedule, and managing risks require a high level of attention to detail. In this project, we are progressing well in scope, time and budget and hence no further contingency plans, other than the below. |
| --- | --- |
| Materials needed | 10% incorporated in the order |
| Labour needed | Back up plan incorporated especially for key personnel |