RIICPL401D

Apply the principles for the installation of underground service using open excavation

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Brian Miller |
| --- | --- |
| Participant signature |  |

| Assessor name | Brett Stoward |
| --- | --- |
| Assessor signature |  |

| Date | 28/05/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 20 |  | Yes | No |

Assessor Comments

- List two (2) types of statutory compliance that is relevant to installing underground service using open excavation.

| Answer | Workplace health and safety Act, 2011 Electrical safety ACT 2002 |  |
| --- | --- | --- |

- Where, in your workplace, would you locate procedures relevant to the installation of underground service using open excavation?

| Answer | Site Office |  |
| --- | --- | --- |

- Identify two (2) methods used to identify and locate other related underground services and utilities.

| Answer | GPR, Potholing. |  |
| --- | --- | --- |

- Identify two (2) engineering survey principles that relate to the installation of underground service using open excavation.

| Answer | Planning, Independent Checks. |  |
| --- | --- | --- |

- In the space below, identify and explain how one (1) environmental management principle impacts on the task of installing underground service using open excavation.

| Answer | Principle | Explanation |  |
| --- | --- | --- | --- |
|  | Sensitive Area | Area Being excavated could be sensitive by culture and by heritage |  |

- Describe three (3) processes that are involved in developing a ‘work plan’.

| Answer | Planning Process | Description |  |
| --- | --- | --- | --- |
|  | List the tasks to complete the job | , Having a clear objective helps you make sure all tasks/steps are developed for the plan and that all the information and data needed can be included in the plan. |  |
|  | Develop a list of actions for each task | Brainstorm a list of actions with others, if you can, and make sure you have someone else check your list as a way of ensuring you haven’t missed anything. |  |
|  | Prepare a timeline/schedule | Starting from the point of ‘Now’ and ending at ‘Job Completed’, build a timeline that includes dates for the completion of the tasks and actions you developed in your list. It is important you get the sequence and timing right so that the job goes smoothly and achieves the timeframes required. |  |

- Describe two (2) estimating principles that are relevant to you in planning for the installation of underground service using open excavation.

| Answer | Estimation Principle | Description |  |
| --- | --- | --- | --- |
|  | Scope definition | Equipment required, Layout |  |
|  | Execution strategy | Constraints, Contract requirements |  |

- Identify three (3) principles of leadership and how they apply to you in your role as a Supervisor in the installation of underground service using open excavation.

| Answer | Leadership Principle | Application in the workplace |  |
| --- | --- | --- | --- |
|  | 1. The demonstration of safety leadership | Ensure that this is clear to all parties through effective and regular communication methods and is linked to performance expectations. |  |
|  | 2. Promote the design for safety in all engineering solutions | fail to safe’ and work to minimise the risk to the safety of others who may come into contact with the structure. |  |
|  | 3. Communicate safety & project related information | keep people in the loop and welcome comments and the sharing of ideas and lessons learnt. |  |

- List three (3) key factors that influence the selection of operational techniques when planning to install underground service using open excavation.

| Answer | The ground conditions, Proximity to other services, The type of installation required or needed |  |
| --- | --- | --- |

- List three (3) key factors that influence your selection of resources when planning to install underground service using open excavation.

| Answer | Types of utilities to be installed, The expected duration or life, The location or environment |  |
| --- | --- | --- |

- Explain the principle of scheduling tasks and activities.

| Answer | The aim is to find the most appropriate person for each task, so that the desired result Will be produced, |  |
| --- | --- | --- |

- In your workplace, what are two (2) key things you must consider when scheduling the delivery of materials to site.

| Answer | Storage capacity/ availability, Contractors making delivery are site compliant. |  |
| --- | --- | --- |

- In the generalised list below, number each task in order of sequence for the installation of underground service using open excavation.

| Answer | Order | Tasks |  |
| --- | --- | --- | --- |
|  | 3 | Plan the work |  |
|  | 9 | Backfill the trench |  |
|  | 6 | Prepare and maintain batters |  |
|  | 4 | Prepare the work environment |  |
|  | 8 | Enclose with bedding materials |  |
|  | 5 | Excavate the trench |  |
|  | 2 | Update service plans and drawings |  |
|  | 1 | Check for any underground or overhead services |  |
|  | 7 | Lay service piping & install services |  |
|  | 10 | Clean up work area |  |

- List three (3) key aspects relevant to managing open excavation underground service installation.

| Answer | Risk assessment Public safety Locating spoil dumps |  |
| --- | --- | --- |

- List five (5) daily tasks you conduct (as the Project Manager / Lead), when managing client and site operational requirements, in relation to the installation of underground service using open excavation.

| Answer | Check safe work practices, Identify new hazards Track materials usage |  |
| --- | --- | --- |

- From the list below, which areas of civil works are related to the installation of underground service using open excavation? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Environmental conservation |  |
|  |  | Infrastructure development |  |
|  |  | Bridge construction |  |
|  |  | Commercial development |  |
|  |  | Rail construction |  |
|  |  | Lifting and cranage |  |
|  |  | Road construction/maintenance |  |
|  |  | Pipeline construction |  |
|  |  | Ship building |  |
|  |  | Industrial development |  |
|  |  | Systems development |  |
|  |  | Road transport |  |

- Identify two (2) places where you can locate information that relates to plant and equipment capabilities and operation.

| Answer | Manufacturers’ representatives, OEM |  |
| --- | --- | --- |

- Describe the process for maintaining plant, equipment, and tools.

| Answer | By conducting scheduled, regular and adequate maintenance of plant and equipment |  |
| --- | --- | --- |

- In your own words, explain three (3) terms that are commonly used in the installation of underground service using open excavation.

| Answer | Excavation – the digging of a trench to said height and depth Bench – to make safe the excavation by cutting back sides to stop any cave in. Back fill - to fill said excavation will material compacting in layers |  |
| --- | --- | --- |

- Calculate the following:

- What is the total volume of the shape below?

10,750,350,000 cubic mm (V = L x W x D )

- What is the surface area of the shape below?

5,811,00    Square  mm ( A = L x W

- In the shape below, calculate the grade of the dotted line using the grade ratio of 1:10. What is the total grade amount?

Depth 1850mm

Length 3725mm

Width 1560mm

Grade 1:10

- You need an excavator for 3 days and have been asked to make sure there is enough diesel to last the whole 3 days.  The excavator uses 15 litres per hour and will be operating for approximately 6 hours per day.  The company buys its diesel at cost ($1.10 per Litre) and it has a policy that requires all orders include a contingency of 10%.

  - What is the total consumption of diesel for the 3 days?

270 LITRES

  - How much diesel will you need to order?

297 LITRES

  - What is the total cost of your order?

326 .70