Project Schedule Template

SIMULATION PROJECT - The information is fictional and provided for the purpose of this simulation.

Stage: Foundation and Structure

| Milestones to be completed | Site preparation, foundation laying, structural framework |
| --- | --- |
| Estimated project progress | 0-30% |
| Start date | 01/04/2023 |
| End date | 30/06/2023 |
| Labour start date | 02/04/2023 |
| Delivery date for materials | 10/04/2023 (Structural Steel), 08/04/2023 (Concrete) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Site Excavation | 02/04/2023 | 07/04/2023 | N/A | Excavation team |
| Foundation Pouring | 08/04/2023 | 12/04/2023 | Ready-Mix Concrete and Reinforcement | Concrete layers and reo fixers |
| Structural Steel Erection | 11/04/2023 | 30/06/2023 | Structural Steel Beams | Steelworkers, crane operators |

Contingency

| Summary of contingency | Weather delays, Concrete Delivery Delays, Steel Fabrication Errors |
| --- | --- |
| Materials needed | Concrete, Reinforcement, structural steel beams |
| Labour needed | Excavators, concrete layers, reo fixers, steel fabricators |

Stage: Exterior and Interior

| Milestones to be completed | Enclosure of building, installation of windows, interior rough-in |
| --- | --- |
| Estimated project progress | 30-60% |
| Start date | 01/07/2023 |
| End date | 30/09/2023 |
| Labour start date | 01/07/2023 |
| Delivery date for materials | 01/07/2023 (Glass Panels), 05/07/2023 (Insulation) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Window Installation | 01/07/2023 | 15/07/2023 | Window Glass Panels | Glaziers |
| Interior Framing and Insulation | 16/07/2023 | 15/08/2023 | Timber, Insulation Materials | Carpenters, insulators |

Contingency

| Summary of contingency | Incorrect window sizing, Material shortages |
| --- | --- |
| Materials needed | Window Glass Panels, Timber, Insulation Materials |
| Labour needed | Glaziers, Carpenters, insulators |

Stage: Finishing and Commissioning

| Milestones to be completed | Painting, fixture installations, final inspections |
| --- | --- |
| Estimated project progress | 60-100% |
| Start date | 01/10/2023 |
| End date | 31/12/2023 |
| Labour start date | 01/10/2023 |
| Delivery date for materials | 25/09/2023 (Paint), 05/10/2023 (Fixtures) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Painting | 01/10/2023 | 20/10/2023 | Paint | Painters |
| Fixture and Finishing Touches | 21/10/2023 | 30/11/2023 | Lighting fixtures, plumbing fixtures, hardware | Electricians, plumbers, general labor |

Contingency

| Summary of contingency | Delays in prior tasks, Supplier delivery issues |
| --- | --- |
| Materials needed | Paint, lighting fixtures, plumbing fixtures and hardware |
| Labour needed | Painters, electricians, plumbers and general labour |