## Forecast Detail
D1A | CT |  | Access Consultant
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 1 | Access Consultant (RFI | 1 | ITEM | 500 | 500
Total Forecasts | [6 empty] | 500
Total for Cost Centre | [6 empty] | 500
D1AE | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
ACOU02 | 22066049 | 1 | Stage 4 Construction Services | 1 | EACH | 1750 | 1750 | 1750
ACOU02 | 22066049 | 2 | Stage 5 | 1 | EACH | 5200 | 5200 | 0
Sum: | [6 empty] | 6950 | 1750
Total for Cost Centre | [6 empty] | 6950 | 1750
D1CE | CT |  | Civil Engineer
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CBAM01 | 22066055 | 1 | Pelican Waters - SCC OPW Civil Prestart Fee | 1 | EACH | 527.27 | 527.27 | 527.27
Sum: | [6 empty] | 527.27 | 527.27
Subcontracts
ACOR01 | 22066018 | 1 | Stage 5 - Civil | 1 | ITEM | 9500 | 9500 | 7600
ACOR01 | 22066018 | 4 | VI:Civil Engineer | 0 |  | 0 | 400 | 400
ACOR01 | 22066018 | 5 | VI:Civil Engineer | 0 |  | 0 | 495 | 495
ACOR01 | 22066018 | 7 | VI:Civil Engineer | 0 |  | 0 | 400 | 400
ACOR01 | 22066018 | 8 | VI:Civil Engineer | 0 |  | 0 | 230 | 230
ACOR01 | 22066018 | 9 | VI:Civil Engineer | 0 |  | 0 | 1512.5 | 1512.5
ACOR01 | 22066018 | 12 | VI:Civil Engineer | 0 |  | 0 | 237.5 | 237.5
ACOR01 | 22066018 | 15 | VI:Civil Engineer | 0 |  | 0 | 247.5 | 247.5
ACOR01 | 22066018 | 16 | VI:Civil Engineer | 0 |  | 0 | 100 | 100
Total Subcontracts | [6 empty] | 13122.5 | 11222.5
Forecast Amounts
|  | 9 | ESC Audit - May | 1 | NO | 500 | 500
|  | 10 | ESC Audit - Jun | 1 | NO | 500 | 500
|  | 11 | ESC Audit - Jul | 1 | NO | 500 | 500
|  | 12 | ESC Audit - Sep | 1 | NO | 500 | 500
|  | 13 | ESC Audit - Oct | 1 | NO | 500 | 500
Total Forecasts | [6 empty] | 2500
Total for Cost Centre | [6 empty] | 16149.77 | 11749.77
D1EE | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
VISI08 | 22066124 | 1 | PMT Easement Survey | 1 | EACH | 6000 | 6000 | 3600
Sum: | [6 empty] | 6000 | 3600
Subcontracts
STPC01 | 22066044 | 1 | Electrical Review of IFC, | 1 | NO | 5720 | 5720 | 1320
STPC01 | 22066044 | 2 | Mechanical IFC, 70% and As | 1 | NO | 5720 | 5720 | 0
STPC01 | 22066044 | 3 | Fire IFC Review, 70% and As | 1 | NO | 5720 | 5720 | 0
Total Subcontracts | [6 empty] | 17160 | 1320
Total for Cost Centre | [6 empty] | 23160 | 4920
D1FE | CT |  | Fire Engineer
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
WALK08 | 22066109 | 1 | Stage 5 Construction Services | 1 | EACH | 1600 | 1600 | 0
Sum: | [6 empty] | 1600 | 0
Forecast Amounts
|  | 3 | Form 12 Allowance/3rd Party | 1 | ITEM | 2200 | 2200
Total Forecasts | [6 empty] | 2200
Total for Cost Centre | [6 empty] | 3800 | 0
D1HE | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
DYFA03 | 22066005 | 1 | Temp Application | 1 | EACH | 570 | 570 | 0
Sum: | [6 empty] | 570 | 0
Subcontracts
ACOR01 | 22066018 | 6 | VI:Hydraulic Engineer | 0 |  | 0 | 2500 | 2500
ACOR01 | 22066018 | 10 | VI:Hydraulic Engineer | 0 |  | 0 | 3000 | 3000
Total Subcontracts | [6 empty] | 5500 | 5500
Total for Cost Centre | [6 empty] | 6070 | 5500
D1KS | CT |  | Kitchen and Laundry Specialist
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
UNIV16 | 22066053 | 1 | Stage 4 Construction Services | 1 | EACH | 1000 | 1000 | 1000
UNIV16 | 22066053 | 3 | Dimensions on Drawings | 1 | EACH | 3600 | 3600 | 3600
UNIV16 | 22066097 | 1 | UFD Laundry Drawings | 1 | EACH | 1400 | 1400 | 1400
UNIV16 | 22066097 | 2 | Stage 5 Drawing Review | 1 | EACH | 2500 | 2500 | 2500
Sum: | [6 empty] | 8500 | 8500
Forecast Amounts
|  | 1 | Final Inspections | 2 | ITEM | 2800 | 5600
|  | 8999 | 020007 Laundry Heat Pump Dryer | 1 | EACH | 900 | 900
Total Forecasts | [6 empty] | 6500
Total for Cost Centre | [6 empty] | 15000 | 8500
D1LD | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
BUTL03 | 22066088 | 1 | Stage 4 - Construction Documentation | 1 | EACH | 3250 | 3250 | 1960
BUTL03 | 22066088 | 2 | Stage 5 - Construction Admin Services | 1 | EACH | 4165 | 4165 | 0
Sum: | [6 empty] | 7415 | 1960
Total for Cost Centre | [6 empty] | 7415 | 1960
D1NC | CT |  | Section J
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CUND02 | 22066051 | 1 | Stage 4 Construction Services | 1 | EACH | 4250 | 4250 | 4250
Sum: | [6 empty] | 4250 | 4250
Forecast Amounts
|  | 8999 | 020012 Western Facade Windows | 1 | EACH | 5000 | 5000
Total Forecasts | [6 empty] | 5000
Total for Cost Centre | [6 empty] | 9250 | 4250
D1SE | CT |  | Structural Engineer
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
ACOR01 | 22066018 | 2 | Stage 5 - Structural | 1 | ITEM | 13600 | 13600 | 12465
ACOR01 | 22066018 | 3 | VI:Structural Engineer | 0 |  | 0 | 115 | 115
ACOR01 | 22066018 | 11 | VI:Structural Engineer | 0 |  | 0 | 1200 | 1200
ACOR01 | 22066018 | 13 | VI:Structural Engineer | 0 |  | 0 | 1200 | 1200
ACOR01 | 22066018 | 14 | VI:Structural Engineer | 0 |  | 0 | 4000 | 4000
CUST19 | 22066020 | 5 | VI:Structural Engineer | 0 |  | 0 | 550 | 550
Total Subcontracts | [6 empty] | 20665 | 19530
Forecast Amounts
|  | 6 | Roof Plant Deck and stair | 2 | NO | 800 | 1600
|  | 8 | External works | 5 | NO | 700 | 3500
Total Forecasts | [6 empty] | 5100
Total for Cost Centre | [6 empty] | 25765 | 19530
D1SL | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
KING03 | 22066119 | 1 | Programming Session | 1 | EACH | 810 | 810 | 810
Sum: | [6 empty] | 810 | 810
Total for Cost Centre | [6 empty] | 810 | 810
D1SP | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
ADGE01 | 22066087 | 1 | Structural Peer Review | 1 | EACH | 5200 | 5200 | 5200
Sum: | [6 empty] | 5200 | 5200
Total for Cost Centre | [6 empty] | 5200 | 5200
D1TM | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
ACCT01 | 22066003 | 1 | TMP | 1 | EACH | 625 | 625 | 625
ACCT01 | 22066003 | 2 | Traffic Guidance Scheme | 1 | EACH | 195 | 195 | 195
Sum: | [6 empty] | 820 | 820
Uncompleted Purchase Orders
PLAN15 | 22066107 | 1 | Traffic Guidance Scheme | 1 | EACH | 400 | 400 | 400
PLAN15 | 22066107 | 2 | Traffic Guidance Scheme | 1 | EACH | 200 | 200 | 200
TTMC02 | 22066050 | 1 | Stage 4 Construction Services | 1 | EACH | 2500 | 2500 | 0
TTMC02 | 22066089 | 1 | Consultancy Stage 3 | 1 | EACH | 412.5 | 412.5 | 412.5
TTMC02 | 22066089 | 2 | Stage 4 | 1 | EACH | 3000 | 3000 | 1430
Sum: | [6 empty] | 6512.5 | 2442.5
Total for Cost Centre | [6 empty] | 7332.5 | 3262.5
D1WF | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
O&MM01 | 22066184 | 1 | Hand Over Manuals | 1 | EACH | 13300 | 13300 | 0
WEBF03 | 22066008 | 1 | WEBFM upfront Fee | 1 | SUM | 24875 | 24875 | 24875
Sum: | [6 empty] | 38175 | 24875
Total for Cost Centre | [6 empty] | 38175 | 24875
D1WM | CT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
UNIV16 | 22066053 | 2 | Stage 4 Construction Services | 1 | EACH | 500 | 500 | 400
Sum: | [6 empty] | 500 | 400
Total for Cost Centre | [6 empty] | 500 | 400
P01BG | PF |  | Bank Gaurantee Fees
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 2 | BG 2.5% for DLP | 1 | ITEM | 28000 | 28000
Total Forecasts | [6 empty] | 28000
Total for Cost Centre | [6 empty] | 28000
P01CW | PF
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
AJGA01 | INSALL23 | 222 | 22066 ROCKPOOL PELICAN WATERS | 3426740 | % | 0.065 | 222738.1 | 154016.4
Sum: | [6 empty] | 222738.1 | 154016.4
Total for Cost Centre | [6 empty] | 222738.1 | 154016.4
P03CF | PF
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
SUNS17 | 22066164 | 1 | Lot 89 Lease | 15 | MONTH | 1896.21 | 28443.15 | 20333.61
Sum: | [6 empty] | 28443.15 | 20333.61
Total for Cost Centre | [6 empty] | 28443.15 | 20333.61
P03FE | OT |  | Fire Extinguishers
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 2 | Fire Extiguisher Replacement | 1 | ITEM | 1988.5 | 1988.5
|  | 3 | Quaterley Testing of FE | 3 | ITEMS | 1250 | 3750
Total Forecasts | [6 empty] | 5738.5
Total for Cost Centre | [6 empty] | 5738.5
P03TE | OT |  | Temporary Electricity
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
MINI01 | 22066076 | 1 | Generator Fuel | 1 | EACH | 301.28 | 301.28 | 301.28
ORIG01 | 22066192 | 1 | Temp Elec jan23 - apr23 | 1 | EACH | 1662.18 | 1662.18 | 1662.18
Sum: | [6 empty] | 1963.46 | 1963.46
Subcontracts
MONT02 | 22066009 | 25 | VI:Temporary Electricity | 0 |  | 0 | 2200 | 2200
Total Subcontracts | [6 empty] | 2200 | 2200
Forecast Amounts
|  | 6 | Temp Power - May-Aug | 1 | NO | 5200 | 5200
|  | 7 | Temp Power - Aug-Nov | 1 | ITEM | 6740 | 6740
|  | 8 | Temporary Elect Protection | 1 | ITEM | 2200 | 2200
Total Forecasts | [6 empty] | 14140
Total for Cost Centre | [6 empty] | 18303.46 | 4163.46
P04DI | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
SERS01 | 22066079 | 1 | Dilap | 1 | EACH | 1200 | 1200 | 1200
Sum: | [6 empty] | 1200 | 1200
Total for Cost Centre | [6 empty] | 1200 | 1200
P04TF | XP |  | Temporary Fencing
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
ATFS01 | 22066007 | 1 | Mesh Temp Fencing | 150 | LM | 18 | 2700 | 2700
ATFS01 | 22066007 | 3 | Mesh Fencing Bracing | 25 | EACH | 45 | 1125 | 1125
ATFS01 | 22066007 | 4 | Pedestrian Gate | 3 | EACH | 120 | 360 | 360
ATFS01 | 22066007 | 6 | Transport | 5 | EACH | 100 | 500 | 500
Sum: | [6 empty] | 4685 | 4685
Uncompleted Purchase Orders
ATFS01 | 22066007 | 2 | Solid Hoarding | 220 | LM | 50 | 11000 | 9387
ATFS01 | 22066007 | 5 | Gate wheels | 4 | EACH | 25 | 100 | 0
ATFS01 | 22066007 | 7 | Day Labour to fix fallen fencing | 1 | EACH | 140 | 140 | 140
Sum: | [6 empty] | 11240 | 9527
Forecast Amounts
|  | 2 | 4wks Add Hire (OCT23) | 4 | WKS | 450 | 1800
Total Forecasts | [6 empty] | 1800
Total for Cost Centre | [6 empty] | 17725 | 14212
P04TR | MT |  | Temporary Roads
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 2 | Reinstatement of Kerbs, | 1 | NO | 5000 | 5000
Total Forecasts | [6 empty] | 5000
Total for Cost Centre | [6 empty] | 5000
P04TS | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
BUNN01 | 22066027 | 1 | Misc | 1 | EACH | 100 | 100 | 76.65
SITE04 | 22066017 | 1 | Site Signs - SItemax | 1 | SUM | 227.1 | 227.1 | 227.1
SITE04 | 22066017 | 5 | Site Signs - SItemax | 1 | EACH | 150.8 | 150.8 | 150.8
SITE04 | 22066047 | 1 | McNab/ Rockpool Banner | 1 | EACH | 3890.2 | 3890.2 | 3890.2
SITE04 | 22066047 | 2 | McNab/ Rockpool Banner holes | 1 | EACH | 385 | 385 | 385
SITE04 | 22066047 | 3 | Scaffold Banner Mesh | 1 | EACH | 827.6 | 827.6 | 827.6
TRAD08 | 22066018 | 1 | Site Signs | 1 | EACH | 1658.02 | 1658.02 | 1658.02
TRAD08 | 22066026 | 1 | Site Signs | 1 | EACH | 1481.53 | 1481.53 | 1421.75
TRAD08 | 22066043 | 1 | Traffic Sign Covers | 1 | EACH | 823.31 | 823.31 | 823.31
TRAD08 | 22066063 | 2 | Misc Site Items | 1 | EACH | 120.65 | 120.65 | 120.65
TRAD08 | 22066063 | 3 | Site Signs | 1 | EACH | 123.6 | 123.6 | 123.6
TRAD08 | 22066063 | 4 | Site signs | 1 | EACH | 183.01 | 183.01 | 183.01
TRAD08 | 22066063 | 5 | Site Diagram Sign | 1 | EACH | 378.81 | 378.81 | 378.81
Sum: | [6 empty] | 10349.63 | 10266.5
Total for Cost Centre | [6 empty] | 10349.63 | 10266.5
P05 | LW
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
PHIL04 |  |  | GEORGE PHILLIPS | 29 |  |  | 1476.48 | 1476.48
PIPE01 |  |  | GRANT PIPER | 10 |  |  | 497.22 | 497.22
SMIT09 |  |  | DANIEL JON SMITH | 15.12 |  |  | 575.85 | 575.85
SMIT10 |  |  | HARRISON WILLIAM PHILLIP SMITH | 9.75 |  |  | 426.43 | 426.43
Sum: | [6 empty] | 2975.98 | 2975.98
Total for Cost Centre | [6 empty] | 2975.98 | 2975.98
P05OS | MT |  | Office Sheds & Furnishings
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
AUSC05 | 22066006 | 18 | Waste Tank Hire | 6.5 | MONTH | 536 | 3219.15 | 3219.15
BUNN01 | 22066062 | 1 | Kitchen Bench : Quote 312720989 | 1.2 | EACH | 384.92 | 431.77 | 431.77
BYLI01 | 22066145 | 1 | Final Pump out | 1 | EACH | 325 | 325 | 325
GLOB33 | 22066074 | 1 | Ablution Block Pump out | 10 | EACH | 265 | 2650 | 2650
KENN01 | 22066031 | 1 | Portaloo Hire | 5.3 | WEEK | 25.45 | 134.87 | 134.87
MANS01 | 22066010 | 2 | Last Shed pathway | 3.6 | M3 | 154 | 554.4 | 554.4
PETT01 | 21ADR007 | 834 | HYAMS M - CIL PRECOMMENCEMENT MEETING | 1 | EACH | 63.73 | 63.73 | 63.73
UNIV25 | 22066024 | 1 | 25t Franna | 5.76 | HR | 175.5 | 1009.13 | 1009.13
UNIV25 | 22066024 | 2 | Rigger/ Dogman | 5.75 | HR | 80 | 460 | 460
Sum: | [6 empty] | 8848.05 | 8848.05
Uncompleted Purchase Orders
ABPA01 | 22066021 | 1 | Programme White Board | 2 | ITEM | 705 | 1410 | 1410
AUSC05 | 22066006 | 1 | 12x9m Office Shed | 66 | WEEKS | 493.95 | 32600.7 | 24015.55
AUSC05 | 22066006 | 2 | 12x3m Lunch Room 1 | 68 | WEEKS | 148.09 | 10070.12 | 7539.28
AUSC05 | 22066006 | 3 | 12x3m Lunch Room 2 | 61 | WEEKS | 148.09 | 9033.49 | 6450
AUSC05 | 22066006 | 4 | 12x3m Lunch Room 3 | 61 | WEEKS | 148.09 | 9033.49 | 6450
AUSC05 | 22066006 | 5 | 12x3m Lunch Room 4 | 61 | WEEKS | 148.09 | 9033.49 | 6450
AUSC05 | 22066006 | 6 | 6x3m First Aid | 66 | WEEKS | 172.2 | 11365.2 | 8496
AUSC05 | 22066006 | 7 | 6x3m Ablution Block | 66 | WEEKS | 156.13 | 10304.58 | 7704.18
AUSC05 | 22066006 | 8 | Retrofit 12x9m office | 1 | ITEM | 3520 | 3520 | 3520
AUSC05 | 22066006 | 9 | Delivery 12x3m loads | 14 | EACH | 1375 | 19250 | 8995
AUSC05 | 22066006 | 10 | Delivery/ Pick up 6x3m loads | 4 | EACH | 630 | 2520 | 1260
AUSC05 | 22066006 | 11 | Install of 12x9 office | 1 | ITEM | 8335 | 8335 | 8335
AUSC05 | 22066006 | 12 | Tie downs w/ certification | 1 | EACH | 1875 | 1875 | 1875
AUSC05 | 22066006 | 13 | Stairs w/ Landings | 1 | EACH | 1835 | 1835 | 1835
AUSC05 | 22066006 | 14 | dismantle 12x9m office | 1 | ITEM | 5500 | 5500 | 0
AUSC05 | 22066006 | 15 | Cleaning Fee | 1 | ITEM | 1342 | 1342 | 0
AUSC05 | 22066006 | 16 | Environment Levy | 1 | EACH | 5.35 | 5.35 | 5.35
AUSC05 | 22066006 | 17 | environmental Levy | 1 | EACH | 4.27 | 4.27 | 4.27
AUSC05 | 22066006 | 19 | Waste Tank Delievry | 2 | EACH | 630 | 1260 | 630
AUSC05 | 22066006 | 20 | environmental levy | 1 | EACH | 7.75 | 7.75 | 7.75
AUSC05 | 22066006 | 21 | environmental levy | 4.75 | EACH | 200 | 950 | 822.16
BIZF02 | 22066015 | 1 | Corner desks (1800x1800) | 7 | EACH | 401.955 | 2813.69 | 0
BIZF02 | 22066015 | 2 | Mobile pedestal Drawers | 7 | EACH | 190 | 1330 | 0
BIZF02 | 22066015 | 3 | delivery/ Assembly | 1 | EACH | 590.9091 | 590.91 | 0
BIZF02 | 22066015 | 4 | Cancellation Fee | 1 | EACH | 473.45 | 473.45 | 473.45
BUNN01 | 22066009 | 2 | Material Setup Site | 1 | EACH | 593.41 | 593.41 | 593.41
BUNN01 | 22066009 | 3 | Office IT set up | 1 | EACH | 777.76 | 777.76 | 777.76
BUNN01 | 22066013 | 1 | Site Set Up | 1 | EACH | 500 | 500 | 350.35
EZYP01 | 22066064 | 1 | Time lapse camera Pole | 1 | EACH | 2252 | 2252 | 2252
GLOB33 | 22066074 | 2 | Ablution Block Pump out - 6000 tank rate | 5 | EACH | 370 | 1850 | 1850
KENN01 | 22066031 | 2 | Pump out | 3 | EACH | 59.09 | 177.27 | 177.27
KENN01 | 22066031 | 3 | delivery | 5 | EACH | 45 | 225 | 225
KENN01 | 22066031 | 4 | Portaloo Hire (Freshwater Skid) | 12 | EACH | 29.55 | 354.6 | 354.57
KENN01 | 22066031 | 5 | Pump out (Freshwater Skid) | 6 | EACH | 154.55 | 927.3 | 927.3
KENN01 | 22066031 | 8 | L4 Portaloo Hire | 20.1 | WEEK | 28.36 | 570.04 | 567.24
KENN01 | 22066031 | 9 | Portaloo Hire | 1 | EACH | 110 | 110 | 110
KENN01 | 22066031 | 10 | Portaloo Hire | 1 | EACH | 113.45 | 113.45 | 0
KENN01 | 22066031 | 11 | Portaloo Hire | 1 | EACH | 73.36 | 73.36 | 0
KENN01 | 22066033 | 1 | Franna Ground Mat Hire | 1 | EACH | 217.64 | 217.64 | 217.64
KENN01 | 22066058 | 1 | Generator Hire | 3 | EACH | 969.09 | 2907.27 | 2907.27
KENN01 | 22066058 | 2 | generator trailer | 3 | EACH | 181.82 | 545.46 | 545.46
KENN01 | 22066058 | 3 | delivery | 1 | EACH | 45 | 45 | 45
KENN01 | 22066058 | 4 | Fuel | 1.148 | EACH | 880.91 | 1011.28 | 1010.55
KLEE03 | 22066014 | 1 | Ice machine hire | 12 | MONTH | 150 | 1800 | 1650
KLEE03 | 22066014 | 2 | delivery | 2 | EACH | 120 | 240 | 120
MCNA10 | 22066030 | 1 | Water Tank hire 5000L | 64 | WEEK | 30 | 1920 | 1320
MCNA10 | 22066030 | 36 | Portaloo Sewer Connect - Level 2 | 32 | WEEKS | 36 | 1152 | 828
MILA02 | 22066028 | 1 | Water Supply | 12 | EACH | 240 | 2880 | 2160
PETT01 | 21ADR007 | 868 | HYAMS M -ADBRI MCNAB ACCOUNT; LIGHTWEIGHT PALLET | 1 | EACH | 232.77 | 232.77 | 232.77
PETT01 | 21ADR007 | 1627 | LOWE A - CLIENT PCG MEETING | 1 | EACH | 13.6 | 13.6 | 13.6
PETT01 | 21ADR007 | 1628 | LOWE A - CLIENT PCG MEETING | 1 | EACH | 102.05 | 102.05 | 102.05
TRAD08 | 22066063 | 33 | TOilet Paper | 1 | EACH | 220.99 | 220.99 | 0
Sum: | [6 empty] | 166275.74 | 115615.23
Forecast Amounts
|  | 4 | Portaloos on Level 4 | 17 | WEEKS | 36 | 612
Total Forecasts | [6 empty] | 612
Total for Cost Centre | [6 empty] | 175735.79 | 124463.28
P05SC | MT |  | Site Communications
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
UVSG01 | 22066186 | 1 | Site Security - Mon-Fri - 19th | 50 | HRS | 45 | 2250 | 2250
UVSG01 | 22066186 | 2 | Site Security Mon-Fri - 26th | 50 | HRS | 45 | 2250 | 2250
UVSG01 | 22066186 | 3 | Site Security Mon-Fri - 2nd | 50 | HRS | 45 | 2250 | 2250
UVSG01 | 22066186 | 4 | Site Security Mon-Fri - 9th | 50 | HRS | 45 | 2250 | 2250
UVSG01 | 22066186 | 5 | Site Security Sat-Sun 14th | 34 | HRS | 45 | 1530 | 1530
UVSG01 | 22066186 | 6 | Site Security Sat-Sun 21st | 34 | HRS | 45 | 1530 | 1530
Sum: | [6 empty] | 12060 | 12060
Uncompleted Purchase Orders
INSI08 | 22066042 | 3 | Site Security Cams - Add ons | 1 | EACH | 3729.2 | 3729.2 | 3729.2
INSI08 | 22066042 | 4 | Monitoring | 12 | EACH | 60 | 720 | 720
INSI08 | 22066042 | 5 | Call out fee | 1 | EACH | 354 | 354 | 354
INSI08 | 22066042 | 6 | Call out Fee | 1 | EACH | 186 | 186 | 186
INSI08 | 22066042 | 7 | Call out fee | 1 | EACH | 90 | 90 | 90
KYOC01 | 21095079 | 12 | Kyocera Copier Oct22 | 1 | EACH | 110 | 110 | 110
KYOC01 | 21095089 | 12 | COPIER NOV 22 CHARGES | 1 | EACH | 110 | 110 | 110
KYOC01 | 21106362 | 18 | 22066 - Rockpool Pelican Waters | 1 | EACH | 90 | 90 | 90
KYOC01 | 21ISS096 | 10 | W2X8502776 - AUGUST 22 | 1 | EACH | 93.05 | 93.05 | 93.05
KYOC01 | 21ISS096 | 36 | W2X8502776 - SEPT 22 | 1 | EACH | 95.44 | 95.44 | 95.44
KYOC01 | 21ISS096 | 67 | W2X8502776 - OCT 22 | 1 | EACH | 129.52 | 129.52 | 129.52
KYOC01 | 21ISS096 | 97 | W2X8502776 - NOV 22 | 1 | EACH | 141.56 | 141.56 | 141.56
KYOC01 | 21ISS096 | 131 | RVQ2705279 - NOV 22 - COPIER MAINTENANCE | 1 | EACH | 0.13 | 0.13 | 0.13
KYOC01 | 21ISS096 | 187 | RVQ2705279 - DEC 22 - COPIER MAINTENANCE | 1 | EACH | 77.24 | 77.24 | 77.24
KYOC01 | 21ISS096 | 193 | W2X8502776 - DEC 22 - COPIER MAINTENANCE | 1 | EACH | 87.11 | 87.11 | 87.11
KYOC01 | 21ISS096 | 201 | RVQ2705279 - JAN 23 - COPIER MAINTENANCE | 1 | EACH | 30.9 | 30.9 | 30.9
KYOC01 | 21ISS096 | 234 | RVQ2705279 - FEB 23 - COPIER MAINTENANCE | 1 | EACH | 64.38 | 64.38 | 64.38
KYOC01 | 21ISS096 | 267 | RVQ2705279 - MAR 23 - COPIER MAINTENANCE | 1 | EACH | 57.37 | 57.37 | 57.37
KYOC01 | 21ISS096 | 303 | RVQ2705279 - APR 23 - COPIER MAINTENANCE | 1 | EACH | 36.63 | 36.63 | 36.63
KYOC01 | 21ISS096 | 332 | RVQ2705279 - MAY 23 - COPIER MAINTENANCE | 1 | EACH | 72.58 | 72.58 | 72.58
OPTU01 | 18041AAU | 35 | TELEPHONE EXPENSES JULY 22 | 1 | EACH | 18.06 | 18.06 | 18.06
OPTU01 | 18216363 | 12 | OPTUS INVOICES AUG 22 | 1 | EACH | 64.16 | 64.16 | 64.16
OPTU01 | 18216363 | 13 | OPTUS INVOICES AUG 22 | 1 | EACH | 27.27 | 27.27 | 27.27
OPTU01 | 18216363 | 31 | OPTUS INVOICES AUG 22 | 1 | EACH | 32.6 | 32.6 | 32.6
OPTU01 | 19175119 | 32 | OPTUS TELEPHONE INVOICE SEPT22 | 1 | EACH | 24.54 | 24.54 | 24.54
OPTU01 | 20036013 | 28 | OPTUS 07.09 - 06.10 | 1 | EACH | 24.54 | 24.54 | 24.54
OPTU01 | 20036013 | 32 | OPTUS 07.09 - 06.10 | 1 | EACH | 55.45 | 55.45 | 55.45
OPTU01 | 21047222 | 22 | OPTUS PHONE CHARGES DEC 22 | 1 | EACH | 24.54 | 24.54 | 24.54
OPTU01 | 21047222 | 33 | OPTUS PHONE CHARGES DEC 22 | 1 | EACH | 55.45 | 55.45 | 55.45
UVSG01 | 22066186 | 7 | Site Security Sat-Sun 28th | 34 | HRS | 45 | 1530 | 922.5
Sum: | [6 empty] | 8131.72 | 7524.22
Forecast Amounts
|  | 1 | Site comms A3 Copier, | 5 | MONTH | 500 | 2500
|  | 2 | Site Security | 3 | WEEKS | 2200 | 6600
Total Forecasts | [6 empty] | 9100
Total for Cost Centre | [6 empty] | 29291.72 | 19584.22
P05SS | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
INSI08 | 22066042 | 1 | Site Security Cams | 1 | EACH | 2417.2 | 2417.2 | 2417.2
INSI08 | 22066042 | 2 | Monitoring | 3 | EACH | 60 | 180 | 180
UVSG01 | 22066186 | 8 | Site Security 5/6-18/6 | 1 | EACH | 7560 | 7560 | 0
Sum: | [6 empty] | 10157.2 | 2597.2
Total for Cost Centre | [6 empty] | 10157.2 | 2597.2
P05TE | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BULK01 | 22066121 | 1 | Bulk Fuel | 1 | EACH | 1200 | 1085.12 | 1085.12
Sum: | [6 empty] | 1085.12 | 1085.12
Total for Cost Centre | [6 empty] | 1085.12 | 1085.12
P07 | IP
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
MCNA10 | 22066030 | 3 | fire extinguisher x 2 | 14.6 | WEEKS | 6 | 87.6 | 87.6
MCNA10 | 22066030 | 4 | first aid box x 2 | 15.2 | WEEKS | 30 | 456 | 456
MCNA10 | 22066030 | 7 | delivery | 1 | EACH | 110 | 110 | 110
Sum: | [6 empty] | 653.6 | 653.6
Uncompleted Purchase Orders
MCNA10 | 22066030 | 5 | 2 x water bubbler | 120 | WEEK | 30 | 3600 | 2444.53
MCNA10 | 22066030 | 6 | padlock hire x 10 | 13.7 | WEEKS | 12.5 | 171.25 | 171.25
Sum: | [6 empty] | 3771.25 | 2615.78
Total for Cost Centre | [6 empty] | 4424.85 | 3269.38
P10BC | LW |  | Building Cadet
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
FOXE01 |  |  | EBONIE FOX | 22.6 |  |  | 909.2 | 909.2
WOOL01 |  |  | JACKSON THOMAS WOOLLETT | 1375.6 |  |  | 54066.4 | 54066.4
Sum: | [6 empty] | 54975.6 | 54975.6
Forecast Amounts
|  | 14 | JUN23 | 2 | WEEKS | 1581 | 3162
|  | 15 | JUL23 | 4 | WEEKS | 1644.24 | 6576.96
|  | 16 | AUG23 | 5 | WEEKS | 1644.24 | 8221.2
|  | 17 | SEP23 | 4 | WEEKS | 1644.24 | 6576.96
|  | 22 | OCT23 | 1 | WEEKS | 1644.24 | 1644.24
Total Forecasts | [6 empty] | 26181.36
Total for Cost Centre | [6 empty] | 81156.96 | 54975.6
P10CA | LW |  | Contracts Administrator
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
CARS02 |  |  | LEVI JOHN BENJAMIN CARSBURG | 1961 |  |  | 128655.93 | 128655.93
HESL01 |  |  | TERRY GLEN HESLIN | 1373.6 |  |  | 86391.63 | 86391.63
WOOL01 |  |  | JACKSON THOMAS WOOLLETT | 212.8 |  |  | 20428.8 | 20428.8
Sum: | [6 empty] | 235476.36 | 235476.36
Forecast Amounts
|  | 47 | May - LC | 1.3 | WEEK | 3636 | 4726.8
|  | 48 | May - JW | 5 | WEEK | 3636 | 18180
|  | 49 | June - LC | 4 | WEEK | 3636 | 14544
|  | 51 | July - LC | 4 | WEEK | 3781.44 | 15125.76
|  | 53 | August - LC | 5 | WEEK | 3781.44 | 18907.2
|  | 55 | September - LC | 4 | WEEK | 3781.44 | 15125.76
|  | 57 | October - LC | 4 | WEEK | 3781.44 | 15125.76
Total Forecasts | [6 empty] | 101735.28
Total for Cost Centre | [6 empty] | 337211.64 | 235476.36
P10DM | LW
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
BELL01 |  |  | CALLUM BELL | 701.04 |  |  | 85526.88 | 85526.88
Sum: | [6 empty] | 85526.88 | 85526.88
Total for Cost Centre | [6 empty] | 85526.88 | 85526.88
P10FM | LW |  | Foreman
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
HAMA01 |  |  | ALEXANDER MICHAEL HAM | 541.05 |  |  | 46679.2 | 46679.2
MACP01 |  |  | JOSH MACPHERSON | 1771.2 |  |  | 140843.2 | 140843.2
Sum: | [6 empty] | 187522.4 | 187522.4
Forecast Amounts
|  | 25 | MAY23 - JM | 3 | WEEKS | 4189 | 12567
|  | 26 | MAY23 - FITOUT FOREMAN | 3 | WEEKS | 4189 | 12567
|  | 27 | MAY23 - FINISHES FOREMAN | 3 | WEEKS | 4189 | 12567
|  | 28 | JUN23 - FITOUT FOREMAN | 4 | WEEKS | 4189 | 16756
|  | 29 | JUN23 - FINISHES FOREMAN | 4 | WEEKS | 4189 | 16756
|  | 30 | JUL23 - FITOUT FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 31 | JUL23 - FINISHES FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 32 | AUG23 - FITOUT FOREMAN | 5 | WEEKS | 4356.56 | 21782.8
|  | 33 | AUG23 - FINISHES FOREMAN | 5 | WEEKS | 4356.56 | 21782.8
|  | 34 | SEP23 - FITOUT FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 35 | SEP23 - FINISHES FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 36 | OCT23 - FITOUT FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 37 | OCT23 - FINISHES FOREMAN | 4 | WEEKS | 4356.56 | 17426.24
|  | 42 | JUN23 - JMAC | 4 | WEEKS | 4189 | 16756
|  | 43 | JUL23 - JMAC | 4 | WEEKS | 4356.56 | 17426.24
|  | 44 | AUG23 - JMAC | 5 | WEEKS | 4356.56 | 21782.8
|  | 45 | SEP23 - JMAC | 4 | WEEKS | 4356.56 | 17426.24
|  | 46 | OCT23 - JMAC | 2 | WEEKS | 4356.56 | 8713.12
Total Forecasts | [6 empty] | 301440.44
Total for Cost Centre | [6 empty] | 488962.84 | 187522.4
P10FM | OT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
MOTO03 | 22066045 | 1 | Site Fuel Card Oct 22 | 1 | EACH | 263.42 | 263.42 | 263.42
MOTO03 | 22066140 | 1 | Site Fuel Card Oct22 (correct) | 1 | EACH | 263.42 | 263.42 | 263.42
Sum: | [6 empty] | 526.84 | 526.84
Total for Cost Centre | [6 empty] | 526.84 | 526.84
P10HS | LW |  | HSEQ Co-Ordinator
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
CLAR03 |  |  | TOBY JOHN CLARKE | 178.7 |  |  | 20288.2 | 20288.2
POWE01 |  |  | SIMON POWELL | 68.17 |  |  | 6163.86 | 6163.86
Sum: | [6 empty] | 26452.06 | 26452.06
Forecast Amounts
|  | 11 | MAY23 - 1Day/Wk | 5 | WEEKS | 798.4 | 3992
|  | 12 | JUN23 - 1Day/Wk | 4 | WEEKS | 798.4 | 3193.6
|  | 13 | JUL23 - 1Day/Wk | 4 | WEEKS | 830.336 | 3321.34
|  | 14 | AUG23 - 1Day/Wk | 5 | WEEKS | 830.336 | 4151.68
|  | 16 | SEP23 - 1Day/Wk | 4 | WEEKS | 830.336 | 3321.34
|  | 17 | OCT23 - 1Day/Wk | 4 | WEEKS | 830.336 | 3321.34
Total Forecasts | [6 empty] | 21301.3
Total for Cost Centre | [6 empty] | 47753.36 | 26452.06
P10LH | LW
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
PIPE01 |  |  | GRANT PIPER | 31.1 |  |  | 1670.38 | 1670.38
Sum: | [6 empty] | 1670.38 | 1670.38
Total for Cost Centre | [6 empty] | 1670.38 | 1670.38
P10PM | LW |  | Project Manager
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
HYAM01 |  |  | MATTHEW SEAN HYAMS | 1159.2 |  |  | 163759.2 | 163759.2
LOWE01 |  |  | ASHLEY SCOTT LOWE | 478.8 |  |  | 69745.2 | 69745.2
MART05 |  |  | LUKE THOMAS MARTIN | 30.4 |  |  | 5797.92 | 5797.92
Sum: | [6 empty] | 239302.32 | 239302.32
Forecast Amounts
|  | 13 | MAY23 | 1.3 | WEEKS | 5651 | 7346.3
|  | 14 | JUN23 | 4 | WEEKS | 5651 | 22604
|  | 15 | JUL23 | 4 | WEEKS | 5877.04 | 23508.16
|  | 16 | AUG23 | 5 | WEEKS | 5877.04 | 29385.2
|  | 17 | SEP23 | 4 | WEEKS | 5877.04 | 23508.16
|  | 18 | OCT23 | 4 | WEEKS | 5877.04 | 23508.16
Total Forecasts | [6 empty] | 129859.98
Total for Cost Centre | [6 empty] | 369162.3 | 239302.32
P10SL | LW |  | Site Labourer
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
DIMA01 |  |  | GIUSEPPE DI MAIO | 7 |  |  | 396.11 | 396.11
HEND03 |  |  | RIC JOHN HENDERSON | 1177.85 |  |  | 49711.83 | 49711.83
THORN01 |  |  | NICHOLAS THORNTON | 32 |  |  | 1302.92 | 1302.92
Sum: | [6 empty] | 51410.86 | 51410.86
Forecast Amounts
|  | 13 | JUN23 | 4 | WEEKS | 2121.6 | 8486.4
|  | 14 | JUL23 | 4 | WEEKS | 2206.464 | 8825.86
|  | 15 | AUG23 | 5 | WEEKS | 2206.464 | 11032.32
|  | 16 | SEP23 | 4 | WEEKS | 2206.464 | 8825.86
|  | 17 | OCT23 | 4 | WEEKS | 2206.464 | 8825.86
|  | 19 | Jun23 Jesse | 1 | WEEKS | 2206.46 | 2206.46
|  | 20 | Jul23 Jesse | 5 | WEEKS | 2206.46 | 11032.3
|  | 21 | Aug23 Jesse | 1 | WEEKS | 2206 | 2206
Total Forecasts | [6 empty] | 61441.06
Total for Cost Centre | [6 empty] | 112851.92 | 51410.86
P10SL | ST |  | External Labour Hire
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
RAPI20 | 22066113 | 1 | labour hire | 1 | EACH | 344.75 | 344.75 | 344.75
RAPI20 | 22066113 | 2 | labour hire | 1 | EACH | 367.2 | 367.2 | 367.2
RAPI20 | 22066113 | 3 | labour hire | 1 | EACH | 367.2 | 367.2 | 0
YORK02 | 22066029 | 1 | Site Labour | 506 | HR | 46.09 | 23321.54 | 23321.5
YORK02 | 22066029 | 2 | Travel | 82 | EACH | 24.01 | 1968.82 | 1968.38
YORK02 | 22066029 | 3 | overtime | 20.75 | HR | 57.9 | 1201.43 | 1201.25
YORK02 | 22066029 | 4 | Site Labour - Forklift | 98.25 | HR | 51.96 | 5105.07 | 5105.05
YORK02 | 22066029 | 5 | Site Labour - Forklift Overtime | 1.25 | EACH | 62.79 | 78.49 | 78.49
YORK02 | 22066029 | 6 | Overtime double time | 2 | HR | 74.44 | 148.88 | 148.83
YORK02 | 22066029 | 7 | Site Labour -Forklift Driver | 1 | EACH | 3000 | 3000 | 2726.54
YORK02 | 22066029 | 8 | Site Labour - Clean | 1 | EACH | 323.59 | 323.59 | 0
Sum: | [6 empty] | 36226.97 | 35261.99
Forecast Amounts
|  | 5 | May - Jesse | 4 | WEEKS | 1250 | 5000
|  | 6 | June - August Labour | 4 | WEEKS | 1250 | 5000
Total Forecasts | [6 empty] | 10000
Total for Cost Centre | [6 empty] | 46226.97 | 35261.99
P10SM | LW |  | Site Manager
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
WYAT01 |  |  | ADRIAN JOHN WYATT | 1475.7 |  |  | 130172.8 | 130172.8
Sum: | [6 empty] | 130172.8 | 130172.8
Forecast Amounts
|  | 13 | MAY23 | 1.5 | WEEKS | 5098 | 7647
|  | 14 | JUN23 | 4 | WEEKS | 5098 | 20392
|  | 15 | JUL23 | 4 | WEEKS | 5301.92 | 21207.68
|  | 16 | AUG23 | 5 | WEEKS | 5301.92 | 26509.6
|  | 17 | SEP23 | 4 | WEEKS | 5301.92 | 21207.68
|  | 18 | OCT23 | 4 | WEEKS | 5301.92 | 21207.68
Total Forecasts | [6 empty] | 118171.64
Total for Cost Centre | [6 empty] | 248344.44 | 130172.8
P10WH | LW |  | HSE Advisor
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
CLAR03 |  |  | TOBY JOHN CLARKE | 27.5 |  |  | 2941.2 | 2941.2
GUES01 |  |  | CLINTON DAVID GUEST | 1659.8 |  |  | 106349.4 | 106349.4
MOSE02 |  |  | RICHARD MURRAY MOSES | 4 |  |  | 461.82 | 461.82
Sum: | [6 empty] | 109752.42 | 109752.42
Forecast Amounts
|  | 11 | MAY23 | 1.3 | WEEKS | 3636 | 4726.8
|  | 12 | JUN23 | 4 | WEEKS | 3636 | 14544
|  | 13 | JUL23 | 4 | WEEKS | 3781.44 | 15125.76
|  | 14 | AUG23 | 5 | WEEKS | 3781.44 | 18907.2
|  | 15 | SEP23 | 4 | WEEKS | 3781.44 | 15125.76
|  | 16 | OCT23 | 4 | WEEKS | 3781.44 | 15125.76
Total Forecasts | [6 empty] | 83555.28
Total for Cost Centre | [6 empty] | 193307.7 | 109752.42
P11AC | OT |  | Staff Accommodation
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CBAM01 | 22066169 | 5 | Ash accomodation | 1 | EACH | 192.85 | 192.85 | 192.85
CBAP01 | 21070012 | 12 | EnPerSo - Ashley Lowe Accom | 1 | EACH | 263.12 | 263.12 | 263.12
CBAP01 | 21070012 | 13 | Pelican Waters - Ashley Lowe Accom | 1 | EACH | 219.15 | 219.15 | 219.15
CBAP01 | 21224328 | 10 | PAD Pelican Waters - Ashley Lowe Accom | 1 | EACH | 290.33 | 290.33 | 290.33
CBAP01 | 21224328 | 36 | EnPerSo - Ashley Lowe Accom we Accom | 1 | EACH | 278.21 | 278.21 | 278.21
CBAP01 | 21224328 | 49 | PAD Pelican Waters - Ashley Lowe Accom | 1 | EACH | 263.35 | 263.35 | 263.35
CBAP01 | 21TRA025 | 38 | PAD Pelican Waters - Ashley Lowe Accom | 1 | EACH | 219.15 | 219.15 | 219.15
CBAP01 | 21TRA029 | 11 | Pelican Waters - Ashley Lowe Accom | 1 | EACH | 204.1 | 204.1 | 204.1
CBAP01 | 21TRA029 | 14 | EnPerSo/Pelican Waters - Ashley Lowe Accom | 1 | EACH | 358.61 | 358.61 | 358.61
CBAP01 | 21TRA030 | 10 | EnPerSo / Pelican Waters - Ashley Lowe Accom | 1 | EACH | 278.21 | 278.21 | 278.21
CBAP01 | 21TRA030 | 15 | EnPerSo / Pelican Waters - Ashley Lowe Accom | 1 | EACH | 207.96 | 207.96 | 207.96
CBAP01 | 21TRA030 | 26 | EnPerSo / Pelican Waters - Ashley Lowe Accom | 1 | EACH | 409.09 | 409.09 | 409.09
CBAP01 | 21TRA030 | 28 | EnPerSo / Pelican Waters - Ashley Lowe Accom | 1 | EACH | 271.82 | 271.82 | 271.82
CBAP01 | 21TRA037 | 29 | EnPerSo / Pelican Resort - Ashley Lowe Accom | 1 | EACH | 377.2 | 377.2 | 377.2
CBAP01 | 21TRA037 | 48 | EnPerSo / Pelican Resort - Ashley Lowe Accom | 1 | EACH | 85.59 | 85.59 | 85.59
Sum: | [6 empty] | 3918.74 | 3918.74
Forecast Amounts
|  | 2 | Ash Accomodation Allowance | 32 | NIGHT | 350 | 11200
Total Forecasts | [6 empty] | 11200
Total for Cost Centre | [6 empty] | 15118.74 | 3918.74
P12 | ST |  | Surveyor
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
CRUX01 | 22066006 | 1 | Site Establishment | 1 | DAY | 740 | 740 | 740
CRUX01 | 22066006 | 2 | Piling | 5 | DAY | 740 | 3700 | 3700
CRUX01 | 22066006 | 3 | Footings | 1 | DAY | 740 | 740 | 740
CRUX01 | 22066006 | 5 | Xlabs | 41 | DAY | 740 | 30340 | 30340
CRUX01 | 22066006 | 6 | External Planters | 2 | DAY | 740 | 1480 | 0
CRUX01 | 22066006 | 7 | Structural Steel | 3 | DAY | 740 | 2220 | 0
CRUX01 | 22066006 | 8 | External Areas (Driveway / | 5 | DAY | 740 | 3700 | 0
Total Subcontracts | [6 empty] | 42920 | 35520
Forecast Amounts
|  | 3 | Misc. Additional Visits | 12 | ITEM | 740 | 8880
Total Forecasts | [6 empty] | 8880
Total for Cost Centre | [6 empty] | 51800 | 35520
P13ES | XP |  | External Scaffolding Hire
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
PETT01 | 21ADR007 | 836 | HYAMS M - AR SCAFFOLD TENDER MEETING | 1 | EACH | 60.91 | 60.91 | 60.91
Sum: | [6 empty] | 60.91 | 60.91
Uncompleted Purchase Orders
BRIS76 | 22066196 | 1 | 64ft Scissor - Hoist Area Works | 1 | EACH | 50 | 50 | 0
FAZE01 | 22066174 | 1 | Guardrail Hire - 4 weeks | 4 | EACH | 1250 | 5000 | 5000
FAZE01 | 22066174 | 2 | Labour - Install and Dismantle | 250 | EACH | 30 | 7500 | 5000
FAZE01 | 22066174 | 3 | Guardrail - Transport | 2 | EACH | 750 | 1500 | 750
KENN01 | 22066039 | 2 | Soffit Acces - Ladder/ Mobile Scaff | 1 | EACH | 542.64 | 542.64 | 0
Sum: | [6 empty] | 14592.64 | 10750
Subcontracts
ARLA01 | 22066017 | 1 | Scaffold to Level 1 | 1 | NO | 86872.5 | 86872.5 | 81267.73
ARLA01 | 22066017 | 2 | Scaffold to Level 2 | 1 | NO | 60812.5 | 60812.5 | 53600.39
ARLA01 | 22066017 | 3 | Scaffold to Level 3 | 1 | NO | 51187.5 | 51187.5 | 46354.38
ARLA01 | 22066017 | 4 | Scaffold to Level 4 | 1 | NO | 45500 | 45500 | 40813.13
ARLA01 | 22066017 | 5 | Scaffold to Level 5 | 1 | NO | 39812.5 | 39812.5 | 39812.5
ARLA01 | 22066017 | 6 | Scaffold to Roof Level | 1 | NO | 35262.5 | 35262.5 | 35262.5
ARLA01 | 22066017 | 7 | Scaffold to Balcony | 1 | NO | 4980 | 4980 | 4980
ARLA01 | 22066017 | 8 | Scaffold to Stair Underside | 1 | NO | 8715 | 8715 | 8715
ARLA01 | 22066017 | 9 | Scaffold to Plant Deck | 1 | NO | 12835 | 12835 | 11560
ARLA01 | 22066017 | 10 | Handrails to Stairwells | 1 | NO | 6650 | 6650 | 5953.57
ARLA01 | 22066017 | 11 | Porte Cochere Scaffold | 1 | NO | 4620 | 4620 | 0
ARLA01 | 22066017 | 12 | Stairwell Catch Platforms x3 | 1 | NO | 14400 | 14400 | 14400
ARLA01 | 22066017 | 13 | Stairwell Catch Handrail x3 | 1 | NO | 14400 | 14400 | 14400
ARLA01 | 22066017 | 14 | Stretcher Stairs | 1 | NO | 20517.6 | 20517.6 | 20517.6
ARLA01 | 22066017 | 15 | Stretcher Stairs | 1 | NO | 20517.6 | 20517.6 | 20517.6
ARLA01 | 22066017 | 16 | Stretcher Stairs Plant Deck | 1 | NO | 2645.25 | 2645.25 | 2388
ARLA01 | 22066017 | 17 | Stretcher Stairs Plant Deck | 1 | NO | 2645.25 | 2645.25 | 2388
ARLA01 | 22066017 | 18 | 1x Access Stair | 1 | NO | 11587.2 | 11587.2 | 11520
ARLA01 | 22066017 | 19 | 1x Liftshaft Scaffold | 1 | NO | 5748 | 5748 | 5748
ARLA01 | 22066017 | 20 | Hoist Strip/Rebuild | 1 | NO | 4700 | 4700 | 1410
ARLA01 | 22066017 | 21 | Preston Open/Close 12x | 1 | NO | 9600 | 9600 | 3348
ARLA01 | 22066017 | 22 | Scaffold Bins Hire 2x | 1 | NO | 6000 | 6000 | 6000
ARLA01 | 22066017 | 23 | Scaffold Containment | 1 | NO | 23500 | 23500 | 23500
ARLA01 | 22066017 | 24 | Design & Engineering | 1 | NO | 4800 | 4800 | 4800
ARLA01 | 22066017 | 25 | VI:External Scaffolding Hire | 0 |  | 0 | 18561.3 | 18561.3
Total Subcontracts | [6 empty] | 516869.7 | 477817.7
Forecast Amounts
|  | 5 | Feb Overhire | 1 | NO | 504 | 504
|  | 6 | March Overhire | 1 | NO | 1305.3 | 1305.3
|  | 7 | April Overhire | 1 | NO | 16727.6 | 16727.6
|  | 8 | May Overhire | 1 | NO | 33556 | 33556
|  | 9 | June Overhire | 1 | NO | 10300.79 | 10300.79
|  | 10 | Edge Protection | 40 | DAYS | 200 | 8000
|  | 11 | 64' Scssior Hire | 4 | WEEKS | 2100 | 8400
|  | 12 | Scissor Pick Up/ Drop Off | 2 | ITEM | 380 | 760
Total Forecasts | [6 empty] | 79553.69
Total for Cost Centre | [6 empty] | 611076.94 | 488628.61
P14MC | XP |  | Mobile Crane Hire
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
FORK01 | 22066112 | 1 | Forklift Hire | 48 | WEEKS | 405 | 19440 | 12592.36
FORK01 | 22066112 | 2 | Slipper Hire | 48 | WKS | 25 | 1200 | 1032
FORK01 | 22066112 | 3 | Delivery/ Connection | 2 | EACH | 393.8 | 787.6 | 393.8
UNIV25 | 22066073 | 1 | 25t Franna | 21.75 | EACH | 175.5 | 3817.13 | 3797.88
UNIV25 | 22066073 | 2 | Dogman | 143.45 | EACH | 80 | 11476 | 11455
UNIV25 | 22066073 | 3 | 16T City Crane Hire | 68.75 | HRS | 171 | 11756.25 | 11756.25
UNIV25 | 22066073 | 4 | Dogman Overtime | 12 | HR | 40 | 480 | 480
UNIV25 | 22066073 | 5 | Operator Overtime | 12 | HR | 40 | 480 | 480
UNIV25 | 22066073 | 6 | 15t Franna | 27.75 | HR | 170 | 4717.5 | 4717.5
UNIV25 | 22066073 | 7 | Fuel hire | 1 | EACH | 66 | 66 | 66
UNIV25 | 22066073 | 8 | 100t - AFS Wall System | 1 | EACH | 4785 | 4785 | 4784
UNIV25 | 22066073 | 9 | 60T Slew Crane | 22.25 | HR | 234 | 5206.5 | 5206.5
UNIV25 | 22066073 | 11 | Fish Cranes Invoice | 1 | EACH | 1890 | 1890 | 1890
UNIV25 | 22066073 | 14 | Crane L5 Bins & L2 Screens | 1 | EACH | 2931.75 | 2931.75 | 0
UNIV25 | 22066073 | 15 | Crane Hoist Demob | 1 | EACH | 4207.5 | 4207.5 | 0
UNIV25 | 22066073 | 16 | Crane Generaotr Removal | 1 | EACH | 573.75 | 573.75 | 0
UNIV25 | 22066073 | 17 | Crane Screen Lift & Yard move | 1 | EACH | 1590 | 1590 | 0
Sum: | [6 empty] | 75404.98 | 58651.29
Forecast Amounts
|  | 3 | Removal of Site Shed | 1 | ITEM | 2440 | 2440
|  | 5 | Containers Lifted Over ATF | 1 | ITEM | 2500 | 2500
|  | 6 | Misc Crane items | 1 | ITEM | 1000 | 1000
Total Forecasts | [6 empty] | 5940
Total for Cost Centre | [6 empty] | 81344.98 | 58651.29
P14TC | ST |  | Cranes, Gantries & Hoists
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
ALLA15 | 22066100 | 2 | Slings | 1 | EACH | 180 | 180 | 180
COAT01 | 22066180 | 1 | Titan Props | 30 | DAYS | 40.8 | 1224 | 693.6
COAT01 | 22066180 | 2 | delivery/ pick up | 2 | EACH | 275 | 550 | 275
UNIV25 | 22066073 | 10 | Tower Crane Down - Replacement 60T Slew | 1 | EACH | 1570 | 1570 | 1570
UNIV25 | 22066073 | 12 | Mobile Crane Hire | 1 | EACH | 680 | 680 | 680
UNIV25 | 22066073 | 13 | Mobile Crane Hire - Tower Crane not working | 1 | EACH | 5087 | 5087 | 5087
WORK11 | 22066150 | 1 | Hoist Labour | 48 | HRS | 49.17 | 2360.16 | 2360.16
WORK11 | 22066150 | 2 | Travel | 6 | EACH | 23.55 | 141.3 | 141.3
Sum: | [6 empty] | 11792.46 | 10987.06
Subcontracts
ACTI02 | 22066012 | 1 | Crane Base | 1 | ITEM | 7300 | 7300 | 7300
ACTI02 | 22066012 | 2 | Crane Hire | 29 | WEEKS | 1500 | 43500 | 43500
ACTI02 | 22066012 | 3 | Crane Errection | 1 | ITEM | 19000 | 19000 | 19000
ACTI02 | 22066012 | 4 | Crane Dismantle | 1 | ITEM | 19000 | 19000 | 0
ACTI02 | 22066012 | 5 | Crane Insurance | 30 | WEEKS | 50 | 1500 | 1500
ACTI02 | 22066012 | 6 | Loading Bay Hire | 58 | WEEKS | 130 | 7540 | 7440
ACTI02 | 22066012 | 7 | Loading Bay Erect / Dismantle | 18 | ITEM | 250 | 4500 | 0
ACTI02 | 22066012 | 8 | Loading Bay Transport | 12 | ITEM | 250 | 3000 | 0
ACTI02 | 22066012 | 9 | VI:Cranes, Gantries & Hoists | 0 |  | 0 | 2800 | 2800
ASPI03 | 22066013 | 1 | Operator - NT | 1500 | HOURS | 62.5 | 93750 | 93750
ASPI03 | 22066013 | 2 | Dogman - NT | 3000 | HOURS | 57.5 | 172500 | 139757.69
ASPI03 | 22066013 | 3 | Operator - OT | 240 | HOURS | 80 | 19200 | 12880
ASPI03 | 22066013 | 4 | Dogman - OT | 480 | HOURS | 75 | 36000 | 11137.5
ASPI03 | 22066013 | 5 | Hoist Driver - NT | 950 | HOURS | 57.5 | 54625 | 44100.7
ASPI03 | 22066013 | 6 | Hoist Driver - OT | 152 | HOURS | 75 | 11400 | 3412.5
ASPI03 | 22066013 | 7 | VI:Cranes, Gantries & Hoists | 0 |  | 0 | 1596 | 1596
ELEC25 | 22066042 | 1 | Hoist Hire | 19 | WEEKS | 1250 | 23750 | 23571.42
ELEC25 | 22066042 | 2 | Hoist Base Design | 1 | ITEM | 3950 | 3950 | 3950
ELEC25 | 22066042 | 3 | Hoist Transport | 1 | ITEM | 2800 | 2800 | 1400
ELEC25 | 22066042 | 4 | Hoist Erection | 1 | ITEM | 11600 | 11600 | 11600
ELEC25 | 22066042 | 5 | Hoist Dismantle | 1 | ITEM | 9130 | 9130 | 0
ELEC25 | 22066042 | 6 | Progressive Climb | 1 | ITEM | 4400 | 4400 | 2200
ELEC25 | 22066042 | 7 | Maintenance & Insurance | 19 | WEEKS | 120 | 2280 | 2262.86
ELEC25 | 22066042 | 8 | VI:Cranes, Gantries & Hoists | 0 |  | 0 | 2190 | 2190
Total Subcontracts | [6 empty] | 557311 | 435348.67
Forecast Amounts
|  | 4 | Additional Crane Hire | 3 | WEEKS | 1750 | 5250
|  | 6 | Additional Hoist Hire | 3 | WEEKS | 1370 | 4110
|  | 11 | Props (each lvl GF-5) | 20 | WEEKS | 15 | 300
|  | 12 | Additional Crane Labour | 2 | WEEKS | 3800 | 7600
Total Forecasts | [6 empty] | 17260
Total for Cost Centre | [6 empty] | 586363.46 | 446335.73
P15 | ST |  | Cleaning
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
DREW01 | 22066035 | 1 | Site Cleaning | 18 | HR | 35 | 630 | 630
OZON01 | 22066092 | 1 | Site Cleaning | 6 | HR | 50 | 300 | 300
Sum: | [6 empty] | 930 | 930
Forecast Amounts
|  | 13 | Monhtly cleaning - Oct | 1 | ITEM | 5000 | 5000
|  | 14 | Monthly Cleaning - Nov | 1 | ITEM | 5000 | 5000
|  | 15 | Additional Cleaning Visits - | 1 | ITEM | 4500 | 4500
|  | 16 | Cleaning Site Temps | 1 | ITEM | 2500 | 2500
Total Forecasts | [6 empty] | 17000
Total for Cost Centre | [6 empty] | 17930 | 930
P15 | XP |  | Bin Hire
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
WHAL01 | 22066034 | 1 | 6m3 Bin | 5 | EACH | 530.4 | 2652 | 2652
WHAL01 | 22066034 | 2 | 10m3 Hook Bin | 3 | EACH | 700 | 2100 | 2100
WHAL01 | 22066034 | 3 | Crane Bin | 6 | EACH | 150 | 900 | 900
WHAL01 | 22066034 | 4 | 15m3 Hook Bin | 74 | EACH | 1200 | 88800 | 88800
WHAL01 | 22066034 | 5 | 10m3 Hook Bin | 1 | EACH | 819.94 | 819.94 | 819.94
WHAL01 | 22066034 | 6 | General Waste Bins x 2 | 9 | EACH | 67.5 | 607.5 | 607.5
WHAL01 | 22066034 | 7 | General Waste Bins (updated rate) | 10 | EACH | 87.66 | 876.6 | 876.6
WHAL01 | 22066034 | 8 | Whale Bins Hire = March last week | 1 | EACH | 4800 | 4800 | 4800
WHAL01 | 22066034 | 9 | Whale Bins Hire = March last week | 1 | EACH | 1200 | 1200 | 1200
WHAL01 | 22066034 | 10 | 7 x 15m Hook Bins | 7 | ITEM | 1200 | 8400 | 8400
WHAL01 | 22066034 | 11 | 1 x 15m Bin | 1 | EACH | 1200 | 1200 | 0
WHAL01 | 22066034 | 12 | 3 x 15m Hook Bin | 3 | EACH | 1200 | 3600 | 0
WHAL01 | 22066034 | 13 | 3 x 15m hook bin | 3 | ITEM | 1200 | 3600 | 0
Sum: | [6 empty] | 119556.04 | 111156.04
Forecast Amounts
|  | 9 | June | 1 | ITEM | 21721.74 | 21721.74
|  | 10 | July | 1 | ITEM | 12444.22 | 12444.22
|  | 11 | August | 1 | ITEM | 10847.32 | 10847.32
|  | 12 | September | 1 | ITEM | 7001.65 | 7001.65
|  | 13 | October | 1 | ITEM | 2645.41 | 2645.41
Total Forecasts | [6 empty] | 54660.34
Total for Cost Centre | [6 empty] | 174216.38 | 111156.04
P15FC | ST |  | Final Clean
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
OZON01 | 22066045 | 1 | External Glazing, | 1 | NO | 10900 | 10900 | 9904.55
OZON01 | 22066045 | 2 | Initial Clean & Final Clean | 150 | NO | 400 | 60000 | 0
OZON01 | 22066045 | 3 | Ground Floor Common Areas | 1 | NO | 11000 | 11000 | 0
OZON01 | 22066045 | 4 | Stairs & Fire Doors | 1 | NO | 800 | 800 | 405
OZON01 | 22066045 | 5 | Carpark & Walkways | 1 | NO | 2900 | 2900 | 0
OZON01 | 22066045 | 6 | Sparkle Clean | 1 | NO | 13500 | 13500 | 0
OZON01 | 22066045 | 7 | Materials & Admin | 1 | NO | 1800 | 1800 | 0
Total Subcontracts | [6 empty] | 100900 | 10309.55
Forecast Amounts
|  | 2 | Re-Clean Areas | 120 | HRS | 50 | 6000
Total Forecasts | [6 empty] | 6000
Total for Cost Centre | [6 empty] | 106900 | 10309.55
P99 | ST |  | Preliminary Contingency
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 1 | Prelim Contingency | 1 | NO | 40000 | 40000
Total Forecasts | [6 empty] | 40000
Total for Cost Centre | [6 empty] | 40000
PO2GO | CT |  | Geotechnical Consultant
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
DOUG01 | 22066075 | 1 | Mobile Crane Pad | 1 | EACH | 450 | 450 | 450
Sum: | [6 empty] | 450 | 450
Forecast Amounts
|  | 1 | Proof Roll Inspections of | 1 | ITEM | 2050 | 2050
Total Forecasts | [6 empty] | 2050
Total for Cost Centre | [6 empty] | 2500 | 450
PO3TS | OT |  | Temporary Sewer & Water Connec
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 6 | Disconnection | 1 | NO | 1200 | 1200
|  | 8 | Consumption Chagres - Nov - | 1 | ITEM | 4000 | 4000
|  | 9 | Consumption Charges - Feb - | 1 | ITEM | 4000 | 4000
|  | 10 | Consumption Charges May - Sep | 1 | ITEM | 4000 | 4000
|  | 11 | Consumption Charges Oct-Nov | 1 | ITEM | 3000 | 3000
Total Forecasts | [6 empty] | 16200
Total for Cost Centre | [6 empty] | 16200
PO4SE | MT |  | Site Expenses
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
TRAD08 | 22066063 | 1 | Misc Site Items | 1 | EACH | 867.34 | 867.34 | 867.34
TRAD08 | 22066063 | 6 | Consumables | 1 | EACH | 647.85 | 96.6 | 96.6
Sum: | [6 empty] | 963.94 | 963.94
Uncompleted Purchase Orders
BARR10 | 22066037 | 1 | Misc | 1 | EACH | 1362.3 | 1362.3 | 1362.3
BARR10 | 22066037 | 2 | GST free | 1 | EACH | 27.95 | 27.95 | 27.95
BARR10 | 22066038 | 1 | Misc | 1 | EACH | 363.95 | 363.95 | 363.95
BUNN01 | 22066019 | 1 | Site Set up Items | 1 | EACH | 547.35 | 547.35 | 497.26
BUNN01 | 22066022 | 1 | Misc items | 1 | EACH | 156.6 | 156.6 | 156.6
CBAM01 | 21ADS077 | 14 | Green Zebra - Rockpool Team Dinner (MP, LC, JW, TH, MH, RK, | 1 | EACH | 1536.82 | 1536.82 | 1536.82
CBAM01 | 22066068 | 1 | August Credit Card | 1 | EACH | 629.36 | 629.36 | 629.36
CBAM01 | 22066086 | 1 | Team Lunch | 1 | EACH | 95.55 | 95.55 | 95.55
CBAM01 | 22066091 | 1 | Matt H Master Card Sept | 1 | EACH | 986.36 | 986.36 | 986.36
CBAM01 | 22066099 | 1 | Matt Green CC - Sep | 1 | EACH | 104.73 | 104.73 | 104.73
CBAM01 | 22066114 | 1 | Matt H - October | 1 | EACH | 489.24 | 489.24 | 489.24
CBAM01 | 22066115 | 1 | Pelican Waters -22066 | 1 | EACH | 306.45 | 306.45 | 306.45
CBAM01 | 22066135 | 1 | December invoices | 1 | EACH | 2276.51 | 2276.51 | 2276.51
CBAM01 | 22066135 | 2 | December invoices - Market Bistro | 1 | EACH | 506.75 | 506.75 | 506.75
CBAM01 | 22066144 | 1 | UNITYWATER - MAROOCH | 1 | EACH | 327.27 | 327.27 | 327.27
CBAM01 | 22066144 | 2 | SQ *THE PASTRY LAB | 1 | EACH | 34.55 | 34.55 | 34.55
CBAM01 | 22066144 | 3 | WOOLWORTHS 2854 | 1 | EACH | 5.23 | 5.23 | 5.23
CBAM01 | 22066144 | 4 | BEAN THERE DONE THAT | 1 | EACH | 9.73 | 9.73 | 9.73
CBAM01 | 22066144 | 5 | GYG CALOUNDRA | 1 | EACH | 73.09 | 73.09 | 73.09
CBAM01 | 22066144 | 6 | PRIMIVO GROUP | 1 | EACH | 252.73 | 252.73 | 252.73
CBAM01 | 22066144 | 7 | PUMA ENERGY PELICAN | 1 | EACH | 114.32 | 114.32 | 114.32
CBAM01 | 22066144 | 8 | WOOLWORTHS 2854 | 1 | EACH | 16.45 | 16.45 | 16.45
CBAM01 | 22066144 | 9 | BWS 2359 | 1 | EACH | 54.55 | 54.55 | 54.55
CBAM01 | 22066144 | 10 | SQ *THE PASTRY LAB | 1 | EACH | 33.64 | 33.64 | 33.64
CBAM01 | 22066144 | 11 | SECURE PARKING - 10 | 1 | EACH | 34.41 | 34.41 | 34.41
CBAM01 | 22066144 | 12 | SECURE PARKING - 10 | 1 | EACH | 34.41 | 34.41 | 34.41
CBAM01 | 22066144 | 13 | COLES 4559 | 1 | EACH | 12.09 | 12.09 | 12.09
CBAM01 | 22066144 | 14 | BEAN THERE DONE THAT | 1 | EACH | 72.73 | 72.73 | 72.73
CBAM01 | 22066144 | 15 | SP SYDNEY TRENDSHOP | 1 | EACH | 85.44 | 85.44 | 85.44
CBAM01 | 22066144 | 16 | BWS 2358 | 1 | EACH | 245.45 | 245.45 | 245.45
CBAM01 | 22066144 | 17 | BEAN THERE DONE THAT | 1 | EACH | 57.27 | 57.27 | 57.27
CBAM01 | 22066144 | 18 | SP SYDNEY TRENDSHOP | -1 | EACH | 85.44 | -85.44 | -85.44
CBAM01 | 22066144 | 19 | Esther Bundellu | 1 | EACH | 48.98 | 48.98 | 48.98
CBAM01 | 22066144 | 20 | URBAN BIRD TRUST | 1 | EACH | 159.86 | 159.86 | 159.86
CBAM01 | 22066144 | 21 | WWW.ALHGROUP.COM* ME&U | 1 | EACH | 11.84 | 11.84 | 11.84
CBAM01 | 22066144 | 22 | WWW.ALHGROUP.COM* ME&U | 1 | EACH | 135.93 | 135.93 | 135.93
CBAM01 | 22066158 | 1 | Rockpool - Neighbours gift | 1 | EACH | 370.82 | 370.82 | 370.82
CBAM01 | 22066169 | 1 | Jacksons 1 on 1 | 1 | EACH | 86.91 | 86.91 | 86.91
CBAM01 | 22066169 | 2 | Site Supplies | 1 | EACH | 204.55 | 204.55 | 204.55
CBAM01 | 22066169 | 3 | PCG Meeting | 1 | EACH | 25 | 25 | 25
CBAM01 | 22066169 | 4 | PCG Meeting | 1 | EACH | 20.23 | 20.23 | 20.23
CBAM01 | 22066169 | 6 | Josh 1 on 1 | 1 | EACH | 81.95 | 81.95 | 81.95
CBAM01 | 22066169 | 7 | Coffee for Rockpool | 1 | EACH | 10.18 | 10.18 | 10.18
CBAM01 | 22066169 | 8 | Clint 1 on 1 | 1 | EACH | 51.68 | 51.68 | 51.68
CBAM01 | 22066183 | 1 | Client Meeting | 1 | EACH | 24.55 | 24.55 | 24.55
CBAM01 | 22066183 | 2 | Client Meeting | 1 | EACH | 73.64 | 73.64 | 73.64
CBAM01 | 22066183 | 3 | Client Meeting | 1 | EACH | 72.27 | 72.27 | 72.27
CBAM01 | 22066183 | 4 | Client Meeting | 1 | EACH | 25.14 | 25.14 | 25.14
CBAM01 | 22066183 | 5 | ESC Audit Gravel | 1 | EACH | 265.78 | 265.78 | 265.78
CBAM01 | 22066183 | 6 | Site Consumables | 1 | EACH | 105.45 | 105.45 | 105.45
CBAM01 | 22066197 | 1 | Ash Lowe Credit Card | 1 | EACH | 782.75 | 782.75 | 0
KAWA02 | 22066157 | 1 | Structures - Function | 1 | EACH | 3290.91 | 3290.91 | 3290.91
PETT01 | 21ADR007 | 902 | HYAMS M - SITE UTENSILS | 1 | EACH | 35.45 | 35.45 | 35.45
PETT01 | 21ADR007 | 903 | HYAMS M - TEA, COFFEE | 1 | EACH | 54 | 54 | 54
PETT01 | 21ADR007 | 912 | WOOLLETT J - SITE CONSUMABLES | 1 | EACH | 39.67 | 39.67 | 39.67
PETT01 | 21ADR007 | 1518 | GUEST C - STATIONARY | 1 | EACH | 27.26 | 27.26 | 27.26
PETT01 | 21ADR007 | 1601 | GUEST C - COVID TESTS FOR SITE TEAM | 1 | EACH | 19.95 | 19.95 | 19.95
PETT01 | 21ADR007 | 1602 | GUEST C - LAMINATING FOR EVAC DIAGRAMS | 1 | EACH | 21.82 | 21.82 | 21.82
PETT01 | 21ADR007 | 1607 | MACPHERSON J - SITE PAYMENTS | 1 | EACH | 160.91 | 160.91 | 160.91
PETT01 | 21ADR007 | 1758 | WOOLLETT J - SITE TEAM LUNCH | 1 | EACH | 112.59 | 112.59 | 112.59
PETT01 | 21ADR007 | 1780 | LOWE A - ONE ON ONE MEETING | 1 | EACH | 85.15 | 85.15 | 85.15
PETT01 | 21ADR007 | 1788 | PIPER G - SITE BEERS FOR TEAM MORAL BUILDING | 1 | EACH | 50 | 50 | 50
PETT01 | 21ADR007 | 1789 | WYATT A - TEAM BEERS | 1 | EACH | 105.45 | 105.45 | 105.45
PETT01 | 22ADR01 | 17 | (10) Wyatt A - 25.05.23 | 1 | EA | 45.45 | 45.45 | 45.45
PETT01 | 22ADR01 | 18 | (10) Wyatt A - 01.06.23 | 1 | EA | 656.6 | 656.6 | 656.6
TRAD08 | 22066018 | 2 | Consumables | 1 | EACH | 606.45 | 606.45 | 606.45
TRAD08 | 22066060 | 1 | Environmental Controls | 1 | EACH | 142.88 | 142.88 | 142.88
TRAD08 | 22066063 | 9 | Kerb Ramps | 1 | EACH | 667.93 | 667.93 | 667.93
TRAD08 | 22066063 | 10 | Misc Site Items | 1 | EACH | 141.39 | 141.39 | 141.39
Sum: | [6 empty] | 19589.21 | 18756.37
Forecast Amounts
|  | 1 | Site Expenses - AL CC | 1 | NO | 2000 | 2000
|  | 2 | Milestones | 1 | EACH | 3350 | 3350
Total Forecasts | [6 empty] | 5350
Total for Cost Centre | [6 empty] | 25903.15 | 19720.31
PO5CA | MT |  | Covered Areas & Walkways
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066009 | 1 | Material Setup Site | 1 | EACH | 200 | 198.28 | 198.28
BUNN01 | 22066132 | 1 | Sundry Bunnings purchases for Covered Walkway (self perform | 1.6 | EACH | 245.88 | 368.83 | 368.83
KENN01 | 22066133 | 1 | Sundry tool hire for covered walkway (self perform team) | 1 | EACH | 500 | 489.86 | 489.86
Sum: | [6 empty] | 1056.97 | 1056.97
Uncompleted Purchase Orders
DOLA01 | 22066110 | 1 | Covered walkway engineering | 1 | EACH | 600 | 600 | 600
STRA01 | 22066126 | 1 | Stratco order | 1 | EACH | 5966.09 | 5966.09 | 5966.09
Sum: | [6 empty] | 6566.09 | 6566.09
Forecast Amounts
|  | 1 | Shed Repair costs for | 1 | ITEM | 2000 | 2000
Total Forecasts | [6 empty] | 2000
Total for Cost Centre | [6 empty] | 9623.06 | 7623.06
PO5TE | MT |  | Generators
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BULK01 | 22066111 | 1 | Invoice 01278717 | 1 | EACH | 535.37 | 535.37 | 535.37
BULK01 | 22066111 | 2 | Invoice 01286141 | 1 | EACH | 423.14 | 423.14 | 423.14
BULK01 | 22066111 | 3 | Invoice 01288798 | 1 | EACH | 612.46 | 612.46 | 612.46
BULK01 | 22066111 | 4 | Invoice 1301476 | 1 | EACH | 820.4 | 820.4 | 820.4
BULK01 | 22066111 | 5 | Invoice 1216626 | 1 | EACH | 1278.36 | 1278.36 | 1278.36
BULK01 | 22066111 | 6 | Invoice 01325319 | 1 | EACH | 713.13 | 713.13 | 713.13
BULK01 | 22066111 | 7 | Invoice 1338420 | 1 | EACH | 491.56 | 491.56 | 491.56
BULK01 | 22066111 | 8 | Invoice 1327614 | 1 | EACH | 298.31 | 298.31 | 298.31
BULK01 | 22066111 | 9 | Invoice 1358757 | 1 | EACH | 705.04 | 705.04 | 705.04
BULK01 | 22066111 | 10 | Invoice 1364042 | 1 | EACH | 720.98 | 720.98 | 720.98
BULK01 | 22066111 | 11 | Invoice 1354280 | 1 | EACH | 743 | 743 | 743
BULK01 | 22066111 | 12 | Invoice 1380319 | 1 | EACH | 401.85 | 401.85 | 401.85
BULK01 | 22066111 | 13 | invoice 1387377 | 1 | EACH | 684.05 | 684.05 | 684.05
BULK01 | 22066111 | 14 | Invoice 1395295 | 1 | EACH | 765.53 | 765.53 | 765.53
BULK01 | 22066111 | 15 | Invoice 1408782 | 1 | EACH | 334.15 | 334.15 | 334.15
BULK01 | 22066111 | 16 | Invoice 1409831 | 1 | EACH | 221.19 | 221.19 | 221.19
BULK01 | 22066111 | 17 | Invoice 1416277 | 1 | EACH | 746.29 | 746.29 | 746.29
BULK01 | 22066111 | 18 | Invoice1425384 | 1 | EACH | 629.55 | 629.55 | 629.55
BULK01 | 22066111 | 19 | Invoice 1431095 | 1 | EACH | 635.92 | 635.92 | 635.92
BULK01 | 22066111 | 20 | Invoice - 1437558 | 1 | EACH | 650.18 | 650.18 | 650.18
BULK01 | 22066111 | 21 | Invoice 1441592 | 1 | EACH | 747.48 | 747.48 | 747.48
BULK01 | 22066111 | 22 | Invoice 1447608 | 1 | EACH | 704.37 | 704.37 | 704.37
BULK01 | 22066111 | 23 | Invoice 1461451 | 1 | EACH | 731.19 | 731.19 | 731.19
BULK01 | 22066111 | 24 | Invoice 1468931 | 1 | EACH | 680.4 | 680.4 | 680.4
BULK01 | 22066111 | 25 | Invoice 1476860 | 1 | EACH | 680.24 | 680.24 | 680.24
BULK01 | 22066111 | 26 | Invoice 1492923 | 1 | EACH | 421.89 | 421.89 | 421.89
BULK01 | 22066111 | 27 | Invoice 1492569 | 1 | EACH | 51.96 | 51.96 | 51.96
BULK01 | 22066111 | 28 | Invoice 1497462 | 1 | EACH | 479.99 | 479.99 | 479.99
BULK01 | 22066111 | 29 | Invoice 1503719 | 1 | EACH | 556.59 | 556.59 | 556.59
BULK01 | 22066111 | 30 | Invoice 1507235 | 1 | EACH | 525.37 | 525.37 | 525.37
MCNA10 | 22066030 | 20 | 20 Kva Generator Hire | 6 | WEEKS | 143.75 | 316.25 | 316.25
Sum: | [6 empty] | 18306.19 | 18306.19
Uncompleted Purchase Orders
BULK01 | 22066111 | 31 | Invoice 01512956 | 1 | EACH | 740.38 | 740.38 | 740.38
BULK01 | 22066111 | 32 | Invoice 1518152 | 1 | EACH | 585.58 | 585.58 | 585.58
BULK01 | 22066111 | 33 | Generator Fuel - May 23.05 to 07.06 | 1 | EACH | 1105.51 | 1105.51 | 1005.01
BULK01 | 22066111 | 34 | Generator Fuel June 7.6.23 | 1 | EACH | 576.52 | 576.52 | 576.52
BULK01 | 22066111 | 35 | Generator Fuel 14.06 | 1 | EACH | 571.68 | 571.68 | 0
GENE10 | 22066120 | 1 | Generator | 1 | EACH | 795 | 795 | 795
GENE10 | 22066120 | 2 | Generator Hire | 26 | WEEK | 700 | 18200 | 18100
GENE10 | 22066120 | 3 | Generator Hire May | 1 | EACH | 3100 | 3100 | 3100
KENN01 | 22066058 | 5 | Generator Hire (Use this one) | 5 | WEEKS | 954.55 | 4772.75 | 4772.72
KENN01 | 22066058 | 6 | Delivery (Use this one) | 2 | EACH | 618.18 | 1236.36 | 1236.36
KENN01 | 22066059 | 6 | Generator | 1 | EACH | 2000 | 2000 | 1909.09
MCNA10 | 22066030 | 21 | 8Kva generator hire | 1 | EACH | 81 | 81 | 81
Sum: | [6 empty] | 33764.78 | 32901.66
Forecast Amounts
|  | 13 | Generator Hire May | 4 | WEEKS | 400 | 1600
|  | 14 | Fuel May | 4 | WEEKS | 700 | 2800
|  | 15 | Generator and Fuel June | 3 | WEEKS | 400 | 1200
|  | 16 | Fuel June | 3 | WEEKS | 700 | 2100
Total Forecasts | [6 empty] | 7700
Total for Cost Centre | [6 empty] | 59770.97 | 51207.85
PO5TT | ST |  | Traffic Control
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
ACCT01 | 22066093 | 1 | Initial Traffic Guidance Schemes | 1 | EACH | 195 | 195 | 195
Sum: | [6 empty] | 195 | 195
Uncompleted Purchase Orders
EAST27 | 22066082 | 1 | 2 man crew day rate | 8.5 | HRS | 117 | 994.5 | 994.5
EAST27 | 22066082 | 2 | Daily Fair Allowance | 4 | HRS | 30 | 120 | 120
EAST27 | 22066095 | 1 | Traffic Control on 23/09 and 30/09 | 1 | EACH | 1805.1 | 1805.1 | 1641
EAST27 | 22066095 | 2 | TC for Crane demob | 1 | EACH | 703.5 | 703.5 | 703.5
Sum: | [6 empty] | 3623.1 | 3459
Forecast Amounts
|  | 1 | Tower Crane Dismantle | 1 | ITEM | 1007.91 | 1007.91
|  | 2 | Roof Sheeting Delivery | 1 | ITEM | 1007.91 | 1007.91
|  | 3 | Containers over Back Fence | 2 | ITEM | 1007.91 | 2015.82
|  | 4 | Footpath Closer Scaffold | 2 | ITEM | 1007.91 | 2015.82
|  | 5 | Miscallanious Visits | 2 | ITEM | 1200 | 2400
Total Forecasts | [6 empty] | 8447.46
Total for Cost Centre | [6 empty] | 12265.56 | 3654
PO6 | OT |  | Stationary and Office Supplies
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
IMPA04 | 22066016 | 1 | Site Office Stationary | 1 | ITEM | 472.99 | 472.99 | 472.99
PETT01 | 21ADR007 | 1348 | GUEST C - LAMINATING POUCHES | 1 | EACH | 27.23 | 27.23 | 27.23
PETT01 | 21ADR007 | 1567 | WYATT A - LAMINATE SHEETS | 1 | EACH | 44.53 | 44.53 | 44.53
PETT01 | 21ADR007 | 1753 | GUEST C - LAMINATING POUCHES FOR SITE | 1 | EACH | 36.31 | 36.31 | 36.31
PETT01 | 21ADR007 | 1813 | GUEST C - RAFFLE TICKETS | 1 | EACH | 7.68 | 7.68 | 7.68
Sum: | [6 empty] | 588.74 | 588.74
Forecast Amounts
|  | 1 | Stationary | 1 | ITEM | 3960 | 3960
|  | 2 | Furniture Dismantle & Removal | 1 | NO | 2500 | 2500
|  | 3 | Office Furniture | 1 | NO | 2200 | 2200
Total Forecasts | [6 empty] | 8660
Total for Cost Centre | [6 empty] | 9248.74 | 588.74
PO7 | IP |  | McNab Equipment Hire
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066080 | 1 | McNab Self Perform Container fit out | 1 | EACH | 1065.22 | 1065.21 | 1065.21
KENN01 | 22066059 | 3 | 15/09 - 27/09 hire | 1 | EACH | 665.91 | 665.91 | 665.91
MCNA10 | 22066030 | 8 | SPT Container | 1 | EACH | 1902.45 | 1902.45 | 1902.45
MCNA10 | 22066030 | 11 | Flammable storage container Large | 52 | WEEKS | 36 | 316.8 | 316.8
MCNA10 | 22066030 | 12 | Delivery | 3 | EACH | 40 | 120 | 120
MCNA10 | 22066030 | 14 | Megaphone Hire | 48 | EACH | 2.5 | 16.5 | 16.5
MCNA10 | 22066030 | 15 | 5 x padlock hire | 48 | EACH | 6.25 | 150 | 150
MCNA10 | 22066030 | 16 | 5 x fire extinguisher | 15 | EACH | 15 | 99 | 99
MCNA10 | 22066030 | 17 | Collection | 2 | EACH | 40 | 80 | 80
MCNA10 | 22066030 | 19 | 1 x First Aid kit | 8 | WEEKS | 15 | 105 | 105
MCNA10 | 22066030 | 22 | 1 x fire extinguisher (off hired) | 1 | EACH | 3 | 3 | 3
MCNA10 | 22066030 | 23 | Sale item - FEX Hooks | 1 | EACH | 180 | 180 | 180
MCNA10 | 22066030 | 24 | 2 x Fire Extinguisher | 45 | WEEKS | 6 | 0 | 0
MCNA10 | 22066030 | 26 | 3 x Water Bubbler | 46 | WEEKS | 90 | 1920 | 1920
MCNA10 | 22066030 | 28 | First Aid Box x 2 | 1 | EACH | 96 | 96 | 96
MCNA10 | 22066030 | 31 | Pie Warmer | 46 | WEEKS | 8 | 148.8 | 148.8
Sum: | [6 empty] | 6868.67 | 6868.67
Uncompleted Purchase Orders
KENN01 | 22066025 | 2 | submersible Pump | 1 | EACH | 207.27 | 207.27 | 207.27
KENN01 | 22066032 | 2 | 12/09 - 26/09 Hire | 1 | EACH | 736.37 | 736.37 | 736.36
KENN01 | 22066032 | 3 | 26/09 - 30/09 Hire | 1 | EACH | 306.55 | 306.55 | 306.55
KENN01 | 22066032 | 4 | Flex Drive Hire | 1 | SUM | 521.46 | 521.46 | 521.45
KENN01 | 22066059 | 4 | Vacuum | 1 | EACH | 671.82 | 671.82 | 671.82
KENN01 | 22066059 | 5 | Smooth Drum Roller | 1 | EACH | 1044.55 | 1044.55 | 1044.55
MCNA10 | 22066030 | 2 | Wheelie Bin Spill Kit | 60 | WEEKS | 9 | 540 | 396
MCNA10 | 22066030 | 9 | Delivery/ Transport | 5 | EACH | 70 | 350 | 350
MCNA10 | 22066030 | 10 | Flammable storage container Medium | 52 | WEEKS | 25 | 1300 | 925
MCNA10 | 22066030 | 13 | Truck Edge Platform | 52 | WEEKS | 25 | 1300 | 1000
MCNA10 | 22066030 | 18 | 11 x fire extinguishers | 4.6182 | WEEKS | 33 | 152.4 | 152.4
MCNA10 | 22066030 | 25 | 10x Padlock hire | 46.3 | WEEKS | 12.5 | 578.75 | 366.25
MCNA10 | 22066030 | 27 | Delivery | 14 | EACH | 40 | 560 | 480
MCNA10 | 22066030 | 29 | H- Vac | 26.2 | WEEKS | 68 | 1781.6 | 1441.6
MCNA10 | 22066030 | 30 | Lux Meter | 46 | WEEKS | 5 | 230 | 130
MCNA10 | 22066030 | 32 | 12 x Water Barriers | 25 | WEEKS | 72 | 1800 | 1764
MCNA10 | 22066030 | 33 | Delivery | 3 | EACH | 70 | 210 | 210
MCNA10 | 22066030 | 34 | 3 x water bubbler | 43 | WEEKS | 90 | 3870 | 2250
MCNA10 | 22066030 | 35 | 7 x FEX Hire ( Compound) | 44.2 | WEEKS | 21 | 928.2 | 508.2
MCNA10 | 22066030 | 37 | Backpack Vacuum | 26 | WEEKS | 87.6 | 2277.6 | 1971
MCNA10 | 22066030 | 38 | 18v 8ah Battery | 26 | WEEKS | 9 | 234 | 202.5
MCNA10 | 22066030 | 39 | 18v Battery Charger | 26 | EACH | 7 | 182 | 157.5
MCNA10 | 22066030 | 40 | Water bubbler | 41 | EACH | 30 | 1230 | 690
MCNA10 | 22066030 | 41 | 1 x 18v battery | 28 | WEEKS | 9 | 252 | 171
MCNA10 | 22066030 | 42 | Blower Battery | 20 | WEEKS | 78.4 | 1568 | 1489.6
MCNA10 | 22066030 | 43 | 4 x water bubblers | 28 | WEEKS | 120 | 3360 | 2160
MCNA10 | 22066030 | 44 | 1 x water bubbler | 26 | WEEKS | 30 | 780 | 480
MCNA10 | 22066030 | 45 | 9 x FEX | 26 | WEEKS | 27 | 702 | 378
MCNA10 | 22066030 | 47 | 5 x FEX | 20 | WEEKS | 15 | 300 | 150
MCNA10 | 22066030 | 49 | M class vac | 1 | EACH | 411.66 | 411.66 | 411.66
MCNA10 | 22066030 | 50 | AED | 23 | WEEKS | 42 | 966 | 336
Sum: | [6 empty] | 29352.23 | 22058.71
Forecast Amounts
|  | 11 | JUL23 | 1 | NO | 750 | 750
|  | 12 | AUG23 | 1 | NO | 750 | 750
|  | 13 | SEP23 | 1 | NO | 750 | 750
Total Forecasts | [6 empty] | 2250
Total for Cost Centre | [6 empty] | 38470.9 | 28927.38
PO7 | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066070 | 1 | Water Pump & Hose from Bunnings | 1 | EACH | 250 | 164.53 | 164.53
Sum: | [6 empty] | 164.53 | 164.53
Total for Cost Centre | [6 empty] | 164.53 | 164.53
PO7 | XP |  | Small Tools
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066009 | 5 | Drew Materials | 1 | EACH | 450.88 | 450.88 | 450.88
BUNN01 | 22066009 | 6 | Misc | 1 | EACH | 103.37 | 103.35 | 103.35
BUNN01 | 22066072 | 1 | misc | 1 | EACH | 200 | 164.99 | 164.99
BUNN01 | 22066085 | 1 | straps | 1 | EACH | 50 | 15.55 | 15.55
BUNN01 | 22066098 | 1 | tie wire and lock | 1 | EACH | 150 | 136.35 | 136.35
BUNN01 | 22066123 | 1 | Misc Items | 1 | EACH | 602.19 | 602.19 | 602.19
BUNN01 | 22066127 | 1 | Misc | 2 | EACH | 100 | 181.01 | 181.01
BUNN01 | 22066127 | 3 | Plywood for lockup | 1 | EACH | 230 | 229.59 | 229.59
BUNN01 | 22066132 | 2 | BUNNINGS BUILDING SUPPLIES | 1 | EACH | 78.08 | 78.07 | 78.07
BUNN01 | 22066143 | 1 | Rebate Misc Items | 1 | EACH | 400 | 332.46 | 332.46
BUNN01 | 22066148 | 1 | Small Tools | 1 | EACH | 200 | 156.25 | 156.25
BUNN01 | 22066152 | 1 | Small Tools | 1 | EACH | 251.28 | 251.28 | 251.28
BUNN01 | 22066154 | 1 | Misc Items | 1.15 | EACH | 550 | 614.26 | 614.26
BUNN01 | 22066160 | 1 | Misc | 1 | EACH | 1100 | 1071.91 | 1071.91
BUNN01 | 22066172 | 1 | Small tools | 1 | EACH | 200 | 109.15 | 109.15
KENN01 | 22066031 | 6 | Portaloo Hire (Freshwater Skid) | 12.4 | EACH | 29.55 | 359.65 | 359.65
KENN01 | 22066133 | 2 | Scrubber hire | 1 | EACH | 1136.37 | 1136.36 | 1136.36
KENN01 | 22066133 | 4 | BBQ | 1 | EACH | 197.05 | 197.05 | 197.05
KENN01 | 22066133 | 5 | Demolition Saw | 1 | EACH | 540.18 | 540.18 | 540.18
KENN01 | 22066133 | 6 | Scrubber Hire | 1 | EACH | 1136.36 | 1136.36 | 1136.36
LYND01 | 22066147 | 1 | Misc Items | 1 | EACH | 324.52 | 295.02 | 295.02
TOTA44 | 22066162 | 1 | Pallet Jack | 1 | EACH | 362.73 | 362.73 | 362.73
Sum: | [6 empty] | 8524.64 | 8524.64
Uncompleted Purchase Orders
ALLA15 | 22066100 | 1 | Slings | 1 | SUM | 304 | 304 | 304
ALLC22 | 22066188 | 1 | Tyre Repair | 1 | EACH | 278.64 | 278.64 | 278.64
BUNN01 | 22066019 | 2 | Misc Items | 1 | EACH | 235.68 | 235.68 | 235.68
BUNN01 | 22066027 | 2 | Misc | 1 | EACH | 258.39 | 258.39 | 258.39
BUNN01 | 22066036 | 1 | misc | 1 | EACH | 178.23 | 178.23 | 178.23
BUNN01 | 22066040 | 1 | Hose & Connections | 1 | EACH | 184.23 | 184.23 | 184.23
BUNN01 | 22066069 | 1 | Hydrated Lime | 1 | EACH | 90 | 90 | 88.03
BUNN01 | 22066071 | 1 | Hydrochloric Acid | 1 | EACH | 50 | 50 | 44.35
BUNN01 | 22066102 | 1 | 20mm Drill bit | 1 | EACH | 148.52 | 148.52 | 148.52
BUNN01 | 22066116 | 2 | Misc | 1 | EACH | 219.39 | 219.39 | 219.39
BUNN01 | 22066127 | 2 | Misc | 1 | EACH | 117.27 | 117.27 | 117.27
BUNN01 | 22066128 | 1 | Supply miscellaneous items for blockwork sill quality workshop | 1 | EACH | 76.29 | 76.29 | 76.29
BUNN01 | 22066141 | 1 | Misc | 1 | EACH | 200 | 200 | 0
BUNN01 | 22066163 | 1 | grout | 1 | EACH | 256.65 | 256.65 | 256.65
BUNN01 | 22066172 | 2 | Small tools | 1 | EACH | 260.83 | 260.83 | 260.83
BUNN01 | 22066191 | 1 | Grinder Blades/ patching Adhes | 1 | EACH | 150 | 150 | 0
BUNN01 | 22066195 | 1 | Push Sweeper | 1 | EACH | 249.59 | 249.59 | 0
KENN01 | 22066031 | 7 | Pump out (Freshwater Skid) | 10 | EACH | 77.27 | 772.7 | 772.7
KENN01 | 22066039 | 1 | ladder hire | 1 | EACH | 185.36 | 185.36 | 185.36
LYND01 | 22066101 | 1 | Ableflex | 1 | EACH | 150 | 150 | 87.91
PELI01 | 22066190 | 1 | Meat Tray - May | 1 | EACH | 100 | 100 | 100
Sum: | [6 empty] | 4465.77 | 3796.47
Forecast Amounts
|  | 1 | Bunnings - Small Tools | 1 | ITEM | 3300 | 3300
|  | 2 | Hire Equipment/Self Perform | 1 | NO | 2100 | 2100
Total Forecasts | [6 empty] | 5400
Total for Cost Centre | [6 empty] | 18390.41 | 12321.11
PO8 | MT |  | Site Safety Equipment
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066116 | 1 | Gazebo | 1 | EACH | 250 | 117.27 | 117.27
BUNN01 | 22066142 | 1 | Chemical Cupboard | 1 | EACH | 406.87 | 406.87 | 406.87
BUNN01 | 22066179 | 2 | Safety Equipment | 1 | EACH | 225.82 | 225.81 | 225.81
KENN01 | 22066133 | 3 | BBQ Hire | 1 | EACH | 60 | 60 | 60
SAFE36 | 22066122 | 1 | Safety gear | 1 | EACH | 161.39 | 161.39 | 161.39
SAFE36 | 22066122 | 2 | Safety gear | 1 | EACH | 200 | 172.17 | 172.17
SAFE36 | 22066122 | 3 | Safety gear | 1 | EACH | 540.57 | 540.57 | 540.57
SAFE36 | 22066122 | 4 | Safety gear | 1 | EACH | 236.92 | 236.92 | 236.92
SAFE36 | 22066122 | 5 | Safety gear | 1 | EACH | 115.98 | 115.98 | 115.98
SAFE36 | 22066122 | 6 | Safety gear | 1 | EACH | 62.89 | 62.89 | 62.89
SAFE36 | 22066122 | 7 | Safety gear | 1 | EACH | 121.7 | 121.7 | 121.7
SAFE36 | 22066122 | 8 | Safety gear | 1 | EACH | 54.57 | 54.57 | 54.57
TRAD08 | 22066063 | 11 | Misc Site Items 11/11/22 | 1 | EACH | 168.89 | 168.89 | 168.89
TRAD08 | 22066063 | 12 | Misc Site Items 18/11/22 | 1 | EACH | 842.1 | 842.09 | 842.09
TRAD08 | 22066063 | 13 | GST Free item 18/11/22 | 1 | EACH | 46.2 | 46.18 | 46.18
TRAD08 | 22066063 | 14 | Misc Site Items 31/10/22 | 1 | EACH | 479.79 | 479.79 | 479.79
TRAD08 | 22066063 | 15 | Misc Site Items | 1 | EACH | 77.91 | 77.91 | 77.91
TRAD08 | 22066063 | 16 | Misc Site Items | 1 | EACH | 755.74 | 755.74 | 755.74
TRAD08 | 22066063 | 17 | Misc Site Items | 1 | EACH | 548.5 | 548.5 | 548.5
TRAD08 | 22066063 | 18 | Hard hat Sweat bands | 1 | EACH | 39.48 | 39.48 | 39.48
TRAD08 | 22066063 | 19 | Misc Site Items | 1 | EACH | 470.75 | 470.75 | 470.75
TRAD08 | 22066063 | 20 | Gloves | 1 | EACH | 218.24 | 218.24 | 218.24
TRAD08 | 22066063 | 21 | Misc Site Items | 1 | EACH | 494.09 | 494.09 | 494.09
TRAD08 | 22066063 | 22 | Misc Site Items | 1 | EACH | 256.31 | 256.31 | 256.31
TRAD08 | 22066063 | 23 | Misc Site Items | 1 | EACH | 28.14 | 28.14 | 28.14
TRAD08 | 22066063 | 24 | Misc Site Items | 1 | EACH | 428.51 | 428.51 | 428.51
TRAD08 | 22066063 | 25 | Misc Site Items | 1 | EACH | 61.05 | 61.05 | 61.05
TRAD08 | 22066063 | 26 | Misc Site Items | 1 | EACH | 496.32 | 496.32 | 496.32
TRAD08 | 22066063 | 27 | Misc Site Items | 1 | EACH | 216.5 | 216.5 | 216.5
TRAD08 | 22066063 | 28 | Misc Site Items | 1 | EACH | 285.41 | 285.41 | 285.41
TRAD08 | 22066063 | 29 | Misc Site Items | 1 | EACH | 99 | 99 | 99
Sum: | [6 empty] | 8289.04 | 8289.04
Uncompleted Purchase Orders
BARR10 | 22066038 | 2 | Slings | 1 | EACH | 144 | 144 | 144
JERR02 | 22066130 | 1 | HSE Roadshow | 1 | EACH | 1600 | 1600 | 1600
SAFE36 | 22066122 | 9 | Safety gear | 1 | EACH | 90.4 | 90.4 | 90.4
SAFE36 | 22066122 | 10 | Safety gear | 1 | EACH | 130.32 | 130.32 | 130.32
SAFE36 | 22066122 | 11 | Safety gear - Gloves | 1 | EACH | 35.61 | 35.61 | 0
SAFE45 | 22066106 | 1 | Classic Black Frame Tinted Lens | 5 | EACH | 31.81 | 159.05 | 0
SAFE45 | 22066125 | 1 | Quote #374 - Classics Black Frame/Tinted UV400 | 10 | EACH | 28.629 | 286.29 | 286.29
SAFE45 | 22066125 | 2 | Shipping | 1 | EACH | 13.64 | 13.64 | 13.64
SAFE45 | 22066181 | 1 | Safestyle sunglasses | 1 | EACH | 422.58 | 422.58 | 422.58
SITE04 | 22066017 | 2 | Site Signs - SItemax | 1 | EACH | 289.5 | 289.5 | 289.5
SITE04 | 22066017 | 3 | Site Signs - SItemax | 1 | EACH | 237.3 | 237.3 | 237.3
SITE04 | 22066017 | 4 | Site Signs - SItemax | 1 | EACH | 67.2 | 67.2 | 67.2
TRAD08 | 22066018 | 3 | Silt Bags | 1 | EACH | 21.64 | 21.64 | 21.64
TRAD08 | 22066018 | 4 | Hand Towels | 1 | EACH | 195.5 | 195.5 | 195.5
TRAD08 | 22066018 | 5 | Misc | 1 | EACH | 361.1 | 361.1 | 361.1
TRAD08 | 22066063 | 7 | Consumables | 1 | EACH | 318.89 | 318.89 | 318.89
TRAD08 | 22066063 | 8 | GST Free Consumable | 1 | EACH | 35.49 | 35.49 | 35.49
TRAD08 | 22066063 | 30 | Misc Site Items | 1 | EACH | 285.49 | 285.49 | 285.49
TRAD08 | 22066063 | 31 | Misc Site Items | 1 | EACH | 300 | 300 | 275.37
TRAD08 | 22066063 | 32 | Glasses/ Silica Bags | 1 | EACH | 336.95 | 336.95 | 0
WIMK01 | 22066178 | 1 | Black Dog Gloves | 42 | PAIRS | 12 | 504 | 504
Sum: | [6 empty] | 5834.95 | 5278.71
Forecast Amounts
|  | 8 | JUN23 - Safety Items | 1 | ITEM | 900 | 900
|  | 9 | JUL23 - Safety Items | 1 | ITEM | 900 | 900
|  | 10 | AUG23 - Safety Items | 1 | ITEM | 900 | 900
|  | 11 | SEP23 - Safety Items | 1 | ITEM | 900 | 900
Total Forecasts | [6 empty] | 3600
Total for Cost Centre | [6 empty] | 17723.99 | 13567.75
T06 | ST |  | BULK EARTHWORKS
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
TURB02 | 22066041 | 1 | Turbid Drums | 1 | EACH | 260 | 260 | 260
Sum: | [6 empty] | 260 | 260
Uncompleted Purchase Orders
AUSS15 | 22066153 | 1 | ESC Audit Item Close Out | 1 | EACH | 491.6 | 491.6 | 491.6
BEBR02 | 22066199 | 1 | Spoil Removal | 1 | EACH | 665.5 | 665.5 | 0
BUNN01 | 22066009 | 4 | Rain tank Dewatering | 1 | SUM | 49.15 | 49.15 | 49.15
GLOB40 | 22066044 | 1 | COMBIGRID 30/30 | 1 | ROLL | 1923.75 | 1923.75 | 1923.75
GLOB40 | 22066044 | 2 | Delivery | 1 | EACH | 240 | 240 | 240
KENN01 | 22066025 | 1 | Flexdrive Motor Hire | 1 | SUM | 568.55 | 568.55 | 568.55
KENN01 | 22066032 | 1 | 26/07 - 28/07 hire | 1 | EACH | 230.91 | 230.91 | 230.91
KENN01 | 22066059 | 1 | Crowd Barriers | 3.2 | WEEKS | 225.455 | 721.46 | 721.46
KENN01 | 22066059 | 2 | Delivery | 2 | EACH | 59.09 | 118.18 | 118.18
TURB02 | 22066012 | 1 | Turbidity Tube | 1 | ITEM | 675 | 675 | 675
TYZA03 | 22066023 | 1 | Site Dewatering | 1 | SUM | 1716.04 | 1716.04 | 1716.04
TYZA03 | 22066023 | 2 | Site Dewatering | 1 | SUM | 1549.04 | 1549.04 | 1549.04
Sum: | [6 empty] | 8949.18 | 8283.68
Subcontracts
AZFI01 | 22066007 | 11 | VI:BULK EARTHWORKS | 0 |  | 0 | 440 | 440
AZFI01 | 22066007 | 12 | VI:BULK EARTHWORKS | 0 |  | 0 | 5030 | 5030
CIVI22 | 22066005 | 1 | Survey - Item | 1 | NO | 3000 | 3000 | 3000
CIVI22 | 22066005 | 2 | Compaction Testing | 1 | NO | 2000 | 2000 | 2000
CIVI22 | 22066005 | 3 | Site Compound - Geofab to | 1671 | M2 | 3.5 | 5848.5 | 5848
CIVI22 | 22066005 | 4 | Site Compound - 100mm CBR 15 | 184 | M3 | 70 | 12880 | 12880
CIVI22 | 22066005 | 5 | Site Compound - Removal of | 171 | M2 | 16 | 2736 | 2736
CIVI22 | 22066005 | 6 | Site Compound - Removal of | 184 | M3 | 33 | 6072 | 6072
CIVI22 | 22066005 | 7 | Sediment & Erosion Control - | 1 | ITEM | 3000 | 3000 | 3000
CIVI22 | 22066005 | 8 | Sediment & Erosion Control - | 310 | M | 9 | 2790 | 2790
CIVI22 | 22066005 | 9 | Stabilized Rock & Entry Grid | 12 | MONTH | 130 | 1560 | 1560
CIVI22 | 22066005 | 10 | 30t of 45 Crushed Concrete - | 1 | T | 390 | 390 | 390
CIVI22 | 22066005 | 11 | Bulk Earthworks - Cut | 1866 | M3 | 13 | 24258 | 24258
CIVI22 | 22066005 | 12 | Bulk Earthworks - Fill | 103 | M3 | 13 | 1339 | 1339
CIVI22 | 22066005 | 13 | Bulk Earthworks - Compact | 155 | M3 | 13 | 2015 | 2015
CIVI22 | 22066005 | 14 | Rainwater Excavation | 1 | NO | 7320 | 7320 | 7320
CIVI22 | 22066005 | 15 | Rainwater Tank Backfill | 178 | M3 | 10 | 1780 | 1780
CIVI22 | 22066005 | 16 | Bio Basin Excavation | 25 | M3 | 25 | 625 | 625
CIVI22 | 22066005 | 17 | Disposal of Topsoil | 918 | M3 | 31.25 | 28687.5 | 28687.5
CIVI22 | 22066005 | 18 | Excavate & Removal of Fill | 1903 | M3 | 30 | 57090 | 57090
CIVI22 | 22066005 | 19 | Piling Pad - Fill & Compact | 282 | M3 | 70 | 19740 | 19740
CIVI22 | 22066005 | 20 | Piling Pad Trim | 2814 | M2 | 3 | 8442 | 8442
CIVI22 | 22066005 | 21 | Piling Pad Layer 1 - 200mm | 563 | M3 | 70 | 39410 | 39410
CIVI22 | 22066005 | 22 | External Area - Carpark | 220 | M3 | 70 | 15400 | 15400
CIVI22 | 22066005 | 23 | External Area - Trim Carpark | 1463 | M2 | 3 | 4389 | 4389
CIVI22 | 22066005 | 24 | External Area - Entrance | 121 | M3 | 70 | 8470 | 8470
CIVI22 | 22066005 | 25 | External Area - Trim | 804 | M2 | 3 | 2412 | 2412
CIVI22 | 22066005 | 26 | External Area - Footpath | 65 | M3 | 70 | 4550 | 4550
CIVI22 | 22066005 | 27 | External Area - Trim | 854 | M2 | 3 | 2562 | 2562
CIVI22 | 22066005 | 28 | VI:BULK EARTHWORKS | 0 |  | 0 | 6690 | 6690
CIVI22 | 22066005 | 29 | VI:BULK EARTHWORKS | 0 |  | 0 | 15610 | 15610
CIVI22 | 22066005 | 30 | VI:BULK EARTHWORKS | 0 |  | 0 | 2970 | 2970
CIVI22 | 22066005 | 31 | VI:BULK EARTHWORKS | 0 |  | 0 | 330 | 330
CIVI22 | 22066005 | 32 | VI:BULK EARTHWORKS | 0 |  | 0 | 3524.5 | 3524.5
CIVI22 | 22066005 | 33 | VI:BULK EARTHWORKS | 0 |  | 0 | 712.5 | 712.5
CIVI22 | 22066005 | 34 | VI:BULK EARTHWORKS | 0 |  | 0 | 770 | 770
CIVI22 | 22066005 | 35 | VI:BULK EARTHWORKS | 0 |  | 0 | 6930 | 6930
CIVI22 | 22066005 | 36 | VI:BULK EARTHWORKS | 0 |  | 0 | 5600 | 5600
CIVI22 | 22066005 | 37 | VI:BULK EARTHWORKS | 0 |  | 0 | 316 | 316
CIVI22 | 22066005 | 38 | VI:BULK EARTHWORKS | 0 |  | 0 | 28500 | 28500
CIVI22 | 22066005 | 40 | VI:BULK EARTHWORKS | 0 |  | 0 | 1517.72 | 1517.72
CIVI22 | 22066005 | 42 | VI:BULK EARTHWORKS | 0 |  | 0 | -22747.55 | -22747.55
Total Subcontracts | [6 empty] | 324959.17 | 324958.67
Forecast Amounts
|  | 4 | Additional CBR for Carpark | 1 | SUM | 13500 | 13500
|  | 5 | Removal CBR and Concrete for | 1 | SUM | 19480 | 19480
|  | 6 | Piling pad trim back | 1 | SUM | 5800 | 5800
|  | 7 | Footpath Prep | 1 | NO | 8472 | 8472
|  | 8 | Bollards | 1 | NO | 2000 | 2000
|  | 9 | Wheel stops | 1 | NO | 3470 | 3470
|  | 10 | Contingency | 1 | SUM | 20000 | 20000
Total Forecasts | [6 empty] | 72722
Total for Cost Centre | [6 empty] | 406890.35 | 333502.35
T06DE | ST |  | DETAILED EXCAVATION
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CLIV04 | 22066146 | 1 | Spoil Removal | 1 | EACH | 550 | 550 | 550
DOUG01 | 22066075 | 2 | Mobile Crane Pad | 1 | EACH | 840 | 840 | 840
DOUG01 | 22066075 | 3 | Geotech Inspections | 1 | EACH | 547.5 | 547.5 | 547.5
SUNS16 | 22066084 | 1 | road cleaning 23, 28 & 29/10 | 1 | EACH | 757.51 | 757.51 | 757.51
SUNS16 | 22066084 | 2 | road cleaning | 1 | EACH | 240 | 240 | 240
TYZA03 | 22066023 | 3 | Service location | 1 | EACH | 2653.11 | 2653.11 | 2653.11
TYZA03 | 22066023 | 4 | Footing Vac ex | 1 | EACH | 933.88 | 933.88 | 933.88
TYZA03 | 22066023 | 5 | Transformer Footings Vac ex | 1 | EACH | 1029.66 | 1029.66 | 1029.66
Sum: | [6 empty] | 7551.66 | 7551.66
Subcontracts
AZFI01 | 22066007 | 16 | VI:DETAILED EXCAVATION | 0 |  | 0 | 320 | 320
AZFI01 | 22066007 | 17 | VI:DETAILED EXCAVATION | 0 |  | 0 | 1710 | 1710
AZFI01 | 22066007 | 19 | VI:DETAILED EXCAVATION | 0 |  | 0 | 4640 | 4640
CIVI22 | 22066005 | 41 | VI:DETAILED EXCAVATION | 0 |  | 0 | 17301.47 | 17301.47
Total Subcontracts | [6 empty] | 23971.47 | 23971.47
Forecast Amounts
|  | 1 | Spoil Removal | 1 | ITEM | 3941 | 3941
|  | 3 | Vac Truck (2x Events) | 2 | NO | 1700 | 3400
Total Forecasts | [6 empty] | 7341
Total for Cost Centre | [6 empty] | 38864.13 | 31523.13
T08 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
AUST270 | 22066056 | 3 | Pile Crop hire | 2 | EACH | 2250 | 4500 | 4500
BEEL02 | 22066094 | 1 | Carry out day works on 23/09 & 28/09 | 1 | EACH | 2053.75 | 2053.75 | 2053.75
DOUG01 | 22066004 | 1 | Additional bore holes | 1 | EACH | 12700 | 12700 | 12700
DOUG01 | 22066004 | 2 | Additional bore holes | 1 | EACH | 1020 | 1020 | 1020
SUNC20 | 22066081 | 1 | Pile Concrete Cutting | 8 | LM | 80 | 640 | 640
SUNC20 | 22066081 | 2 | Hourly | 1.5 | HR | 85 | 127.5 | 127.5
SUNC20 | 22066081 | 3 | Establishment | 1 | EACH | 50 | 50 | 50
SUNC20 | 22066081 | 4 | Pile Cropping | 1 | EACH | 222.5 | 222.5 | 222.5
SUNC20 | 22066081 | 5 | Pile Cropping | 1 | EACH | 1260 | 1260 | 1260
Sum: | [6 empty] | 22573.75 | 22573.75
Uncompleted Purchase Orders
ALLA15 | 22066065 | 1 | Lifting Swivel for Piling Rig | 1 | EACH | 475 | 475 | 475
AUST270 | 22066056 | 1 | Pile Crop hire | 2 | WEEKS | 2850 | 5700 | 5700
AUST270 | 22066056 | 2 | Mob/ Demob | 2 | EACH | 200 | 400 | 400
PILE03 | 22066104 | 1 | Pile Testing | 1 | EACH | 1500 | 1500 | 1500
SHAK02 | 22066083 | 1 | Reo Welding | 1 | EACH | 1000 | 1000 | 1000
Sum: | [6 empty] | 9075 | 9075
Subcontracts
AZFI01 | 22066007 | 13 | VI:PILING | 0 |  | 0 | 4210 | 4210
CIVI22 | 22066005 | 39 | VI:PILING | 0 |  | 0 | 5022.5 | 5022.5
DOWE01 | 22066028 | 1 | Pile Trimming Package | 1 | NO | 73010 | 73010 | 73010
WAGS01 | 22066003 | 1 | Establishment | 1 | NO | 22670 | 22670 | 22670
WAGS01 | 22066003 | 3 | Supply of Precast Piles | 1 | EA | 787300 | 787300 | 787300
WAGS01 | 22066003 | 4 | Install of Piles | 1 | EA | 274730 | 274730 | 274730
WAGS01 | 22066003 | 5 | design, supply and install | 1 | EA | 25300 | 25300 | 25300
WAGS01 | 22066003 | 6 | VI:PILING | 0 |  | 0 | -38325 | -38325
Total Subcontracts | [6 empty] | 1153917.5 | 1153917.5
Total for Cost Centre | [6 empty] | 1185566.25 | 1185566.25
T091 | MT |  | CONCRETE SUPPLY
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
MANS01 | 22066010 | 1 | Concrete Supply | 2 | EACH | 1000 | 2000 | 1612
MANS01 | 22066077 | 1 | Footings | 518.7 | M3 | 160 | 82992 | 82992
MANS01 | 22066077 | 2 | Blinding to Footings | 11 | M3 | 150 | 1650 | 1650
MANS01 | 22066077 | 3 | Testing | 97 | EACH | 180 | 17460 | 17400
MANS01 | 22066077 | 4 | Ground Floor - Columns | 30.1 | M3 | 184 | 5538.4 | 5538.4
MANS01 | 22066077 | 5 | Crane Base | 57.6 | M3 | 170 | 9792 | 9792
MANS01 | 22066077 | 6 | Small Cartage Fee | 5.4 | EACH | 35 | 189 | 189
MANS01 | 22066077 | 7 | Ground Floor Lift Pit Walls | 7.8 | M3 | 172 | 1341.6 | 1341.6
MANS01 | 22066077 | 8 | Water Proofing Additive - Penatron | 7.8 | M3 | 90 | 702 | 702
MANS01 | 22066077 | 9 | SOG | 357.9 | M3 | 160 | 57264 | 57248
MANS01 | 22066077 | 10 | AFS Concrete Supply | 37 | M3 | 208 | 7696 | 7696
MANS01 | 22066077 | 11 | Suspended Slab - L1 | 527.9 | EACH | 170 | 89743 | 89743
MANS01 | 22066077 | 12 | AFS Supply 26/10/22 | 1 | EACH | 1314 | 1314 | 1314
MANS01 | 22066077 | 13 | Stairs - GF (2 inch) | 3 | M3 | 179 | 537 | 537
MANS01 | 22066077 | 14 | Accelerator 1% 40mpa | 9 | M3 | 5.6 | 50.4 | 50.4
MANS01 | 22066077 | 15 | Stairs - GF | 6 | M3 | 170 | 1020 | 1020
MANS01 | 22066077 | 16 | AFS - 3/11/22 | 1 | EACH | 5879.2 | 5879.2 | 5879.2
MANS01 | 22066077 | 17 | AFS - 12/11/22 | 1 | EACH | 1414.4 | 1414.4 | 1414.4
MANS01 | 22066077 | 18 | L1 - Columns (accidentally 50Mpa) | 18.4 | M3 | 189 | 3477.6 | 3477.6
MANS01 | 22066077 | 19 | Suspended SLab L2 | 355 | M3 | 170 | 60350 | 60350
MANS01 | 22066077 | 20 | Level 2 Columns | 16.2 | M3 | 179 | 2899.8 | 2899.8
MANS01 | 22066077 | 21 | AFS 29/11/22 | 1 | EACH | 2780 | 2780 | 2780
MANS01 | 22066077 | 22 | Level 3 Suspended Slab | 352.8 | M3 | 170 | 59976 | 59976
MANS01 | 22066077 | 23 | Strip Footings - N40 | 12.5 | M3 | 170 | 2125 | 2074
MANS01 | 22066077 | 24 | L2 Columns N50 mix | 5.4 | M3 | 189 | 1020.6 | 1020.6
MANS01 | 22066077 | 25 | L3 Columns | 19.4 | M3 | 179 | 3472.6 | 3472.6
MANS01 | 22066077 | 26 | MG Block Fill - Backcharged | 25 | M3 | 180 | 4500 | 4500
MANS01 | 22066077 | 27 | L4 Suspended Slab | 356 | M3 | 170 | 60520 | 60520
MANS01 | 22066077 | 28 | L3 Columns 40/10/200 | 6.3 | M3 | 198 | 1247.4 | 1247.4
MANS01 | 22066077 | 29 | L4 Columns | 16.5 | EACH | 179 | 2953.5 | 2953.5
MANS01 | 22066077 | 30 | L4 Columns - Rytec Mix | 8.5 | M3 | 198 | 1683 | 1683
MANS01 | 22066077 | 31 | L5 Suspended Slab | 346.4 | M3 | 170 | 58888 | 58888
MANS01 | 22066077 | 32 | GF Remaining Stair Landings | 14 | M3 | 179 | 2506 | 2506
MANS01 | 22066077 | 33 | L5 Columns (N40/10/100 mix) | 5.6 | M3 | 174 | 974.4 | 974.4
MANS01 | 22066077 | 34 | L5 Columns N40/10/150 mix | 5 | M3 | 179 | 895 | 895
MANS01 | 22066077 | 35 | Roof Suspended Slabs | 75.8 | EACH | 170 | 12886 | 12886
MANS01 | 22066077 | 36 | Ground Floor Slab Infill - Kitchen | 1 | EACH | 335.4 | 335.4 | 0
READ03 | 22066129 | 1 | Concrete Supply - Holcim 8.11.22 | 1 | EACH | 3134.2 | 3134.2 | 3134.2
READ03 | 22066129 | 2 | Concrete Supply - Holcim 11.11.22 | 1 | EACH | 7489.2 | 7489.2 | 7489.2
READ03 | 22066129 | 3 | Concrete Supply - Holcim | 1 | EACH | 1355.75 | 1355.75 | 1355.75
Sum: | [6 empty] | 582052.45 | 581202.05
Subcontracts
MGBR01 | 22066019 | 20 | VI:CONCRETE SUPPLY | 0 |  | 0 | -4500 | -4500
Total Subcontracts | [6 empty] | -4500 | -4500
Forecast Amounts
|  | 4 | Concrete - Footings | 1 | NO | 8923.2 | 8923.2
|  | 12 | Concrete - External Works | 1 | NO | 78276 | 78276
|  | 13 | Concrete - Misc items | 1 | NO | 7585.92 | 7585.92
|  | 14 | 125mm deep paving treatment | 1 | NO | 5467 | 5467
|  | 15 | External works 4% wasteage | 1 | NO | 2950 | 2950
|  | 8999 | 020027 Traffic Island - | 1 | EACH | 240 | 240
|  | 89999 | 020022 Cafe Entrance - Deleted | 1 | ITEM | -648 | -648
Total Forecasts | [6 empty] | 102794.12
Total for Cost Centre | [6 empty] | 680346.57 | 576702.05
T091 | ST |  | CONCRETE LABOUR
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
SUNC20 | 22066081 | 7 | Concrete Cutting | 1 | EACH | 3600 | 3467.89 | 3467.89
SUNC20 | 22066081 | 8 | Concrete Cutting | 1 | EACH | 1609.94 | 1609.94 | 1609.94
Sum: | [6 empty] | 5077.83 | 5077.83
Uncompleted Purchase Orders
KERB08 | 22066194 | 1 | Kerbing to Carpark | 1 | EACH | 5000 | 5000 | 0
KERB08 | 22066194 | 2 | Kerbing to Traffic Island | 1 | EACH | 200 | 200 | 0
SUNC20 | 22066081 | 10 | Concrete Cutting | 1 | EACH | 1043.97 | 1043.97 | 1043.97
Sum: | [6 empty] | 6243.97 | 1043.97
Subcontracts
AZFI01 | 22066007 | 1 | Detailed Excavation | 1 | NO | 75000 | 75000 | 75000
AZFI01 | 22066007 | 2 | Labour - Pour Footings | 1 | NO | 25000 | 25000 | 25000
AZFI01 | 22066007 | 3 | Slabs - Ground and Suspended | 1 | NO | 264272 | 264272 | 264271.7
AZFI01 | 22066007 | 4 | External Road | 1 | NO | 31810 | 31810 | 0
AZFI01 | 22066007 | 5 | Carpark | 1 | NO | 36175 | 36175 | 0
AZFI01 | 22066007 | 6 | Footpaths | 1 | NO | 38115 | 38115 | 0
AZFI01 | 22066007 | 7 | Booster Slab & PMT | 1 | NO | 1125 | 1125 | 0
AZFI01 | 22066007 | 8 | Columns | 1 | NO | 21000 | 21000 | 21000
AZFI01 | 22066007 | 9 | Stairs | 1 | NO | 13000 | 13000 | 13000
AZFI01 | 22066007 | 10 | External Machine Hire - | 1 | NO | 4503 | 4503 | 0
AZFI01 | 22066007 | 14 | VI:CONCRETE LABOUR | 0 |  | 0 | 340 | 340
AZFI01 | 22066007 | 15 | VI:CONCRETE LABOUR | 0 |  | 0 | 170 | 170
AZFI01 | 22066007 | 20 | VI:CONCRETE LABOUR | 0 |  | 0 | 1520 | 1520
AZFI01 | 22066007 | 21 | VI:CONCRETE LABOUR | 0 |  | 0 | -1770 | -1770
AZFI01 | 22066007 | 22 | VI:CONCRETE LABOUR | 0 |  | 0 | 2600 | 2600
AZFI01 | 22066007 | 23 | VI:CONCRETE LABOUR | 0 |  | 0 | 4480 | 4480
MGSO01 | 22066024 | 1 | Aquaron 200 Medi+ | 7897 | M2 | 7 | 55279 | 55279
MGSO01 | 22066024 | 2 | Aquaron 1000 | 118 | M2 | 5 | 590 | 590
MGSO01 | 22066024 | 3 | Prject Management & QA Docs | 1 | NO | 2500 | 2500 | 2500
MGSO01 | 22066024 | 4 | VI:CONCRETE LABOUR | 0 |  | 0 | 2100 | 2100
MGSO01 | 22066024 | 5 | VI:CONCRETE LABOUR | 0 |  | 0 | 3600 | 3600
MGSO01 | 22066024 | 6 | VI:CONCRETE LABOUR | 0 |  | 0 | 4920 | 4920
MGSO01 | 22066024 | 7 | VI:CONCRETE LABOUR | 0 |  | 0 | 3000 | 3000
MGSO01 | 22066024 | 8 | VI:CONCRETE LABOUR | 0 |  | 0 | 4790 | 4790
Total Subcontracts | [6 empty] | 594119 | 482390.7
Forecast Amounts
|  | 5 | Out of Sequence Works | 1 | NO | 5000 | 5000
|  | 9 | Sawcuts | 1 | NO | 5000 | 5000
|  | 8997 | 020027 Traffic Island - bollar | 1 | EACH | 500 | 500
|  | 8999 | 020027 Traffic Island - Azfirm | 1 | EACH | 700 | 700
Total Forecasts | [6 empty] | 11200
Total for Cost Centre | [6 empty] | 616640.8 | 488512.5
T091PU | XP |  | CONCRETE PUMPING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
MEAL08 | 22066048 | 1 | Footings - Pumping | 1 | SUM | 14636.8 | 14636.8 | 14636.8
MEAL08 | 22066048 | 2 | October Claim (Ground SOG) | 1 | EACH | 17972.4 | 17972.4 | 17972.4
MEAL08 | 22066048 | 3 | November Claim | 1 | EACH | 21784.7 | 21584.7 | 21584.7
MEAL08 | 22066048 | 4 | December Claim | 1 | EACH | 18690.7 | 18690.7 | 18690.7
MEAL08 | 22066048 | 5 | January Claim | 1 | EACH | 9003 | 9003 | 9003
MEAL08 | 22066048 | 6 | Feb Claim | 1 | EACH | 17910.4 | 17910.4 | 17910.4
Sum: | [6 empty] | 99798 | 99798
Uncompleted Purchase Orders
MEAL08 | 22066048 | 7 | March Claim | 1 | EACH | 11071.2 | 11071.2 | 11071.2
MEAL09 | 22066090 | 1 | September Claim | 1 | ITEM | 14636.8 | 14636.8 | 14636.8
Sum: | [6 empty] | 25708 | 25708
Forecast Amounts
|  | 18 | External - Carpark | 1 | ITEM | 6289.5 | 6289.5
|  | 19 | External - Driveway | 1 | ITEM | 5949 | 5949
|  | 20 | External - Footpaths | 1 | ITEM | 6176 | 6176
|  | 21 | Washout Bags | 54 | ITEM | 100 | 5400
|  | 22 | Trade reserves | 1 | ITEM | 5000 | 5000
Total Forecasts | [6 empty] | 28814.5
Total for Cost Centre | [6 empty] | 154320.5 | 125506
T091T | MT |  | CONCRETE TESTING & SUNDRIES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
HIBB04 | 22066193 | 1 | May Works - Lift & Preston | 1 | EACH | 3263.7 | 3263.7 | 3263.7
KENN01 | 22066059 | 7 | Hammerdrill - columns L5 | 1 | EACH | 405 | 405 | 404.91
Sum: | [6 empty] | 3668.7 | 3668.61
Forecast Amounts
|  | 1 | Saw Cutting | 350 | LM | 25 | 8750
|  | 2 | Joint Sealing | 1000 | LM | 8 | 8000
Total Forecasts | [6 empty] | 16750
Total for Cost Centre | [6 empty] | 20418.7 | 3668.61
T092 | MT |  | REINFORCEMENT SUPPLY
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
LYND01 | 22066108 | 1 | 30-40mm Plastic Deck Chairs | 1 | EACH | 100 | 49.5 | 49.5
MESH01 | 22066117 | 1 | Starter Caps | 1 | EACH | 300 | 206.8 | 206.8
SUNC20 | 22066081 | 6 | Pile Cropping | 1 | EACH | 1300 | 1300 | 1300
WIRE01 | 22066078 | 17 | Ground Floor Walls - Zone 2 | 1 | EACH | 22953.9 | 22573.9 | 22573.9
WIRE01 | 22066078 | 22 | Ancillary Delivery | 1 | SUM | 1496 | 1461 | 1461
Sum: | [6 empty] | 25591.2 | 25591.2
Uncompleted Purchase Orders
LYND01 | 22066101 | 2 | Ancillary Items | 1 | EACH | 550 | 550 | 321.33
RIMC04 | 22066096 | 1 | Revised Reo Measure | 14 | HRS | 50 | 700 | 700
WIRE01 | 22066078 | 1 | South Zone Capping Beams & Pile Caps | 1 | EACH | 18616.74 | 18616.74 | 18616.74
WIRE01 | 22066078 | 2 | South Zone Combined Footing | 1 | EACH | 12238.77 | 12238.77 | 12238.77
WIRE01 | 22066078 | 3 | Footing L Bars N32 | 1 | EACH | 440.82 | 440.82 | 440.82
WIRE01 | 22066078 | 4 | GF Columns | 1 | EACH | 6563.22 | 6563.22 | 6563.22
WIRE01 | 22066078 | 5 | Crane Base Footing | 1 | EACH | 8029.46 | 8029.46 | 8029.46
WIRE01 | 22066078 | 6 | Crane Base L Bar | 1 | EACH | 739.63 | 739.63 | 739.63
WIRE01 | 22066078 | 7 | Blockwalls - GF Zone 1 | 1 | EACH | 18818.84 | 18818.84 | 18818.84
WIRE01 | 22066078 | 8 | Capping, Pile Caps and STrip Footings - Zone 3 | 1 | EACH | 25491.72 | 25491.72 | 25491.72
WIRE01 | 22066078 | 9 | Reo Sok Delivery - Footings | 1 | EACH | 595.6 | 595.6 | 595.6
WIRE01 | 22066078 | 10 | Pad footings, Pile Caps & Strip Footings - Zone 2 | 1 | EACH | 8275.29 | 8275.29 | 8275.29
WIRE01 | 22066078 | 11 | Capping Beams - Zone 2 | 1 | EACH | 11334.92 | 11334.92 | 11334.92
WIRE01 | 22066078 | 12 | Combined Footing - Zone 2 | 1 | EACH | 29204.12 | 29204.12 | 29204.12
WIRE01 | 22066078 | 13 | Combined Footings - Zone 3 | 1 | EACH | 11480.01 | 11480.01 | 11480.01
WIRE01 | 22066078 | 14 | GF - L1 Blockwork - Zone 2 | 1 | EACH | 4505.37 | 4505.37 | 4505.37
WIRE01 | 22066078 | 15 | GF-L1 Columns - Zone 2 | 1 | EACH | 7459.31 | 7459.31 | 7459.31
WIRE01 | 22066078 | 16 | Footings Stock Bar | 1 | EACH | 2138.14 | 2138.14 | 2138.14
WIRE01 | 22066078 | 18 | Ground floor sundries | 1 | EACH | 1771.66 | 1771.66 | 1771.66
WIRE01 | 22066078 | 19 | GF-L1 Columns - Zone 3 | 1 | EACH | 4042.54 | 4042.54 | 4042.54
WIRE01 | 22066078 | 20 | GF Walls - Zone 3 | 1 | EACH | 19159.68 | 19159.68 | 19159.68
WIRE01 | 22066078 | 21 | GF Slab - Zone 1 | 1 | EACH | 8754.82 | 8754.82 | 8754.82
WIRE01 | 22066078 | 23 | SOG - Z3 | 1 | EACH | 12672.84 | 12672.84 | 12672.84
WIRE01 | 22066078 | 24 | GF-L1 Columns - Zone 3 resupply | 1 | EACH | 1469.79 | 1469.79 | 1469.79
WIRE01 | 22066078 | 25 | SOG - Z2 | 1 | EACH | 12977.34 | 12977.34 | 12977.34
WIRE01 | 22066078 | 26 | Suspended Slabs - L1 Z1 | 1 | EACH | 22015.02 | 22015.02 | 22015.02
WIRE01 | 22066078 | 27 | Suspended Slabs - L1 Z1 Misc | 1 | EACH | 3445 | 3445 | 3445
WIRE01 | 22066078 | 28 | GF-L1 Zone 2 Block walls 2nd lift | 1 | EACH | 4862.44 | 4862.44 | 4862.44
WIRE01 | 22066078 | 29 | Stairs - GF - L1 | 1 | EACH | 1633.32 | 1633.32 | 1633.32
WIRE01 | 22066078 | 30 | Suspended Slabs - L1 Z1 2nd | 1 | EACH | 17852.42 | 17852.42 | 17852.42
WIRE01 | 22066078 | 31 | GF-L1 - Zone 3 Resupply | 1 | EACH | 1766.04 | 1766.04 | 1766.04
WIRE01 | 22066078 | 32 | Columns - L1 | 1 | EACH | 11674.99 | 11674.99 | 11674.99
WIRE01 | 22066078 | 33 | L1 Shear Studs | 1 | EACH | 5134.87 | 5134.87 | 5134.87
WIRE01 | 22066078 | 34 | GF-L1 Conc Walls Resupply | 1 | EACH | 6126.84 | 6126.84 | 6126.84
WIRE01 | 22066078 | 35 | Suspended Slab - L1 Stock Bar | 1 | EACH | 1718.64 | 1718.64 | 1718.64
WIRE01 | 22066078 | 36 | Columns - L1 additional bar | 1 | EACH | 369.72 | 369.72 | 369.72
WIRE01 | 22066078 | 37 | Suspended Slab - L1 Z2 A, B layer | 1 | EACH | 30853.48 | 30853.48 | 30853.48
WIRE01 | 22066078 | 38 | Suspended Slab - L1 Stock Bar 2 | 1 | EACH | 3002 | 3002 | 3002
WIRE01 | 22066078 | 39 | L1 - AFS Starters Zone 2 | 1 | EACH | 620.15 | 620.15 | 620.15
WIRE01 | 22066078 | 40 | Suspended Slab - L1 Zone 2 top layer | 1 | EACH | 23963.07 | 23963.07 | 23963.07
WIRE01 | 22066078 | 41 | Z1 - L1 Blockwork | 1 | EACH | 8678.13 | 8678.13 | 8678.13
WIRE01 | 22066078 | 42 | Z3 GF blockwork | 1 | EACH | 9823.13 | 9823.13 | 9823.13
WIRE01 | 22066078 | 43 | Zone 1 - L1 AFS and Block walls | 1 | EACH | 17653.06 | 17653.06 | 17653.06
WIRE01 | 22066078 | 44 | Suspended Slab - L1 Z3 | 1 | EACH | 21449.36 | 21449.36 | 21449.36
WIRE01 | 22066078 | 45 | Suspended Slab - L1 Z3 top layer | 1 | EACH | 16612.12 | 16612.12 | 16612.12
WIRE01 | 22066078 | 46 | L1-2 Z2 AFS walls and Block | 1 | EACH | 21133.15 | 21133.15 | 21133.15
WIRE01 | 22066078 | 47 | L2-3 Columns Pour 1 | 1 | EACH | 5404.04 | 5404.04 | 5404.04
WIRE01 | 22066078 | 48 | Level 2 Suspended Slab Z A - BTM | 1 | EACH | 15635.84 | 15635.84 | 15635.84
WIRE01 | 22066078 | 49 | Level 2 Suspended Slab ZA - Top | 1 | EACH | 13290.17 | 13290.17 | 13290.17
WIRE01 | 22066078 | 50 | L2 Zone A Stair 3 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 51 | L1-L2 AFS walls Pour 3 | 1 | EACH | 3448.74 | 3448.74 | 3448.74
WIRE01 | 22066078 | 52 | L1-L2 Blockwalls Pour 3 | 1 | EACH | 10502.15 | 10502.15 | 10502.15
WIRE01 | 22066078 | 53 | Plastic Deck Chairs 30/40mm | 1 | EACH | 273.94 | 273.94 | 273.94
WIRE01 | 22066078 | 54 | L1-2 Stair 2 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 55 | L1-2 CC5A x 1 | 1 | EACH | 638.32 | 638.32 | 638.32
WIRE01 | 22066078 | 56 | L2 Pour 2 A,B layer | 1 | EACH | 19838.6 | 19838.6 | 19838.6
WIRE01 | 22066078 | 57 | L1-2 PBW2A Walls | 1 | EACH | 20678.65 | 20678.65 | 20678.65
WIRE01 | 22066078 | 58 | Stud rails - L2 South | 1 | EACH | 4458.54 | 4458.54 | 4458.54
WIRE01 | 22066078 | 59 | L2 Pour 2 Additional Beam | 1 | EACH | 219.62 | 219.62 | 219.62
WIRE01 | 22066078 | 60 | L2 Main Stud Rails | 1 | EACH | 5277.92 | 5277.92 | 5277.92
WIRE01 | 22066078 | 61 | L2 Slab Pour 2 - C, D Layer | 1 | EACH | 16031.47 | 16031.47 | 16031.47
WIRE01 | 22066078 | 62 | L2 P1 Blockwork | 1 | EACH | 10634.93 | 10634.93 | 10634.93
WIRE01 | 22066078 | 63 | L2 Slab P3 - A, B Layer | 1 | EACH | 13160.04 | 13160.04 | 13160.04
WIRE01 | 22066078 | 64 | L2 Pour 3 - C, D Layer | 1 | EACH | 10288.17 | 10288.17 | 10288.17
WIRE01 | 22066078 | 65 | L2 P3 Columns | 1 | EACH | 2663.7 | 2663.7 | 2663.7
WIRE01 | 22066078 | 66 | L2 Walls Pour 2 | 1 | EACH | 15881.18 | 15881.18 | 15881.18
WIRE01 | 22066078 | 67 | L2-3 Column Resupply | 1 | EACH | 235.36 | 235.36 | 235.36
WIRE01 | 22066078 | 68 | L3 Stud Rails - South | 1 | EACH | 4458.54 | 4458.54 | 4458.54
WIRE01 | 22066078 | 69 | L3 Slab Pour 1 - A,B Layer | 1 | EACH | 14573.68 | 14573.68 | 14573.68
WIRE01 | 22066078 | 70 | L3 P1 - Hobs | 1 | EACH | 231.47 | 231.47 | 231.47
WIRE01 | 22066078 | 71 | L2-3 Stair 3 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 72 | L3 Misc | 1 | EACH | 260.26 | 260.26 | 260.26
WIRE01 | 22066078 | 73 | L3 P1 - Columns | 1 | EACH | 5325.04 | 5325.04 | 5325.04
WIRE01 | 22066078 | 74 | L3 P1 - C, D layer | 1 | EACH | 13290.17 | 13290.17 | 13290.17
WIRE01 | 22066078 | 75 | L2 P2 - Top and Columns | 1 | EACH | 4005.91 | 4005.91 | 4005.91
WIRE01 | 22066078 | 76 | L2 - Walls P3 | 1 | EACH | 7258.41 | 7258.41 | 7258.41
WIRE01 | 22066078 | 77 | L1-2 Stairs | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 78 | L3 Main Stud rails | 1 | EACH | 5277.92 | 5277.92 | 5277.92
WIRE01 | 22066078 | 79 | L2 - suspended slab P2 btm | 1 | EACH | 16631.59 | 16631.59 | 16631.59
WIRE01 | 22066078 | 80 | L2-3 Stair 2 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 81 | L3 P2 Beam | 1 | EACH | 1319.69 | 1319.69 | 1319.69
WIRE01 | 22066078 | 82 | L3 P2 Top Slab | 1 | EACH | 16031.47 | 16031.47 | 16031.47
WIRE01 | 22066078 | 83 | L3 P1 Block | 1 | EACH | 10257.71 | 10257.71 | 10257.71
WIRE01 | 22066078 | 84 | L3 P2 Columns | 1 | EACH | 3962.46 | 3962.46 | 3962.46
WIRE01 | 22066078 | 85 | L3 P3 BTM & Stair | 1 | EACH | 11925.54 | 11925.54 | 11925.54
WIRE01 | 22066078 | 86 | L3 P3 Columns | 1 | EACH | 2628.15 | 2628.15 | 2628.15
WIRE01 | 22066078 | 87 | L3 P2 Blockwalls | 1 | EACH | 14232.06 | 14232.06 | 14232.06
WIRE01 | 22066078 | 88 | L3 P3 Top | 1 | EACH | 9515.94 | 9515.94 | 9515.94
WIRE01 | 22066078 | 89 | L3-4 Stair 3 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 90 | L4-5 Columns P1 | 1 | EACH | 5240.11 | 5240.11 | 5240.11
WIRE01 | 22066078 | 91 | L4-5 Columns P2 | 1 | EACH | 3905.19 | 3905.19 | 3905.19
WIRE01 | 22066078 | 92 | L4-L4 Columns P3 | 1 | EACH | 2543.23 | 2543.23 | 2543.23
WIRE01 | 22066078 | 93 | L4 Suspended Slab | 1 | EACH | 14573.68 | 14573.68 | 14573.68
WIRE01 | 22066078 | 94 | L4 Pour 1 Hobs | 1 | EACH | 231.47 | 231.47 | 231.47
WIRE01 | 22066078 | 95 | Galv Mesh - Backcharge | 1 | EACH | 1540 | 1540 | 1540
WIRE01 | 22066078 | 96 | L4 P2 Bottom | 1 | EACH | 16631.59 | 16631.59 | 16631.59
WIRE01 | 22066078 | 97 | L4 P2 Beam | 1 | EACH | 1319.69 | 1319.69 | 1319.69
WIRE01 | 22066078 | 98 | L3 P3 Blockwalls | 1 | EACH | 8115.56 | 8115.56 | 8115.56
WIRE01 | 22066078 | 99 | Stair Mesh | 1 | EACH | 785.57 | 785.57 | 785.57
WIRE01 | 22066078 | 100 | L4 P2 Top | 1 | EACH | 16031.47 | 16031.47 | 16031.47
WIRE01 | 22066078 | 101 | L3-4 Stair 2 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 102 | L4 Main - Stud Rails | 1 | EACH | 5277.92 | 5277.92 | 5277.92
WIRE01 | 22066078 | 103 | L4 Stud Rails - South | 1 | EACH | 4458.54 | 4458.54 | 4458.54
WIRE01 | 22066078 | 104 | L4 P1 Blockwalls | 1 | EACH | 10257.71 | 10257.71 | 10257.71
WIRE01 | 22066078 | 105 | L4 P3 BTM | 1 | EACH | 9476.54 | 9476.54 | 9476.54
WIRE01 | 22066078 | 106 | L4 P3 HOB | 1 | EACH | 231.47 | 231.47 | 231.47
WIRE01 | 22066078 | 107 | L3-4 Stair 1 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 108 | L4 P3 TOP | 1 | EACH | 9515.94 | 9515.94 | 9515.94
WIRE01 | 22066078 | 109 | L5 Stud Rails - Main | 1 | EACH | 4458.54 | 4458.54 | 4458.54
WIRE01 | 22066078 | 110 | L5 Stud Rails - South | 1 | EACH | 5277.92 | 5277.92 | 5277.92
WIRE01 | 22066078 | 111 | L4 P2 Blockwalls | 1 | EACH | 2526.23 | 2526.23 | 2526.23
WIRE01 | 22066078 | 112 | L4-5 Stair 3 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 113 | L4 P2 Block walls additional | 1 | EACH | 1853.34 | 1853.34 | 1853.34
WIRE01 | 22066078 | 114 | L5 P1 BTM | 1 | EACH | 14615.15 | 14615.15 | 14615.15
WIRE01 | 22066078 | 115 | L5-RF Columns | 1 | EACH | 5296.77 | 5296.77 | 5296.77
WIRE01 | 22066078 | 116 | L4 P3 Blockwalls | 1 | EACH | 8117.53 | 8117.53 | 8117.53
WIRE01 | 22066078 | 117 | L5 P1 Top | 1 | EACH | 13290.17 | 13290.17 | 13290.17
WIRE01 | 22066078 | 118 | Plastic Request | 1 | EACH | 396.27 | 396.27 | 396.27
WIRE01 | 22066078 | 119 | L4 P1 Top | 1 | EACH | 13290.17 | 13290.17 | 13290.17
WIRE01 | 22066078 | 120 | L5 P2 BTM | 1 | EACH | 16631.59 | 16631.59 | 16631.59
WIRE01 | 22066078 | 121 | L5 P2 Beam & Starter | 1 | EACH | 1420.42 | 1420.42 | 1420.42
WIRE01 | 22066078 | 122 | L4-5 Stair 2 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 123 | L5 P2 Top | 1 | EACH | 16031.47 | 16031.47 | 16031.47
WIRE01 | 22066078 | 124 | Urgent Order L5 | 1 | EACH | 768.67 | 768.67 | 768.67
WIRE01 | 22066078 | 125 | L5 - RF Walls pour 1 | 1 | EACH | 9154.04 | 9154.04 | 9154.04
WIRE01 | 22066078 | 126 | L5 P3 BTM and Hobs | 1 | EACH | 11058.51 | 11058.51 | 11058.51
WIRE01 | 22066078 | 127 | L5 Stair 1 | 1 | EACH | 1057.02 | 1057.02 | 1057.02
WIRE01 | 22066078 | 128 | Roof - Stair 3 Lid | 1 | EACH | 1369.59 | 1369.59 | 1369.59
WIRE01 | 22066078 | 129 | L5 P3 Top | 1 | EACH | 9515.94 | 9515.94 | 9515.94
WIRE01 | 22066078 | 130 | L5 walls Pour 2 | 1 | EACH | 17497.69 | 17497.69 | 17497.69
WIRE01 | 22066078 | 131 | Plant Deck BTM | 1 | EACH | 10286.79 | 10286.79 | 10286.79
WIRE01 | 22066078 | 132 | L5 - RF Walls P3 | 1 | EACH | 249.55 | 249.55 | 249.55
WIRE01 | 22066078 | 133 | L5-RF walls p2 galv | 1 | EACH | 544.3 | 544.3 | 544.3
WIRE01 | 22066078 | 134 | Stair Lid 1 | 1 | EACH | 1742.86 | 1742.86 | 1742.86
WIRE01 | 22066078 | 135 | L5 - P3 blockwalls | 1 | EACH | 4107.49 | 4107.49 | 4107.49
WIRE01 | 22066078 | 136 | Roof Plant Deck Top | 1 | EACH | 3715.37 | 3715.37 | 3715.37
Sum: | [6 empty] | 1063144.24 | 1062915.57
Subcontracts
C&SS01 | 22066021 | 40 | L3 Pour 2 Top | 8.021 | TONNE | 740 | 5935.54 | 5935.54
Total Subcontracts | [6 empty] | 5935.54 | 5935.54
Forecast Amounts
|  | 9 | External Reo | 1 | SUM | 25720.85 | 25720.85
|  | 10 | Deliveries | 1 | SUM | 1900 | 1900
|  | 12 | Additional External Area Reo | 1 | ITEM | 9500 | 9500
|  | 8999 | 020027 Traffic Island - reo su | 1 | EACH | 180 | 180
|  | 89998 | 020022 Cafe Entrance - Deducte | 1 | ITEM | -432 | -432
Total Forecasts | [6 empty] | 36868.85
Total for Cost Centre | [6 empty] | 1131539.83 | 1094442.31
T092 | ST |  | REINFORCEMENT PLACING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
C&SS01 | 22066021 | 1 | Footings Bar Install | 18.988 | TONNE | 740 | 14051.12 | 14051.12
C&SS01 | 22066021 | 2 | Schedule No: 593191 | 12.81 | TONNE | 740 | 9479.4 | 9479.4
C&SS01 | 22066021 | 3 | Schedule No: 593190 | 5.43 | TONNE | 740 | 4018.2 | 4018.2
C&SS01 | 22066021 | 4 | Schedule No: 593186 | 3.59 | TONNE | 740 | 2656.6 | 2656.6
C&SS01 | 22066021 | 5 | Schedule No: 591469 | 14.18 | TONNE | 740 | 10493.2 | 10493.2
C&SS01 | 22066021 | 6 | Schedule No: 591461 | 3.15 | TONNE | 740 | 2331 | 2331
C&SS01 | 22066021 | 7 | Schedule No: 591458 | 4 | TONNE | 740 | 2960 | 2960
C&SS01 | 22066021 | 8 | VI:REINFORCEMENT PLACING | 0 |  | 0 | 675 | 675
C&SS01 | 22066021 | 9 | VI:REINFORCEMENT PLACING | 0 |  | 0 | 300 | 300
C&SS01 | 22066021 | 10 | Schedule No: 591462 | 5.64 | TONNE | 740 | 4173.6 | 4173.6
C&SS01 | 22066021 | 11 | Schedule No: 595081 | 1.93 | SUM | 740 | 1428.2 | 1428.2
C&SS01 | 22066021 | 12 | Schedule No: 598667 | 10.61 | TONNE | 740 | 7851.4 | 7851.4
C&SS01 | 22066021 | 13 | Schedule No: 598684 | 8.94 | TONNE | 740 | 6615.6 | 6615.6
C&SS01 | 22066021 | 14 | VI:REINFORCEMENT PLACING | 0 |  | 0 | 3300 | 3300
C&SS01 | 22066021 | 17 | Schedule No: L1 Pour 2 BTM | 14.982 | TONNE | 740 | 11086.68 | 11086.68
C&SS01 | 22066021 | 18 | Schedule No: 600058 | 5.725 | TONNE | 740 | 4236.5 | 4236.5
C&SS01 | 22066021 | 19 | Schedule No: 600839 | 10.119 | TONNE | 740 | 7488.06 | 7488.06
C&SS01 | 22066021 | 20 | Schedule No: 600606 | 12.037 | TONNE | 740 | 8907.38 | 8907.38
C&SS01 | 22066021 | 21 | Schedule No: 601414 | 0.774 | TONNE | 740 | 572.76 | 572.76
C&SS01 | 22066021 | 22 | Zone 3 Level 1 Top layer | 8.315 | TONNE | 740 | 6153.1 | 6153.1
C&SS01 | 22066021 | 23 | Zone 1 Level 2 Bottom Steel | 7.436 | TONNE | 740 | 5502.64 | 5502.64
C&SS01 | 22066021 | 24 | Zone 1 Level 2 Top Steel | 6.633 | TONNE | 740 | 4908.42 | 4908.42
C&SS01 | 22066021 | 25 | Stairs | 5 | EACH | 500 | 2500 | 2500
C&SS01 | 22066021 | 26 | Schedule No: 604405 | 9.477 | TONNE | 740 | 7012.98 | 7012.98
C&SS01 | 22066021 | 27 | Schedule No: 604414 | 8.021 | TONNE | 740 | 5935.54 | 5935.54
C&SS01 | 22066021 | 28 | Level 1 Stud Rails | 48 | EACH | 30 | 1440 | 1440
C&SS01 | 22066021 | 29 | L2 Stud Rails | 96 | EACH | 30 | 2880 | 2880
C&SS01 | 22066021 | 30 | Schedule No: 604818 | 6.203 | TONNE | 740 | 4590.22 | 4590.22
C&SS01 | 22066021 | 31 | Schedule No: 604821 | 5.113 | TONNE | 740 | 3783.62 | 3783.62
C&SS01 | 22066021 | 32 | Schdule No: 602822 | 6.795 | TONNE | 740 | 5028.3 | 5028.3
C&SS01 | 22066021 | 33 | Schedule No: 606870 | 6.633 | TONNE | 740 | 4908.42 | 4908.42
C&SS01 | 22066021 | 34 | L4 P1 Top | 6.633 | TONNE | 740 | 4908.42 | 4908.42
C&SS01 | 22066021 | 35 | L4 P1 Btm | 6.795 | TONNE | 740 | 5028.3 | 5028.3
C&SS01 | 22066021 | 36 | L3 Columns | 1.876 | TONNE | 740 | 1388.24 | 1388.24
C&SS01 | 22066021 | 37 | L3 Pour 3 Top | 4.722 | TONNE | 740 | 3494.28 | 3494.28
C&SS01 | 22066021 | 38 | L3 Pour 3 Btm | 5.476 | TONNE | 740 | 4052.24 | 4052.24
C&SS01 | 22066021 | 39 | L2-3 Stairs | 3 | ITEM | 500 | 1500 | 1500
C&SS01 | 22066021 | 41 | L3 Pour 2 BTM | 7.75 | REIN | 740 | 5735 | 5735
C&SS01 | 22066021 | 42 | L4 Stud Rails | 68 | EACH | 30 | 2040 | 2040
C&SS01 | 22066021 | 43 | Tie Wire Cost | 1 | SUM | 1975 | 1975 | 1975
C&SS01 | 22066021 | 44 | L4 Pour 2 BTM | 7.75 | TONNE | 740 | 5735 | 5735
C&SS01 | 22066021 | 45 | L4 P2 Top Steel | 8.021 | TONNE | 740 | 5935.54 | 5935.54
C&SS01 | 22066021 | 46 | L4 Pour 2 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 47 | L4 P3 BTM | 5.016 | TONNE | 740 | 3711.84 | 3711.84
C&SS01 | 22066021 | 48 | L4 Pour 3 TOP | 4.722 | TONNE | 740 | 3494.28 | 3494.28
C&SS01 | 22066021 | 49 | L4 P3 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 50 | L5 P1 BTM | 6.816 | TONNE | 740 | 5043.84 | 5043.84
C&SS01 | 22066021 | 51 | L5 P1 TOP | 6.633 | TONNE | 740 | 4908.42 | 4908.42
C&SS01 | 22066021 | 52 | L5 P2 BTM | 7.75 | TONNE | 740 | 5735 | 5735
C&SS01 | 22066021 | 53 | L5 P2 TOP | 8.021 | TONNE | 740 | 5935.54 | 5935.54
C&SS01 | 22066021 | 54 | L5 P2 Shear and Starters | 0.623 | TONNE | 740 | 461.02 | 461.02
C&SS01 | 22066021 | 55 | L5 P2 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 56 | L5 P3 BTM | 5.037 | TONNE | 740 | 3727.38 | 3727.38
C&SS01 | 22066021 | 57 | L5 P3 Top | 4.722 | TONNE | 740 | 3494.28 | 3494.28
C&SS01 | 22066021 | 58 | L5 P3 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 59 | L4 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 60 | L4 Column | 5.537 | TONNE | 740 | 4097.38 | 4097.38
C&SS01 | 22066021 | 61 | L5 Stairs | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 62 | L5 Columns | 2.537 | TONNE | 740 | 1877.38 | 1877.38
C&SS01 | 22066021 | 63 | Roof Stair | 1 | ITEM | 500 | 500 | 500
C&SS01 | 22066021 | 64 | Roof Slab | 6.298 | TONNE | 740 | 4660.52 | 4660.52
C&SS01 | 22066021 | 65 | day works march | 20 | HOURS | 75 | 1500 | 1500
Total Subcontracts | [6 empty] | 251206.84 | 251206.84
Forecast Amounts
|  | 5 | Level 2 | 1 | SUM | 4925.94 | 4925.94
|  | 6 | level 3 | 1 | SUM | 2794.24 | 2794.24
|  | 8 | Level 5 | 1 | SUM | 1110 | 1110
|  | 9 | roof | 1 | SUM | 1320.9 | 1320.9
|  | 10 | Day Labour (Drilling) | 115 | SUM | 75 | 8625
Total Forecasts | [6 empty] | 18776.08
Total for Cost Centre | [6 empty] | 269982.92 | 251206.84
T093 | ST |  | FORMWORK
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
TKFO01 | 22066008 | 1 | Lift Pit | 1 | NO | 5900 | 5900 | 5900
TKFO01 | 22066008 | 2 | Ground Level Verticals | 1 | NO | 36400 | 36400 | 34580
TKFO01 | 22066008 | 3 | Level 1 | 1 | NO | 252500 | 252500 | 252500
TKFO01 | 22066008 | 4 | Level 1 Verticals | 1 | NO | 24450 | 24450 | 24450
TKFO01 | 22066008 | 5 | Level 2 | 1 | NO | 171000 | 171000 | 171000
TKFO01 | 22066008 | 6 | Level 2 Verticals | 1 | NO | 24450 | 24450 | 24450
TKFO01 | 22066008 | 7 | Level 3 | 1 | NO | 170000 | 170000 | 170000
TKFO01 | 22066008 | 8 | Level 3 Verticals | 1 | NO | 24450 | 24450 | 24450
TKFO01 | 22066008 | 9 | Level 4 | 1 | NO | 170000 | 170000 | 170000
TKFO01 | 22066008 | 10 | Level 4 Verticals | 1 | NO | 24450 | 24450 | 24450
TKFO01 | 22066008 | 11 | Level 5 | 1 | NO | 170000 | 170000 | 170000
TKFO01 | 22066008 | 12 | Level 5 Verticals | 1 | NO | 24450 | 24450 | 24450
TKFO01 | 22066008 | 13 | Lids | 1 | NO | 35450 | 35450 | 35450
TKFO01 | 22066008 | 14 | Stairs | 1 | NO | 66500 | 66500 | 66500
TKFO01 | 22066008 | 15 | VI:FORMWORK | 0 |  | 0 | 140250 | 140250
TKFO01 | 22066008 | 16 | VI:FORMWORK | 0 |  | 0 | 12680 | 12680
TKFO01 | 22066008 | 17 | VI:FORMWORK | 0 |  | 0 | -13926.4 | -13926.4
TKFO01 | 22066008 | 19 | VI:FORMWORK | 0 |  | 0 | 1497.5 | 1497.5
Total Subcontracts | [6 empty] | 1340501.1 | 1338681.1
Forecast Amounts
|  | 3 | Day Labour Works | 2.5 | LEVEL | 1150 | 2875
Total Forecasts | [6 empty] | 2875
Total for Cost Centre | [6 empty] | 1343376.1 | 1338681.1
T094 | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
KENN01 | 22066131 | 1 | Rotary hammer drill required for starters into block (where AFS was unable to be supplied in time - backcharge) | 2.4 | EACH | 609.09 | 1327.45 | 1327.45
Sum: | [6 empty] | 1327.45 | 1327.45
Uncompleted Purchase Orders
AFSS01 | 22066061 | 1 | Logicwall 200mm | 351.6 | M2 | 98 | 34456.8 | 10955.41
AFSS01 | 22066061 | 2 | Logic wall 262mm | 31.18 | M2 | 120 | 3741.6 | 853.2
AFSS01 | 22066061 | 3 | Screw FC 8G x 25mm Box of 1000 Uncollated | 3 | EACH | 37.1 | 111.3 | 111.3
Sum: | [6 empty] | 38309.7 | 11919.91
Total for Cost Centre | [6 empty] | 39637.15 | 13247.36
T094 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
KRBG01 | 22066025 | 1 | Permanent Formwork Package | 1 | NO | 53720.95 | 53720.95 | 51220.95
KRBG01 | 22066025 | 2 | VI:Permanent Formwork | 0 |  | 0 | -8338.35 | -8338.35
KRBG01 | 22066025 | 3 | VI:Permanent Formwork | 0 |  | 0 | -4400 | -4400
KRBG01 | 22066025 | 4 | VI:Permanent Formwork | 0 |  | 0 | -1752.46 | -1752.46
KRBG01 | 22066025 | 5 | VI:Permanent Formwork | 0 |  | 0 | -1116.44 | -1116.44
MGBR01 | 22066019 | 13 | VI:Permanent Formwork | 0 |  | 0 | 2400 | 2400
MGBR01 | 22066019 | 15 | VI:Permanent Formwork | 0 |  | 0 | 2000 | 2000
TKFO01 | 22066008 | 18 | VI:Permanent Formwork | 0 |  | 0 | 1373 | 1373
Total Subcontracts | [6 empty] | 43886.7 | 41386.7
Total for Cost Centre | [6 empty] | 43886.7 | 41386.7
T11 | ST |  | MASONRY - BLOCKWORK
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BRIS76 | 22066105 | 1 | 26' Electric Scissor Lift | 4 | WEEKS | 320 | 1280 | 1280
BRIS76 | 22066105 | 2 | Delivery / Collection | 3 | EACH | 160 | 480 | 480
REEC02 | 22066118 | 1 | Supply 15x 200x75x90 Degree HDPE Scupper to Pelican Waters | 1 | EACH | 1035 | 1035 | 1035
SUNC20 | 22066081 | 9 | Blockies Concrete Cutting | 1 | EACH | 1814.25 | 1814.25 | 1814.25
SUNC20 | 22066081 | 11 | Concrete Cutting - MG Backcharge | 1 | EACH | 516.3 | 516.3 | 516.3
Sum: | [6 empty] | 5125.55 | 5125.55
Uncompleted Purchase Orders
BRIS76 | 22066105 | 3 | 26' Electric Scissor Lift | 14.2 | WEEKS | 280 | 3976 | 4584
CUTC02 | 22066149 | 2 | MG Back charge | 1 | EACH | 508 | 508 | 508
Sum: | [6 empty] | 4484 | 5092
Subcontracts
M&CJ01 | 22066039 | 1 | Blockwork Joint Sealing | 752 | LM | 9.8 | 7369.6 | 7369.6
M&CJ01 | 22066039 | 2 | Form 12 | 1 | ITEM | 750 | 750 | 750
M&CJ01 | 22066039 | 4 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 15376.2 | 15376.2
MGBR01 | 22066019 | 1 | Blockwork Ground | 1 | NO | 484000 | 484000 | 459800
MGBR01 | 22066019 | 2 | Blockwork Level 1 | 1 | NO | 196000 | 196000 | 196000
MGBR01 | 22066019 | 3 | Blockwork Level 2 | 1 | NO | 157000 | 157000 | 157000
MGBR01 | 22066019 | 4 | Blockwork Level 3 | 1 | NO | 152000 | 152000 | 152000
MGBR01 | 22066019 | 5 | Blockwork Level 4 | 1 | NO | 152000 | 152000 | 152000
MGBR01 | 22066019 | 6 | Blockwork Level 5 | 1 | NO | 209000 | 209000 | 209000
MGBR01 | 22066019 | 7 | Blockwork Roof Plant Deck | 1 | NO | 30000 | 30000 | 30000
MGBR01 | 22066019 | 8 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 300 | 300
MGBR01 | 22066019 | 11 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 3500 | 3500
MGBR01 | 22066019 | 12 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 1200 | 1200
MGBR01 | 22066019 | 17 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 245 | 245
MGBR01 | 22066019 | 18 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | 36500 | 36500
MGBR01 | 22066019 | 19 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | -2900 | -2900
MGBR01 | 22066019 | 21 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | -508 | -508
MGBR01 | 22066019 | 22 | VI:MASONRY - BLOCKWORK | 0 |  | 0 | -1814.25 | -1814.25
Total Subcontracts | [6 empty] | 1440018.55 | 1415818.55
Forecast Amounts
|  | 4 | Caulking to Blockwork | 940 | LM | 9.8 | 9212
|  | 9 | Fireplace | 1 | NO | 4534 | 4534
|  | 10 | Access for Level 5 Blockwork | 1 | NO | 7450 | 7450
|  | 13 | Drilling & Epoxy Starters to | 5 | LEVEL | 1100 | 5500
Total Forecasts | [6 empty] | 26696
Total for Cost Centre | [6 empty] | 1476324.1 | 1426036.1
T12 | ST |  | STRUCTURAL STEEL
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
BEEL02 | 22066035 | 1 | Porte Cochere & Wanderers | 1 | NO | 74000 | 74000 | 0
BEEL02 | 22066035 | 2 | Window Headers & Supports | 1 | NO | 8270 | 8270 | 8270
BEEL02 | 22066035 | 3 | L5 Window Headers & Columns | 1 | NO | 22215 | 22215 | 22215
BEEL02 | 22066035 | 4 | Installation of L5 Columns | 1 | NO | 2960 | 2960 | 0
BEEL02 | 22066035 | 5 | VI:STRUCTURAL STEEL | 0 |  | 0 | 780 | 780
BEEL02 | 22066035 | 6 | VI:STRUCTURAL STEEL | 0 |  | 0 | 3643 | 3643
BEEL02 | 22066035 | 7 | VI:STRUCTURAL STEEL | 0 |  | 0 | 930 | 930
BEEL02 | 22066035 | 8 | VI:STRUCTURAL STEEL | 0 |  | 0 | 5998 | 5998
BEEL02 | 22066035 | 9 | VI:STRUCTURAL STEEL | 0 |  | 0 | -2960 | -2960
BEEL02 | 22066035 | 10 | VI:STRUCTURAL STEEL | 0 |  | 0 | -1845 | -1845
BEEL02 | 22066035 | 14 | VI:STRUCTURAL STEEL | 0 |  | 0 | 160 | 160
BEEL02 | 22066035 | 15 | VI:STRUCTURAL STEEL | 0 |  | 0 | -2331 | -2331
BEEL02 | 22066035 | 16 | VI:STRUCTURAL STEEL | 0 |  | 0 | 7360 | 7360
UNIV24 | 22066037 | 28 | VI:STRUCTURAL STEEL | 0 |  | 0 | -5180 | -5180
Total Subcontracts | [6 empty] | 114000 | 37040
Forecast Amounts
|  | 89999 | 020022 Cafe Entrance - PFC and | 1 | ITEM | 1760 | 1760
Total Forecasts | [6 empty] | 1760
Total for Cost Centre | [6 empty] | 115760 | 37040
T13 | ST |  | METALWORK
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
CUST09 | 22066031 | 1 | Pool Fence to Cafe | 1 | SUM | 12897.46 | 12897.46 | 0
CUST09 | 22066031 | 2 | Juliet Balcony Balustrading | 1 | SUM | 32013.9 | 32013.9 | 30244.45
CUST09 | 22066031 | 3 | Supply/ Install Sun Hoods | 1 | SUM | 8434.44 | 8434.44 | 0
CUST09 | 22066031 | 4 | Horizontal Building Screening | 1 | SUM | 305989.95 | 305989.95 | 290690.44
CUST09 | 22066031 | 5 | Stair Screening | 1 | SUM | 43526.41 | 43526.41 | 34532.43
CUST09 | 22066031 | 6 | Bike Storage Screening, G3, | 1 | SUM | 8073.46 | 8073.46 | 0
CUST09 | 22066031 | 7 | Electronic Sliding Gates | 1 | SUM | 29334.98 | 29334.98 | 0
CUST09 | 22066031 | 8 | Transformer Enclosure | 1 | SUM | 7848.82 | 7848.82 | 0
CUST09 | 22066031 | 9 | B10-15 Shade Screening | 1 | SUM | 11166.6 | 11166.6 | 0
CUST09 | 22066031 | 10 | External Feature Screens | 1 | SUM | 43199.39 | 43199.39 | 0
CUST09 | 22066031 | 11 | Pergolas 1,3 & 4 Battens | 1 | SUM | 43320.32 | 43320.32 | 0
CUST09 | 22066031 | 12 | Boundary Fencing 1800mm | 1 | SUM | 48215.18 | 48215.18 | 0
CUST09 | 22066031 | 13 | VI:METALWORK | 0 |  | 0 | 6737 | 6737
CUST09 | 22066031 | 14 | VI:METALWORK | 0 |  | 0 | 3563.15 | 3563.15
CUST09 | 22066031 | 15 | VI:METALWORK | 0 |  | 0 | 11668.5 | 11668.5
CUST09 | 22066031 | 16 | VI:METALWORK | 0 |  | 0 | 4861.02 | 4861.02
Total Subcontracts | [6 empty] | 620850.58 | 382296.99
Forecast Amounts
|  | 1 | Convex Mirror for Maintenance | 1 | ITEM | 474.77 | 474.77
|  | 9 | Bike racks | 1 | ITEM | 6456.82 | 6456.82
|  | 10 | Alum Screen Footings | 1 | ITEM | 5000 | 5000
|  | 12 | Dentist Enclosure - | 1 | ITEM | 3259.75 | 3259.75
|  | 89999 | 020022 Additional Pool Fence | 1 | ITEM | 2494.78 | 2494.78
Total Forecasts | [6 empty] | 17686.12
Total for Cost Centre | [6 empty] | 638536.7 | 382296.99
T13RC | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
WAST02 | 22066015 | 1 | Lump Sum Laundry Chute | 1 | ITEM | 20500 | 20500 | 0
Total Subcontracts | [6 empty] | 20500 | 0
Total for Cost Centre | [6 empty] | 20500 | 0
T14 | ST |  | ROOFING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
UNDE06 | 22066036 | 1 | Roofing Subcontract | 1 | NO | 273620 | 273620 | 177853
UNDE06 | 22066036 | 2 | VI:ROOFING | 0 |  | 0 | 9450.89 | 9450.89
UNDE06 | 22066036 | 3 | VI:ROOFING | 0 |  | 0 | 1056 | 1056
Total Subcontracts | [6 empty] | 284126.89 | 188359.89
Forecast Amounts
|  | 4 | Additional Service | 1 | ITEM | 1400 | 1400
|  | 6 | Gutter Guard Credit to Client | 1 | SUM | 4380 | 4380
Total Forecasts | [6 empty] | 5780
Total for Cost Centre | [6 empty] | 289906.89 | 188359.89
T14RS | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
MARS07 | 22066040 | 1 | Roof Access System | 1 | SUM | 50955 | 50955 | 46410
MARS07 | 22066040 | 2 | VI:ROOF ACCESS & SAFETY | 0 |  | 0 | -3475 | -3475
Total Subcontracts | [6 empty] | 47480 | 42935
Total for Cost Centre | [6 empty] | 47480 | 42935
T15 | ST |  | WATERPROOFING & TANKING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
MMWA01 | 22066027 | 1 | Lift Pit Waterproofing | 1 | ITEM | 5235 | 5235 | 5235
MMWA01 | 22066032 | 1 | Plant Deck & Lower Roof | 1 | ITEM | 18275 | 18275 | 0
MMWA01 | 22066032 | 2 | Wanderers Deck | 1 | ITEM | 10200 | 10200 | 0
MMWA01 | 22066032 | 3 | Slab Extensions | 1 | ITEM | 23725 | 23725 | 3900
MMWA01 | 22066032 | 4 | Wet Areas (ensuites) | 1 | ITEM | 114112.5 | 114112.5 | 65250
MMWA01 | 22066032 | 5 | Wet Areas (common) | 1 | ITEM | 52812.5 | 52812.5 | 0
MMWA01 | 22066032 | 6 | Reveals | 1 | ITEM | 58275 | 58275 | 58275
MMWA01 | 22066032 | 7 | VI:WATERPROOFING & TANKING | 0 |  | 0 | 1020 | 1020
MMWA01 | 22066032 | 9 | VI:WATERPROOFING & TANKING | 0 |  | 0 | 540 | 540
Total Subcontracts | [6 empty] | 284195 | 134220
Forecast Amounts
|  | 3 | Client Credit for Removed | 1 | ITEM | 2025 | 2025
|  | 8999 | 020012 Waterproofing Water | 1 | EACH | 2500 | 2500
Total Forecasts | [6 empty] | 4525
Total for Cost Centre | [6 empty] | 288720 | 134220
T16 | LW
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Payroll
DAVI13 |  |  | KYE ROBERT DAVIS | 138.78 |  |  | 6594.5 | 6594.5
NIEL04 |  |  | KYLE JAMES NIELSEN | 189.83 |  |  | 9643.4 | 9643.4
PHIL04 |  |  | GEORGE PHILLIPS | 223.19 |  |  | 11889.38 | 11889.38
PIPE01 |  |  | GRANT PIPER | 112 |  |  | 1133.88 | 1133.88
SEST03 |  |  | LUKE SESTRO | 269.85 |  |  | 4475.31 | 4475.31
SMIT09 |  |  | DANIEL JON SMITH | 7.5 |  |  | 348.63 | 348.63
SPAL01 |  |  | JAMES SPALDING | 9 |  |  | 459.27 | 459.27
THORN01 |  |  | NICHOLAS THORNTON | 52.75 |  |  | 2138.27 | 2138.27
WEEK02 |  |  | SAVANNAH WEEKS | 9.75 |  |  | 253.64 | 253.64
WELL03 |  |  | REECE WELLUPPILLAI | 100.2 |  |  | 3446.36 | 3446.36
Sum: | [6 empty] | 40382.64 | 40382.64
Total for Cost Centre | [6 empty] | 40382.64 | 40382.64
T16 | ST |  | CARPENTRY - MISCELLANEOUS
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BUNN01 | 22066166 | 1 | SPT - Misc | 1 | EACH | 300 | 264.52 | 264.52
BUNN01 | 22066175 | 1 | Construction Supplies | 1 | EACH | 250 | 151.58 | 151.58
KJBO01 | 22066170 | 1 | SPT - Truss Fixings | 1 | EACH | 125.98 | 125.98 | 125.98
KJBO01 | 22066170 | 2 | SPT - Truss Fixings | 1 | EACH | 71.28 | 71.28 | 71.28
KJBO01 | 22066170 | 3 | SPT - Truss Fixings | 1 | EACH | 86 | 86 | 86
KJBO01 | 22066170 | 4 | SPT - Truss Fixings | 1 | EACH | 110.85 | 110.85 | 110.85
Sum: | [6 empty] | 810.21 | 810.21
Uncompleted Purchase Orders
BRIS76 | 22066105 | 4 | 13' Electrc Scissor Lift - SPT | 5.2 | WEEK | 160 | 832 | 832
BRIS76 | 22066105 | 5 | 13' Electric Scissor Lift - SPT | 5.2 | WEEK | 160 | 832 | 832
BRIS76 | 22066105 | 6 | SPT - Delivery | 1 | EACH | 200 | 200 | 200
BRIS76 | 22066105 | 7 | Collection | 1 | EACH | 160 | 160 | 160
BUNN01 | 22066155 | 1 | Carpentry Truss Materials | 1 | EACH | 1000 | 1000 | 281.37
BUNN01 | 22066161 | 1 | Self Perform | 1 | EACH | 300 | 300 | 161.77
BUNN01 | 22066168 | 1 | SPT - Speed Bracing | 1 | EACH | 471.77 | 471.77 | 471.77
BUNN01 | 22066175 | 2 | Construction Supplies | 1 | EACH | 46 | 46 | 46
BUNN01 | 22066179 | 1 | Skirting Supply | 1 | EACH | 1034.78 | 1034.78 | 1034.78
BUNN01 | 22066185 | 1 | Pine Moulding | 105 | LENGT | 9.92 | 1041.6 | 956.08
BUNN01 | 22066198 | 1 | Skirting Order | 80 | LENGT | 9.92 | 793.6 | 0
INTR03 | 22066151 | 1 | SK06 - 66x12 | 2322 | LM | 3 | 6966 | 0
INTR03 | 22066151 | 2 | SK93 - 185 x 18 | 848 | LM | 15.17 | 12864.16 | 3916.08
INTR03 | 22066151 | 3 | Deliveries | 4 | NO | 410 | 1640 | 410
INTR03 | 22066151 | 4 | SK 93 185x18mm Additional | 1.1 | EACH | 2591.88 | 2851.07 | 0
INTR03 | 22066151 | 5 | Sk93 185x18mm Additional | 1 | EACH | 2116.8 | 2116.8 | 0
KENN01 | 22066133 | 7 | Soffit scaffold hire | 1 | EACH | 542.64 | 542.64 | 542.64
KJBO01 | 22066170 | 5 | SPT - Truss Fixings | 1 | EACH | 46.22 | 46.22 | 46.22
MCNA10 | 22066030 | 46 | SPT - Hire Items | 1 | EACH | 3380.12 | 3380.12 | 3380.12
MCNA10 | 22066030 | 48 | SPT Hired Items | 1 | EACH | 2158.81 | 2158.81 | 2158.81
PETT01 | 21ADR007 | 1737 | PIPER G - POLE PLATE HOLES | 1 | EACH | 222.73 | 222.73 | 222.73
SYDN01 | 22066156 | 1 | SPT - Roof Truss Install | 1 | EACH | 500 | 500 | 210.91
Sum: | [6 empty] | 40000.3 | 15863.28
Subcontracts
APEX08 | 22066030 | 9 | Carpentry - Fixout | 1 | NO | 108000 | 108000 | 21600
APEX08 | 22066030 | 10 | Carpentry - Fitoff | 1 | NO | 96000 | 96000 | 0
APEX08 | 22066030 | 12 | VI:CARPENTRY - MISCELLANEOUS | 0 |  | 0 | 12110 | 12110
APEX08 | 22066030 | 14 | VI:CARPENTRY - MISCELLANEOUS | 0 |  | 0 | 12500 | 12500
CUST19 | 22066020 | 7 | VI:CARPENTRY - MISCELLANEOUS | 0 |  | 0 | -1485 | -1485
Total Subcontracts | [6 empty] | 227125 | 44725
Forecast Amounts
|  | 3 | Skirting | 1 | ITEM | 2000 | 2000
|  | 7 | Lantham Bump Rail to Bin Room | 1 | ITEM | 4600 | 4600
|  | 8 | Lantham Bump Rail to Laundry | 1 | ITEM | 5000 | 5000
|  | 9 | Bump Rail Install | 1 | ITEM | 3500 | 3500
|  | 89999 | 020025 Storerooms - skirting | 1 | ITEM | 364.08 | 364.08
Total Forecasts | [6 empty] | 15464.08
Total for Cost Centre | [6 empty] | 283399.59 | 61398.49
T16TT | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
BUNN01 | 22066171 | 1 | Valley Gutter Materials | 1 | EACH | 462 | 462 | 462
STRA01 | 22066167 | 1 | Additional Roof Truss Material | 1 | EACH | 782.68 | 782.68 | 782.68
Sum: | [6 empty] | 1244.68 | 1244.68
Subcontracts
CUST19 | 22066020 | 1 | 10% Deposit | 1 | SUM | 17613 | 17613 | 17613
CUST19 | 22066020 | 2 | 90% upon Delivery | 1 | SUM | 158517 | 158517 | 158517
CUST19 | 22066020 | 3 | VI:TRUSSES | 0 |  | 0 | 2465 | 2465
CUST19 | 22066020 | 4 | VI:TRUSSES | 0 |  | 0 | 8070 | 8070
CUST19 | 22066020 | 6 | VI:TRUSSES | 0 |  | 0 | -782.68 | -782.68
CUST19 | 22066020 | 8 | VI:TRUSSES | 0 |  | 0 | 250 | 250
Total Subcontracts | [6 empty] | 186132.32 | 186132.32
Total for Cost Centre | [6 empty] | 187377 | 187377
T17 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CUTC02 | 22066149 | 3 | Rebate Cutting | 1 | EACH | 1038.3 | 1038.3 | 1038.3
SUNC36 | 22066187 | 1 | Glazing Rebates | 1 | EACH | 195 | 195 | 195
Sum: | [6 empty] | 1233.3 | 1233.3
Subcontracts
FITO01 | 22066016 | 1 | Shop Drawings | 1 | ITEM | 8500 | 12010 | 12010
FITO01 | 22066016 | 2 | Aluminium Frames & Glazed | 1 | ITEM | 1222098 | 1222098 | 1102948.18
FITO01 | 22066016 | 3 | Crimsafe | 1 | ITEM | 69529 | 69529 | 0
FITO01 | 22066016 | 4 | Waterstop Sill Angles | 1 | ITEM | 19613 | 19613 | 17766
FITO01 | 22066016 | 5 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | 31980 | 31980
FITO01 | 22066016 | 6 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | -20260 | -20260
FITO01 | 22066016 | 7 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | 1015 | 1015
FITO01 | 22066016 | 8 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | 1790 | 1790
FITO01 | 22066016 | 9 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | -4950 | -4950
INGL01 | 22066052 | 1 | Servery Windows | 1 | NO | 9209.1 | 9209.1 | 0
UNIV24 | 22066037 | 22 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | 20000 | 20000
UNIV24 | 22066037 | 27 | VI:ALUMINIUM WINDOWS & DOORS | 0 |  | 0 | 4500 | 4500
Total Subcontracts | [6 empty] | 1366534.1 | 1166799.18
Total for Cost Centre | [6 empty] | 1367767.4 | 1168032.48
T18 | MT |  | DOOR & SUNDRY HARDWARE
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
HAFE01 | 22066177 | 1 | Sliding Door Track | 1 | EACH | 138 | 138 | 138
HAFE01 | 22066177 | 2 | Sliding Door Track - Rail | 1 | EACH | 45 | 45 | 45
Sum: | [6 empty] | 183 | 183
Uncompleted Purchase Orders
HAFE01 | 22066134 | 1 | Lump Sum Door Hardware Supply | 1 | EACH | 66374.95 | 66374.95 | 45203.15
Sum: | [6 empty] | 66374.95 | 45203.15
Subcontracts
APEX08 | 22066030 | 11 | VI:DOOR & SUNDRY HARDWARE | 0 |  | 0 | 14400 | 14400
RICK01 | 22066026 | 12 | VI:DOOR & SUNDRY HARDWARE | 0 |  | 0 | 17428 | 17428
Total Subcontracts | [6 empty] | 31828 | 31828
Forecast Amounts
|  | 2 | Deliveries | 11 | NO | 22 | 242
|  | 5 | Miscallaneous Hardware | 1 | NO | 5150 | 5150
|  | 89999 | 020025 Storerooms - door hardw | 1 | ITEM | 599.2 | 599.2
Total Forecasts | [6 empty] | 5991.2
Total for Cost Centre | [6 empty] | 104377.15 | 77214.15
T18 | ST |  | TIMBER DOORS & FRAMES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
RICK01 | 22066046 | 1 | Early-works door frame supply to the Rockpool Pelican Waters Project which includes the following frames: D33, D35, D36, D37, D38, 2x D45, D46, 2x F1, F2, & F4. Shop drawings and delivery to Spitfire Bank Drive Pelican Waters included in fee. | 1 | EACH | 3256 | 3256 | 3256
RICK01 | 22066046 | 2 | Additional 2 Frames | 1 | EACH | 660 | 660 | 660
RICK01 | 22066046 | 3 | Epoxy Primer - 5 Frames | 1 | EACH | 275 | 275 | 275
Sum: | [6 empty] | 4191 | 4191
Subcontracts
APEX08 | 22066030 | 13 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | 2933.5 | 2933.5
BEST05 | 22066033 | 1 | Lump Sum Roller Door | 1 | ITEM | 5291 | 5291 | 5291
BEST05 | 22066033 | 2 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | -466 | -466
RICK01 | 22066026 | 1 | Supply only Fire Rated | 1 | ITEM | 14717.01 | 10526.01 | 10526.01
RICK01 | 22066026 | 2 | Supply only Non Rated | 1 | ITEM | 119153.26 | 119153.26 | 119153.26
RICK01 | 22066026 | 3 | Supply only Non Rated Doors | 1 | ITEM | 109123.96 | 109123.96 | 25218
RICK01 | 22066026 | 4 | Supply only Fire Rated Doors | 1 | ITEM | 23577.6 | 23577.6 | 4849.2
RICK01 | 22066026 | 5 | Certification | 1 | ITEM | 1700 | 1700 | 0
RICK01 | 22066026 | 6 | Freight for Frames | 18 | EA | 225 | 4050 | 4050
RICK01 | 22066026 | 7 | Freight for Doors | 18 | EA | 350 | 6300 | 700
RICK01 | 22066026 | 8 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | 8825.29 | 8825.29
RICK01 | 22066026 | 9 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | 6448 | 6448
RICK01 | 22066026 | 10 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | -10605.35 | -10605.35
RICK01 | 22066026 | 11 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | -2933.5 | -2933.5
RICK01 | 22066026 | 13 | VI:TIMBER DOORS & FRAMES | 0 |  | 0 | -12240 | -12240
Total Subcontracts | [6 empty] | 271683.77 | 161749.41
Forecast Amounts
|  | 89999 | 020025 Storerooms - door suppl | 1 | ITEM | 500 | 500
|  | 90000 | Door Frames - Delay Costs | 1 | NO | 12240 | 12240
Total Forecasts | [6 empty] | 12740
Total for Cost Centre | [6 empty] | 288614.77 | 165940.41
T19 | ST |  | CEILINGS & PARTITIONS
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
APEX08 | 22066030 | 1 | C&P Ground Level | 1 | NO | 500000 | 500000 | 400000
APEX08 | 22066030 | 3 | C&P Level 1 | 1 | NO | 500000 | 500000 | 475000
APEX08 | 22066030 | 4 | C&P Level 2 | 1 | NO | 500000 | 500000 | 475000
APEX08 | 22066030 | 5 | C&P Level 3 | 1 | NO | 500000 | 500000 | 475000
APEX08 | 22066030 | 6 | C&P Level 4 | 1 | NO | 500000 | 500000 | 400000
APEX08 | 22066030 | 7 | C&P Level 5 | 1 | NO | 500000 | 500000 | 250000
APEX08 | 22066030 | 8 | Soffits | 1 | NO | 76446 | 76446 | 76446
APEX08 | 22066030 | 15 | VI:CEILINGS & PARTITIONS | 0 |  | 0 | 11240 | 11240
APEX08 | 22066030 | 16 | VI:CEILINGS & PARTITIONS | 0 |  | 0 | 1590 | 1590
Total Subcontracts | [6 empty] | 3089276 | 2564276
Forecast Amounts
|  | 3 | Additonal Access Panels | 165 | NO | 160 | 26400
|  | 4 | Mech Grille Framing | 150 | NO | 130 | 19500
Total Forecasts | [6 empty] | 45900
Total for Cost Centre | [6 empty] | 3135176 | 2564276
T20 | ST |  | JOINERY & BENCHTOPS
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
BRIS76 | 22066057 | 1 | Forklift Hire | 8 | WEEKS | 600 | 4800 | 4800
BRIS76 | 22066057 | 2 | Forklift Rotator | 8 | WEEKS | 50 | 400 | 400
BRIS76 | 22066057 | 3 | Forklift Slippers | 8 | WEEKS | 50 | 400 | 400
BRIS76 | 22066057 | 4 | Delivery | 2 | ITEM | 550 | 1100 | 1100
MCNA01 | 22066103 | 1 | 20% DEPOSIT JOINERY CONTRACT (BRUN KITCHENS) | 65000 | USD | 1.6 | 104000 | 97842.7
MCNA01 | 22066103 | 2 | 80% BALANCE JOINERY CONTRACT (BRUN KITCHENS) | 240915.28 | USD | 1.6 | 385464.45 | 0
MCNA01 | 22066103 | 3 | CONTRA TO MOVE TO MCNA13 | -240915.28 | USD | 1.6 | -385464.45 | 0
MCNA13 | 22066200 | 1 | 80% BALANCE JOINERY CONTRACT | 240915.28 | USD | 1.6 | 385464.45 | 188884.53
Sum: | [6 empty] | 496164.45 | 293427.23
Subcontracts
BOUT06 | 22066022 | 1 | Joinery - Ground Floor | 1 | SUM | 75179.22 | 75179.22 | 10744.16
BOUT06 | 22066022 | 2 | Joinery - Level 1 | 1 | SUM | 25577.7 | 25577.7 | 24298.83
BOUT06 | 22066022 | 3 | Joinery - Level 2 | 1 | SUM | 30751.58 | 30751.58 | 29214.01
BOUT06 | 22066022 | 4 | Joinery - Level 3 | 1 | SUM | 30751.58 | 30751.58 | 26138.85
BOUT06 | 22066022 | 5 | Joinery - Level 4 | 1 | SUM | 30751.59 | 30751.59 | 1537.57
BOUT06 | 22066022 | 6 | Joinery - Level 5 | 1 | SUM | 30751.59 | 30751.59 | 1537.57
BOUT06 | 22066022 | 7 | VI:JOINERY & BENCHTOPS | 0 |  | 0 | 4050 | 4050
BOUT06 | 22066022 | 8 | VI:JOINERY & BENCHTOPS | 0 |  | 0 | 18250 | 18250
BOUT06 | 22066022 | 9 | VI:JOINERY & BENCHTOPS | 0 |  | 0 | 4700 | 4700
BOUT06 | 22066022 | 13 | VI:JOINERY & BENCHTOPS | 0 |  | 0 | -1580 | -1580
BOUT06 | 22066022 | 17 | VI:JOINERY & BENCHTOPS | 0 |  | 0 | -14809 | -14809
FOUR02 | 22066049 | 1 | Stone Benchtop Subcontract | 1 | SUM | 33266 | 33266 | 0
INGL01 | 22066052 | 2 | Servery Splashbacks | 1 | NO | 14809.1 | 14809.1 | 0
PARA15 | 22066046 | 1 | Joinery Install Level 1 | 1 | NO | 29700 | 29700 | 29700
PARA15 | 22066046 | 2 | Joinery Install Level 2 | 1 | NO | 30000 | 30000 | 30000
PARA15 | 22066046 | 3 | Joinery Install Level 3 | 1 | NO | 30000 | 30000 | 30000
PARA15 | 22066046 | 4 | Joinery Install Level 4 | 1 | NO | 30000 | 30000 | 30000
PARA15 | 22066046 | 5 | Joinery Install Level 5 | 1 | NO | 30000 | 30000 | 0
Total Subcontracts | [6 empty] | 432149.36 | 223781.99
Forecast Amounts
|  | 8 | Additional Storage | 1 | ITEM | 7000 | 7000
|  | 9 | Bedroom Joinery Protection | 1 | ITEM | 12500 | 12500
|  | 12 | Remaining Scozia was $464,141 | 1 | ITEM | 314807.55 | 314807.55
|  | 13 | Hair Salon Mirrors | 1 | ITEM | 6500 | 6500
|  | 8999 | 020006 Kitchenette | 1 | EACH | 450 | 450
|  | 90001 | ST to LM Credit to client | 1 | ITEM | 14978 | 14978
Total Forecasts | [6 empty] | 356235.55
Total for Cost Centre | [6 empty] | 1284549.36 | 517209.22
T21 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
LAMB04 | 22066023 | 1 | Kitchen (K) Lump Sum | 1 | ITEM | 45859 | 45859 | 9171.8
LAMB04 | 22066023 | 2 | Servery (S) Lump Sum | 1 | ITEM | 83893.65 | 83893.65 | 16778.73
LAMB04 | 22066023 | 3 | Cafe (C) Lump Sum | 1 | ITEM | 6836.35 | 6836.35 | 1367.27
LAMB04 | 22066023 | 4 | Laundry (L) Lump Sum | 1 | ITEM | 7313 | 7313 | 1462.6
LAMB04 | 22066023 | 5 | Pan Room Bench | 1 | ITEM | 11850 | 11850 | 2370
LAMB04 | 22066023 | 6 | Coldroom & Freezer | 1 | ITEM | 60723 | 60723 | 12144.6
LAMB04 | 22066023 | 7 | Installation / Delivery | 1 | ITEM | 28525 | 28525 | 5705
Total Subcontracts | [6 empty] | 245000 | 49000
Total for Cost Centre | [6 empty] | 245000 | 49000
T22 | ST |  | FLOOR COVERINGS
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
FLOO13 | 22066029 | 1 | CP-01 Supply/Install | 1 | SUM | 19520 | 19520 | 8784
FLOO13 | 22066029 | 2 | CP-02 Supply/Install | 1 | SUM | 7546 | 7546 | 0
FLOO13 | 22066029 | 3 | CP-03 Supply/Install | 1 | SUM | 4200 | 4200 | 0
FLOO13 | 22066029 | 4 | CP-04 Supply/Install | 1 | SUM | 95844 | 95844 | 0
FLOO13 | 22066029 | 5 | CP-05 Supply/Install | 1 | SUM | 46942 | 46942 | 0
FLOO13 | 22066029 | 6 | CP-06 Supply/Install | 1 | SUM | 197802 | 197802 | 0
FLOO13 | 22066029 | 7 | CP-07 Supply/Install | 1 | SUM | 770 | 770 | 0
FLOO13 | 22066029 | 8 | CP-08 Supply/Install | 1 | SUM | 7956 | 7956 | 0
FLOO13 | 22066029 | 9 | VL-01 Supply/Install | 1 | SUM | 96860 | 96860 | 58825.46
FLOO13 | 22066029 | 10 | VL-02 Supply/Install | 1 | SUM | 6072 | 6072 | 0
FLOO13 | 22066029 | 11 | VL-03 Supply/Install | 1 | SUM | 40850 | 40850 | 10775.02
FLOO13 | 22066029 | 12 | VL-04 Supply/Install | 1 | SUM | 33747.7 | 33747.7 | 33747.7
FLOO13 | 22066029 | 13 | VL-05 Supply/Install | 1 | SUM | 4519.8 | 4519.8 | 0
FLOO13 | 22066029 | 14 | VL-06 Supply/Install | 1 | SUM | 8976 | 8976 | 0
FLOO13 | 22066029 | 15 | VL-07 Supply/Install | 1 | SUM | 27178 | 27178 | 27178
FLOO13 | 22066029 | 16 | VL-08 Supply/Install | 1 | SUM | 49708 | 49708 | 34541.65
FLOO13 | 22066029 | 17 | VL-10 Supply/Install | 1 | SUM | 38480 | 38480 | 17202
FLOO13 | 22066029 | 18 | VL-11 Supply/Install | 1 | SUM | 37734 | 37734 | 16287.2
FLOO13 | 22066029 | 19 | Ramping to Finishes | 1 | SUM | 5950 | 5950 | 297.5
FLOO13 | 22066029 | 20 | 3mm fload coat to Vinyl | 2385.5455 | M2 | 22 | 52482 | 16056
FLOO13 | 22066029 | 21 | Carpet Protection - Plastic | 1 | SUM | 10210 | 10210 | 0
FLOO13 | 22066029 | 22 | Vinyl Protection - Rhino | 1 | SUM | 13459.5 | 13459.5 | 4037.85
FLOO13 | 22066029 | 23 | 3mm Fload coat to ensuites | 605.4545 | M2 | 22 | 13320 | 2664
FLOO13 | 22066029 | 24 | Grinding | 6 | LEVEL | 880 | 5280 | 0
FLOO13 | 22066029 | 25 | Silicon to Perimeter | 1 | SUM | 19840 | 19840 | 0
FLOO13 | 22066029 | 26 | Wall Vinyl to Chute Room | 1 | SUM | 2464 | 2464 | 0
FLOO13 | 22066029 | 27 | VI:FLOOR COVERINGS | 0 |  | 0 | -15199.3 | -15199.3
FLOO13 | 22066029 | 28 | VI:FLOOR COVERINGS | 0 |  | 0 | -1170 | -1170
FLOO13 | 22066029 | 29 | VI:FLOOR COVERINGS | 0 |  | 0 | -33747.7 | -33747.7
FLOO13 | 22066029 | 30 | VI:FLOOR COVERINGS | 0 |  | 0 | -27178 | -27178
FLOO13 | 22066029 | 31 | VI:FLOOR COVERINGS | 0 |  | 0 | 25662 | 25662
FLOO13 | 22066029 | 32 | VI:FLOOR COVERINGS | 0 |  | 0 | 16550 | 16550
UNIV24 | 22066037 | 24 | VI:FLOOR COVERINGS | 0 |  | 0 | 43342.5 | 43342.5
Total Subcontracts | [6 empty] | 855970.5 | 238655.88
Forecast Amounts
|  | 3 | Carpet Tiles Floor Leveling | 1 | ITEM | 4000 | 4000
|  | 4 | Additional Floor Prep | 6 | LEVEL | 6000 | 36000
|  | 6 | Possible epoxy flooring | 1 | ITEM | 19469.5 | 19469.5
|  | 7 | Concrete sealing to loading | 1 | ITEM | 6760 | 6760
|  | 89998 | 020022 Cafe Entrance - Tactile | 1 | ITEM | 1170 | 1170
|  | 89999 | Vinyl 04 Credit | 1 | ITEM | 5000 | 5000
|  | 90000 | Vinyl 07 Credit | 1 | ITEM | 272.8 | 272.8
Total Forecasts | [6 empty] | 72672.3
Total for Cost Centre | [6 empty] | 928642.8 | 238655.88
T23 | MT |  | TILING SUPPLY
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
SKHE01 | 22066137 | 1 | TL-04B | 8.12 | M2 | 109.9 | 0 | 0
SKHE01 | 22066137 | 2 | TL-17 | 5.94 | M2 | 109.9 | 0 | 0
Sum: | [6 empty] | 0 | 0
Uncompleted Purchase Orders
DIYT01 | 22066136 | 1 | TL-01 | 0.1 | M2 | 29.95 | 3 | 0
DIYT01 | 22066136 | 2 | TL-01B | 0.1 | M2 | 29.95 | 3 | 0
DIYT01 | 22066136 | 3 | TL-02 | 0.01 | M2 | 64.95 | 0.65 | 0
DIYT01 | 22066136 | 4 | TL-02B | 0.01 | M2 | 64.95 | 0.65 | 0
DIYT01 | 22066136 | 5 | TL-03 | 158.14 | M2 | 17.95 | 2838.61 | 0
DIYT01 | 22066136 | 6 | TL-04A | 0.1 | M2 | 64.95 | 6.5 | 0
DIYT01 | 22066136 | 7 | TL-07 | 0.01 | M2 | 64.95 | 0.65 | 0
DIYT01 | 22066136 | 8 | TL-08 | 0.01 | M2 | 64.95 | 0.65 | 0
DIYT01 | 22066136 | 9 | TL-09 | 0.1 | M2 | 58.95 | 5.9 | 0
DIYT01 | 22066136 | 10 | TL-10 | 0.1 | LM | 5 | 0.5 | 0
DIYT01 | 22066136 | 11 | TL-11 | 0.01 | M2 | 58.95 | 0.59 | 0
DIYT01 | 22066136 | 12 | TL-12 | 0.01 | M2 | 32.95 | 0.33 | 0
DIYT01 | 22066136 | 13 | TL-14 | 0.01 | M2 | 32.95 | 0.33 | 0
DIYT01 | 22066136 | 14 | TL-15 | 0.01 | M2 | 58.95 | 0.59 | 0
DIYT01 | 22066136 | 15 | TL-16 | 0.01 | M2 | 58.95 | 0.59 | 0
DIYT01 | 22066136 | 16 | TL-20 | 0.01 | M2 | 32.95 | 0.33 | 0
DIYT01 | 22066136 | 17 | Freight Delivery 1 | 1 | EACH | 1083.5 | 1083.5 | 1083.5
NATI13 | 22066139 | 1 | NT16-5155FL Beaton Steel Grey Paver 600x600x20mm | 198 | M2 | 40 | 7920 | 7920
NATI13 | 22066139 | 2 | TL18A | 2 | M2 | 80.1 | 160.2 | 160.2
NATI13 | 22066139 | 3 | TL18B | 2.36 | M2 | 80.1831 | 189.23 | 189
NATI13 | 22066139 | 4 | TL18C | 1.42 | M2 | 80 | 113.6 | 113.4
NATI13 | 22066139 | 5 | TL18D | 1.2 | M2 | 80 | 96 | 96
NATI13 | 22066139 | 6 | TL19 | 44 | M2 | 18 | 792 | 792
NATI13 | 22066139 | 7 | Freight | 9 | EACH | 80 | 720 | 720
Sum: | [6 empty] | 13937.4 | 11074.1
Forecast Amounts
|  | 3 | Artedomus Tile - Hairdresser | 1 | ITEM | 1500 | 1500
|  | 7 | Extra Over for Adbri Paver | 1 | ITEM | 7392.08 | 7392.08
|  | 8 | Additional Wastage | 1 | ITEM | 9000 | 9000
|  | 8999 | 020006 Tea Making Station | 1 | EACH | 560 | 560
|  | 89998 | Freight | 1 | ITEM | 1250 | 1250
Total Forecasts | [6 empty] | 19702.08
Total for Cost Centre | [6 empty] | 33639.48 | 11074.1
T23 | ST |  | TILING INSTALL
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
SIXS01 | 22066043 | 1 | Tiling Ensuite Walls | 1 | NO | 266423.92 | 266423.92 | 133211.96
SIXS01 | 22066043 | 2 | Tiling Tea Bench Splashback | 1 | NO | 4783.79 | 4783.79 | 0
SIXS01 | 22066043 | 3 | Common Area GF - Hair Salon, | 1 | NO | 52326.94 | 52326.94 | 0
SIXS01 | 22066043 | 4 | Tiling GF Amenities Floor | 1 | NO | 3187.61 | 3187.61 | 0
SIXS01 | 22066043 | 5 | Tiling GF Amenities Wall | 1 | NO | 19533.64 | 19533.64 | 0
SIXS01 | 22066043 | 6 | Tiling GF Cafe, Salon, | 1 | NO | 8272.25 | 8272.25 | 0
SIXS01 | 22066043 | 7 | Tiling Common Area lvl 1 | 1 | NO | 7829.42 | 7829.42 | 0
SIXS01 | 22066043 | 8 | Tiling Common Area lvl 1 | 1 | NO | 6732.04 | 6732.04 | 0
SIXS01 | 22066043 | 9 | Tiling Common Area lvl1 | 1 | NO | 36489 | 36489 | 0
SIXS01 | 22066043 | 10 | Tiling Common Area lvl 2-5 | 1 | NO | 31317.68 | 31317.68 | 0
SIXS01 | 22066043 | 11 | Tiling Common Area lvl 2-5 | 1 | NO | 23724.39 | 23724.39 | 0
SIXS01 | 22066043 | 12 | Tiling External Work Wall | 1 | NO | 36251.67 | 36251.67 | 0
SIXS01 | 22066043 | 13 | Vertical Movement | 1 | NO | 27760 | 27760 | 19432
SIXS01 | 22066043 | 14 | Vinyl Area Bedding Ensuite | 1 | NO | 49536.54 | 49536.54 | 39629.23
SIXS01 | 22066043 | 15 | GF Kitchen, and Amenities | 1 | NO | 15505.26 | 15505.26 | 0
SIXS01 | 22066043 | 16 | L1-5 Amenities, Pan Room, | 1 | NO | 24378.37 | 24378.37 | 19502.69
SIXS01 | 22066043 | 17 | Vinyl and Tile Transition | 1 | NO | 26748.55 | 26748.55 | 21398.84
Total Subcontracts | [6 empty] | 640801.07 | 233174.72
Forecast Amounts
|  | 3 | Bedding | 1 | ITEM | 2500 | 2500
Total Forecasts | [6 empty] | 2500
Total for Cost Centre | [6 empty] | 643301.07 | 233174.72
T23C | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
SLAT01 | 22066138 | 1 | Tuscan Blue Crazy Pave | 203.5001 | M2 | 61.75 | 12566.13 | 12566.13
Sum: | [6 empty] | 12566.13 | 12566.13
Total for Cost Centre | [6 empty] | 12566.13 | 12566.13
T24 | ST |  | PAINTING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
BBCP03 | 22066176 | 1 | Painting External Works | 2 | WEEKS | 12750 | 25500 | 25500
BBCP03 | 22066176 | 2 | Painting External Works | 2 | WEEKS | 12750 | 8330 | 8330
Sum: | [6 empty] | 33830 | 33830
Subcontracts
UNIV24 | 22066037 | 8 | Paint Ground | 1 | NO | 109475.5 | 109475.5 | 17824.1
UNIV24 | 22066037 | 9 | Paint Level 1 | 1 | NO | 88561 | 88561 | 41139.1
UNIV24 | 22066037 | 10 | Paint Level 2 | 1 | NO | 83332.5 | 83332.5 | 51681.45
UNIV24 | 22066037 | 11 | Paint Level 3 | 1 | NO | 81352.5 | 81352.5 | 61966.95
UNIV24 | 22066037 | 12 | Paint Level 4 | 1 | NO | 81187.5 | 81187.5 | 49762.7
UNIV24 | 22066037 | 13 | Paint Level 5 | 1 | NO | 85121.5 | 85121.5 | 19576
UNIV24 | 22066037 | 14 | Paint Roof | 1 | NO | 4192.5 | 4192.5 | 4042.5
UNIV24 | 22066037 | 15 | Linemarking | 1 | NO | 3505 | 3505 | 0
UNIV24 | 22066037 | 16 | Stair Nosing | 1 | NO | 2655 | 2655 | 0
UNIV24 | 22066037 | 17 | Stairwells Stipple Finish | 1 | NO | 26055 | 26055 | 0
UNIV24 | 22066037 | 18 | Sealing Window Frames | 1 | NO | 20280 | 20280 | 16224
UNIV24 | 22066037 | 19 | Sealing Aluminium Cladding | 1 | NO | 5570 | 5570 | 0
UNIV24 | 22066037 | 20 | Paint Structural Steel | 1 | NO | 5180 | 5180 | 0
UNIV24 | 22066037 | 21 | Wallpaper | 1 | NO | 3532 | 3532 | 0
UNIV24 | 22066037 | 25 | VI:PAINTING | 0 |  | 0 | -19900 | -19900
Total Subcontracts | [6 empty] | 580100 | 242316.8
Forecast Amounts
|  | 2 | Touch Up Allowance | 100 | HRS | 80 | 8000
|  | 8999 | 020027 Traffic Island - painti | 1 | EACH | 220 | 220
|  | 89999 | 020025 Storerooms - Painting | 1 | ITEM | 1100 | 1100
Total Forecasts | [6 empty] | 9320
Total for Cost Centre | [6 empty] | 623250 | 276146.8
T24R | ST |  | RENDER
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
UNIV24 | 22066037 | 1 | Render - Ground | 1 | NO | 81474 | 81474 | 48884.4
UNIV24 | 22066037 | 2 | Render Level 1 | 1 | NO | 42994 | 42994 | 42994
UNIV24 | 22066037 | 3 | Render Level 2 | 1 | NO | 35890 | 35890 | 35890
UNIV24 | 22066037 | 4 | Render Level 3 | 1 | NO | 31450 | 31450 | 31450
UNIV24 | 22066037 | 5 | Render Level 4 | 1 | NO | 31080 | 31080 | 31080
UNIV24 | 22066037 | 6 | Render Level 5 | 1 | NO | 31080 | 31080 | 31080
UNIV24 | 22066037 | 7 | Render Roof | 1 | NO | 9032 | 9032 | 9032
UNIV24 | 22066037 | 23 | VI:RENDER | 0 |  | 0 | 56750 | 56750
UNIV24 | 22066037 | 26 | VI:RENDER | 0 |  | 0 | 5250 | 5250
Total Subcontracts | [6 empty] | 325000 | 292410.4
Forecast Amounts
|  | 3 | AFS Walls - External | 74 | M2 | 37 | 2738
Total Forecasts | [6 empty] | 2738
Total for Cost Centre | [6 empty] | 327738 | 292410.4
T25 | ST |  | HYDRAULIC SERVICES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
VEER01 | 22066011 | 1 | CCTV Conduit Inspection | 1 | EACH | 535 | 535 | 535
Sum: | [6 empty] | 535 | 535
Uncompleted Purchase Orders
MANS01 | 22066066 | 1 | DYFA Back Charge Conc | 14 | EACH | 142 | 1988 | 1988
MEAL08 | 22066067 | 1 | DYFA Conc Pump Back Charge | 1 | EACH | 1028 | 1028 | 1028
SPEL01 | 22066002 | 1 | SPEL Basins | 1 | EACH | 77543 | 77543 | 68745
SPEL01 | 22066002 | 2 | 12 month DLP Maintenance | 1 | EACH | 4662 | 4662 | 0
Sum: | [6 empty] | 85221 | 71761
Subcontracts
DYFA02 | 22066002 | 1 | Fire Pump | 1 | NO | 23650 | 23650 | 23650
DYFA02 | 22066002 | 2 | Cold Water Supply | 1 | NO | 18350 | 18350 | 18350
DYFA02 | 22066002 | 3 | GIT - 2KL Lint Trap | 1 | NO | 9500 | 9500 | 7125
DYFA02 | 22066002 | 4 | GIT - 5KL Grease Trap | 1 | NO | 13990 | 13990 | 10492.5
DYFA02 | 22066002 | 5 | HW Plant | 1 | NO | 130200 | 130200 | 130200
DYFA02 | 22066002 | 6 | HW Reticulation Pump | 1 | NO | 3100 | 3100 | 0
DYFA02 | 22066002 | 7 | RWP | 1 | NO | 5300 | 5300 | 5300
DYFA02 | 22066002 | 8 | SW Pits | 1 | NO | 31800 | 31800 | 31800
DYFA03 | 22066001 | 1 | Ground - Sewer | 1 | NO | 60183.17 | 60183.17 | 54164.85
DYFA03 | 22066001 | 2 | Ground - Tradewaste | 1 | NO | 28317.21 | 28317.21 | 28317.21
DYFA03 | 22066001 | 3 | Ground - Stormwater | 1 | NO | 70881.03 | 70881.03 | 70881.03
DYFA03 | 22066001 | 4 | Ground - Cold Water Service | 1 | NO | 47773.37 | 47773.37 | 47773.37
DYFA03 | 22066001 | 5 | Ground Hot Water Service | 1 | NO | 31845.02 | 31845.02 | 31845.01
DYFA03 | 22066001 | 6 | Ground - Rainwater Service | 1 | NO | 7214.07 | 7214.07 | 7214.07
DYFA03 | 22066001 | 7 | Ground - Fire Service | 1 | NO | 64467.95 | 64467.95 | 51574.36
DYFA03 | 22066001 | 8 | Ground - Amenities Rough In | 1 | NO | 39429.44 | 39429.44 | 39429.44
DYFA03 | 22066001 | 9 | Ground - Amenities Fit Off | 1 | NO | 14750.33 | 14750.33 | 0
DYFA03 | 22066001 | 10 | Hair Dressing Salon - Rough | 1 | NO | 2560.38 | 2560.38 | 2560.38
DYFA03 | 22066001 | 11 | Hairdressing Salon - Fitoff | 1 | NO | 991.58 | 991.58 | 0
DYFA03 | 22066001 | 12 | Hairdressing Salon - Sewer | 1 | NO | 2650.84 | 2650.84 | 2650.84
DYFA03 | 22066001 | 13 | Level 1 - Sewer | 1 | NO | 44439.86 | 44439.86 | 44439.86
DYFA03 | 22066001 | 14 | Level 1 - Tradewaste | 1 | NO | 3731.98 | 3731.98 | 3731.98
DYFA03 | 22066001 | 15 | Level 1 - Stormwater | 1 | NO | 16388.3 | 16388.3 | 3277.67
DYFA03 | 22066001 | 16 | Level 1 - Cold Water Service | 1 | NO | 6913.64 | 6913.64 | 6913.64
DYFA03 | 22066001 | 17 | Level 1 - Hot Water Service | 1 | NO | 12505.1 | 12505.1 | 5002.04
DYFA03 | 22066001 | 18 | Level 1 - Fire Service | 1 | NO | 3134.82 | 3134.82 | 3134.82
DYFA03 | 22066001 | 19 | Level 1 - Amenities Rough In | 1 | NO | 3907.59 | 3907.59 | 3907.59
DYFA03 | 22066001 | 20 | Level 1 - Amenities Fitoff | 1 | NO | 7603.37 | 7603.37 | 0
DYFA03 | 22066001 | 21 | Level 1 - Resident Room | 1 | NO | 20329.5 | 20329.5 | 20329.5
DYFA03 | 22066001 | 22 | Level 1 - Resident Room | 1 | NO | 17610.6 | 17610.6 | 17610.6
DYFA03 | 22066001 | 23 | Level 2 - Sewer | 1 | NO | 44439.86 | 44439.86 | 44439.86
DYFA03 | 22066001 | 24 | Level 2 - Tradewaste | 1 | NO | 3731.98 | 3731.98 | 3731.98
DYFA03 | 22066001 | 25 | Level 2 - Stormwater | 1 | NO | 16388.3 | 16388.3 | 3277.67
DYFA03 | 22066001 | 26 | Level 2 - Cold Water Service | 1 | NO | 7977.57 | 7977.57 | 7977.57
DYFA03 | 22066001 | 27 | Level 2 - Hot Water Service | 1 | NO | 91614.73 | 91614.73 | 91614.73
DYFA03 | 22066001 | 28 | Level 2 - Fire Service | 1 | NO | 3134.82 | 3134.82 | 3134.82
DYFA03 | 22066001 | 29 | Level 2 - Amenities Rough In | 1 | NO | 11932.91 | 11932.91 | 11932.91
DYFA03 | 22066001 | 30 | Level 2 - Amenities Fitoff | 1 | NO | 7603.37 | 7603.37 | 3522.12
DYFA03 | 22066001 | 31 | Level 2 - Resident Room | 1 | NO | 20329.5 | 20329.5 | 20329.5
DYFA03 | 22066001 | 32 | Level 2 - Resident Room | 1 | NO | 17610.6 | 17610.6 | 0
DYFA03 | 22066001 | 33 | Level 3 - Sewer | 1 | NO | 44439.86 | 44439.86 | 44439.86
DYFA03 | 22066001 | 34 | Level 3 - Stormwater | 1 | NO | 16388.3 | 16388.3 | 16388.3
DYFA03 | 22066001 | 35 | Level 3 - Tradewaste | 1 | NO | 3731.98 | 3731.98 | 3731.98
DYFA03 | 22066001 | 36 | Level 3 - Cold Water Service | 1 | NO | 3840.3 | 3840.3 | 3840.3
DYFA03 | 22066001 | 37 | Level 3 - Hot Water Service | 1 | NO | 5495.16 | 5495.16 | 5495.16
DYFA03 | 22066001 | 38 | Level 3 - Fire Service | 1 | NO | 3134.82 | 3134.82 | 3134.82
DYFA03 | 22066001 | 39 | Level 3 - Amenities Rough In | 1 | NO | 3907.59 | 3907.59 | 3907.59
DYFA03 | 22066001 | 40 | Level 3 - Amenities Fitoff | 1 | NO | 7603.37 | 7603.37 | 0
DYFA03 | 22066001 | 41 | Level 3 - Resident Room | 1 | NO | 20329.5 | 20329.5 | 20329.5
DYFA03 | 22066001 | 42 | Level 3 Resident Room Fitoff | 1 | NO | 17610.6 | 17610.6 | 0
DYFA03 | 22066001 | 43 | Level 4 - Sewer | 1 | NO | 44439.86 | 44439.86 | 44439.86
DYFA03 | 22066001 | 44 | Level 4 - Stormwater | 1 | NO | 16388.3 | 16388.3 | 16388.3
DYFA03 | 22066001 | 45 | Level 4 - Tradewaste | 1 | NO | 3731.98 | 3731.98 | 3731.98
DYFA03 | 22066001 | 46 | Level 4 - Cold Water Service | 1 | NO | 8438.29 | 8438.29 | 8438.29
DYFA03 | 22066001 | 47 | Level 4 - Hot Water Service | 1 | NO | 91614.73 | 91614.73 | 91614.72
DYFA03 | 22066001 | 48 | Level 4 - Fire Service | 1 | NO | 3134.82 | 3134.82 | 2821.34
DYFA03 | 22066001 | 49 | Level 4 - Amenities Rough In | 1 | NO | 11932.91 | 11932.91 | 11932.91
DYFA03 | 22066001 | 50 | Level 4 - Amenities Fitoff | 1 | NO | 7603.37 | 7603.37 | 0
DYFA03 | 22066001 | 51 | Level 4 - Resident Room | 1 | NO | 20329.5 | 20329.5 | 20329.5
DYFA03 | 22066001 | 52 | Level 4 - Resident Room | 1 | NO | 17610.6 | 17610.6 | 0
DYFA03 | 22066001 | 53 | Level 5 - Sewer | 1 | NO | 44439.86 | 44439.86 | 44439.86
DYFA03 | 22066001 | 54 | Level 5 - Stormwater | 1 | NO | 16388.3 | 16388.3 | 16388.3
DYFA03 | 22066001 | 55 | Level 5 - Tradewaste | 1 | NO | 3731.98 | 3731.98 | 3731.98
DYFA03 | 22066001 | 56 | Level 5 - Cold Water Service | 1 | NO | 3840.3 | 3840.3 | 3840.3
DYFA03 | 22066001 | 57 | Level 5 - Hot Water Service | 1 | NO | 5495.16 | 5495.16 | 5495.16
DYFA03 | 22066001 | 58 | Level 5 - Fire Service | 1 | NO | 3134.82 | 3134.82 | 2821.34
DYFA03 | 22066001 | 59 | Level 5 - Amenities Rough In | 1 | NO | 3907.59 | 3907.59 | 0
DYFA03 | 22066001 | 60 | Level 5 - Amenities Fitoff | 1 | NO | 7603.37 | 7603.37 | 0
DYFA03 | 22066001 | 61 | Level 5 - Resident Room | 1 | NO | 20329.5 | 20329.5 | 15247.13
DYFA03 | 22066001 | 62 | Level 5 - Resident Room | 1 | NO | 17610.6 | 17610.6 | 0
DYFA03 | 22066001 | 63 | Roof - Sewer | 1 | NO | 1324.72 | 1324.72 | 1324.72
DYFA03 | 22066001 | 64 | Roof - Tradewaste | 1 | NO | 433.16 | 433.16 | 433.16
DYFA03 | 22066001 | 65 | Roof - Stormwater | 1 | NO | 2452.19 | 2452.19 | 2452.19
DYFA03 | 22066001 | 66 | Civil Stormwater with Insitu | 1 | NO | 163274.4 | 163274.4 | 146946.96
DYFA03 | 22066001 | 67 | Water Meters | 1 | NO | 38943.04 | 38943.04 | 38943.04
DYFA03 | 22066001 | 68 | Project Management & | 1 | NO | 376388.5 | 376388.5 | 327458.01
DYFA03 | 22066001 | 69 | Design & Seismic | 1 | NO | 46984.24 | 46984.24 | 46984.24
DYFA03 | 22066001 | 70 | Preliminaries | 1 | NO | 73728.08 | 73728.08 | 64143.44
DYFA03 | 22066001 | 71 | VI:HYDRAULIC SERVICES | 0 |  | 0 | -1988 | -1988
DYFA03 | 22066001 | 72 | VI:HYDRAULIC SERVICES | 0 |  | 0 | -1028 | -1028
DYFA03 | 22066001 | 73 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 12196 | 12196
DYFA03 | 22066001 | 74 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 1507 | 1507
DYFA03 | 22066001 | 75 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 5944 | 5944
DYFA03 | 22066001 | 76 | VI:HYDRAULIC SERVICES | 0 |  | 0 | -1695 | -1695
DYFA03 | 22066001 | 77 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 470 | 470
LAGW01 | 22066034 | 1 | Level 1 Part 1 | 1 | NO | 9450 | 9450 | 9450
LAGW01 | 22066034 | 2 | Level 1 Part 2 | 1 | NO | 3888 | 3888 | 3888
LAGW01 | 22066034 | 3 | Level 2 Part 1 | 1 | NO | 8022 | 8022 | 8022
LAGW01 | 22066034 | 4 | Level 2 Part 2 | 1 | NO | 3550 | 3550 | 3550
LAGW01 | 22066034 | 5 | Level 3 Part 1 | 1 | NO | 7750 | 7750 | 7750
LAGW01 | 22066034 | 6 | Level 3 Part 2 | 1 | NO | 3550 | 3550 | 3550
LAGW01 | 22066034 | 7 | Level 4 Part 1 | 1 | NO | 7750 | 7750 | 7750
LAGW01 | 22066034 | 8 | Level 4 Part 2 | 1 | NO | 3550 | 3550 | 3550
LAGW01 | 22066034 | 9 | Level 5 Part 1 | 1 | NO | 7750 | 7750 | 7750
LAGW01 | 22066034 | 10 | Level 5 Part 2 | 1 | NO | 3550 | 3550 | 3550
LAGW01 | 22066034 | 11 | Roof Part 1 | 1 | NO | 1190 | 1190 | 1190
LAGW01 | 22066034 | 12 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 1695 | 1695
MMWA01 | 22066032 | 8 | VI:HYDRAULIC SERVICES | 0 |  | 0 | 6250 | 6250
Total Subcontracts | [6 empty] | 2233349.44 | 1966602.16
Forecast Amounts
|  | 3 | Strip Drain | 15 | M | 400 | 6000
|  | 4 | Floor Wastes to Vinyl Install | 180 | NO | 80 | 14400
|  | 6 | Re-work Cisterns | 1 | NO | 5000 | 5000
|  | 10 | Temp waterproofing | 1 | NO | 10000 | 10000
|  | 11 | Install SPEL Storm Sacks | 1 | NO | 2560 | 2560
|  | 12 | Detailed Excavation - Revisit | 1 | NO | 6000 | 6000
|  | 13 | Puddle Flanges - WP | 1 | ITEM | 3000 | 3000
Total Forecasts | [6 empty] | 46960
Total for Cost Centre | [6 empty] | 2366065.44 | 2038898.16
T25HF | MT |  | SANITARY HARDWARE/HYDRAULIC FF
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
KJBO01 | 22066173 | 1 | Fixings | 1 | EACH | 100 | 100 | 0
REEC02 | 22066054 | 1 | Level G | 1 | SUM | 29631 | 29631 | 2907.02
REEC02 | 22066054 | 2 | Level G - GST Free | 1 | SUM | 626 | 626 | 0
REEC02 | 22066054 | 3 | Level 1 | 1 | SUM | 116198 | 116198 | 109554.5
REEC02 | 22066054 | 4 | Level 1 - GST Free | 1 | SUM | 15616 | 15616 | 13936.5
REEC02 | 22066054 | 5 | Level 2 | 1 | SUM | 116414 | 116414 | 60603
REEC02 | 22066054 | 6 | Level 2 - GST Free | 1 | SUM | 256 | 256 | 0
REEC02 | 22066054 | 7 | Level 3 | 1 | SUM | 116414 | 116414 | 8903
REEC02 | 22066054 | 8 | Level 3 - GST Free | 1 | SUM | 7936 | 7936 | 0
REEC02 | 22066054 | 9 | Level 4 | 1 | SUM | 116414 | 116414 | 8923
REEC02 | 22066054 | 10 | Level 4 - GST Free | 1 | SUM | 7936 | 7936 | 0
REEC02 | 22066054 | 11 | Level 5 | 1 | SUM | 116414 | 116414 | 8768.5
REEC02 | 22066054 | 12 | Level 5 - GST Free | 1 | SUM | 7936 | 7936 | 0
REEC02 | 22066054 | 13 | Freight & Handling | 20 | EA | 5 | 100 | 20
REEC02 | 22066054 | 14 | L2 - GST Free over run | 1 | EACH | 3861 | 3861 | 0
REEC02 | 22066054 | 15 | Level 1 - Over Run | 1 | EACH | 2547.5 | 2547.5 | 0
SURE10 | 22066165 | 1 | Grab Rail - Nurse Call Button inc | 150 | EACH | 190 | 28500 | 28500
SURE10 | 22066165 | 2 | Grab Rail - Drop down rail | 150 | EACH | 160 | 24000 | 24000
SURE10 | 22066165 | 3 | Grab Rail - Freight | 1 | EACH | 1950 | 1950 | 1950
Sum: | [6 empty] | 712849.5 | 268065.52
Forecast Amounts
|  | 8999 | 020006 Tea Making Station | 1 | EACH | 4129 | 4129
Total Forecasts | [6 empty] | 4129
Total for Cost Centre | [6 empty] | 716978.5 | 268065.52
T26 | ST |  | ELECTRICAL SERVICES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
MONT02 | 22066009 | 1 | Incoming Comms & Electrical | 1 | ITEM | 35270 | 35270 | 35270
MONT02 | 22066009 | 2 | Site Consumer Mains | 1 | SUM | 82700 | 82700 | 82700
MONT02 | 22066009 | 3 | Generator Bump-in Connection | 1 | SUM | 20000 | 20000 | 0
MONT02 | 22066009 | 4 | Submains | 1 | SUM | 134900 | 134900 | 47215
MONT02 | 22066009 | 5 | Cable Supports | 1 | SUM | 44100 | 44100 | 33075
MONT02 | 22066009 | 6 | MSB | 1 | SUM | 80900 | 80900 | 33978
MONT02 | 22066009 | 7 | Distribution Switchboard | 1 | SUM | 100900 | 100900 | 0
MONT02 | 22066009 | 8 | Lighting Install | 1 | SUM | 272700 | 272700 | 95445
MONT02 | 22066009 | 9 | Lighting Control System | 1 | SUM | 90700 | 90700 | 27210
MONT02 | 22066009 | 10 | Luminaires General | 1 | SUM | 399890 | 399890 | 0
MONT02 | 22066009 | 11 | Luminaires Feature | 1 | SUM | 160200 | 160200 | 16020
MONT02 | 22066009 | 12 | Luminaires External Landscape | 1 | SUM | 72760 | 72760 | 0
MONT02 | 22066009 | 13 | Emergency & Exit Lighting | 1 | SUM | 102850 | 102850 | 46282.5
MONT02 | 22066009 | 14 | Small Power Services | 1 | SUM | 248500 | 248500 | 161525
MONT02 | 22066009 | 15 | Communications Service | 1 | SUM | 132030 | 132030 | 85819.5
MONT02 | 22066009 | 16 | Testing & Commissioning | 1 | SUM | 13900 | 13900 | 0
MONT02 | 22066009 | 17 | Shop Drawings & As Builts | 1 | SUM | 5000 | 5000 | 2500
MONT02 | 22066009 | 18 | MATV | 1 | SUM | 52800 | 52800 | 7920
MONT02 | 22066009 | 19 | Solar | 1 | SUM | 109500 | 109500 | 0
MONT02 | 22066009 | 20 | Prelims | 1 | SUM | 34400 | 34400 | 30960
MONT02 | 22066009 | 21 | Security Interface | 1 | SUM | 6200 | 6200 | 0
MONT02 | 22066009 | 22 | MATV Install | 1 | SUM | 28700 | 28700 | 4879
MONT02 | 22066009 | 23 | Temp Power | 1 | SUM | 12600 | 12600 | 12600
MONT02 | 22066009 | 24 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 3000 | 3000
MONT02 | 22066009 | 26 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 4640 | 4640
MONT02 | 22066009 | 27 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 695 | 695
MONT02 | 22066009 | 28 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 1195 | 1195
MONT02 | 22066009 | 29 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 7345 | 7345
MONT02 | 22066009 | 30 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 2785 | 2785
MONT02 | 22066009 | 31 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 885.5 | 885.5
MONT02 | 22066009 | 32 | VI:ELECTRICAL SERVICES | 0 |  | 0 | 5980 | 5980
Total Subcontracts | [6 empty] | 2268025.5 | 749924.5
Forecast Amounts
|  | 4 | Crane Power & Modifications | 1 | ITEM | 13000 | 13000
|  | 5 | Warning system to maint. gate | 1 | ITEM | 1000 | 1000
|  | 6 | Nurse Call Lighting | 1 | ITEM | 37500 | 37500
|  | 89999 | 020025 Storerooms - Lights | 1 | ITEM | 780 | 780
Total Forecasts | [6 empty] | 52280
Total for Cost Centre | [6 empty] | 2320305.5 | 749924.5
T27 | ST |  | MECHANICAL SERVICES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
CUTC02 | 22066149 | 1 | Applied Air Back Charge | 1 | EACH | 224.4 | 224.4 | 224.4
SUNC20 | 22066081 | 12 | Concrete Cutting | 1 | EACH | 282.8 | 282.8 | 282.8
Sum: | [6 empty] | 507.2 | 507.2
Subcontracts
APPL03 | 22066010 | 1 | Pipe and Pipe Materials | 1 | ITEM | 126720 | 126720 | 104022
APPL03 | 22066010 | 2 | AC's, Fans and Equipment | 1 | ITEM | 445112 | 445112 | 285052
APPL03 | 22066010 | 3 | Duct, Flex, Grilles | 1 | ITEM | 167470 | 167470 | 129250
APPL03 | 22066010 | 4 | Electrical Materials | 1 | ITEM | 62550 | 62550 | 0
APPL03 | 22066010 | 5 | Engineering & Drawings | 1 | ITEM | 42930 | 42930 | 42930
APPL03 | 22066010 | 6 | Pipe Installation | 1 | ITEM | 239526 | 239526 | 224687.1
APPL03 | 22066010 | 7 | Electrical Install | 1 | ITEM | 160800 | 160800 | 136680
APPL03 | 22066010 | 8 | Duct Install | 1 | ITEM | 264132 | 264132 | 224512.2
APPL03 | 22066010 | 9 | Comissioning | 1 | ITEM | 36960 | 36960 | 374.4
APPL03 | 22066010 | 10 | VI:MECHANICAL SERVICES | 0 |  | 0 | -1500 | -1500
APPL03 | 22066010 | 11 | VI:MECHANICAL SERVICES | 0 |  | 0 | -224.4 | -224.4
Total Subcontracts | [6 empty] | 1544475.6 | 1145783.3
Forecast Amounts
|  | 2 | Door grilles | 1 | NO | 10000 | 10000
|  | 3 | Plinths | 1 | ITEM | 5000 | 5000
|  | 4 | Bin Room Ventilation | 1 | ITEM | 5000 | 5000
Total Forecasts | [6 empty] | 20000
Total for Cost Centre | [6 empty] | 1564982.8 | 1146290.5
T28 | ST |  | LIFT SERVICES
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
KONE01 | 22066004 | 1 | Lift 1 and 2 | 1 | NO | 312500 | 312500 | 288075
KONE01 | 22066004 | 2 | Full Depth Stainless Steel | 13 | NO | 1750 | 22750 | 0
KONE01 | 22066004 | 3 | VI:LIFT SERVICES | 0 |  | 0 | 2244 | 2244
KONE01 | 22066004 | 4 | VI:LIFT SERVICES | 0 |  | 0 | 6063 | 6063
Total Subcontracts | [6 empty] | 343557 | 296382
Forecast Amounts
|  | 2 | Builders Lift extra weeks | 4 | WEEKS | 150 | 600
Total Forecasts | [6 empty] | 600
Total for Cost Centre | [6 empty] | 344157 | 296382
T29 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
FIRE15 | 22066011 | 1 | Fire Sprinklers | 1 | ITEM | 397173.1 | 397173.1 | 337597.14
FIRE15 | 22066011 | 2 | Fire Detection | 1 | SUM | 186639.28 | 186639.28 | 111983.58
FIRE15 | 22066011 | 3 | Fire Evacuation Plans | 1 | SUM | 2820 | 2820 | 0
FIRE15 | 22066011 | 4 | Fire Extinguishers | 1 | SUM | 3367.62 | 3367.62 | 0
FIRE15 | 22066011 | 5 | VI:FIRE SERVICES | 0 |  | 0 | 1100 | 1100
Total Subcontracts | [6 empty] | 591100 | 450680.72
Total for Cost Centre | [6 empty] | 591100 | 450680.72
T30 | ST |  | LANDSCAPING
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
AHFE01 | 22066048 | 1 | Fencing Subcontract | 1 | NO | 43000 | 43000 | 0
SCOT42 | 22066047 | 1 | Landscaping Package | 1 | NO | 320780 | 320780 | 0
Total Subcontracts | [6 empty] | 363780 | 0
Forecast Amounts
|  | 9 | water features | 1 | ITEM | 17500 | 17500
|  | 10 | Re-Turf Site Compound | 1 | ITEM | 5000 | 5000
|  | 89998 | 020022 Cafe Entrance - Garden | 1 | ITEM | 1728 | 1728
|  | 90000 | Flagpoles x2 | 1 | QUOTE | 10502.87 | 10502.87
|  | 90001 | Trellis Structure | 1 | NO | 7971.05 | 7971.05
Total Forecasts | [6 empty] | 42701.92
Total for Cost Centre | [6 empty] | 406481.92 | 0
T32 | ST |  | SIGNAGE
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
SUNQ03 | 22066051 | 2 | Stat Signage Package | 1 | NO | 30350 | 30350 | 0
SUNQ03 | 22066051 | 3 | VI:SIGNAGE | 0 |  | 0 | 700 | 700
SUNQ03 | 22066051 | 4 | VI:SIGNAGE | 0 |  | 0 | 860 | 860
SUNQ03 | 22066051 | 5 | VI:SIGNAGE | 0 |  | 0 | 385 | 385
Total Subcontracts | [6 empty] | 32295 | 1945
Forecast Amounts
|  | 1 | Additional Signage | 1 | ITEM | 4055 | 4055
Total Forecasts | [6 empty] | 4055
Total for Cost Centre | [6 empty] | 36350 | 1945
T98 | ST |  | Trade Contingency
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 1 | Trade Contingency | 1 | NO | 90000 | 90000
Total Forecasts | [6 empty] | 90000
Total for Cost Centre | [6 empty] | 90000
T9901 | ST
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
SUNQ03 | 22066051 | 1 | Corporate Signage Package | 1 | NO | 27455 | 27455 | 19230
Total Subcontracts | [6 empty] | 27455 | 19230
Total for Cost Centre | [6 empty] | 27455 | 19230
T9903 | ST |  | Corner and Door Protection
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Forecast Amounts
|  | 1 | Corner and Door Protection | 1 | ITEM | 30000 | 30000
Total Forecasts | [6 empty] | 30000
Total for Cost Centre | [6 empty] | 30000
T9904 | ST |  | Reception, Hairsalon and Priva
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
BOUT06 | 22066022 | 14 | VI:Reception, Hairsalon and Pr | 0 |  | 0 | 3442 | 3442
BOUT06 | 22066022 | 15 | VI:Reception, Hairsalon and Pr | 0 |  | 0 | 1080 | 1080
BOUT06 | 22066022 | 16 | VI:Reception, Hairsalon and Pr | 0 |  | 0 | 9580 | 9580
Total Subcontracts | [6 empty] | 14102 | 14102
Forecast Amounts
|  | 89998 | 020023 Service Coordination an | 1 | ITEM | 500 | 500
|  | 89999 | 020023 Joinery Shop Drawings | 1 | ITEM | 705.1 | 705.1
Total Forecasts | [6 empty] | 1205.1
Total for Cost Centre | [6 empty] | 15307.1 | 14102
T9905 | ST |  | Nurse Call, Electronic Access
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Uncompleted Purchase Orders
LFSB01 | 22066189 | 1 | Nurse Call Cutouts in Frames | 1 | EACH | 1155 | 1155 | 1155
Sum: | [6 empty] | 1155 | 1155
Subcontracts
CABL04 | 22066041 | 1 | Advance Care IP Nurse Call | 1 | NO | 381000 | 381000 | 137160
CABL04 | 22066041 | 2 | CCTV | 1 | NO | 55300 | 55300 | 17696
CABL04 | 22066041 | 3 | Access Control | 1 | NO | 224000 | 224000 | 71680
CABL04 | 22066041 | 4 | Intercom | 1 | NO | 5300 | 5300 | 0
CABL04 | 22066041 | 5 | VI:Nurse Call, Electronic Acce | 0 |  | 0 | 10343.98 | 10343.98
CABL04 | 22066041 | 6 | VI:Nurse Call, Electronic Acce | 0 |  | 0 | -252.52 | -252.52
CABL04 | 22066041 | 7 | VI:Nurse Call, Electronic Acce | 0 |  | 0 | 3501.77 | 3501.77
CABL04 | 22066041 | 8 | VI:Nurse Call, Electronic Acce | 0 |  | 0 | 9900 | 9900
CABL04 | 22066041 | 9 | VI:Nurse Call, Electronic Acce | 0 |  | 0 | 3300 | 3300
Total Subcontracts | [6 empty] | 692393.23 | 253329.23
Forecast Amounts
|  | 2 | Install Electric Strikes | 4 | VISIT | 611.25 | 2445
Total Forecasts | [6 empty] | 2445
Total for Cost Centre | [6 empty] | 695993.23 | 254484.23
T9907 | ST |  | Metalwork AL1 Design Rationali
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Subcontracts
BEEL02 | 22066035 | 11 | VI:Metalwork AL1 Design Ration | 0 |  | 0 | 72153 | 72153
BEEL02 | 22066035 | 12 | VI:Metalwork AL1 Design Ration | 0 |  | 0 | 23500 | 23500
CUST09 | 22066031 | 17 | VI:Metalwork AL1 Design Ration | 0 |  | 0 | 15187.23 | 15187.23
Total Subcontracts | [6 empty] | 110840.23 | 110840.23
Forecast Amounts
|  | 89997 | 020026 Traffic Control Allowan | 1 | ITEM | 1992 | 1992
|  | 89998 | 020026 Epoxy Paint to Structur | 1 | ITEM | 2625 | 2625
|  | 89999 | 020026 Structural Steel Connec | 1 | ITEM | 3643 | 3643
Total Forecasts | [6 empty] | 8260
Total for Cost Centre | [6 empty] | 119100.23 | 110840.23
TO92 | MT
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Completed Purchase Orders
RIMC04 | 22066001 | 1 | Reo Remeasure | 40 | HRS | 50 | 2000 | 2000
Sum: | [6 empty] | 2000 | 2000
Total for Cost Centre | [6 empty] | 2000 | 2000
Creditor | Order/Contract # |  | Description | Qty | Measure | Rate | Amount | Authorised
Total for Cost Centre
Total Subcontracts | [6 empty] | 24294789.66 | 17261056.21
Total Purchase Orders | [6 empty] | 4399501.14 | 3418457.57
Total Labour | [6 empty] | 1165620.7 | 1165620.7
Total Forecast | [6 empty] | 2442516.23
Total for Job | [6 empty] | 32302427.73 | 21845134.48

## Job Finalisation
Creditor | Order/Contract # | Ordered Amount | Authorised | Outstanding | Creditor | Order/Contract # | Contract Amount | Authorised | Outstanding | Description | Amount
Uncompleted Purchase Orders |  |  |  | 954322.62 | Subcontracts |  |  |  | 7033733.45 | Forecast Amounts | 2442516.23
ACOU02 | 22066049 | 6950 | 1750 | 5200 | ACOR01 | 22066018 | 38737.5 | 35702.5 | 3035 | Access Consultant (RFI | 500
AFSS01 | 22066061 | 38309.7 | 11919.91 | 26389.79 | ACTI02 | 22066012 | 108140 | 81540 | 26600 | BG 2.5% for DLP | 28000
AJGA01 | INSALL23 | 222738.1 | 154016.4 | 68721.7 | AHFE01 | 22066048 | 43000 | 0 | 43000 | August | 10847.32
ATFS01 | 22066007 | 11240 | 9527 | 1713 | APEX08 | 22066030 | 3335219.5 | 2627819.5 | 707400 | July | 12444.22
AUSC05 | 22066006 | 137845.44 | 94394.54 | 43450.9 | APPL03 | 22066010 | 1544475.6 | 1145783.3 | 398692.3 | June | 21721.74
BEBR02 | 22066199 | 665.5 | 0 | 665.5 | ARLA01 | 22066017 | 516869.7 | 477817.7 | 39052 | October | 2645.41
BIZF02 | 22066015 | 5208.05 | 473.45 | 4734.6 | ASPI03 | 22066013 | 389071 | 306634.39 | 82436.61 | September | 7001.65
BRIS76 | 22066105 | 6000 | 6608 | -608 | AZFI01 | 22066007 | 533690 | 421961.7 | 111728.3 | AUG23 | 8221.2
BRIS76 | 22066196 | 50 | 0 | 50 | BEEL02 | 22066035 | 214833 | 137873 | 76960 | JUL23 | 6576.96
BULK01 | 22066111 | 3579.67 | 2907.49 | 672.18 | BEST05 | 22066033 | 4825 | 4825 | 0 | JUN23 | 3162
BUNN01 | 22066013 | 500 | 350.35 | 149.65 | BOUT06 | 22066022 | 248476.26 | 118183.99 | 130292.27 | OCT23 | 1644.24
BUNN01 | 22066019 | 783.03 | 732.94 | 50.09 | CABL04 | 22066041 | 692393.23 | 253329.23 | 439064 | SEP23 | 6576.96
BUNN01 | 22066027 | 358.39 | 335.04 | 23.35 | CIVI22 | 22066005 | 341813.14 | 341812.64 | 0.5 | Additional CBR for Carpark | 13500
BUNN01 | 22066141 | 200 | 0 | 200 | CRUX01 | 22066006 | 42920 | 35520 | 7400 | Bollards | 2000
BUNN01 | 22066155 | 1000 | 281.37 | 718.63 | C&SS01 | 22066021 | 257142.38 | 257142.38 | 0 | Contingency | 20000
BUNN01 | 22066161 | 300 | 161.77 | 138.23 | CUST09 | 22066031 | 636037.81 | 397484.22 | 238553.59 | Footpath Prep | 8472
BUNN01 | 22066185 | 1041.6 | 956.08 | 85.52 | CUST19 | 22066020 | 185197.32 | 185197.32 | 0 | Piling pad trim back | 5800
BUNN01 | 22066191 | 150 | 0 | 150 | DOWE01 | 22066028 | 73010 | 73010 | 0 | Removal CBR and Concrete for | 19480
BUNN01 | 22066195 | 249.59 | 0 | 249.59 | DYFA02 | 22066002 | 235890 | 226917.5 | 8972.5 | Wheel stops | 3470
BUNN01 | 22066198 | 793.6 | 0 | 793.6 | DYFA03 | 22066001 | 1929514.44 | 1671739.66 | 257774.78 | 020025 Storerooms - skirting | 364.08
BUTL03 | 22066088 | 7415 | 1960 | 5455 | ELEC25 | 22066042 | 60100 | 47174.28 | 12925.72 | Bump Rail Install | 3500
CBAM01 | 22066197 | 782.75 | 0 | 782.75 | FIRE15 | 22066011 | 591100 | 450680.72 | 140419.28 | Lantham Bump Rail to Bin Room | 4600
COAT01 | 22066180 | 1774 | 968.6 | 805.4 | FITO01 | 22066016 | 1332825 | 1142299.18 | 190525.82 | Lantham Bump Rail to Laundry | 5000
DIYT01 | 22066136 | 3946.37 | 1083.5 | 2862.87 | FLOO13 | 22066029 | 812628 | 195313.38 | 617314.62 | Skirting | 2000
DYFA03 | 22066005 | 570 | 0 | 570 | FOUR02 | 22066049 | 33266 | 0 | 33266 | Additonal Access Panels | 26400
EAST27 | 22066095 | 2508.6 | 2344.5 | 164.1 | INGL01 | 22066052 | 24018.2 | 0 | 24018.2 | Mech Grille Framing | 19500
FAZE01 | 22066174 | 14000 | 10750 | 3250 | KONE01 | 22066004 | 343557 | 296382 | 47175 | ESC Audit - Jul | 500
FORK01 | 22066112 | 21427.6 | 14018.16 | 7409.44 | KRBG01 | 22066025 | 38113.7 | 35613.7 | 2500 | ESC Audit - Jun | 500
GENE10 | 22066120 | 22095 | 21995 | 100 | LAGW01 | 22066034 | 61695 | 61695 | 0 | ESC Audit - May | 500
HAFE01 | 22066134 | 66374.95 | 45203.15 | 21171.8 | LAMB04 | 22066023 | 245000 | 49000 | 196000 | ESC Audit - Oct | 500
INTR03 | 22066151 | 26438.03 | 4326.08 | 22111.95 | MARS07 | 22066040 | 47480 | 42935 | 4545 | ESC Audit - Sep | 500
KENN01 | 22066031 | 3323.72 | 3134.08 | 189.64 | M&CJ01 | 22066039 | 23495.8 | 23495.8 | 0 | Additional Cleaning Visits - | 4500
KENN01 | 22066039 | 728 | 185.36 | 542.64 | MGBR01 | 22066019 | 1416422.75 | 1392222.75 | 24200 | Cleaning Site Temps | 2500
KENN01 | 22066059 | 4961.01 | 4870.01 | 91 | MGSO01 | 22066024 | 76779 | 76779 | 0 | Monhtly cleaning - Oct | 5000
KERB08 | 22066194 | 5200 | 0 | 5200 | MMWA01 | 22066027 | 5235 | 5235 | 0 | Monthly Cleaning - Nov | 5000
KJBO01 | 22066173 | 100 | 0 | 100 | MMWA01 | 22066032 | 285210 | 135235 | 149975 | 020027 Traffic Island - Azfirm | 700
KLEE03 | 22066014 | 2040 | 1770 | 270 | MONT02 | 22066009 | 2270225.5 | 752124.5 | 1518101 | 020027 Traffic Island - bollar | 500
LYND01 | 22066101 | 700 | 409.24 | 290.76 | OZON01 | 22066045 | 100900 | 10309.55 | 90590.45 | Out of Sequence Works | 5000
MANS01 | 22066010 | 2000 | 1612 | 388 | PARA15 | 22066046 | 149700 | 119700 | 30000 | Sawcuts | 5000
MANS01 | 22066077 | 568073.3 | 567610.9 | 462.4 | RICK01 | 22066026 | 281353.27 | 171418.91 | 109934.36 | External - Carpark | 6289.5
MCNA01 | 22066103 | 104000 | 97842.7 | 6157.3 | SCOT42 | 22066047 | 320780 | 0 | 320780 | External - Driveway | 5949
MCNA10 | 22066030 | 38327.39 | 28954.42 | 9372.97 | SIXS01 | 22066043 | 640801.07 | 233174.72 | 407626.35 | External - Footpaths | 6176
MCNA13 | 22066200 | 385464.45 | 188884.53 | 196579.92 | STPC01 | 22066044 | 17160 | 1320 | 15840 | Trade reserves | 5000
MILA02 | 22066028 | 2880 | 2160 | 720 | SUNQ03 | 22066051 | 59750 | 21175 | 38575 | Washout Bags | 5400
O&MM01 | 22066184 | 13300 | 0 | 13300 | TKFO01 | 22066008 | 1341874.1 | 1340054.1 | 1820 | 020022 Cafe Entrance - Deleted | -648
RAPI20 | 22066113 | 1079.15 | 711.95 | 367.2 | UNDE06 | 22066036 | 284126.89 | 188359.89 | 95767 | 020027 Traffic Island - | 240
REEC02 | 22066054 | 658299.5 | 213615.52 | 444683.98 | UNIV24 | 22066037 | 967762.5 | 597389.7 | 370372.8 | 125mm deep paving treatment | 5467
SAFE36 | 22066122 | 256.33 | 220.72 | 35.61 | WAGS01 | 22066003 | 1071675 | 1071675 | 0 | Concrete - External Works | 78276
SAFE45 | 22066106 | 159.05 | 0 | 159.05 | WAST02 | 22066015 | 20500 | 0 | 20500 | Concrete - Footings | 8923.2
SPEL01 | 22066002 | 82205 | 68745 | 13460 | Total Subcontracts |  | 24294789.66 | 17261056.21 | 7033733.45 | Concrete - Misc items | 7585.92
SUNS17 | 22066164 | 28443.15 | 20333.61 | 8109.54 | [5 empty] | External works 4% wasteage | 2950
SYDN01 | 22066156 | 500 | 210.91 | 289.09 | [5 empty] | Joint Sealing | 8000
TRAD08 | 22066026 | 1481.53 | 1421.75 | 59.78 | [5 empty] | Saw Cutting | 8750
TRAD08 | 22066063 | 3113.2 | 2530.63 | 582.57 | [5 empty] | August - LC | 18907.2
TTMC02 | 22066050 | 2500 | 0 | 2500 | [5 empty] | July - LC | 15125.76
TTMC02 | 22066089 | 3412.5 | 1842.5 | 1570 | [5 empty] | June - LC | 14544
UNIV16 | 22066053 | 5100 | 5000 | 100 | [5 empty] | May - JW | 18180
UNIV25 | 22066073 | 61314.38 | 51970.13 | 9344.25 | [5 empty] | May - LC | 4726.8
UVSG01 | 22066186 | 9090 | 922.5 | 8167.5 | [5 empty] | October - LC | 15125.76
VISI08 | 22066124 | 6000 | 3600 | 2400 | [5 empty] | September - LC | 15125.76
WALK08 | 22066109 | 1600 | 0 | 1600 | [5 empty] | Corner and Door Protection | 30000
WHAL01 | 22066034 | 119556.04 | 111156.04 | 8400 | [5 empty] | Shed Repair costs for | 2000
YORK02 | 22066029 | 35147.82 | 34550.04 | 597.78 | [5 empty] | Additional Crane Hire | 5250
Sum: |  | 2755650.49 | 1801327.87 | 954322.62 | [5 empty] | Additional Crane Labour | 7600
[10 empty] | Additional Hoist Hire | 4110
[10 empty] | Props (each lvl GF-5) | 300
[10 empty] | Spoil Removal | 3941
[10 empty] | Vac Truck (2x Events) | 3400
[10 empty] | 020025 Storerooms - door hardw | 599.2
[10 empty] | Deliveries | 242
[10 empty] | Miscallaneous Hardware | 5150
[10 empty] | 020025 Storerooms - Lights | 780
[10 empty] | Crane Power & Modifications | 13000
[10 empty] | Nurse Call Lighting | 37500
[10 empty] | Warning system to maint. gate | 1000
[10 empty] | June - August Labour | 5000
[10 empty] | May - Jesse | 5000
[10 empty] | 64' Scssior Hire | 8400
[10 empty] | April Overhire | 16727.6
[10 empty] | Edge Protection | 8000
[10 empty] | Feb Overhire | 504
[10 empty] | June Overhire | 10300.79
[10 empty] | March Overhire | 1305.3
[10 empty] | May Overhire | 33556
[10 empty] | Scissor Pick Up/ Drop Off | 760
[10 empty] | Re-Clean Areas | 6000
[10 empty] | Form 12 Allowance/3rd Party | 2200
[10 empty] | Fire Extiguisher Replacement | 1988.5
[10 empty] | Quaterley Testing of FE | 3750
[10 empty] | 020022 Cafe Entrance - Tactile | 1170
[10 empty] | Additional Floor Prep | 36000
[10 empty] | Carpet Tiles Floor Leveling | 4000
[10 empty] | Concrete sealing to loading | 6760
[10 empty] | Possible epoxy flooring | 19469.5
[10 empty] | Vinyl 04 Credit | 5000
[10 empty] | Vinyl 07 Credit | 272.8
[10 empty] | AUG23 - FINISHES FOREMAN | 21782.8
[10 empty] | AUG23 - FITOUT FOREMAN | 21782.8
[10 empty] | AUG23 - JMAC | 21782.8
[10 empty] | JUL23 - FINISHES FOREMAN | 17426.24
[10 empty] | JUL23 - FITOUT FOREMAN | 17426.24
[10 empty] | JUL23 - JMAC | 17426.24
[10 empty] | JUN23 - FINISHES FOREMAN | 16756
[10 empty] | JUN23 - FITOUT FOREMAN | 16756
[10 empty] | JUN23 - JMAC | 16756
[10 empty] | MAY23 - FINISHES FOREMAN | 12567
[10 empty] | MAY23 - FITOUT FOREMAN | 12567
[10 empty] | MAY23 - JM | 12567
[10 empty] | OCT23 - FINISHES FOREMAN | 17426.24
[10 empty] | OCT23 - FITOUT FOREMAN | 17426.24
[10 empty] | OCT23 - JMAC | 8713.12
[10 empty] | SEP23 - FINISHES FOREMAN | 17426.24
[10 empty] | SEP23 - FITOUT FOREMAN | 17426.24
[10 empty] | SEP23 - JMAC | 17426.24
[10 empty] | Day Labour Works | 2875
[10 empty] | Fuel June | 2100
[10 empty] | Fuel May | 2800
[10 empty] | Generator and Fuel June | 1200
[10 empty] | Generator Hire May | 1600
[10 empty] | Proof Roll Inspections of | 2050
[10 empty] | AUG23 | 18907.2
[10 empty] | JUL23 | 15125.76
[10 empty] | JUN23 | 14544
[10 empty] | MAY23 | 4726.8
[10 empty] | OCT23 | 15125.76
[10 empty] | SEP23 | 15125.76
[10 empty] | AUG23 - 1Day/Wk | 4151.68
[10 empty] | JUL23 - 1Day/Wk | 3321.34
[10 empty] | JUN23 - 1Day/Wk | 3193.6
[10 empty] | MAY23 - 1Day/Wk | 3992
[10 empty] | OCT23 - 1Day/Wk | 3321.34
[10 empty] | SEP23 - 1Day/Wk | 3321.34
[10 empty] | Detailed Excavation - Revisit | 6000
[10 empty] | Floor Wastes to Vinyl Install | 14400
[10 empty] | Install SPEL Storm Sacks | 2560
[10 empty] | Puddle Flanges - WP | 3000
[10 empty] | Re-work Cisterns | 5000
[10 empty] | Strip Drain | 6000
[10 empty] | Temp waterproofing | 10000
[10 empty] | 020006 Kitchenette | 450
[10 empty] | Additional Storage | 7000
[10 empty] | Bedroom Joinery Protection | 12500
[10 empty] | Hair Salon Mirrors | 6500
[10 empty] | Remaining Scozia was $464,141 | 314807.55
[10 empty] | ST to LM Credit to client | 14978
[10 empty] | 020007 Laundry Heat Pump Dryer | 900
[10 empty] | Final Inspections | 5600
[10 empty] | 020022 Cafe Entrance - Garden | 1728
[10 empty] | Flagpoles x2 | 10502.87
[10 empty] | Re-Turf Site Compound | 5000
[10 empty] | Trellis Structure | 7971.05
[10 empty] | water features | 17500
[10 empty] | Builders Lift extra weeks | 600
[10 empty] | Access for Level 5 Blockwork | 7450
[10 empty] | Caulking to Blockwork | 9212
[10 empty] | Drilling & Epoxy Starters to | 5500
[10 empty] | Fireplace | 4534
[10 empty] | AUG23 | 750
[10 empty] | JUL23 | 750
[10 empty] | SEP23 | 750
[10 empty] | Bin Room Ventilation | 5000
[10 empty] | Door grilles | 10000
[10 empty] | Plinths | 5000
[10 empty] | 020022 Additional Pool Fence | 2494.78
[10 empty] | Alum Screen Footings | 5000
[10 empty] | Bike racks | 6456.82
[10 empty] | Convex Mirror for Maintenance | 474.77
[10 empty] | Dentist Enclosure - | 3259.75
[10 empty] | 020026 Epoxy Paint to Structur | 2625
[10 empty] | 020026 Structural Steel Connec | 3643
[10 empty] | 020026 Traffic Control Allowan | 1992
[10 empty] | Containers Lifted Over ATF | 2500
[10 empty] | Misc Crane items | 1000
[10 empty] | Removal of Site Shed | 2440
[10 empty] | Install Electric Strikes | 2445
[10 empty] | Portaloos on Level 4 | 612
[10 empty] | 020025 Storerooms - Painting | 1100
[10 empty] | 020027 Traffic Island - painti | 220
[10 empty] | Touch Up Allowance | 8000
[10 empty] | Prelim Contingency | 40000
[10 empty] | AUG23 | 29385.2
[10 empty] | JUL23 | 23508.16
[10 empty] | JUN23 | 22604
[10 empty] | MAY23 | 7346.3
[10 empty] | OCT23 | 23508.16
[10 empty] | SEP23 | 23508.16
[10 empty] | 020023 Joinery Shop Drawings | 705.1
[10 empty] | 020023 Service Coordination an | 500
[10 empty] | Day Labour (Drilling) | 8625
[10 empty] | Level 2 | 4925.94
[10 empty] | level 3 | 2794.24
[10 empty] | Level 5 | 1110
[10 empty] | roof | 1320.9
[10 empty] | 020022 Cafe Entrance - Deducte | -432
[10 empty] | 020027 Traffic Island - reo su | 180
[10 empty] | Additional External Area Reo | 9500
[10 empty] | Deliveries | 1900
[10 empty] | External Reo | 25720.85
[10 empty] | AFS Walls - External | 2738
[10 empty] | Additional Service | 1400
[10 empty] | Gutter Guard Credit to Client | 4380
[10 empty] | 020006 Tea Making Station | 4129
[10 empty] | 020012 Western Facade Windows | 5000
[10 empty] | Additional Signage | 4055
[10 empty] | Site comms A3 Copier, | 2500
[10 empty] | Site Security | 6600
[10 empty] | Milestones | 3350
[10 empty] | Site Expenses - AL CC | 2000
[10 empty] | AUG23 | 11032.32
[10 empty] | Aug23 Jesse | 2206
[10 empty] | JUL23 | 8825.86
[10 empty] | Jul23 Jesse | 11032.3
[10 empty] | JUN23 | 8486.4
[10 empty] | Jun23 Jesse | 2206.46
[10 empty] | OCT23 | 8825.86
[10 empty] | SEP23 | 8825.86
[10 empty] | AUG23 | 26509.6
[10 empty] | JUL23 | 21207.68
[10 empty] | JUN23 | 20392
[10 empty] | MAY23 | 7647
[10 empty] | OCT23 | 21207.68
[10 empty] | SEP23 | 21207.68
[10 empty] | AUG23 - Safety Items | 900
[10 empty] | JUL23 - Safety Items | 900
[10 empty] | JUN23 - Safety Items | 900
[10 empty] | SEP23 - Safety Items | 900
[10 empty] | Bunnings - Small Tools | 3300
[10 empty] | Hire Equipment/Self Perform | 2100
[10 empty] | Ash Accomodation Allowance | 11200
[10 empty] | Furniture Dismantle & Removal | 2500
[10 empty] | Office Furniture | 2200
[10 empty] | Stationary | 3960
[10 empty] | External works | 3500
[10 empty] | Roof Plant Deck and stair | 1600
[10 empty] | 020022 Cafe Entrance - PFC and | 1760
[10 empty] | Misc. Additional Visits | 8880
[10 empty] | Temporary Elect Protection | 2200
[10 empty] | Temp Power - Aug-Nov | 6740
[10 empty] | Temp Power - May-Aug | 5200
[10 empty] | 4wks Add Hire (OCT23) | 1800
[10 empty] | Reinstatement of Kerbs, | 5000
[10 empty] | Consumption Chagres - Nov - | 4000
[10 empty] | Consumption Charges - Feb - | 4000
[10 empty] | Consumption Charges May - Sep | 4000
[10 empty] | Consumption Charges Oct-Nov | 3000
[10 empty] | Disconnection | 1200
[10 empty] | Bedding | 2500
[10 empty] | 020006 Tea Making Station | 560
[10 empty] | Additional Wastage | 9000
[10 empty] | Artedomus Tile - Hairdresser | 1500
[10 empty] | Extra Over for Adbri Paver | 7392.08
[10 empty] | Freight | 1250
[10 empty] | 020025 Storerooms - door suppl | 500
[10 empty] | Door Frames - Delay Costs | 12240
[10 empty] | Trade Contingency | 90000
[10 empty] | Containers over Back Fence | 2015.82
[10 empty] | Footpath Closer Scaffold | 2015.82
[10 empty] | Miscallanious Visits | 2400
[10 empty] | Roof Sheeting Delivery | 1007.91
[10 empty] | Tower Crane Dismantle | 1007.91
[10 empty] | 020012 Waterproofing Water | 2500
[10 empty] | Client Credit for Removed | 2025
[10 empty] | Total Forecasts | 2442516.23