Assessment Workbook 2

BSB51415 Diploma

of Project Management

Constraint Management

Version 1.11 Produced 18 October 2018

Copyright © 2021 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following Training Package update | 1.0 |
| 22 June 2017 | Updated Table of Contents | 1.1 |
| 18 October 2018 | Change to Practical Assessment | 1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Written Questions	5

Part 1 – Project Scope	5

Part 2 – Project Time	17

Part 3 – Project Cost	26

Part 4 – Project Quality	30

Case Study	36

Instructions to Student	36

Introduction	37

Workbook Checklist	51

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 2 |  |  |
| --- | --- | --- | --- |
| TITLE: | Constraint Management |  |  |
| FIRST AND SURNAME: | Justin Thomsen |  |  |
| PHONE: | 0412330368 |  |  |
| EMAIL: | Jthomsen75@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name : J.Thomsen |  | Signature: | Date: 26/09/20 |

# Written Questions

Part 1 – Project Scope

| - Which of the following are project initiation documentation required at the start of the project? Select all that apply. |  |
| --- | --- |
|  | - Communications log |
|  | - Project plan |
|  | - Work Breakdown Structure (WBS) |
|  | - Gantt Chart |
|  | - Project charter |
|  | - Risk management |

| - Which of the following are components of a project scope-management plan? Select all that apply. |  |
| --- | --- |
|  | - Project deliverables |
|  | - Project staff assignments |
|  | - Change request |
|  | - Project justification |
|  | - Product description |
|  | - Performance reports |
|  | - Project objectives |
|  | - Project funding requirements |
|  | - Quality metrics |
|  | - Budget forecasts |

- In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

The project scope outlines in detail what the project is constructed of and how the project is managed. Outlining the exact scope is how the management team can successfully complete a project on time and on budget. Alterations to the scope, for example client submitting a change request, will alter the scope plan. This alteration will directly affect both time and cost by adding to the project duration and budget. Both of these alterations will require an amendment to the project scope and resubmitted to the client for approval.

| - Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request? Select all that apply. |  |
| --- | --- |
|  | - The deliverables may not meet quality requirements. |
|  | - Grammatical and typo errors are found in the project initiation documents. |
|  | - The deliverables may not be what the client wanted, even though they were covered in the project plan. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - Observance of non-working holidays affecting project time. |
|  | - Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant. |
|  | - Failure of equipment needed to produce the deliverables. |
|  | - Missing documentations in the project’s information system. |
|  | - Raw materials are no longer available. |
|  | - Supplier or contractor closing business. |

| - Which of the following are procedures that typically must be followed under change control processes? Select all that apply. |  |
| --- | --- |
|  | - Project manager seeks advice from supervisor regarding changes in cost. |
|  | - Project manager assigns a project team member to recalculate for the critical path. |
|  | - Project manager provides the change request to the appropriate stakeholder for approval. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - The project manager updates the project plan and other documentation where required. |
|  | - Project manager drafts the change request. |
|  | - Project manager delegates the authority to the project team members in advising other stakeholders of the changes. |
|  | - The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes. |
|  | - Details of the proposed change to be communicated to the project manager. |
|  | - The project sponsor and owner may automatically terminate the project contract. |

| - The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Method | Description |
| c | Units completed | - Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion. |
| a | Incremental milestones | - In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements. |
| d | Start / finish | - This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled. |
| b | Weighted or equivalent units | - This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed. |

| - Which of the following are activities involved in decomposition of the total work project? Select all that apply. |  |
| --- | --- |
|  | - Summarise project tasks in the form of a written report. |
|  | - Identify and analyse the deliverables and related work. |
|  | - Structure and organise the work breakdown structure (WBS). |
|  | - Arrange the smallest project tasks to form an aggregate representation of the total project task |
|  | - Decompose the upper work breakdown structure (WBS) levels into lower level detailed components. |
|  | - Calculate duration and resource effort for each project task. |
|  | - Develop and assign identification codes to the WBS components. |
|  | - Inspect whether work and deliverables meet requirements and product acceptance criteria. |
|  | - List resources required for each project task. |
|  | - Verify that the degree of decomposition of the work is necessary and sufficient. |

- List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

- Using phases of the project life cycle as the first level of decomposition - Using major deliverables as the first level of decomposition - Using subprojects which may be developed by organizations outside the project team such as the contracted work

| - The following are some problem areas in scope management. In your own words, briefly discuss each problem area. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Problem areas | Discussion |
| Scope creep | The uncontrolled expansion to product or project scope without adjustments to time, cost, and resources. As the scope of the project alters its affects are directly related to time and budgets. An unmanaged scope creep will have a negative effect on any project. |
| Sponsor / project owner approval | All changes to scope / project plan will require sponsor approval and management team consultation. If this is not completed in a timely manner this may slow project productivity. Approval must be undertaken in the correct way using project change request form and logged in the change register. |
| Project team accountability | The project team are a set of individuals who support the project manager in performing the work of the project to achieve its objectives. Each member needs to be accountable for their part of the management process. If one member were not to uphold their position in the team, this outcome may affect other team members in a negative way causing a further adverse effect to the project. |

- In your own words, discuss the significance of scope management. Do not exceed 150 words.

Scope is a process of developing a detailed description of the project. Benefit of managing this is that it describes the project and acceptance standards. Managing the scope will provide access to project information like assumption logs, requirements documentation and risk registers. With the management team using techniques like data analysis, decision making and expert judgement, managing the scope will aid in progress and efficiency across the project. The preparation of a detailed project scope statement is critical to project success and builds upon the major deliverables, assumptions, and constraints that are documented during project initiation. The degree and level of detail to which the project scope statement defines the work that will be performed and the work that is excluded can help determine how well the project management team can control the overall project scope

| - The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process. |  |
| --- | --- |
| Project Scope Management | Tool or technique |
| Collect requirements | Expert judgement and data gathering |
| Define scope | Decision making and product analysis |
| Create WBS | Expert judgement and decomposition |
| Verify scope | Inspection and decision making |
| Control scope | Data analysis |

| - Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles. |  |
| --- | --- |
| Roles (list five (5)) | Responsibilities (List at least one (1) for each role) |
| Understand the project | Know why the project is initiated, what are the key stakeholders expectations ? |
| Scope management | Ensure that all requirements can be turned into deliverables |
| Time management | Responsible for compiling the schedule baseline |
| Cost management | Responsible for compiling the cost baseline |
| Quality management | Planning the QA and QC activities to achieve client needs |

Part 2 – Project Time

| - The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| b | Analogous estimating | - This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration. |
| a | Parametric estimating | - This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project. |
| e | Three-point estimating | - This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them. |
| c | Expert judgement estimating | - Contingencies are accounted for into the overall project schedule to account for schedule uncertainties. |
| d | Reserve analysis | - This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:Te=To +4 x Tm + Tp6 . |

| - The following are estimation tools techniques used in determining activity resource. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| d | Expert judgment | - Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries. |
| e | Alternative analysis | - In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources. |
| a | Published estimating data | - This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates. |
| b | Bottom-Up estimating | - This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise. |
| c | Project management software | - These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource. |

| - In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Parameter | Discussion |
| ES | Earliest start time-the earliest time at which the task can start, allowing that any prior task must be completed first. |
| EF | The earliest start time for the task on top of the time taken to finish the task |
| LF | The latest time a task can be finished without delaying the project |
| LS | The latest finish time minus the time needed to finish the task |

| - Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline? Select all that apply. |  |
| --- | --- |
|  | - Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule. |
|  | - The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases. |
|  | - Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline. |
|  | - Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work. |
|  | - Developing the schedule baseline starts and ends in the planning phase of the project. |

| - Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. Which of the following are processes that are involved in schedule control? Select all that apply. |  |
| --- | --- |
|  | - Determining the current status of the project schedule. |
|  | - Defining activities or specific actions to be performed to produce project deliverables |
|  | - Influencing the factors that create schedule changes |
|  | - Decomposing total project work into its lowest levels. |
|  | - Determining that the project schedule has changed |
|  | - Estimating duration and resource effort for the project. |
|  | - Managing the actual changes as they occur. |

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words. - List three (3) project data generated from the Gantt Chart. - List three (2) limitations of the Gantt Chart.

- The Gantt chart is useful for planning and scheduling projects. It is used to assess how long a project will take, determine the resources needed, and plan the order in which tasks are completed. - Visual out line of project schedule - Start and end date of the project Relationship between tasks Progress of the project Calculate key milestones Allocate resources to each task - The format is not common, often needs to be changed to PDF for distribution The area of the Gantt chart page is very large and hard to print The progress of each task is subjective so a project manager may be tempted to exaggerate the progress of a task to make the chart look better

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words. - List three (3) project data generated from the Critical Path Method. - Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

- Critical path is a step by step management method used to identify processes on the critical path. It’s a method that breaks down the project into smaller work tasks, illustrates them in a flow chart and then estimates project start and completion dates based on durations of each task. - Parameters of each task Activities on the critical path Critical elements on the project - The critical path is a visual display of the sequence of tasks. The limitation of this method may be the addition of works to a project that impact on this path. The increased workflow may directly effect this path and without a possible input of labor or cash flow the dates set by the critical path will not be completed and have a detrimental effect on others tasks that occur after the effect. This will mean a readjustment of the PERT chart and critical path.

| - The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Project scheduling tools and techniques | Description |
| b | Schedule network analysis | - This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. |
| a | Critical Path Analysis | - This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts |
| d | Schedule compression | - They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations. |
| c | Automated scheduling tools | - This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. |

| - Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules? Select all that apply. |  |
| --- | --- |
|  | - Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components. |
|  | - The work breakdown structure (WBS) identifies project personnel who are responsible for each project task. |
|  | - Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work. |
|  | - The work breakdown structure (WBS) is used to represent the full project scope of the project. |
|  | - The work breakdown structure provides the relationships among all components of the project and the project deliverables. |
|  | - The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables. |
|  | - Project work at lowest levels are not included in the work breakdown structure (WBS) |

Part 3 – Project Cost

| - The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Estimating costs | Estimating the costs is the part of the project dedicated to approximately valuing the resources needed to complete a project. Estimating cost is reliant on the information know at a given point in time. |
| Determine budget | Determining the budget is a process of combining the estimated costs of individual processes to construct an authorized cost baseline, including budgets while excluding management reserves. |
| Control cost | Controlling cost is the process of monitoring the project status to update the project budget and manage changes to the cost baseline. |

| - The following are different tools and techniques used in cost management. Match each to its correct description. Write the letters that correspond in the spaces provided. |  |  |
| --- | --- | --- |
|  | Strategy | Description |
| b | Analogous estimating | - This is used to establish both the contingency reserves and the management reserves for the project with regards to cost. |
| c | Parametric estimating | - This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters. |
| e | Cost aggregation | - This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project. |
| a | Reserve analysis | - These are used to develop mathematical models to predict total project costs. |
| d | Historical relationships | - Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project. |
| g | Earned value management | - In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline. |
| f | Variance analysis | - This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. |

- List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

- Using an effective tool to manage project finances, e.g. spreadsheet of software package. - Sending invoices on a regular basis - Paying invoices promptly - Checking incoming invoices against contracts, quotes and agreements.

- You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123). - In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. - In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope. - In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures. Do not exceed 100 words for each discussion.

- The project management policy reviews the company’s core values and gives a broad representation of how Bigger Than Big conducts management procedures across all of their projects. With a standard approach to project management and the implementation of strategic priorities, the policy discusses the minimum requirements for governance and management of projects. The policy aims to improve management while making the project more visible to Bigger Than Big Management Corporation. It is outlining a broad model to be used across all projects. This model is specific to projects with Bigger Than Big and to be used in conjunction with the organizational unit plan. b. This procedure reviews process and management responsibilities accompanied by the management of Bigger Than Big. The purpose is to understand the project management policy, procedures and lifecycle by interpreting the process that are undertaken across the project. The scope defines a project as” a body of work with distinct start and end dates that progresses through defined phases and adheres to a formal project management methodology”. c. There are 5 phases that are recommended for a project to follow. 1. The pre-initiate phase outlays the foundation of the project. It outlines project milestones achievable with appropriate business justification. Key tasks of this phase are making initial assessment of the project size and governance structure and a complete business case. 2. The initiate phase summarizes how the project will be executed. This phase has two outcomes with a detailed model of work outcomes and confirmation of project arrangements suggested in the business case. 3. plan phase instructs how the project will be undertaken. The major activity in this phase is the addition of detailed schedule and budget information to the project initiation document. 4. the implement phase highlights how project outputs will be delivered. 5. The close phase is used to formally close the project.

Part 4 – Project Quality

| - In your own words, discuss each of the following key concepts in Quality Management. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Key Concepts in Quality Management | Discussion |
| Customer satisfaction | Customer satisfaction is a way of gauging how a project is progressing. Customers will judge the project by its outputs and mark the project poor or of high standard regardless of project team’s considerations. Customer expectations need to be met in order to have a free flowing project |
| Prevention over inspection | Prevention over inspection is relative to at what point is money is spent to correct defects. Is the money spent at the beginning of the project to prevent the failure (cost of quality) or is the spending left till the end of the project? Understandably, these are known as the cost of conformance and the cost of non-conformance. It is normally cost effective to prevent the mistake prior to it happening. |
| Continuous improvement | Continuous improvement is a key element of prevention over inspection. Basically, as the name states, it is the continued effort to improve your project. This task is undertaken by studying the project for any lessons learned that may be applied to other projects. |

- In your own words, discuss the difference between Quality Assurance and Quality Control. Do not exceed 100 words.

Quality assurance is process orientated. It is the testing of the processes that are used in the production of the product. Quality control is product orientated. It is the testing of the product and the detection of defects. Quality control is important in allowing or denying a products use in the project.

| - The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| People standards | People standards relates to the quality and qualifications of the people that are working on the project. To be installing high level equipment in a building construction project you need people with a qualification/standard to work at this level and qualifications to work with certain types of machinery. |
| Process standards | Process standards are the process involved in auditing a project. All parts of a project must be kept to a standard by audits so that there is continuity to the next phase. |
| Product / service standards | Product / service standards involve quality control in relation to the end product. It means complying with standards that are relevant to the project or service. |

| - The following are quality assurance and control methods, techniques and tools. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Methods, tools, techniques | Description |
| h | Benchmarking standards | - This is a distribution of dots comparing two variables. If the two variables are completely independent, you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it. |
| g | Brainstorming sessions | - These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis. |
| d | Control charts | - It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes. |
| f | Flowcharts | - These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors. |
| b | Histograms | - It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results. |
| e | Pareto charts | - A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions. |
| c | Run charts | - It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions. |
| a | Scatter grams | - These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies. |

- List five (5) responsibilities of the project manager in quality management.

- Determine the quality standards for the project deliverables - Determine the quality standards for the project process - Document all the required standards in the project plan - Ensure the organizational quality requirements are met for the delivery of the project - Leading the project QA and QC activities

| - The following are methods used in managing continuous improvement. In your own words, discuss each method. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Six Sigma | Is a set of tools and techniques to aid in improving work processes. It aids in improving the quality of the output of the process by eliminating the cause of the mistake. |
| Lean Six Sigma | Lean six sigma is a combined effort from the project team in removing waste from the project. It eliminates inefficiencies in time, overproduction, defects and motion to name a few. |
| Total Quality Management | Total quality management is a comprehensive approach that aims to improve the quality of products and services through ongoing refinements in response to project management team communication. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You have already provided advice to Awesome Landscapes in the previous workbook. Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off. As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario. The documents you need to complete the succeeding tasks can be accessed through the following links: Project Charter version 2 (.pdf) Project Plan version 2 (.pdf) Project Gantt Chart version 2 (.mpp) Project Gantt Chart version 2 (.pdf) Project Network Diagram version 2 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- List the three (3) project deliverables in Phase 1.

- Phase 1 – pre building Remove vegetation in areas being cleared and replanting/maintaining the plants for replanting in stage 3 Access roads through the existing forest for builders to access each building site. Retaining walls to provide stability around the buildings. Included three additional retaining walls as per updated site plan. - Phase 2 – building support - Phase 3 – planting and landscaping

| - Discuss the project constraints in terms of scope, time, cost, and quality. |  |
| --- | --- |
| Scope | The scope constraints are outline by detailing what the project will deliver. This is done by highlighting what is included as a deliverable and what is to be excluded on the project. |
| Time | Time constraints are documented with the aid of GANNT charts and schedules. In this instance the time was altered by the addition of the extra works to the chalets |
| Cost | Cost constraints are outline with the aid of the project budget. Section 4 .1 provides a budget table outlining the allowed for expenditure across all phases and process. Section 4 goes on to explain the projects contingency fund and where the source of the funds will be paid from. |
| Quality | Quality constraints are dictated by the inspections that are undertaken. Section 5 outlines that there are 3 main requirements in this project, that being, council regulations, building regulations and licensing for operation of equipment. Quality assurance process will have monthly audits and the local council will inspect the construction on a monthly basis, the project manager also has an extensive list of audits that needed to be conducted throughout the project. |

| - Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. Write 1 – 12 in the spaces provided; where 1 go first and 12 go last. |  |
| --- | --- |
| 8 | Remove weeds |
| 11 | Plant additional plants |
| 2 | Move gravel to car park |
| 1 | Expand car park |
| 12 | Remove greenhouses |
| 9 | Plant plants from greenhouses |
| 3 | Seal car park |
| 6 | Soil preparation |
| 7 | Add boulders |
| 5 | Construct stone paving pathway |
| 10 | Purchase additional plants |
| 4 | Landscape over old access roads |

- Review the Project Plan. The change request has outlined one change in the scope of the project. - What is the change in scope? - How does this change in scope impact the overall duration of the project? - How does this change in scope impact the quality aspect of the project?

- More retaining walls being added to project, consequently more chalets needed to be built. - Normally, the increase to the project scope would directly affect the project output. In this case, the additional resourcing from J.P Digging will prevent any change to the project timeframe. The total number of hours required to complete the work will increase to 140 from 120 hours. The start date of the project will be brought back by one week (starting on 27 July). No other project timeframes have been changed. - The change has an added risk to quality due to the delay in getting the plan approved by council.

- Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request? Do not exceed 100 words.

The change request lists the change to be three new walls need to be added. The addition of three extra retaining walls has also resulted in additional time being allocated to the excavation of the incoming utilities and septic system. As illustrated in appendix 4, effort and duration of tasks, the hours associated with the additions has increased, in particular in stages 1.2, 1.3 and stage 2.2. This increase is reflected in appendix 6 as total costs. All cost can be attributed to either the new construction of the retaining or the modification to the previously installed utilities and septic lines. The additional 20 hours are also accounted for in the budget. The budget is breaking down the costs into efficiencies to understand the cost of the change request better.

- Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

The project manager Sam NG, is responsible. By analyzing the change request (appendix 38) the changes are explained. The risks relating to the scope and program are clearly explained with notes on the additional costings and additional weeks’ work required to the beginning of the program. Stakeholders Susan Wills, Stephen Lyons and Kim Nguyen are all required to sign and date the request for the work to proceed.

- Access and review the Gantt Chart version 2. - What important tasks are not included in the project Gantt Chart? - Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

- Works associated with the change request and quality inspections. - The task involved with the change request effect many categories across the GANTT chart. From the construction of the retaining walls to the modification to the incoming septic lines, extra time will be needed to be added to complete these tasks properly. If these were properly programed into the Gannt Chart there would be the opportunity to complete these additions without the problems associated with revisiting a task. With these tasks not included in the correct project documentation, the risk is that they will not be completed ( or maybe even started ) or done out of sequence which had a detriment effect on all tasks that follow from that point. Quality inspections also need to be included to the GANNT chart so as the project manager can allow appropriate time for peroration and attendance of the inspections.

- List the three (3) personnel who signed off on the change request.

- Susan Wills - Stephen Lyons - Kim Nguyen

- What is the total increase in cost of the project as a result of this change request?

Appendix 7 outlines the detailed costings per task. This change relates to the additional retaining walls required in the project. task number 15 has increase from $17460 to $18960. Task number 16 has increased from $215800 to $25760. Task number 17 has increased from $16280 to $ 18760. Also increases in the cost of the management associated with the addition. The cost of the addition to the final project cost is $462153 from $444253, the cost of the addition consequently equals $17900.

- List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

- Monitoring and maintaining partially and fully constructed buildings - Monitoring and maintaining the main road. - Creation of additional retaining walls. - Onsite security - Any building, decorating or furnishing of the chalets.

- Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. Do not exceed 50 words.

The change request form has been completed and suspected to have been submitted to the client, being Susan wills (program manager, Massive Eco development corporation) for review. The request states that the council has been informed with Stephan Lyons listed as a stakeholder to be notified. Appendix 38, change request, has been completed. Appendix 37, the change register, will be updated once all stakeholders have signed and agreed to terms of the change request. All changes to the plan have been highlighted yellow being the first change, and at a face to face meeting with stakeholders the request will be signed where the changes will be communicated and implemented by the project manager .

- Access and review the Gantt Chart version 2. It shows double bars for each task. - What do the coloured bars represent? - What do the grey bars represent? - Why do the grey and coloured bards do not match up in the Gantt chart?

- Dark blue = progress Light blue = manual progress - Project summary - The dark grey bars are a summary of the phase and they are the total of all of the stages represented by the colored bars

- Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. Do not include the task ‘Project Management’.

- Move plants to glasshouse and dispose - Install road gravel - Delivery of granite boulders

- If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely: - Construction of retaining walls. - Install and compact soil behind walls. According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

Appendix 32, statement of work J.P Digging, explains that the soil to be used for compaction behind the retaining walls is to be taken from another area of the project. By starting this process early there is the time to accumulate the soil required for compaction and be compacting as the wall is being constructed at the same time. The required TimeLine and milestone dates also explains how the 2 process start on the same date and the walls is completed on Friday 21 September and backfilling is completed on the Monday 24 September. This slightly contradicts the Gannt chart which says the walls will be completed on the 23rd and the backfilling on the 15th.

- According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’, - Which tasks, if any, are immediately delayed? - Will this delay push out the completion of the project? Why or why not? - Discuss how this could affect the resourcing of the project. - List one (1) risk that could arise from this issue.

- Erect signage item 59 and soil preparation for the detailed landscaping item 62 - There will be a delay to the project as task 57 is on the critical path. Resourcing will need to be relocated from other areas to complete this task causing subsequent delay to other areas. - As with a lot of projects, resourcing will increase as the project nears completion. At this point in this project it is nearly complete and the addition labor / machinery will reassure the project will be completed on time. - The increase in labor will directly affect the budget. Productivity must increase to complete the project on an earlier date. with a larger work force

- What is the total budget for the project expenditure?

The project budget for this project has been increased from $444253 to the new total of $462153 with a surplus of $87847 to absorb any additional cost that the project may incur.

- Sam is very concerned about the cash flow of the project. - What is the problem? - What would you suggest be done to rectify the cash flow issue?

- The cash flow chart demonstrates the negative effect the change request 1 has to the budget. There is a steady decline in funds until 30/09/17 where the change has commenced and payments are being made for the change. - The change may be moved to a more appropriate time in the program where awesome landscapes could mitigate the risk by having been paid for previous phases and consequently have more funds to rely on.

- Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-Development Corporation to absorb some or all of these cost increases. Your discussion must be 200 – 300 words in length. Guidance: The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

Awesome landscapes are entitled to request additional funding from Massive Eco-development. The additional retaining walls have been noted in section 2.1 deliverables as being part of the inclusions to the package. It is noted in phase 1 – per building that “retaining walls to provide stability around the buildings. Includes three additional retaining wall as per updated site plan.” This inclusion to the project plan is highlighted yellow to also indicate that it is in the first issue of updates, this process is outlined in section 1.3 change control. Section 1.3 continues to state that if council approval is required that once granted the plan will be modified as required. At this stage in the project plan I do not believe that the change request has been received back from council with no clear indication attached to state that there are new conditions. Consequently, the change register, appendix 27, has not been updated indicating that it has not been submitted to the client for approval. Also the lack of signatures on the change request also indicates that the client has not yet approved the additional costs. The costings and increased times associated with the change are all clearly documented as an updated change to the original plan in appendix’s 4 effort and duration of tasks, appendix 5 task dependency worksheet and appendix 6 summary costing per phase. All of this documented information would lead to an acceptable request for funding to the change request

- Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project. Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Justin Thomsen (project manager awesome landscapes ) |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: | Overall Project Status: |  |  |  |  |  |  |  |
| Audit Date: | Audit Number: |  | Audit Leader: |  |  |  |  |  |
| Audit Team: |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To request funding from the principal regarding the additional works |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. completion of appendix 38 project change request templet. |  | Assessment: | Comment: |  |  |  |  |  |
| 2. communication with council and conformity with council approval and codes. |  | Assessment: | Comment: |  |  |  |  |  |
| 3. communication with client and management team of change to project |  | Assessment: | Comment: |  |  |  |  |  |
| 4. subcontractors consulted and information combined in change request |  | Assessment: | Comment: |  |  |  |  |  |
| 5. budget reflective of all monetary changes to the plan appendix 8 ,project cash flow and appendix 7, detail costing per task. |  | Assessment: | Comment: |  |  |  |  |  |
| 6. all changes to the project highlighted to indicate the correct change procedures |  | Assessment: | Comment: |  |  |  |  |  |
| 7. apply to all relevant building standards and codes |  | Assessment: | Comment: |  |  |  |  |  |
| 8. project plan correctly updated |  | Assessment: | Comment: |  |  |  |  |  |
| 9.are quality assurance documents and drawings being updated in accordance with the change |  | Assessment: | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes |  | no |  |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |
| Audit Report Submitted To: |  |  |  | Date: |  |  |  |  |

- Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions: - What was the cause of the unsatisfactory results? - What action would you recommend to prevent the issue coming up again in this project?

- For part 2, communication breakdown within the management team. It seems that not enough and not the correct information was supplied to the worksite. This could be overcome with simple team meeting to review the changes. This lack of information led to the delay in works experienced in part 3. Again, properly conveyed information at the commencement of the task would have prevented the loss of time on the workface. - As explained in recommended actions, more management time is required prior to issuing the change to the workface. Relevant drawings / plans and standards need to be presented to the workface in an appropriate package including the documentation related to the additional work

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng |  |  |  |  |  |  |  |  |
| Date: 17 August 2015 |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: Implementation | Overall Project Status: On schedule |  |  |  |  |  |  |  |
| Audit Date: 17 August 2011 | Audit Number: 26 |  | Audit Leader: Sam Ng |  |  |  |  |  |
| Audit Team: Sam Ng, John Cowley, Ann Deak. |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the communication and reporting processes. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are tasks being communicated to site supervisor in a reasonable amount of time? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| 2. Are tasks being communicated to site supervisor of sufficient detail? |  | Assessment: Not satisfactory. | Comment: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. |  |  |  |  |  |
| 3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time? |  | Assessment: Not satisfactory. | Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. |  |  |  |  |  |
| 4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular, detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. Project manager to prepare task briefs in enough time to add the required level of detail. 2. Task briefs are to be supplied with all relevant attachments such as detailed plans. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes | x | no |  |
| Audit Report Submitted To: Kim Nguyen |  |  |  | Date: 24/08/2015 |  |  |  |  |

- The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. Guidance: Your Cost Management Plan must cover the following quality objectives and criteria. - Meeting with contractual requirements. - Paying invoices on time. - Ensure invoices are sent out in time. - Ensuring financial reporting is done on time. - Include a calendar of when payments are likely to be due. - Comparison of actual cash flow against projected cash flow.

A) All associated meetings relating to costing of this management plan will be coordinated via the requirements in the communications analysis worksheet, appendix 21. B) All invoices will be paid as per section 4.5 of the project plan, source of funds. Invoices will be raised on the first working day of the month following the due date of each progress payment. Payments listed below.  Payment 1: 50% initial payment at the commencement of phase 1.  Payment 2: 20% progress payment upon completion of all phase 1 deliverables and delivery of project progress report.  Payment 3: 20% progress payment upon completion of all phase 2 deliverables and delivery of project progress report.  Payment 4: 10% final payment upon completion of all phase 3 deliverables and delivery of the project final report. C) invoices are to be sent out in accordance with the project program. All invoices will be raised on the first working day of the month following the due date of each progress payment D)All financial reporting is projected in appendix 8, project cash flow. The reporting of these finances will be done as requested in appendix 20 – communications plan. E)

F) Projected cash flow charts have been supplied in appendix 8.  They demonstrate the actual cash flow taken from figures in the project cash flow table and transposed onto the attached    s-curve graph. This graph highlights the changes that change request1 have onto the project budget.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Part 1 – Project Scope a Part 2 – Project Time Part 3 – Project Cost Part 4 – Project Quality Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document