Assessment Workbook 2

BSB51415 Diploma

of Project Management

Constraint Management

Version 1.11 Produced 18 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following Training Package update | 1.0 |
| 22 June 2017 | Updated Table of Contents | 1.1 |
| 18 October 2018 | Change to Practical Assessment | 1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Written Questions	5

Part 1 – Project Scope	5

Part 2 – Project Time	17

Part 3 – Project Cost	26

Part 4 – Project Quality	30

Case Study	36

Instructions to Student	36

Introduction	37

Workbook Checklist	51

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 2 |  |  |
| --- | --- | --- | --- |
| TITLE: | Constraint Management |  |  |
| FIRST AND SURNAME: | Nicky Harrison-Atholwood |  |  |
| PHONE: | 0409279247 |  |  |
| EMAIL: | roberight@hotmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Nicky Harrison-Atholwood |  | Signature: NMH | Date: 18/02/2020 |

# Written Questions

Part 1 – Project Scope

| - Which of the following are project initiation documentation required at the start of the project? Select all that apply. |  |
| --- | --- |
|  | - Communications log |
|  | - Project plan |
|  | - Work Breakdown Structure (WBS) |
|  | - Gantt Chart |
|  | - Project charter |
|  | - Risk management |

| - Which of the following are components of a project scope-management plan? Select all that apply. |  |
| --- | --- |
|  | - Project deliverables |
|  | - Project staff assignments |
|  | - Change request |
|  | - Project justification |
|  | - Product description |
|  | - Performance reports |
|  | - Project objectives |
|  | - Project funding requirements |
|  | - Quality metrics |
|  | - Budget forecasts |

- In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

Project scope, cost and time are all fully interrelated and any adjustment to made to any of these will directly impact the other. Ie. – change in scope to perhaps add in an additional retaining wall will then impact the cost increase to build it and time increase to build it.

| - Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request? Select all that apply. |  |
| --- | --- |
|  | - The deliverables may not meet quality requirements. |
|  | - Grammatical and typo errors are found in the project initiation documents. |
|  | - The deliverables may not be what the client wanted, even though they were covered in the project plan. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - Observance of non-working holidays affecting project time. |
|  | - Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant. |
|  | - Failure of equipment needed to produce the deliverables. |
|  | - Missing documentations in the project’s information system. |
|  | - Raw materials are no longer available. |
|  | - Supplier or contractor closing business. |

| - Which of the following are procedures that typically must be followed under change control processes? Select all that apply. |  |
| --- | --- |
|  | - Project manager seeks advice from supervisor regarding changes in cost. |
|  | - Project manager assigns a project team member to recalculate for the critical path. |
|  | - Project manager provides the change request to the appropriate stakeholder for approval. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - The project manager updates the project plan and other documentation where required. |
|  | - Project manager drafts the change request. |
|  | - Project manager delegates the authority to the project team members in advising other stakeholders of the changes. |
|  | - The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes. |
|  | - Details of the proposed change to be communicated to the project manager. |
|  | - The project sponsor and owner may automatically terminate the project contract. |

| - The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Method | Description |
| C | Units completed | - Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion. |
| A | Incremental milestones | - In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements. |
| D | Start / finish | - This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled. |
| B | Weighted or equivalent units | - This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed. |

| - Which of the following are activities involved in decomposition of the total work project? Select all that apply. |  |
| --- | --- |
|  | - Summarise project tasks in the form of a written report. |
|  | - Identify and analyse the deliverables and related work. |
|  | - Structure and organise the work breakdown structure (WBS). |
|  | - Arrange the smallest project tasks to form an aggregate representation of the total project task |
|  | - Decompose the upper work breakdown structure (WBS) levels into lower level detailed components. |
|  | - Calculate duration and resource effort for each project task. |
|  | - Develop and assign identification codes to the WBS components. |
|  | - Inspect whether work and deliverables meet requirements and product acceptance criteria. |
|  | - List resources required for each project task. |
|  | - Verify that the degree of decomposition of the work is necessary and sufficient. |

- List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

- Using phases of the project lifecycle as the first level of decomposition, with the product and project deliverables inserted at the second level - Using major deliverables as the first level of decomposition - Using subprojects which may be developed by organisations outside the project team such as contract work.

| - The following are some problem areas in scope management. In your own words, briefly discuss each problem area. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Problem areas | Discussion |
| Scope creep | These are small incremental changes to scope that occur throughout the project, often the PM isn’t aware until the changes become quite substantial. |
| Sponsor / project owner approval | Any changes in scope management will need to be signed off / approved by the sponsor / project owner |
| Project team accountability | Ensure that the Project Team members fully understand the scope of the project while agreeing on how the project goals will be met. |

- In your own words, discuss the significance of scope management. Do not exceed 150 words.

Effective scope management is important as it ensures the project team members full understand the scope of the project while agreeing on how the project goals will be met. It helps avoid the problems and challenges that a project potentially faces with every growing scope. The project scope defines what is and what isn’t included in the project and controls what gets added or removed as the project is executed.

| - The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process. |  |
| --- | --- |
| Project Scope Management | Tool or technique |
| Collect requirements | Group decision technique |
| Define scope | Product analysis |
| Create WBS | Decomposition |
| Verify scope | Inspection |
| Control scope | Variance Analysis |

| - Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles. |  |
| --- | --- |
| Roles (list five (5)) | Responsibilities (List at least one (1) for each role) |
| Understanding the Project | Deliverables of the project |
| Scope Management | Take down all requirements and turn them into work packages |
| Time Management | Scheduling the project |
| Cost Management | Coming up with a cost baseline |
| Quality Management | Plan QA & QC Activities |

Part 2 – Project Time

| - The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| B | Analogous estimating | - This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration. |
| A | Parametric estimating | - This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project. |
| E | Three-point estimating | - This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them. |
| C | Expert judgement estimating | - Contingencies are accounted for into the overall project schedule to account for schedule uncertainties. |
| D | Reserve analysis | - This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:Te=To +4 x Tm + Tp6 . |

| - The following are estimation tools techniques used in determining activity resource. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| D | Expert judgment | - Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries. |
| E | Alternative analysis | - In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources. |
| A | Published estimating data | - This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates. |
| B | Bottom-Up estimating | - This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise. |
| C | Project management software | - These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource. |

| - In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Parameter | Discussion |
| ES | Earliest start time – the earliest time at which the task can start, given that any predecessor tasks must be completed first. |
| EF | Earliest Finish time – the earliest start time for the task plus the time required to complete the task |
| LF | Latest Finish Time – The latest time in which the task can be completed without delaying the project. |
| LS | Latest Start Time- The latest finish time minus the time required complete the task |

| - Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline? Select all that apply. |  |
| --- | --- |
|  | - Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule. |
|  | - The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases. |
|  | - Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline. |
|  | - Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work. |
|  | - Developing the schedule baseline starts and ends in the planning phase of the project. |

| - Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. Which of the following are processes that are involved in schedule control? Select all that apply. |  |
| --- | --- |
|  | - Determining the current status of the project schedule. |
|  | - Defining activities or specific actions to be performed to produce project deliverables |
|  | - Influencing the factors that create schedule changes |
|  | - Decomposing total project work into its lowest levels. |
|  | - Determining that the project schedule has changed |
|  | - Estimating duration and resource effort for the project. |
|  | - Managing the actual changes as they occur. |

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words. - List three (3) project data generated from the Gantt Chart. - List three (2) limitations of the Gantt Chart.

- Ganntt charts are used for planning and scheduling projects, they help assess how long a project should take , determine the resources needed, and plan the order in which tasks are completed. - To provide a visual outline of the project To show progress of the project Allows you to allocate resources to each task - The format (MS project) is not common so it needs to be PDF’d to distribute The area of the gantt chart pages is very large and often difficult to print.

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words. - List three (3) project data generated from the Critical Path Method. - Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

- CPM is a step by step project management technique to identify activities on the critical path – it break the project into several work tasks, displays them in a flow chart and then calculates to project duration based on estimated durations for each task. - Parameters of each task – ES – EF – LS - LF Activities on the critical path Critical elements in the project - It is only as useful and accurate as the information put into it. Incorrect info such as task durations along the critical path then the entire duration of the project could be clown out.

| - The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Project scheduling tools and techniques | Description |
| B | Schedule network analysis | - This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. |
| A | Critical Path Analysis | - This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts |
| D | Schedule compression | - They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations. |
| C | Automated scheduling tools | - This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. |

| - Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules? Select all that apply. |  |
| --- | --- |
|  | - Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components. |
|  | - The work breakdown structure (WBS) identifies project personnel who are responsible for each project task. |
|  | - Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work. |
|  | - The work breakdown structure (WBS) is used to represent the full project scope of the project. |
|  | - The work breakdown structure provides the relationships among all components of the project and the project deliverables. |
|  | - The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables. |
|  | - Project work at lowest levels are not included in the work breakdown structure (WBS) |

Part 3 – Project Cost

| - The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Estimating costs | Analogous estimating – uses values of costing from a previous/similar project. Parametric estimating – uses statistical relationship between historical data and other variables to calculate and estimate for cost. |
| Determine budget | Cost aggregation – cost estimates are combined by work packages in accordance with WBS Reserve Analysis – used to establish both contingency reserves and management reserves regarding costs for the project Historical Relationships - used to develop mathematical models to predict total project costs |
| Control cost | Earned Value Management – used as a performance measurement, integrates scope / cost/ schedule measure to help assess & measure project performance & progress Variance Analysis – Cost & performance measurements are used to assess the magnitude of variation to the original cost Bbaseline |

| - The following are different tools and techniques used in cost management. Match each to its correct description. Write the letters that correspond in the spaces provided. |  |  |
| --- | --- | --- |
|  | Strategy | Description |
| B | Analogous estimating | - This is used to establish both the contingency reserves and the management reserves for the project with regards to cost. |
| C | Parametric estimating | - This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters. |
| E | Cost aggregation | - This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project. |
| A | Reserve analysis | - These are used to develop mathematical models to predict total project costs. |
| D | Historical relationships | - Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project. |
| G | Earned value management | - In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline. |
| F | Variance analysis | - This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. |

- List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

- Using an effective tool for managing the project finances (Spreadsheet / software package etc) - Sending invoices on a regular basis - Paying invoices promptly - Checking incoming invoices against contracts / quotes / agreements etc

- You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123). - In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. - In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope. - In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures. Do not exceed 100 words for each discussion.

- The policy is designed to specify the minimum essential elements In the management of projects to assist in articulating scope, involving stakeholders, managing risk and maximizing project benefits. It is designed to improve the way in which company projects are managed as they progress to completion and to increase the visibility of projects and there processes. Projects must operate in the context of policies and procedures of company as determined from time to time including but not limited to the risk management policy, the delegations of authority policy, the procurement policy and the leading and managing change framework. - The project management procedure applies to projects in Bigger than Big, a project is a body of work with distinct start and finish dates that progress through defined phases and adheres to a formal project management methodology. It results in the transformation of a business function and or delivery of one or more outcomes. - Pre-initiate phase –builds the foundation of a project and is often triggered when an individual identifies the need to solve a problem, improve a process or implement a new service Initiate phase – this phase has 2 outcomes 1 / The preparation of a detailed model of the work required to achieve the project objectives; & confirmation of the in-principle funding decisions & project arrangements suggested in the Business Case. Plan phase – provides further detail about how the project will be Conducted. The major activity in this phase is the addition of detailed schedule and budget information to the Project Initiation Document. Implement phase – The implementation plan consists of all the activities related to systems, staff, processes and training that must be completed to achieve the intended project outputs. Close phase - The Close Phase is the formal closure of the delivery component of the project. It has two main outcomes: 1/ The handover of project outputs to the operational areas responsible for ongoing support and maintenance (if applicable to the project); 2/ The evaluation of the success of the project (also known as Benefits Realisation Analysis).

Part 4 – Project Quality

| - In your own words, discuss each of the following key concepts in Quality Management. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Key Concepts in Quality Management | Discussion |
| Customer satisfaction | Is a key measure and indicator of the project’s quality |
| Prevention over inspection | COQ includes money spent during the project to avoid failures and money spent during and after the project due to failures |
| Continuous improvement | A concept that exists in all of the major quality management approaches such as six sigma & TQM. It is the key aspect of prevention over inspection. |

- In your own words, discuss the difference between Quality Assurance and Quality Control. Do not exceed 100 words.

Quality control is the testing of the end result products and detection of defects, its primarily an inspection function. Whereas Quality assurance is the testing of processes in producing the product. It is sometimes known as defect prevention and is primarily an audit function.

| - The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| People standards | Include qualifications and experience – appropriate tickets for specific jobs / task. |
| Process standards | Standards for processing & delivering the project involving QA auditing. |
| Product / service standards | Standards that look at the end product involving QC standards |

| - The following are quality assurance and control methods, techniques and tools. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Methods, tools, techniques | Description |
| H | Benchmarking standards | - This is a distribution of dots comparing two variables. If the two variables are completely independent you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it. |
| G | Brainstorming sessions | - These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis. |
| D | Control charts | - It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes. |
| F | Flowcharts | - These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors. |
| B | Histograms | - It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results. |
| E | Pareto charts | - A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions. |
| C | Run charts | - It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions. |
| A | Scatter grams | - These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies. |

- List five (5) responsibilities of the project manager in quality management.

- Work health and safety - Environmental issues - Equal opportunity - Industrial relations - Anti-Discrimination

| - The following are methods used in managing continuous improvement. In your own words, discuss each method. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Six Sigma | Set of techniques and tools for process improvement. It improves the quality of the output of a process by identifying and removing the cause of defects and minimizing variability in manufacturing and business processes. |
| Lean Six Sigma | A methodology that relies on a collaborative project team effort to improve performance by systematically removing waste to eliminate the 8 types waste; time, inventory, motion, waiting, overproduction, over processing, defects & Skills (TIMWOODS) |
| Total Quality Management | A comprehensive and structured approach to project management that seeks to improve the quality of products and services through ongoing refinements in response to continuous feed back. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You have already provided advice to Awesome Landscapes in the previous workbook. Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off. As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario. The documents you need to complete the succeeding tasks can be accessed through the following links: Project Charter version 2 (.pdf) Project Plan version 2 (.pdf) Project Gantt Chart version 2 (.mpp) Project Gantt Chart version 2 (.pdf) Project Network Diagram version 2 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- List the three (3) project deliverables in Phase 1.

- Removal of vegetation in areas being cleared and replanting / maintaining the plants for replanting in phase 3. - Access roads through the existing forest for builders to access each building site - Retaining walls to provide stability around the building ( including 3 new additional retaining walls.)

| - Discuss the project constraints in terms of scope, time, cost, and quality. |  |
| --- | --- |
| Scope | The natural environment must be carefully preserved as per council strict requirements for environmentally sensitive areas. |
| Time | Completion of all work within 9 months |
| Cost | There is a fixed budget of $550,000 |
| Quality | The landscaping work must work around the building construction. Quality must be maintained to strict council requirements for environmentally sensitive areas. |

| - Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. Write 1 – 12 in the spaces provided; where 1 go first and 12 go last. |  |
| --- | --- |
| 8 | Remove weeds |
| 11 | Plant additional plants |
| 2 | Move gravel to car park |
| 1 | Expand car park |
| 12 | Remove greenhouses |
| 9 | Plant plants from greenhouses |
| 3 | Seal car park |
| 6 | Soil preparation |
| 7 | Add boulders |
| 5 | Construct stone paving pathway |
| 10 | Purchase additional plants |
| 4 | Landscape over old access roads |

- Review the Project Plan. The change request has outlined one change in the scope of the project. - What is the change in scope? - How does this change in scope impact the overall duration of the project? - How does this change in scope impact the quality aspect of the project?

- Three new retaining walls to be built - It has increased the overall duration by 20 hours, however increase in additional resources will relieve the overall increase. - Ensuring additional work is carried out to council regulations / requirements to maintain quality

- Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request? Do not exceed 100 words.

Because there is only 1 new change in scope from the original contract, this change in scope has an impact on budget. However the change in scope will also have an impact on time and resources and a flow on effect as to why the different parts of the financial table have increased in areas this can be covered in contingency.

- Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

Project Manager for Awesome Landscapes

- Access and review the Gantt Chart version 2. - What important tasks are not included in the project Gantt Chart? - Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

- Milestones - The project sponsor isn’t going to be interested in hearing about the completion of each individual task – they are going to be interested in hearing about the achievement of a milestone, however there are none indicated on this ganttchart.

- List the three (3) personnel who signed off on the change request.

- Susan Willis – Program Manager – Massive Eco-Development - Stephen Lyons – Planning Manager - Cascade Peak Shire Council - Kim Nguyen – Director – Awesome Landscapes

- What is the total increase in cost of the project as a result of this change request?

$17,900.00

- List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

- Installation of utilities - Installation of service points at either road or chalet end - Installation of pipes and tanks - Construction of septic system buildings or other infrastructure - Provisions or delivery of pipes and tanks

- Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. Do not exceed 50 words.

Yes, the project plan follows the change control procedure. All required parties have signed off the change request and items 1-10 on the change control procedure have been satisfied throughout the project plan.

- Access and review the Gantt Chart version 2. It shows double bars for each task. - What do the coloured bars represent? - What do the grey bars represent? - Why do the grey and coloured bards do not match up in the Gantt chart?

- Task & Manual summary rollup - The Project base line & the project schedule determined at the start of the project ( Where do I find this information??) - Because the project schedule has changed as a result of the change request.

- Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. Do not include the task ‘Project Management’.

- Delivery of granite boulders - Move plants to greenhouse and dispose

- If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely: - Construction of retaining walls. - Install and compact soil behind walls. According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

*** Conflicting Dates *** The Gantt chart says the Install & compact soil will be completed by the 15th September??? However If you are to read the “Required Timeline & Milestone Dates” Document , the retaining wall construction needs to be completed by Friday 21st of September & the Install & Compact soil completed by Monday 23rd September .

- According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’, - Which tasks, if any, are immediately delayed? - Will this delay push out the completion of the project? Why or why not? - Discuss how this could affect the resourcing of the project. - List one (1) risk that could arise from this issue.

- Erection of signs & Soil prep could be delayed if item 57 needs to be completed before they can start – if not then no. - This will depend on how long the delay for completion of item 57 is and if it impacts other tasks??? - Workers set to start new tasks may not be needed - Potential push out of end date.

- What is the total budget for the project expenditure?

$462,153.00

- Sam is very concerned about the cash flow of the project. - What is the problem? - What would you suggest be done to rectify the cash flow issue?

- There is a major decrease in cash flow 30/09 with a significant increase the following month. - Adjust project schedules to balance out cash flow and keep project in the black.

- Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-development Corporation to absorb some or all of these cost increases. Your discussion must be 200 – 300 words in length. Guidance: The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

Awesome Landscapes should seek further funding for the retaining walls as they are a legitimate claim for additional funding, and contingency should not be used to cover significant costs of variations.

- Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project. Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

*Completed highlighted fields*

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: | Overall Project Status: |  |  |  |  |  |  |  |
| Audit Date: | Audit Number: |  | Audit Leader: |  |  |  |  |  |
| Audit Team: |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: Variation Approval |  |  |  |  |  |  |  |  |
| Audit of Management of Project: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| 1. |  | Assessment: | Comment: |  |  |  |  |  |
| 2. |  | Assessment: | Comment: |  |  |  |  |  |
| 3. |  | Assessment: | Comment: |  |  |  |  |  |
| 4. |  | Assessment: | Comment: |  |  |  |  |  |
| 5. |  | Assessment: | Comment: |  |  |  |  |  |
| 6. |  | Assessment: | Comment: |  |  |  |  |  |
| 7. |  | Assessment: | Comment: |  |  |  |  |  |
| 8. |  | Assessment: | Comment: |  |  |  |  |  |
| 9. |  | Assessment: | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes |  | no |  |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |
| Audit Report Submitted To: |  |  |  | Date: |  |  |  |  |

- Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions: - What was the cause of the unsatisfactory results? - What action would you recommend to prevent the issue coming up again in this project?

- Lack of communication: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. - Seek clarifications prior to tasks starting so that there is no interruptions pertaining to that task. Requirements of tasked should be clarified prior to task starting. Details of task requirements should be readily available through documentation and site / team meetings.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng |  |  |  |  |  |  |  |  |
| Date: 17 August 2015 |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: Implementation | Overall Project Status: On schedule |  |  |  |  |  |  |  |
| Audit Date: 17 August 2011 | Audit Number: 26 |  | Audit Leader: Sam Ng |  |  |  |  |  |
| Audit Team: Sam Ng, John Cowley, Ann Deak. |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the communication and reporting processes. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are tasks being communicated to site supervisor in a reasonable amount of time? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| 2. Are tasks being communicated to site supervisor of sufficient detail? |  | Assessment: Not satisfactory. | Comment: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. |  |  |  |  |  |
| 3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time? |  | Assessment: Not satisfactory. | Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. |  |  |  |  |  |
| 4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. Project manager to prepare task briefs in enough time to add the required level of detail. 2. Task briefs are to be supplied with all relevant attachments such as detailed plans. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes | x | no |  |
| Audit Report Submitted To: Kim Nguyen |  |  |  | Date: 24/08/2015 |  |  |  |  |

- The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. Guidance: Your Cost Management Plan must cover the following quality objectives and criteria. - Meeting with contractual requirements. - Paying invoices on time. - Ensure invoices are sent out in time. - Ensuring financial reporting is done on time. - Include a calendar of when payments are likely to be due. - Comparison of actual cash flow against projected cash flow.

All accounts payable and receivable to be paid on the 30th of each month as per the contract. Head Contract claim will be issued on the 30th of each month to be paid on the 30th of the following month (30 day accounts). All invoices received by the 30th of the month will be paid on the 30th of the following month to keep cash flow balance. Date paid; % of Contract; $$. 30th October; 54%; $249,562.62. 30th November; 6.5%; $30,039.94. 30th December; 6%; $27,729.18. 30th January; 9.5%; $43,904.53. 28th February; 17.5%; $80,876.77. 30th March; 6.5%; $30,039.94. 30th April; 0%; $0. Total; 100%; $462,153.00.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Part 1 – Project Scope Part 2 – Project Time Part 3 – Project Cost Part 4 – Project Quality Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document