## Sheet1
Project | Lot 8 Rees Court, Palm Beach Qld 4221 (Mr & Mrs Simcoe)
Site Manager | Jie Dong
Area | Activity | days | Start Date | Finish Date | time axis 2021-11-01 to 2022-05-22
 | time axis 2021-11-01 to 2022-05-22
Procurement Phase/Pre-construction Phase
1 | Survey & Layout Contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed; 2021-12-27: Public Holiday; 2021-12-28: Public Holiday; 2022-01-03: Public Holiday
2 | Site Clearing and excavation Contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
3 | Plumbing, Pool material purchase and installation contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
4 | Electrical material purchase and installation contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
5 | Foundationa and Concrete |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
6 | Flooring Purchase contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
7 | Supply of Roof tiles and timbers |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
8 | Supply of White goods Contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
9 | Supply of Tap Wear Contract |  |  |  | 2021-11-02: Tender Selection; 2021-11-08: RFQ Process and approval; 2021-11-15: ITT Issue and Tender Open; 2021-11-22: Tender Open; 2021-11-29: Tender Evaluation and RFA Preparation; 2021-12-06: Tender Evaluation and RFA Preparation; 2021-12-13: Contract Preparation and draft contract sent out; 2021-12-20: Contract Executed
Construction Phase
1 | Staking Lot Lines | 0.25 | 2022-01-10 | 2022-01-10 | 2022-01-26: Public Holiday; 2022-04-15: Public Holiday; 2022-04-18: Public Holiday; 2022-04-25: Public Holiday; 2022-05-02: Public Holiday
2 | Lot Clearing | 1.25 | 2022-01-10 | 2022-01-11 | bar: 2022-01-10 to 2022-01-11
3 | Excavation | 1.5 | 2022-01-11 | 2022-01-12 12:00 | bar: 2022-01-11 to 2022-01-12
4 | Temporary Power | 1 | 2022-01-12 12:00 | 2022-01-13 12:00 | bar: 2022-01-12 to 2022-01-13
5 | Layout | 1 | 2022-01-13 12:00 | 2022-01-14 12:00 | bar: 2022-01-13 to 2022-01-14
6 | Foundation and Concrete Pour | 5 | 2022-01-17 12:00 | 2022-01-21 12:00 | bar: 2022-01-17 to 2022-01-21
7 | Plumbing Rough-In | 3 | 2022-01-24 | 2022-01-27 | bar: 2022-01-24 to 2022-01-25; 2022-01-27
8 | Pool | 2 | 2022-01-28 | 2022-01-31 | bar: 2022-01-28; 2022-01-31
9 | Slab on Grade | 5 | 2022-02-01 | 2022-02-07 | bar: 2022-02-01 to 2022-02-04; 2022-02-07
10 | Frame Walls | 3 | 2022-02-08 | 2022-02-10 | bar: 2022-02-08 to 2022-02-10
11 | Roof Trusses | 3 | 2022-02-11 | 2022-02-15 | bar: 2022-02-11; 2022-02-14 to 2022-02-15
12 | Structural Plywood Sheathing | 1 | 2022-02-16 | 2022-02-16 | bar: 2022-02-16
13 | Roof Vents | 1 | 2022-02-17 | 2022-02-17 | bar: 2022-02-17
14 | Roofing Underlayment | 1 | 2022-02-18 | 2022-02-18 | bar: 2022-02-18
15 | Roofing-Tile | 1 | 2022-02-21 | 2022-02-21 | bar: 2022-02-21
16 | Windows | 1 | 2022-02-22 | 2022-02-22 | bar: 2022-02-22
17 | HVAC Rough-In | 2 | 2022-02-23 | 2022-02-24 | bar: 2022-02-23 to 2022-02-24
18 | Electrical Rough-In | 2 | 2022-02-25 | 2022-02-28 | bar: 2022-02-25; 2022-02-28
19 | Cable and Data Lines | 3 | 2022-03-01 | 2022-03-03 | bar: 2022-03-01 to 2022-03-03
20 | Insulation | 1 | 2022-03-04 | 2022-03-04 | bar: 2022-03-04
21 | Drywall | 2 | 2022-03-07 | 2022-03-08 | bar: 2022-03-07 to 2022-03-08
22 | Connect Utilities | 3 | 2022-03-09 | 2022-03-11 | bar: 2022-03-09 to 2022-03-11
23 | Exterior Masonry and Siding | 3 | 2022-03-14 | 2022-03-16 | bar: 2022-03-14 to 2022-03-16
24 | Exterior and Interior Paint | 2 | 2022-03-17 | 2022-03-18 | bar: 2022-03-17 to 2022-03-18
25 | Doors and Millwork | 3 | 2022-03-21 | 2022-03-23 | bar: 2022-03-21 to 2022-03-23
26 | Cabinets - Kitchen and Bath | 3 | 2022-03-24 | 2022-03-28 | bar: 2022-03-24 to 2022-03-25; 2022-03-28
27 | Counter Tops | 1 | 2022-03-29 | 2022-03-29 | bar: 2022-03-29
28 | Finish Lighting/Electric | 5 | 2022-03-30 | 2022-04-05 | bar: 2022-03-30 to 2022-04-01; 2022-04-04 to 2022-04-05
29 | Finish Plumbing | 5 | 2022-04-06 | 2022-04-12 | bar: 2022-04-06 to 2022-04-08; 2022-04-11 to 2022-04-12
30 | Flooring | 3 | 2022-04-13 | 2022-04-19 | bar: 2022-04-13 to 2022-04-14; 2022-04-19
31 | Finish HVAC | 2 | 2022-04-20 | 2022-04-21 | bar: 2022-04-20 to 2022-04-21
32 | Mirrors | 1 | 2022-04-22 | 2022-04-22 | bar: 2022-04-22
33 | Door Hardware | 2 | 2022-04-26 | 2022-04-27 | bar: 2022-04-26 to 2022-04-27
34 | Grading, Irrigation and Drainage | 3 | 2022-04-28 | 2022-05-03 | bar: 2022-04-28 to 2022-04-29; 2022-05-03
35 | Appliance Installation | 3 | 2022-05-04 | 2022-05-06 | bar: 2022-05-04 to 2022-05-06
36 | Gutters | 1 | 2022-05-09 | 2022-05-09 | bar: 2022-05-09
37 | Decks, Patio and landscaping | 2 | 2022-05-10 | 2022-05-11 | bar: 2022-05-10 to 2022-05-11
38 | Driveway and Sidewalks | 2.5 | 2022-05-12 | 2022-05-16 | bar: 2022-05-12 to 2022-05-13; 2022-05-16
39 | Fencing | 2.5 | 2022-05-16 | 2022-05-18 | bar: 2022-05-16 to 2022-05-18
40 | Final Walk-Through and Touch-Ups | 1 | 2022-05-19 | 2022-05-19 | bar: 2022-05-19
41 | Final Construction Cleanup | 1 | 2022-05-20 | 2022-05-20 | bar: 2022-05-20
90