Assessment Workbook 1

BSB51415 Diploma

of Project Management

The Project Life Cycle

Version 1.11 Produced 16 October 2018

Copyright © 2019 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 14 April 2016 | Version 1.0 produced following Training Package update | V1.0 |
| 22 June 2017 | Updated Table of Contents. | V1.1 |
| 16 October 2018 | Change to Practical Assessment | V1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Cover Sheet	4

Written Questions	5

Case Study	16

Instructions to Student	16

Introduction	17

Workbook Checklist	26

# Assessment Workbook Cover Sheet

| WORKBOOK: | Workbook 1 |  |  |
| --- | --- | --- | --- |
| TITLE: | The Project Life Cycle |  |  |
| FIRST AND SURNAME: | Zane Campbell |  |  |
| PHONE: | 0458207628 |  |  |
| EMAIL: | zanecampbell2308@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :zane campbell |  | Signature: zc | Date: 29/10/19 |

# Written Questions

| - Below are the different stages of the lifecycle of a project. Match each lifecycle stage to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Stage | Description |
| c | Scoping | - It is during this phase that a project management plan is developed all comprehensive of individual plans for – cost, scope, time, quality, communication, risk and resources. Some of the important activities that mark this phase are -making WBS, development of schedule, milestone charts, GANTT charts, estimating and reserving resources, planning dates and modes of communication with stakeholders based on milestones, deadlines and important deliveries. |
| a | Planning | - It is in this phase that the project deliverable is developed and completed, adhering to the plan as developed in the previous phase. The project execution and project monitoring and Control are the 2 phases that mostly occur simultaneously. A lot of project management tasks during this phase capture project metrics through tasks like status meetings and project development updates, status reports, human resource development and performance reports. |
| b | Implementation | - A project is formally started, named and defined at a broad level during this phase. Project sponsors and other important stakeholders perform their due diligence on whether or not to undertake a project, or choose to undertake one project over another. Depending on the nature of the project, feasibility studies are conducted or as it may require. |
| e | Monitoring | - It includes a series of important tasks such as making the delivery, relieving resources, reward and recognition to the team members and formal termination of contractors in case they were employed on the project. |
| d | Closing | - This phase mostly deals with measuring the project performance and progression with respect to the project management plan. Scope verification and control to check and monitor for scope creep, change control to track and manage changes to project requirement, calculating key performance indicators for cost and time are to measure the degree of variation if any and in which case corrective measures are determined and suggested to keep project on track. |

- Consider a project that you are currently working on or you would most likely work on in the future. Provide an outline of typical project phases that would take place during the Implementation Stage of this project.

Once the client had awared work our companey went into detailed work instructions were agreed opon as well as budget, weather and posible job/contract extenstions were signed off. Then at this point we initiated the following overlapping phase 2 phase shedule: phase 1: site prep, plant and asset requistion and mobilization, personel establishment/ crew prep e.g. site induction, permit sign offs, Voc's, SOP publication, initial site survey and benchmarks to be placed, signage and barraciading to be erected. e.g safety signs and company contact and boundry boards to signify our company duristiction in the mine site. As well as site contact and com channel's. phase 2: break ground, begin actual construction of dam buttress reinforcment. building of new ramps for next phase/lift of tailings dam. Quarry crew to start sourcing/crushing rock for drainage and de-cante. also small crew to begin clay conditoning for capping of inner dam wall and tie in's to existing base core phase 3: Start next bench lift behind previouse crew as they finish off and move onto de-cante construction. once initial crew finish reinforcment, final structural lift to start phase 4: finalistion of works.Conditioned clay capping to placed and trimed behined final lift. drainage and drainage rock to be cut in and placed. phase 5: final works and finishing touches are to begin e.g. clean up, trim to conformance, re-hab/ enviromental controls, de-mob any unnecessary plant or equipment as it becomes unutilized. completion of all contracted works. Also over all phases constant monitoring and qulity audit's to be performed, e.g. compaction and moisture testing to be performed by third party contractor, Survey conformance by client and contractor. all of wich are to be done at requiered milstones or phase sign off's. also a point to note is if the client wishes to impliment extra works new contracts are to be drawn up or day works to be signed off on. this usally happens around phase 4 to 5

| - The following are various structures in which the Implementation Stage of the project can be carried out. Match each structure to its correct descripition. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Structure |  | Description |
| d | Sequential phase-to-phase relationship | - Projects intended to respond to high levels of change and ongoing stakeholder involvement. Also very iterative and incremental but differ in iterations being very rapid (2-4 weeks) and are fixed in time and cost. |
| e | Overlapping phase-to-phase relationship | - The project phases (more commonly known as iterations) repeat one or more project activities as the project team’s understanding of the product increases. |
| c | Predictive life cycle | - The project phases repeat one or more project activities as the project team’s understanding of the product increases. |
| b | Iterative/incremental life cycle | - In this structure, a new phase starts only when a previous phase is complete. The step-by-step nature of this approach reduces uncertainty, but may eliminate options for reducing the schedule. |
| a | Adaptive Life Cycle | - This is where a phase starts prior to the completion of a previous one. This can sometimes be applied as an example of the schedule compression technique called fast tracking. Overlapping phases may increase risk and can result in rework if a subsequent phase progresses before accurate information is available from the previous phase. |

| - Which of the following are activities that usually take place as part of the closing of a project? Select all that apply. |  |
| --- | --- |
|  | - Project evaluation |
|  | - Warrantee requirements |
|  | - Create communications log |
|  | - Develop project management plan |
|  | - Writing and delivery of project final report |
|  | - Finalisation of accounts and other financial documentation |
|  | - Delvelop project charter |
|  | - Handover of project deliverables |
|  | - Settling of financial liabilities |
|  | - Project evaluation |
|  | - Identify stakeholders |
|  | - Signing off by the project sponsor |
|  | - Finalise lessons learnt documentation and communicating it where needed |
|  | - Transition of responsibility or ownership of project deliverables or products |
|  | - Archiving of project documentation |

| - The following are different methodologies used to break project objectives into achievable project deliverables. Match each of the following to its correct description. Write the letter of your answer in the spaces provided. |  |  |
| --- | --- | --- |
| Methodology |  | Description |
| d | Project governance | - A document that formally authorises a project or a phase. It includes the initial requirements that satisfy the stakeholders’ needs and expectations. It provides the overall high level description of the strategies and goals of your project. |
| b | Project management information system | - An automated tool, such as scheduling software tool, a configuration management system, and information collection and distribution system or web interfaces to other outline automated systems. |
| a | Project charter | - A document covering all the details of the project down to a very detailed level. It can be presented in the form of a Gantt chart or any other document that displays project activities along a timeline. |
| e | Work Breakdown Structure | - It provides a management structure for the project manager and their team to deliver the project. It provides the support, processes and tools needed for the project to be delivered. |
| c | Project plan | - A document detailing the subdivision of project deliverables into smaller more manageable components. |

| - Below are different types of project governance models. Match each model to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Project governance model |  | Description |
| b | Programmatic Based | - In this model, project managers have a high level of authority to manage and control the project resources. The project manager in this structure has total authority over the project and can acquire resources needed to accomplish project objectives from within or outside the parent organization, subject only to the scope, quality, and budget constraints identified in the project. |
| c | Matrix Based | - A traditional structure in which program sector managers have formal authority over most resources. It is only suitable for projects within one program sector. |
| a | Project Based | - This model allows program units to focus on their specific technical competencies and allow projects to be staffed with specialists from throughout the organisation. |

| - List two (2) documentation that must be created to record strategies and goals for integration processes. In your own words, briefly describe each documentation. Do not exceed fifty (50) words for each discussion |  |
| --- | --- |
| Documentation | Discussion |
| Project charter | The project charter is the initialising document that gets handed out from the client, mainly outlinning the main factors and details of the project, e.g. what the project is, Budget, time frame and quality required for project. The project charter is expected to change over scope period. Then once planning stage is over the project charter is concrete. |
| Project Plan | The project plan is a Pm's main tool to running a successful project. It outline's and provides all: milestones, deadlines, scope, schedual, budget, crew requirments, machinery requiered and management and client structure. all of wich are covered in high detail and in depth analisis and explanation. |

| - Consider the communication media you would utilise in project management. - List three (3) communication media you would utilise in project management. - Discuss how each communication media is applied on various projects. |  |
| --- | --- |
| Communication media | Discussion |
| Phone | Phone's /mobile phone's are a great quick way of comunication between all partys(client, management team and employees/ crew). as well as phone confrence when being in a team/ management meetings is not pluasable. mobiles are fast becoming a vital tool in my industry as easy and reliable resource for comunication, information access, evidence of work ect. |
| E-mail | E-mail is still a major player for comunication as it leaves a didgital trail and documentation sharing. E-mail's may still be followed up with verbal confamation when it contains important documents or comunictions. |
| Face to face meetings | Face to face meetings are always going to be a great way of comunicating weather it be with client or crew. It give's a more personal touch to the resoning behind a comunication/ information delivery rather than reading it in a text or email. it’s a good way to have brainstorming sessions or problem solving meetings as back and forth happen more fluently. It also helps with crew moral/motivation as you communicate on a more personal level. |

| - Discuss how each of the following communication methods below is applied on various projects. - Verbal communication - Non-verbal communication - Written communication In your discussion, include at least one (1) specific example or scenario on how each communication method is applied on various projects. |  |
| --- | --- |
| Communication Method | Discussion (with at least one (1) specific example or scenario for each communication method) |
| Verbal communication | Is the sharing/discusion of information between individuals or crew. you can use this method for a range of different comunication, eg, to negotiate, problem solve, inquire, motivate and evaluate, in all aspects of a project/ job. -team progress meetings |
| Non-verbal communication | is what reffers to all forms of body languge, hand gestures, postures and the general way you hold yourself. Sometimes this speaks louder then words or says what we cant say verbaly. the biggest example I consider the most important is the hand shake followed with a professional body languge. Esspecialy on first impresions with potential clients or stakeholders. |
| Written communication | These are E-mail, written reports, test reports, letters, site documentsand safty alert bulitens. -veriation requests -status reports |

| - List two (2) types of project management information systems (PMIS) and, in your own words, discuss how each is applied in project management. Do not exceed 50 words for each discussion. |  |
| --- | --- |
| Information systems | Application |
| Computer-based PMIS | is so an individual has access to the tools, information and techniques used to gather, implament and disspurse the information. this is done instantly rather than waiting days or weeks for it to be done manualy. |
| Web-based PMIS | is very similar to computer base but as it is web based your entire company/ crew/ management team have access to the same project info and documentation giving them better advantages for uniformaty when teams may be working or based in different sites. |

| - The following are methods used to evaluate information systems and communication processes. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Method |  | Description |
| d | System quality | - A performance measure to evaluate the efficiency of an investment (such as in this case, resources used to facilitate project communication). It measures the return on an investment relative to the investment’s cost. |
| b | Information quality | - The information system is assessed in terms of accuracy of output, promptness of output, precision of output, reliability of output, arrival of output, output completions, and output format |
| a | ROI | - It is a useful tool for performing retrospective analyses of the characteristics of internal communication. With the help of this model we can obtain several interpretations of the characteristics of project communications which help improve the communication process and also the project management process. |
| c | Internal Communication Analysis Model | - The information system is assessed in terms of response time, accessibility, realization of user’s demands, correction of mistakes, model and data safety, system documentation and procedures, system flexibility and system compatibility. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You will be working in this project in every case study assessment throughout this course. The project involves the landscaping of a new eco-resort. The company has hired you on the basis of your ability to analyse project methodology, not on your knowledge of the nature of the landscaping work they perform. At this stage of the project the project charter and project plan have already been developed. You have been assigned to examine the project plan before the project launches in three months’ time. In particular you have been asked the following questions which you will need to provide answers for upon examination of the project charter and the project plan. The documents you need to complete the succeeding tasks can be accessed by accessing the following links: Project Charter version 1 (.pdf) Project Plan version 1 (.pdf) Project Gantt Chart (.mpp) Project Gantt Chart (.pdf) Project Network Diagram (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

| - List all personnel (name, title / designation, and company) who are required to sign off on the Project Plan before the project is endorsed for commencement. Discuss why each personnel you listed are required to sign off on the Project Plan. Do not exceed fifty (50) words for each discussion. |  |  |
| --- | --- | --- |
| Personnel | Title / Designation, Company | Discussion |
| Susan Wills | Program Manager-Massive Eco-Development Corporation | As Susan is the primary Program manager for M.E.D.C the "Project sponsor" so the project has finacial backing. Commitment for paying for the project |
| Stephen Lyons | Planning Manager-Cascade peak Shire council | To signify that the project plan adhers to council rules and regulations and has council aproval for planed works. |
| Kate Chan | Project Manager-Timber Home Construction Ltd | acknolegment of responsibility for construction of planed assets to guide lines provided and aproved |
| Kim Nguyen | Director-Awsome Landscapes Pty Ltd | as director of A.L. they are acknowledging the acceptence and commitment of responsibilty for delivery of the project and initilization of project. |
| Sam Ng | Project manager-Awesome Landscapes Pty Ltd | As P.M for A.L they are accepting responsibility for the deliverables for the project and the quality out-come of the job. also to meet all standards set out in the project plan. |

- Review the Project Plan. - Does the Project Plan show evidence that the project has been appropriately approved for commencement? - Does the Project Plan show evidence that it has been distributed to all stakeholders who are required to have a copy? Guidance: If it has been approved and distibuted, indicate which section(s) or page(s) in the Project Plan indicate so. If not, explain what needs to be done to have the project approved for commencement.

- The project plan does show evidence that the project plan has been aproved and signed off on the 1st initial relese with no amendments or reviews. This can be found on page 6 of 141

- There is evidence that the document (project plan) has been distributed to all main partys and staek holders but there is a small note stating the project plan must be distributed to all members of the project steering comitee. in saying this there is no list in the project plan stating all committee members, weather that be befor or after aproval.

- How will the Project Outcomes be reported?

All urgent informal correspondence to take place directly between Sam Ng (project manager, Awesome) and Robert Hinson (project manager, Massive). •Weekly meetings to be held between Susan Wills (Program Manager, Massive), Robert Hinson (Project Manager, Massive), Kate Chan (Project Manager, Timber), Kim Nguyen (Director, Awesome), and Sam Ng (Project Manager, Awesome) •Reports to be send quarterly, or with any change request, to by Sam Ng (Project Manager, Awesome) to Susan Wills (Program Manager, Massive), Robert Hinson (Project Manager, Massive), Kate Chan (Project Manager, Timber), and Kim Nguyen (Director, Awesome).

- List all personnel (name, title/designation, company) who must have a copy of the Project Progress Reports. Discuss why each personnel you listed must have a copy of the Project Progress . Do not exceed fifty (50) words for each discussion.

| Personnel | Title / Designation, Company | Discussion |
| --- | --- | --- |
| Susan Wills | P,m, Massive Eco Development corporation | as stated in the project plan all steering commity personel must recive a copy of project report. As well as to ensure contracters are meeting requiered targets for progress budget and safety. |
| Stephen Lyons | planning manager, Cascade Peak shire council | to ensure contracters are meeting requiered targets for progress, budget safety and quality are met. |
| Kate chan | P,m, timber home construction ltd | To make sure that timelines deadline are on track of the other projects, so that they know when there work can start or continue. |
| Kim nguyen | Director Awsome landscapes pty ltd | to ensure that the work that their crew are performing is meeting qulity, time frames and budgets. |
| Sam Ng | P,M, Awsome landscapes | To make sure that timelines deadline are on track of the other projects, so that they know when there work can start or continue. |
| Robert Hinson | P.M. -massive eco-development corperation | To ensure contracters are meeting requiered targets for progress, budget, safety and quality are met. |

| - At which stage of the project life cycle is the project? Assume the current date is 7 May 20xx, where 20xx is the current year. |  |
| --- | --- |
|  | - Scoping |
|  | - Planning |
|  | - Monitoring |
|  | - Implementation |
|  | - Closing |

- Discuss how Massive Eco-development Corporation is going to maintain effective integration between the three projects? Your discussion must be 100 – 200 words in length. Guidance: Why have the three projects been planned separately rather than being integrated into one single project? Discuss factors that ensure the effective running of the three projects running together as separate projects.

The effective aspect of having three separate projects and thus having three different project mangers to collaberate and organize the smooth running and qulity controll of each project at a smaller size making it efficent and logical. each project can have a P,M, that specilizes in those specific aspects or feil ds of each project eg, earthworks/landscaping and another in building and construction for just an example. Also the other positive being that the project manager only having one project/ job under them mean qulity control and site monitoring can be done at a more comprehensive, thorough and more regular intervals as they don’t have to deal with all the other projects.

| - In your own words, discuss each of the following processes involved in the Closing Stage of the project. Do not exceed 150 words for each discussion. |  |
| --- | --- |
| Payment of Remaining Invoices | As the project reaches its closure hand over stage and all official works are completed to specified requirements set out in the project plan, final invoices from contractors and sub-contractors will have been lodged with the project sponser as well as any outstanding invoices from suppliers. It is the projects sponsers duty to make sure that this happens, if not peniltys and action from the contractor will apply. Once Payment of remaining invoices has happened/ recived then the next stage can occure. |
| Project Closure Meeting Documentation | The project closure meeting documentation involes the following, Finilisation of project plan preperation of final handover documentation any out-standing invoices/ contract payments and assosiated costs for final audit council approval/ final audit Lesson learnt reports Gantt completed charts These documents are all to be completed and signed off by the appropreat partys and persons along with full completion report and updated version of the project plan, thus showing all completed. (at time of project closure meeting formal acceptance and closure must be complete to be signed off). |
| Pre-meeting Audit | external/indipendant project auditor to examin all project plans and documents assosiated with it(as above documents). This is to ensure all project documents are complete and done so with due diligence. This is to be done Prior to the final project meeting |
| Final Project Meeting | All Steering committee members to attend final projevt meeting and each member to be provided with the following project documention for achival and meeting requierments. -Project completion report -Final version of project plan -Project archives checklist -Formal acceptance and closure document (document template provided for this, it must be signed off by the signatories of the project steering committee.) In this meeting lesson lernt documentation will also be reviewed and discussed for lessons relevante to future projects recognised by the committee. |
| Final Project Invoice | once the final project documentation has successfully been delivered, the company may raise an invoice to the project sponsore for final contract payment for succsseful project delivery. |
| Project Archival | Upon last and final payment all project documents and documentation may be archived, this is aided with the project archived checklist (this is provided in the project plan document templates), also these are to be stored as hard copys and digitaly. this means all hard copy documents must be scaned to didgit copys and stored on a archival hard drive in a folder clearly identifying the project name and date of archiving |

- How will the project be monitored?

Regular audits from internal at the end of each stage. this will be done by the project manager. as well as Council audits for construction on a monthly basis. Regular team meetings management and crews

- Review the objectives of the project. - Do the objectives of the project align with the business objectives of Awesome Landscapes? Explain your reasoning. - Do the objectives of the project align with business objectives of project sponsor organisation? Explain your reasoning. Each discussion must be between 50 – 150 words.

- The objectives of the project and awsome landscaping do align with each other over a broad outlook. If you take into consideration the enviromentel aspecte of both of them, they say the use of native plants of the reigon and the project says blends naturaly with surrounding forest. enviromently friendly aganst the other saying minimal impact to flora and fauna by the project. maintain established walking trails on cascade peak To have good time management and budget control.

- Yes the project objectives do align with both the project and sponsor organisation. when you look at the project plan you can see that their goal is to succsessfully deliver the project and maintain the partnership between both companys for future projects, also for local contracting and suppler use, and to establish this resort in closer proximity to cascade peak mountain region, as well as constructing an ecologically friendly resort.

- Sam has a gut feeling there will be some changes to the project once it commences. A rumour is spreading that there are going to be some additional chalets built requiring the construction of three more retaining walls than what appears in the project plan. He has specifically asked if he can approve and sign off on the extra construction himself knowing there is quite a big contingency budget to the project. Explain the procedure Sam would follow regarding the construction of the three additional retaining walls. Your discussion must not exceed 500 words. Guidance Answer Sam’s question by providing in your own words a specific procedure for the approval of the construction of three additional retaining walls. When mentioning any people in the procedure, list them by name and job title.

once Sam Ng (project manager awsome landscapes) has recived some sort of official comformation wether it be verbal or writen from the project sponser (Massive Eco-Development corperation) then he will have to get drawings and survey done for the extra works to be performed on the site of the extension, this then will be submitted with a draft project change request (template prvided in appendix 38) with budget cost requierments for excavation, procument of extra retaining wall moduals and instalation of, The next step would be to subbmit this to the requierd project program manager member for review . being: Susan Wills (program Manger massive Eco-development corperation) at this stage the draft change request will then go to cascade peak shire council planing manage being, Stephen lyons (planing Manager - cascade peak shire council) from here he will advise if a new council approvel is need with the intended changes/ perameters of the project. If changes are required then Massive eco-developments program manger Susan wills initiate the application process as needed. when council approval has been granted and if changes are needed the project plan and other project documentation will be ajusted when required eg change request register (appendix 37). all of these will be clearly colour coded by highlighted text and all omited and nul-void text must be formated with strike through to show it has been deleted with relivent highlighting. The next step is a face to face meeting to examin the change request documentation and all modified documentation with the foloowing people; Susan Wills (Program Manager – Massive Eco-Development Corporation), Stephen Lyons (Planning Manager - Cascade Peak Shire Council), Kate Chan (Project Manager - Timber HomeConstruction Ltd), Kim Nguyen (Director – Awesome Landscapes Pty Ltd), Sam Ng, (ProjectManager – Awesome Landscapes Pty Ltd) and any other stakeholders directly impacted on the change request. The change request is then to be signed off by Susan Wills (Program Manager – Massive Eco-DevelopmentCorporation), Stephen Lyons (Planning Manager - Cascade Peak Shire Council), and Kim Nguyen(Director – Awesome Landscapes Pty Ltd). in conclusion of all of these stages and steps being successfull the changes and works will be implemented in the approved new schedule and program.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document