Assessment Workbook 2

Assessment Workbook 2

BSB51415 Diploma

of Project Management

Constraint Management

Version 1.11 Produced 18 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following Training Package update | 1.0 |
| 22 June 2017 | Updated Table of Contents | 1.1 |
| 18 October 2018 | Change to Practical Assessment | 1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Written Questions	5

Part 1 – Project Scope	5

Part 2 – Project Time	17

Part 3 – Project Cost	26

Part 4 – Project Quality	30

Case Study	36

Instructions to Student	36

Introduction	37

Workbook Checklist	51

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 2 |  |  |
| --- | --- | --- | --- |
| TITLE: | Constraint Management |  |  |
| FIRST AND SURNAME: | BRYDON HOGARTH |  |  |
| PHONE: | 0432738800 |  |  |
| EMAIL: | Hogarthbrydon@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :brydon |  | Signature: b.hogarth | Date: 15/04/2020 |

# Written Questions

Part 1 – Project Scope

| - Which of the following are project initiation documentation required at the start of the project? Select all that apply. |  |
| --- | --- |
|  | - Communications log |
|  | - Project plan |
|  | - Work Breakdown Structure (WBS) |
|  | - Gantt Chart |
|  | - Project charter |
|  | - Risk management |

| - Which of the following are components of a project scope-management plan? Select all that apply. |  |
| --- | --- |
|  | - Project deliverables |
|  | - Project staff assignments |
|  | - Change request |
|  | - Project justification |
|  | - Product description |
|  | - Performance reports |
|  | - Project objectives |
|  | - Project funding requirements |
|  | - Quality metrics |
|  | - Budget forecasts |

- In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

If a project is estimated correctly the cost and time can be calculated using the scope. If there is a change to the scope, eg, adding more work it will take more time and cost more.

| - Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request? Select all that apply. |  |
| --- | --- |
|  | - The deliverables may not meet quality requirements. |
|  | - Grammatical and typo errors are found in the project initiation documents. |
|  | - The deliverables may not be what the client wanted, even though they were covered in the project plan. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - Observance of non-working holidays affecting project time. |
|  | - Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant. |
|  | - Failure of equipment needed to produce the deliverables. |
|  | - Missing documentations in the project’s information system. |
|  | - Raw materials are no longer available. |
|  | - Supplier or contractor closing business. |

| - Which of the following are procedures that typically must be followed under change control processes? Select all that apply. |  |
| --- | --- |
|  | - Project manager seeks advice from supervisor regarding changes in cost. |
|  | - Project manager assigns a project team member to recalculate for the critical path. |
|  | - Project manager provides the change request to the appropriate stakeholder for approval. |
|  | - The stakeholder considers the change request and advises the project manager. |
|  | - The project manager updates the project plan and other documentation where required. |
|  | - Project manager drafts the change request. |
|  | - Project manager delegates the authority to the project team members in advising other stakeholders of the changes. |
|  | - The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes. |
|  | - Details of the proposed change to be communicated to the project manager. |
|  | - The project sponsor and owner may automatically terminate the project contract. |

| - The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Method | Description |
| C | Units completed | - Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion. |
| A | Incremental milestones | - In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements. |
| D | Start / finish | - This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled. |
| B | Weighted or equivalent units | - This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed. |

| - Which of the following are activities involved in decomposition of the total work project? Select all that apply. |  |
| --- | --- |
|  | - Summarise project tasks in the form of a written report. |
|  | - Identify and analyse the deliverables and related work. |
|  | - Structure and organise the work breakdown structure (WBS). |
|  | - Arrange the smallest project tasks to form an aggregate representation of the total project task |
|  | - Decompose the upper work breakdown structure (WBS) levels into lower level detailed components. |
|  | - Calculate duration and resource effort for each project task. |
|  | - Develop and assign identification codes to the WBS components. |
|  | - Inspect whether work and deliverables meet requirements and product acceptance criteria. |
|  | - List resources required for each project task. |
|  | - Verify that the degree of decomposition of the work is necessary and sufficient. |

- List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

- Using Phases of a project life cycle - Using major deliverables - Using subprojects

| - The following are some problem areas in scope management. In your own words, briefly discuss each problem area. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Problem areas | Discussion |
| Scope creep | Scope creep is when small changes to a scope go unnoticed until they become a bigger problem. |
| Sponsor / project owner approval | Where the PM seeks approval to proceed with the project |
| Project team accountability | The you are working with is responsible for the assigned tasks. |

- In your own words, discuss the significance of scope management. Do not exceed 150 words.

Scope management defines what you and your team are there to do and what the client expects you to do. Just as important it also defines what you are not expected to do. It helps avoid problems that a project faces with a growing scope. Without defining the scope at the start the time and cost of the project cannot be predicted.

| - The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process. |  |
| --- | --- |
| Project Scope Management | Tool or technique |
| Collect requirements | interviews |
| Define scope | Expect judgement |
| Create WBS | Decomposition |
| Verify scope | Inspection |
| Control scope | Variance analysis |

| - Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles. |  |
| --- | --- |
| Roles (list five (5)) | Responsibilities (List at least one (1) for each role) |
| Understanding the project | The pm recognises, why the project has started, the stakeholders expectations and the deliverables of the project |
| Scope management | The pm has turned the stakeholders requirements and turned them into work packages |
| Time management | Scheduling the project and coming up with a timeline to follow |
| Cost management | The PM is to come up with the overall cost baseline of the project |
| Quality management | The PM must define what good quality means in the project for the stakeholders |

Part 2 – Project Time

| - The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| B | Analogous estimating | - This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration. |
| A | Parametric estimating | - This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project. |
| E | Three-point estimating | - This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them. |
| C | Expert judgement estimating | - Contingencies are accounted for into the overall project schedule to account for schedule uncertainties. |
| D | Reserve analysis | - This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:Te=To +4 x Tm + Tp6 . |

| - The following are estimation tools techniques used in determining activity resource. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| D | Expert judgment | - Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries. |
| E | Alternative analysis | - In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources. |
| A | Published estimating data | - This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates. |
| B | Bottom-Up estimating | - This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise. |
| C | Project management software | - These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource. |

| - In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Parameter | Discussion |
| ES | The earliest time a task can start, given the any prior tasks must be firstly completed. |
| EF | The earliest start time plus the time required to complete the task. |
| LF | Latest time the task can be completed without delaying the project. |
| LS | Latest finish time for the task minus the time taken to complete the task. |

| - Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline? Select all that apply. |  |
| --- | --- |
|  | - Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule. |
|  | - The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases. |
|  | - Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline. |
|  | - Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work. |
|  | - Developing the schedule baseline starts and ends in the planning phase of the project. |

| - Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. Which of the following are processes that are involved in schedule control? Select all that apply. |  |
| --- | --- |
|  | - Determining the current status of the project schedule. |
|  | - Defining activities or specific actions to be performed to produce project deliverables |
|  | - Influencing the factors that create schedule changes |
|  | - Decomposing total project work into its lowest levels. |
|  | - Determining that the project schedule has changed |
|  | - Estimating duration and resource effort for the project. |
|  | - Managing the actual changes as they occur. |

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words. - List three (3) project data generated from the Gantt Chart. - List three (2) limitations of the Gantt Chart.

- A Gantt chart is used to graphically display projects activities, scheduling and sequence tasks are required to be completed in. - Length of time required finishing a project. Resources needed to complete tasks. Order of tasks and completion requirements of tasks. - The area of a Gantt chart is large and difficult to print The progress of a task is subjective and can be manipulated to make the chart look better.

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words. - List three (3) project data generated from the Critical Path Method. - Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

- Review all the activities to be completed and deciding the best way to complete them in the shortest amount of time - Parameters of each task Activities on the critical path Critical elements of the project - The critical path method can be altered by changing timeframes as previously none affected tasks or fragments can become additions to the critical path when schedules shift.

| - The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Project scheduling tools and techniques | Description |
| B | Schedule network analysis | - This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. |
| A | Critical Path Analysis | - This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts |
| D | Schedule compression | - They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations. |
| C | Automated scheduling tools | - This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. |

| - Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules? Select all that apply. |  |
| --- | --- |
|  | - Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components. |
|  | - The work breakdown structure (WBS) identifies project personnel who are responsible for each project task. |
|  | - Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work. |
|  | - The work breakdown structure (WBS) is used to represent the full project scope of the project. |
|  | - The work breakdown structure provides the relationships among all components of the project and the project deliverables. |
|  | - The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables. |
|  | - Project work at lowest levels are not included in the work breakdown structure (WBS) |

Part 3 – Project Cost

| - The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Estimating costs | The process of developing an approximate dollar value needed to complete the project to the scope. |
| Determine budget | Combining the estimated costs of all work packages and activities. |
| Control cost | Managing the budget, development and changes of the project, as well as recording up to date actual expenditure. |

| - The following are different tools and techniques used in cost management. Match each to its correct description. Write the letters that correspond in the spaces provided. |  |  |
| --- | --- | --- |
|  | Strategy | Description |
| B | Analogous estimating | - This is used to establish both the contingency reserves and the management reserves for the project with regards to cost. |
| C | Parametric estimating | - This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters. |
| E | Cost aggregation | - This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project. |
| A | Reserve analysis | - These are used to develop mathematical models to predict total project costs. |
| D | Historical relationships | - Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project. |
| G | Earned value management | - In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline. |
| F | Variance analysis | - This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. |

- List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

- Paying invoices promptly - Sending invoices on a regular basis - Checking incoming invoices against contract, quotes and agreements. - Use of an effective tool for managing project finances

- You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123). - In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. - In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope. - In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures. Do not exceed 100 words for each discussion.

- The policy has been designed for a large company with multiple project managers and accommodates the needs of those across the entire bigger and big corporation. Outlining basic responsibilities to be ensuring accurate project management that represents the company. - The scope refers to defining a body of work with a distinct start and end.. The purpose of the project management procedures is to ensure efficient management by defining the steps preformed throughout the lifecycle of a project. - The Bigger than Big Project management procedures have a detailed breakdown of the five phases. Pre initiate, Initiate, Plan, Implement, Close.

Part 4 – Project Quality

| - In your own words, discuss each of the following key concepts in Quality Management. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Key Concepts in Quality Management | Discussion |
| Customer satisfaction | Managing the expectations of the customer is extremely important, for the reputation of the company and hoping to continue working with them in the future |
| Prevention over inspection | Rectifying defects or faults during the project can save time but not having to look at them after. |
| Continuous improvement | Ongoing upgrades to products, time management and servicing during a project or projects is essential |

- In your own words, discuss the difference between Quality Assurance and Quality Control. Do not exceed 100 words.

Quality assurance is the development of process and techniques to prevent defects during the course of the project and quality control is the testing of products to uncover defects during the final stages of the project.

| - The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| People standards | Requirements of people working on the projects including qualifications and experience. |
| Process standards | The standards of the processes to be used in delivering the project including quality assurance. |
| Product / service standards | The standard of the end result product which involves quality control. |

| - The following are quality assurance and control methods, techniques and tools. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Methods, tools, techniques | Description |
| H | Benchmarking standards | - This is a distribution of dots comparing two variables. If the two variables are completely independent you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it. |
| G | Brainstorming sessions | - These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis. |
| D | Control charts | - It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes. |
| F | Flowcharts | - These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors. |
| B | Histograms | - It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results. |
| E | Pareto charts | - A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions. |
| C | Run charts | - It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions. |
| A | Scatter grams | - These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies. |

- List five (5) responsibilities of the project manager in quality management.

- Conducting or co ordinating project audits. - Leading or co ordinating project QA and QC activities. - Determining the quality standards for project deliverables - Determining the quality standards for projects process - Documenting all the required standards in the project plan

| - The following are methods used in managing continuous improvement. In your own words, discuss each method. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Six Sigma | Techniques used for improvement by identifying defects and removing them |
| Lean Six Sigma | Combing lean manufacturing/enterprise and six sigma to get rid of the eight kinds of waste – time, inventory, motion, waiting, overproduction, over processing, defects and skills |
| Total Quality Management | Using feedback and refinement to continually improve the quality of the project |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You have already provided advice to Awesome Landscapes in the previous workbook. Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off. As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario. The documents you need to complete the succeeding tasks can be accessed through the following links: Project Charter version 2 (.pdf) Project Plan version 2 (.pdf) Project Gantt Chart version 2 (.mpp) Project Gantt Chart version 2 (.pdf) Project Network Diagram version 2 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- List the three (3) project deliverables in Phase 1.

- Removal of vegetation in areas being cleared and replanting/maintaining the plants for replanting in stage 3 - Access roads through the existing forest for builders to access each building site - Retaining walls to provide stability around the buildings includes three additional walls.

| - Discuss the project constraints in terms of scope, time, cost, and quality. |  |
| --- | --- |
| Scope | The project is broken into 3 stages, - Stage 1 – Prebuilding. - Stage 2 – Building support - Stage 3 – Planting and Landscaping |
| Time | Completion of all work with in nine months |
| Cost | Fixed budget of $550,000 plus GST |
| Quality | All work must meet council requirements and environmental standards |

| - Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. Write 1 – 12 in the spaces provided; where 1 go first and 12 go last. |  |
| --- | --- |
| 8 | Remove weeds |
| 11 | Plant additional plants |
| 2 | Move gravel to car park |
| 1 | Expand car park |
| 12 | Remove greenhouses |
| 9 | Plant plants from greenhouses |
| 3 | Seal car park |
| 6 | Soil preparation |
| 7 | Add boulders |
| 5 | Construct stone paving pathway |
| 10 | Purchase additional plants |
| 4 | Landscape over old access roads |

- Review the Project Plan. The change request has outlined one change in the scope of the project. - What is the change in scope? - How does this change in scope impact the overall duration of the project? - How does this change in scope impact the quality aspect of the project?

- Add 3 retaining walls - The project starts earlier and has been brough forward from 3rd of august to 27th of July - Bringing the project forward shouldn’t affect the quality or impact on any other works

- Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request? Do not exceed 100 words.

The change has a lot of flow on effects in stage 1 as highlighted in the detailed costing per task table of the project plan. This shows that not just the extra physical work itself must be calculated but also from a management side of things the cost and time will increase. This gives a far more accurate depiction of what the overall out of pocket cost will be for the company

- Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

The project management team

- Access and review the Gantt Chart version 2. - What important tasks are not included in the project Gantt Chart? - Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

- The second part of change request 1, services to additional units as per updated site plan - If even one task is missing from the Gantt chart can cause a flow on effect onto the next tasks. Delaying the project as a hole and interrupting work flow.

- List the three (3) personnel who signed off on the change request.

- Susan Wills - Stephen Lyons - Kim Nguyen

- What is the total increase in cost of the project as a result of this change request?

$17,900

- List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

- Onsite security - Any building, decorating or furnishing of the chalets - Installation of pipes and tanks - Weather damage - Installation of utilities

- Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. Do not exceed 50 words.

NO, The addition of the three retraining walls is done correctly but the adding of additional services is in the budget but is missing from the gantt chart and hasn’t been listed as one of the tasks .

- Access and review the Gantt Chart version 2. It shows double bars for each task. - What do the coloured bars represent? - What do the grey bars represent? - Why do the grey and coloured bards do not match up in the Gantt chart?

- The blue lines are the actual and current program - The project program that was established at the beginning of the project - They are different due to the additional works and subsequent delays

- Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. Do not include the task ‘Project Management’.

- Moving plants to glass house and dispose - Delivery of granite bolders

- If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely: - Construction of retaining walls. - Install and compact soil behind walls. According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

The install and compact soil will be completed on the 15th of September so same will not witness that activity. But works and compacting the soil could start on the finished section of the retaining wall so the two tasks could happen at the same time.

- According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’, - Which tasks, if any, are immediately delayed? - Will this delay push out the completion of the project? Why or why not? - Discuss how this could affect the resourcing of the project. - List one (1) risk that could arise from this issue.

- 59, Erect signage - yes, each delay in the previous task would push back the next. Until the end of the project was delayed. - At this stage, delivery dates may have been scheduled so you may have the boulders in 63 arriving before they are needed, unless plans are made to reschedule adding cost to the management time. - Compressing the time line will add pressure to the workers also if the gear arrives earlier than needed it might also add double handling where it could be avoided

- What is the total budget for the project expenditure?

$462 153.00

- Sam is very concerned about the cash flow of the project. - What is the problem? - What would you suggest be done to rectify the cash flow issue?

- Awesome landscapes has enough reserve cash of $224,724. And the total cost of the first stage with the changes is $247,768. Leaving awesome landscapes unable to complete the first phase. Which means they will not collect there first payment. - If more intervals of payment where added e.g., a payment for completion of certain work sin the middle of a phase. Not just a large payment at the end of the phase. The cash flow would be steadier.

- Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-development Corporation to absorb some or all of these cost increases. Your discussion must be 200 – 300 words in length. Guidance: The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

Awesome Landscapes should definitely seek and increase in funding as they are estimated to be out of pocket $$17,900 because of there changes which has effect cash flow for the company. A minimum of this figure should be given to the relevant stakeholders at Massive Eco-development Corporation for their approval before the works commence. Massive Eco-development Corporation might pull out of the changes not realising the cost involved. However If the cost is disclosed before hand and is agreed apron by the stakeholder’s prior then the invoice apron completion of the additional works should be paid without any surprises to the stakeholder. Awesome landscapes should not be expected to wear the cost of a change wanted by the client.

- Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project. Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Brydon hogarth |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: | Overall Project Status: |  |  |  |  |  |  |  |
| Audit Date: | Audit Number: 01 |  | Audit Leader: |  |  |  |  |  |
| Audit Team: Brydon Hogarth |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: Are workplace health and safety standards being met |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Is all the required PPE being wore on site? |  | Assessment: | Comment: |  |  |  |  |  |
| 2. Are deliveries being unloaded in a safe manner? |  | Assessment: | Comment: |  |  |  |  |  |
| 3. Are proper road management techniques being used? E.g. Barrier and trained traffic control |  | Assessment: | Comment: |  |  |  |  |  |
| 4. Are the chemicals on site being stored correctly? |  | Assessment: | Comment: |  |  |  |  |  |
| 5. Are proper exclusion zones being established? |  | Assessment: | Comment: |  |  |  |  |  |
| 6. Are the correct distances being maintained around excavation equipment? |  | Assessment: | Comment: |  |  |  |  |  |
| 7. Is all the equipment in the correct service date? |  | Assessment: | Comment: |  |  |  |  |  |
| 8. Is waste being disposed of correctly ? |  | Assessment: | Comment: |  |  |  |  |  |
| 9. Is there adequate signage in place ? |  | Assessment: | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes |  | no |  |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |
| Audit Report Submitted To: |  |  |  | Date: |  |  |  |  |

- Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions: - What was the cause of the unsatisfactory results? - What action would you recommend to prevent the issue coming up again in this project?

- Communication - Scheduling a meeting with the project team and assuring information is being passed on to all relevant people

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng |  |  |  |  |  |  |  |  |
| Date: 17 August 2015 |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: Implementation | Overall Project Status: On schedule |  |  |  |  |  |  |  |
| Audit Date: 17 August 2011 | Audit Number: 26 |  | Audit Leader: Sam Ng |  |  |  |  |  |
| Audit Team: Sam Ng, John Cowley, Ann Deak. |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the communication and reporting processes. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are tasks being communicated to site supervisor in a reasonable amount of time? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| 2. Are tasks being communicated to site supervisor of sufficient detail? |  | Assessment: Not satisfactory. | Comment: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. |  |  |  |  |  |
| 3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time? |  | Assessment: Not satisfactory. | Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. |  |  |  |  |  |
| 4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. Project manager to prepare task briefs in enough time to add the required level of detail. 2. Task briefs are to be supplied with all relevant attachments such as detailed plans. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes | x | no |  |
| Audit Report Submitted To: Kim Nguyen |  |  |  | Date: 24/08/2015 |  |  |  |  |

- The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. Guidance: Your Cost Management Plan must cover the following quality objectives and criteria. - Meeting with contractual requirements. - Paying invoices on time. - Ensure invoices are sent out in time. - Ensuring financial reporting is done on time. - Include a calendar of when payments are likely to be due. - Comparison of actual cash flow against projected cash flow.

Cost management plan A surplus of cash at the start for contingency is important. And designating what and when the money is going to be used for the $224,724 will be essential with meeting the contractual requirements in phase 1 and paying the invoices that will be due during this phase, before receiving the first and largest payment from massive eco-development corporation. It is critical that all the contractual requirements are met during the job so that payments have no reason to be delayed. By referring to the Gantt chart along the course of the project all the invoices for subcontractors, materials the awesome landscapes are expected to pay can organize onto a calendar and money can be set-aside for them. By referring to this calendar we can make sure invoices can be set out on time. Constantly auditing done by the project manager during the project will make sure that all the necessary financial reporting and the actual cash flow is comparing to what was projected in the project plan.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Part 1 – Project Scope Part 2 – Project Time Part 3 – Project Cost Part 4 – Project Quality Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document