| Construction Scope of Work: | Concrete footpath entering the BESS fence area adjacent to main entrance sliding gate |  |
| --- | --- | --- |
| Proposed Date of Works: | Friday 26th and Saturday 27th September 2025 |  |
| Scope | Friday 26th – Site Establishment, excavation and formwork Saturday 27th – Concrete pour, smooth and level and demobilise site |  |
| Job Durations: | 2 days |  |
| Location: | 305 Swanbank Road Swanbank 4306 QLD |  |
| Area: | North-West corner of the fenced BESS Area |  |
| Contractor Support | DM Coastal undertaking the scope of works. New worker to contact Project HSE Specialist to complete the site induction. Attend Prestart Meeting at 06:30 am. |  |
| Personnel: | - Contractor Supervisor - Contractor Excavator Operator - Contractor Carpenter (x2) - Contractor Concreter (x2) - Concrete Delivery Driver - Contractor Concrete Tester |  |
| Plant & Machinery: | Excavator. Concrete Truck. Tipper Truck and Trailer. Rammer Compactor. |  |
| Construction materials | Suppliers – Boral (DMG) or Hy-tec Concrete Boral (DMG). Wet concrete approximate total volume is 6 cubic metres. Approximate Delivery time 07:00am. Reinforced Steel mesh. |  |
| Concrete Area | 13m (length) x 3m (width) x 0.15m (Thickness) |  |
| Hazardous Chemical | Wet mix concrete SDS Concrete Form Release Agent SDS |  |
| Waste Disposal | Wash Bay 01 - Concrete wastage or wash down |  |
| Applicable HSE Documentations | Safety Management Plan Construction Environmental Management Plan Vehicle Movement Plan SWMS Conduit Installation In Ground SWMS Excavator Operation SWMS Concreting SWMS Excavation Excavation Permit Hazchat |  |
| Design Drawing | SBK-DRW-2025-008 |  |
| Performance Task Monitoring | SWMS Observation YUR1020 Inspection and Test Plan |  |
| Job Planning completed by |  |  |
| NAME: Sooty Phomsouvanh |  | Date: 19/09/2025 |