BSBPMG407A

Apply risk management techniques

ASSESSMENT SUMMARY

The assessment activities for BSBPMG407A Apply risk management techniques cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Jonathan Van Der Merwe |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

BSBPMG407A

Apply risk management techniques

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Jonathan Van Der Merwe |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 16 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Describe a project below. Conduct a SWOT analysis for the project. Identify at least two (2) points per area.

| Project description | Project description Supply of Earthmoving Plant (WET HIRE): Excavator, Front end Loader, risk assessment to be provided for each piece of plant. |
| --- | --- |

| Answer | Area | Detail |  |
| --- | --- | --- | --- |
|  | S | The project will see the upgrading of all Rail platforms throughout the city CBD, increasing the size, capacity and innovation, Project is scheduled to run for 24 months. |  |
|  | W | Projects is subject to high risk working conditions. This has the potential for delays due to safety requirements, which could impact schedule and budget. |  |
|  | O | Project requires high level of skilled work force. Screening of all workers/contractors/equipment is essential and crucial. Safety around high risk assets, and public requires competencies of all personal prior to commencement. Strong need to attract the best operators/personal. |  |
|  | T | Safety around public and all electrical assets, as this is a live high risk environment. Any incidents in this environment could result in serious delays in schedule, resulting in budget blowout. |  |

Consider the project you identified in Q1. For each of the areas identified in the table below, identify one (1) risk that may arise.

| Answer | Area | Project risk |  |
| --- | --- | --- | --- |
|  | Environmental | Live environment with rail passengers in transit, multiple trade workers/operators on site, high risk electrical environment and rail movement, as well as large plant movement pose a constant risk. |  |
|  | Finance | Any delays due to accident or incident could delay the schedule and effect budget. |  |
|  | Human resources | As project runs 24/7, fatigue management is very high risk. Scheduling will need to be strict, operators/workers not permitted to work outside recommended hours per shift. There must be sufficient breaks taken and adhered to. Work injury/accidents/incidents will affect scheduling and budget. |  |
|  | Legal | Failure to adhere to strict OH&S protocols/safety could result in fines/stop work notices. These affect both scheduling and budget. |  |
|  | Technology | Any incidents/accidents involving live electrical assets could result in shut down of rail corridor. All plant operators/workers working within the high risk area need to be fully trained and up to date with all safety equipment and protocols. These are extended to plant technology requirements such as height limiters/emergency stops to avoid contact with live electrical assets, contact with the public in live traffic areas. |  |

Using ticks, identify whether each of the risk analysis methods listed below is either ‘qualitative’ or ‘quantitative’.

| Answer | Qualitative | Quantitative | Method |  |
| --- | --- | --- | --- | --- |
|  |  |  | Analyses expected monetary value |  |
|  |  |  | Considers likelihood of occurrence and impact on projective objectives |  |
|  |  |  | Ranks risks |  |

Refer to the Risk Matrix below when responding to Q4.

| Matrix | A: Catastrophic | B: Major | C: Moderate | D: Minor | E: Insignificant |
| --- | --- | --- | --- | --- | --- |
| 1: Almost certain | E | E | H | H | M |
| 2: Likely | E | H | H | M | M |
| 3: Occasionally | H | H | M | M | L |
| 4: Unlikely | H | M | M | L | L |
| 5: Rare | M | M | L | L | L |

| E: Extreme | H: High | M: Medium | L: Low |
| --- | --- | --- | --- |

Referring to your responses in Q2. rate each of the risks you identified using the Risk Matrix shown above. Identify the Likelihood and Impact you have determined, plus the overall risk rating. 

Prioritise each risk from 1 to 5 (1 = highest priority, 5 = lowest priority).

| Answer | Area | Risk rating | Priority |  |
| --- | --- | --- | --- | --- |
|  | Environmental | Likelihood: Likely Impact: Catastrophic Risk rating: Extreme | 1 |  |
|  | Finance | Likelihood: Likely Impact: Major Risk rating: High | 2 |  |
|  | Human resources | Likelihood: Likely Impact: Catastrophic Risk rating: Extreme | 1 |  |
|  | Legal | Likelihood: Likely Impact: Major Risk rating: High | 2 |  |
|  | Technology | Likelihood: Likely Impact: Major Risk rating: High | 1 |  |

Order the elements of the hierarchy of control, from 1 to 6 (i.e. most effective to least effective).

| Answer | Label (1 – 6) | Element |  |
| --- | --- | --- | --- |
|  | 3 | Isolate the hazard |  |
|  | 6 | Provide and use Personal Protective Equipment (PPE) |  |
|  | 1 | Eliminate the hazard |  |
|  | 4 | Control the hazard by engineering means |  |
|  | 5 | Control the hazard by administrative means |  |
|  | 2 | Substitute the hazard |  |

Referring to your responses in Q2. propose one (1) risk control for the risk identified in each of the areas listed below.

| Answer | Area | Risk control |  |
| --- | --- | --- | --- |
|  | Environmental | Eliminate the hazard. Separate the work area from the public movement (redesign the space), conduct critical works after hours. |  |
|  | Finance | Control the hazard by engineering means. Have plans/procedures in place prior to commencement to anticipate possible delays/setbacks, have a contingency |  |
|  | Human resources | Eliminate the hazard. Dedicate a Safety Officer to monitor potential high-risk areas/fatigue management and all potential hazards. |  |
|  | Legal | Eliminate the hazard. High level of supervision/spotters by project Managers and Safety Officer, ensuring safety and operational requirements are being met, maintained by all site personal. Maintaining safety and operational protocols. |  |
|  | Technology | Isolate the hazard. Separate all high risk areas of work site with barricades. Use of height limiter technology and reverse squarers and cameras, ensuring no contact with live electrical assets, public, workers, and rail assets. |  |

Which of the following parties should be consulted and agree to proposed risk managed strategies, plans and reporting mechanisms? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Project manager |  |
|  |  | Project specialist |  |
|  |  | Team members |  |

True or False (Tick your response): Organisations all use the same risk analysis methods, techniques and tools.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify the four (4) options that may be followed once you have established the revised risk level.

| Answer | - Do nothing - Implement risk controls - Reassess the risk - Accept the risk |  |
| --- | --- | --- |

What is the name of the risk level measured after risk controls have been implemented? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Initial risk |  |
|  |  | Revised risk |  |
|  |  | Residual risk |  |
|  |  | Updated risk |  |

On what document should incidents be recorded?

| Answer | Issues register |  |
| --- | --- | --- |

What is to be completed when a variation is to be made to the project?

| Answer | Risk reviews |  |
| --- | --- | --- |

True or False (Tick your response): You should report opportunities for action in the same way as risks.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify two (2) types of documents that may be referred to when conducting a review of a risk management plan.

| Answer | - Project Files and records - Risk diaries, incident logs, occurrence reports |  |
| --- | --- | --- |

Explain the relevance of evaluating project outcomes (e.g. agreed major milestones) as part of reviewing risk management activities.

| Answer | The project outcomes review will determine the effectiveness of the risk management activities. It will also provide information to improve risk assessments, learn lessons from events, changes, trends, successes, and failures. Assist in identifying emerging risks. |  |
| --- | --- | --- |

True or False (Tick your response): You may refer to past projects for lessons learned regarding risk management, even when the past projects are not identical to the current one.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

BSBPMG407A

Apply risk management techniques

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

BSBPMG407A

Apply risk management techniques

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to apply risk management techniques to complex projects– including, assisting with risk analysis, risk management planning and undertaking a review of risk management outcomes. A complex project is defined as a project which involves: - The need for a comprehensive and multi-faceted project plan - The need for a formal internal or external communications strategy - A dedicated and diverse project budget - Multiple administrative components - Multiple operational components - A wide range of stakeholders - A project operations team The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - SWMS review checklist completed by the Participant - Task JSA completed by the Participant - SWMS signed by the Participant - Design risk assessment completed by the Participant The observer is to outline the details of each project observed in the ‘Observer comments’ section. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment. |  |  |  |
| Resources required: Project records. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Contribute to identifying and prioritising potential risks throughout the project life cycle. |  |  |  |
| - Within delegated authority, provide input to develop risk management strategies and risk management plans within established guidelines. |  |  |  |
| - Establish risk analysis methods, techniques and tools to assist in the analysis of risks. |  |  |  |
| - Ensure reporting mechanisms for risks were planned for and agreed to. |  |  |  |
| - Undertake control activities in accordance with agreed project and risk management plans to achieve project objectives. |  |  |  |
| - Measure progress and act on perceived, potential or actual risks within authority – or report to others for response. |  |  |  |
| - Contribute to the implementation of agreed risk approaches and the amendment of plans to reflect the changing environment. |  |  |  |
| - Identify and report opportunities for action in the same way as risks. |  |  |  |
| - Contribute to the ongoing review of project outcomes to determine the effectiveness of risk management activities, accessing project records and other available information. |  |  |  |
| - Report risk management issues and responses to others for lessons learned or application in future projects. |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments