## Comparison
[5 empty] | Print Date: | 2022-08-09 12:51 |  |  |  |  | Project: | PB2T
SEYMOUR WHYTE CONSTRUCTIONS PTY LTD | [10 empty] | Work Package: | Girders | 1 | of | 1
PROVIDER ANALYSIS SHEET | [10 empty] | Date Required On Site: | End of August
EQUALISATION
|  |  | Bidder: | SWC Budget |  |  | Supplier A |  |  | Supplier B |  |  | Supplier C
SMS Rating:
|  |  | Quotation Reference No: | . |  |  | N/A |  |  | N/A |  |  | N/A
|  |  | Date of Quotation: | . |  |  | 2021-05-21 |  |  | 2021-05-24 |  |  | NA
Item | Description | QTY | Unit | Rate | Value | Comments | Rate | Value | Comments | Rate | Value | Comments | Rate | Value | Comments
| BR01 - Fibre cement sheeting | 264 |  | 300 | 79200
| BR02 - Fibre cement sheeting | 360 |  | 300 | 108000
| 0.835x1.2 | 342 | Ea |  |  |  | 40 | 13680
| 0.835x0.9 | 372 | Ea |  |  |  | 60 | 22320
| 0.835x0.845 | 171 | Ea |  |  |  | 40 | 6840
| 0.835x0.745 | 15 | Ea |  |  |  | 60 | 900
| FC SHEET 2400 X 1200 X 24MM | 355 | Ea | [6 empty] | 190 | 67450
| Delivery Fee | 1 | Ea |  |  |  | 500 | 500 |  |  | 0 |  |  | 0
| Additional 18mm sheets cut to size for deck section greater than 400mm thick | 1 | Ea |  |  |  | 5000 | 5000 |  | 5000 | 5000
|  |  | EQUALISED TOTAL |  | 187200 |  |  | 49240 |  |  | 72450 |  |  | 0
|  |  | SUBCONTRACT-SUPPLIER TOTAL |  | -187200 |  |  | 49240 |  |  | 72450 |  |  | 0
Trade Checks
Bid Recommendation |  |  |  | Cutting to Size |  |  | Included |  |  | Not included in Rates
Recommendation is to award the package to Suppler A for supply of FC sheeting. They are the cheapest rate and have good past experience dealing with FC sheeting for Girder tubs specifically with girders supplier quickcell. All other suppliers who quotes were requested from had not previously supplied for use with girders. |  |  |  | Deliviery |  |  | Included |  |  | Not included in Rates
|  |  |  | Inclusions / Exclusions | [5 empty] | Material would require cutting onsite (Additional Cost) |  |  | Would not supply direct