## Demolition Checklist
4010 Practical Activity 1
Demolition Checklist
YES NO N/A | STEPS | COMMENTS/ADDITIONAL INFO
Permits & Paperwork
Hold a current demolition license
Pay any relevant fees required to hold your license
Complete any documents your council requires
Create a site plan
Create a safety plan if the demolition is occurring in a public space or adjacent to other buildings
Acquire the necessary permit for the job
Services to be disconnected & checked
Electrical
Gas
Sewer
Water pipes
Any other live wires
Telecomms
Site Preparation
Have appropriate safety equipment in place
Have all workers wearing appropriate safety gear
Check all heavy machinery for defects, leaks etc.
Determine if you will be dealing with hazardous materials (e.g. asbestos) and have a safety plan in place for this
Determine the method of demolition
- Manual demolition
- Mechanical demolition
Brief all workers on this method
- Demolition of roofs
- Roof access
- Demolition of walls
- Demolition of floors & members
- Demolition of framework
- Working on suspended floors
- Masonary & brick arches
Have all workers demonstrate their knowledge of the process
Before work begins, determine where and how the waste and debris will be disposed of
Create a transport method and disposal space for hazardous materials
Inform any neighbours or nearby tenants of the demolition work before the day of
Manage any risks and hazards before demolition work begins
- Working from height
- Fire prevention
- Powered mobile plant
- Exclusion zoes & public access protection
Have workers trained in first aid
Have workers know the route to the nearest hospital should an emergency arise
Have an emergency plan in place
Assign tasks to the appropriate engineers and workers
Conduct a pre-demolition walkthrough before work begins

## Concrete Inspection Checklist
4010 Practical Activity 2
Concrete Inspection Checklist - Reinforced Raft (per NCC Vol 2 Part 3.25)
YES NO N/A | STEPS | COMMENTS/ADDITIONAL INFO
| Pre-Placement Checklist | refer NCC Vol 2 Part 3.25 Table 3.2.5.4a & Figure 3.2.5.3a
Centre line as per drawing
Formwork & Staging as per drawing & in plum
Construction joint location as per drawing
Steel reinforcement diameter / spacing & coating as per drawing
Cover to the reinforcement and overlap as per drawing
Shuttering aligned & in plumb
RLs and reference levels as per drawing
Embedment part check, i.e. insert plates, nipple etc as per drawing
Placement of water stoppers, if any
Location of construction joint
Water tightness of shuttering, if required
Quality of water - potaable & clean
Quality of materials - as per specification
Slab depth - 300mm
Bottom reinforment 3-L11TM
Slab fabric SL92
Internal and external edge beams must be arranged to form an integral structural grid
Where external beams are wider than 300 mm, an extra bottom bar or equivalent of the same bar size is required for each 100 mm additional width.
Alternative reinforcement sizes must comply with AS 2870
Internal beam details and spacings must comply with Figure 3.2.5.3a. At a re-entrant corner where an external beam continues as an internal beam, the internal beam details must be continued for a length of 1 m into the external beam.
A 10% increase in spacings is permitted where the spacing in the other direction is 20% less than that specified
| Inspection During Placement | refer NCC Vol 2 Part 3.25 Table 3.2.5.4a
Water cement ratio as per specification
Surface preparation by mortar bedding - fresh mortar
Slump testing - as required
Adequacy of vibration
Segregation of aggregates not allowed
Removal of temporary spacers & ties - to be removed
Check for shuttering prop displacement
Continuity of operations
Post Placement Inspection
Observation for honeycombing - not allowed
Line & Level as per drawing
Surface Finish as per drawing
Cracks and air bubbles - not allowed
Method of curing as specified
Checked for stripping/removal of formwork supports after specified duration
Checked for position of embedment
Repair and finish all surface defects
Surface of part of structure is ok and allowed for subsequent activity/backfilling
Other, if any
|  |  | Centre line | As per drawing
|  | 2 | Formwork & Staging | As per drawing & in exact plum
|  | 3 | Construction joint location* | As per drawing
|  | 4 | Steel reinforcement diameter / spacing & coating* | As per drawing
|  | 5 | Cover to the reinforcement and overlap* | As per drawing
|  | 6 | Shuttering | Aligned as per drawing and in plumb
|  | 7 | RLs and reference levels | As per drawing
|  | 8 | Embedment part check, i.e. insert plates, nipple etc | As per drawing
|  | 9 | Placement of water stoppers, if any*
|  | 10 | Location of construction joint
|  | 11 | Water tightness of shuttering, if required | No water seepage allowed
|  | 12 | Quality of water | Potable and clean
|  | 13 | Measuring jar for water pouring | As per water content requirement
|  | 14 | Quality of materials | As per specification