## ALL
RESIDENTIAL SUBMISSION PLAN
Task Name | Date for Submission | Forms, information and supporting evidence to be submitted | Fees and charges
Engagement Notice of Building Certifier | 2024-06-13 | This is done by the Building Certifier • Form 56 - Notice to the local government that a private certifier has been engaged | Nil
Qleave | 2024-06-24 | • Online Levy Payment form • Project Finalisation form | 1150
Development / Building Approval | 2024-06-27 | This is done by the Building Certifier • DA Form 2 - Building work only • Owners consent • Architectural Plans • Structural Engineering Plans and form 15 design certificate • Hydrualic Engineering Plans and form 15 Design Certificate • Energy efficiency assessment report • Body Corporate approval | 1872
Archiving with GCCC | 2024-10-23 | This is done by the building certifier | New work BCA Approval (Classes 1-9) - $192.00