CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Paul Newton |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for CPCCBC4003A | Competent | Not Yet Competent |
| Outcome for CPCCBC4016A | Competent | Not Yet Competent |
| Outcome for CPCCBC4032A | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 51 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Order the following elements of an agreement from 1 to 4.

| Answer | Element Number | Element |  |
| --- | --- | --- | --- |
|  | 2 | Acceptance |  |
|  | 4 | Consideration |  |
|  | 3 | Intention of legal consequences |  |
|  | 1 | Offer |  |

When would an offer be considered to have lapsed?

| Answer | An offer will lapse when -the time for Acceptance expires If the offer is withdrawn before it is accepted After a reasonable time in the circumstances. |  |
| --- | --- | --- |

What happens to the offer if new terms are suggested?

| Answer | An Offer can be ‘counter offered’ where new terms are suggested, which can be accepted or regected. |  |
| --- | --- | --- |

What does it mean when a contract is supported by ‘valuable consideration’?

| Answer | Valuable consideration means- one party promises to do something in return for a promise from another party -Usually the consideration is the payment of money. |  |
| --- | --- | --- |

Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

| Answer | People suffering from mental disability , Intoxicated individuals .or senile people may be deemed to not have the capacity to enter into a contract |  |
| --- | --- | --- |

- Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

| Answer | Consent is implied in every agreement Consent is an act of reason and deliberation Apparent Consent may no exist in the case of Mistake, Fraud, undue influence, innocent misrepresentation all of which are defences to the enforcement of the contract. |  |
| --- | --- | --- |

Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

| Answer | Queensland Building and Construction Commision -QBCC |  |
| --- | --- | --- |

Under what laws are domestic building contracts regulated?

| Answer | Domestic Building contracts are regulated with Schedule 1B of the Queensland Building and Construction Commision Act 1991 (the ‘QBCC ACT’) This Legislation applies to Domestic building contracts entered into from Ist July 2015. |  |
| --- | --- | --- |

Domestic building contracts must be put in writing once the work exceeds what value?

| Answer | $ 3300 is the maximum total value of domestic building work before a contract is required. |  |
| --- | --- | --- |

A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

| Answer | The QBCC Act requires that commercial contracts for building work valued at more than $10000 must be in place prior to commencing any work. |  |
| --- | --- | --- |

Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

| Answer | Within 5 Days of entering into the contract |  |
| --- | --- | --- |

What are the benefits of having a written contract in place between parties?

| Answer | All the terms are in writing for both the protection of the Builder and the Client. Builders progress payments are stipulated on contract . Cost adjustments and extension of time maybe required in some cases and can be performed through a written contract |  |
| --- | --- | --- |

Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Clauses |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Acceptances | 1 - B | A | Provide specific reasons that allow the contract period to be adjusted |  |
|  | 2 | Cost adjustments | 2 - E | B | A provision for which remedies can be sought if breached |  |
|  | 3 | Extensions of time | 3 - A | C | Specifically outlines the tasks to be completed as part of the construction work |  |
|  | 4 | Payments | 4 - D | D | Outlines the requirements for deposits |  |
|  | 5 | Scope of work | 5 - C | E | Address the risk of rise/fall of expenses |  |
|  | 6 | Term | 6 - F | F | Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding |  |

Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Contract estimate |  |
|  |  | Contract request |  |
|  |  | Preliminary agreement |  |

True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

| Answer | Contract name | Description |  |
| --- | --- | --- | --- |
|  | Level 2 QBCC | Renos, extensions and repairs –For value $20000 and over |  |
|  | QBCC -New home construction contract | For the construction of an entire house |  |
|  | Master builders -Comercial Minor works contract | A lump sum contract for Minor Comercial work valued up to $100000 |  |
|  | Comercial cost plus(master Builders) | A cost plus contract for commercial projects where lump sum can not be determined. |  |

Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

| Answer | Master Builders -Commercial Minor Works Contract |  |
| --- | --- | --- |

Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

| Answer | QBCC- Level 1 -For Renovations, extensions and repairs valued $3300 up to $19999. |  |
| --- | --- | --- |

Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Builder’s Licence | You should only deal with QBCC licensed contractors. If not Licensed the work is not covered under the home warranty scheme. |  |
|  | Contract price | If the contract price is fixed it must show on the first page. If not fixed, the method for calculating it must be shown in the contract schedule. |  |
|  | Building approvals and inspections | Building inspections and approvals are the responsibility of the building certifier, who may be engaged by either the Builder or Client. |  |
|  | Practical completion and handover | PC or Practical completion is when the construction has been completed in accordance with the contract including any plans and specifications. |  |
|  | Implied warranties | Schedule 1B of the act sets out statutory warranties. Warranty period is 6 years for structural defects. 1 year for non-structural defects. |  |

- Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Engineer specifications |  |
|  |  | Plans, drawings and specifications |  |
|  |  | Prime Cost Items Schedule |  |
|  |  | Processes for applying for extensions of time |  |
|  |  | Product catalogues |  |
|  |  | Project timelines and schedules |  |
|  |  | Provisional Sums Schedule |  |
|  |  | Rise and fall calculations |  |
|  |  | Site conditions report |  |
|  |  | Soil and sedimentation report |  |

What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

| Answer | A Prime cost Schedule is a schedule of the ‘PC’ items—Pc items can be An amount allowed for in a contract sum to purchase specified items such as Tiles, tapware and bathroom fittings. A Provisional Sums schedule is a schedule of the ‘PS ‘---A Provisional Sum is generally An amount included in a contract sum to cover work and materials not detailed when entering a contract, such as -Excavation work , tree clearing and rock breaking. These things are unforeseen to to the hidden nature .If the provisional sum is exceeded , the difference is added to the contract sum. |  |
| --- | --- | --- |

Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

| Answer | Cost adjustments may apply to – -Labour and Materials -Costs such as-duties and taxes or shipping and transport. -Currency exchange rates for goods purchased oversees. |  |
| --- | --- | --- |

True or False (Tick your response): Variations can be requested by both the client and the builder.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

| Answer | Client Variations and /or subsequent time extensions due to Variations are to be in writing, i |  |
| --- | --- | --- |

Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

| Answer | Fair Trading act 1989 (QLD) This Act applies to the builder/ company . |  |
| --- | --- | --- |

Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

| Answer | Make reasonable inquiries about why you want to borrow the money. Make reasonable inquiries about your financial situation. Take reasonable steps to verify your financial situation. Assess whether you can meet the financial obligations of the credit contract (and whether it will meet your needs) Determine that the credit contract is ‘not unsuitable’ for you |  |
| --- | --- | --- |

What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

| Answer | Schedule 1B of the QBCC Act provides for a cooling off period, giving the consumer the option to withdraw from the contract within five days of receipt of the signed contract . |  |
| --- | --- | --- |

What are the maximum deposits recommended for a residential building project?

| Answer | Maximum 5% of contract sum- Total value of work over $20000 Maximum $10% of contract sum -Total between $3300 and under $20000. |  |
| --- | --- | --- |

Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

| Answer | 1 – Deposit – 5% 2 – Base stage—15% 3 – frame stage—20% 4 –enclosed stage –25% 5 – Fixing’s stage –20% 6 – practical completion Balance |  |
| --- | --- | --- |

- You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

| Answer | No , No more than 5% Deposit can be accepted . |  |
| --- | --- | --- |

- Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

| Answer | Breach | Explanation |  |
| --- | --- | --- | --- |
|  | Breach of condition under contract | Conditions: These are essential terms. If a condition is not fulfilled, the nature of the contract is drastically changed. |  |
|  | Breach of warranty under contract | Warranties (NB. This is not the same as a ‘guarantee’): If a warranty is not fulfilled, the nature of the contract is not drastically changed. |  |

What does repudiation of a contract mean?

| Answer | Repudiation occurs when a party to a contract is unwilling to perform their contractual obligations – through acknowledgement or their actions are totally inconsistent with their obligations under the contract. Where a party is unwilling to perform under the agreement (i.e. for reasons other than poor performance), this may be deemed a termination of ‘convenience’ Repudiation does not automatically bring a contract to an end. The injured party can elect to either continue with the contract or accept the repudiation and move to terminate the contract. However, the ‘injured’ party must act with caution – because if the situation is not deemed to be a repudiation, by acting the terminate the contract the ‘injured’ party may themselves be repudiating the contract and could be liable to pay damages. |  |
| --- | --- | --- |

True or False (Tick your response): In the event of repudiation, the injured party has two options:

- Continue with the contract

- Accept the repudiation and move to terminate the contract

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

| Answer | Caution must be taken because the contract will not be automatically terminated if Repudiation occurs. |  |
| --- | --- | --- |

What does ‘abandonment of contract’ mean?

| Answer | Abandonment of a contract is when both parties in a binding contract act in a way that makes the original contract no longer valid . Abandonment of a contract may occur when both parties breach a contract and violate their agreement terms. |  |
| --- | --- | --- |

A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

| Answer | Yes Termination for Cause A termination for cause can only take place if one party cannot completely fulfill their contractual duties. An example of this would be a contractor terminating their contract for cause because the owner failed to pay them in the time that was determined in the contract. However, an owner could also terminate a contract for cause if the contractor cannot perform the work in accordance to the timeline in the contract. Termination for Convenience A termination for convenience, however, is when a contract is terminated when there is no contract breach made by the other party. Instead, a termination for convenience is only legal when it is expressly written in the contract. A termination for convenience clause tends to be added in contracts because it allows for both parties to end their responsibilities in a way that does not lead to litigation or harm of either party. It will allow for the contractor to collect any payments for completed work, as well as the owner being able to dodge paying damages for terminating the project. |  |
| --- | --- | --- |

Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

| Answer |  | Yes |  |  |
| --- | --- | --- | --- | --- |
|  |  | No |  |  |

If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

| Answer | What must occur to perform the contract A reasonable time in which the contract must be completed A statement of the consequences of not performing in accordance with the notice |  |
| --- | --- | --- |

True or False (Tick your response): Where the notice given (as per Q39. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

| Answer | Final contract to be paid on practical completion , not at handover. Defects and omissions should be discussed at the pre-handover inspection and addressed prior to handover. |  |
| --- | --- | --- |

Explain the concept ‘conditions for completion at the cost of the contractor’.

| Answer | the amount of money (damages) required to complete performance (finish the job) when a contract has been breached by the failure to perform. Example: when a general contractor breaches by not completing a house, the cost of completion is the actual cost of bringing in a new builder to finish what is left to do. The actual costs become the measure of damages rather than an estimate of cost based on percentage of work to be done. |  |
| --- | --- | --- |

Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

| Answer | A 'document which evidences a warranty against defects' must state: - what you as the business (giving the warranty) must do if goods are faulty or defective – for example, repair or replace the goods - what the consumer must do to entitle them to claim the warranty – for example, cease using the goods when a fault arises or contact the supplier or manufacturer and point to the defect - the following information about the business giving the warranty: - name - business address - telephone number - email address (if any) - the warranty period – how long the warranty lasts for - what a consumer must do to claim under the warranty – how to contact you and where to send the claim - whether you or the consumer are responsible for expenses associated with a warranty claim and how the consumer can claim back any expenses incurred - that the benefits provided to the consumer by the warranty are in addition to other rights and remedies available to the consumer under the law |  |
| --- | --- | --- |

Name one (1) person you should consult if you are considering ousting a contractor from a building site.

| Answer | Obtain legal advice. |  |
| --- | --- | --- |

What document should you refer to if you are considering ousting a contractor from a building site?

| Answer | QBCC- early dispute resolution (EDR) |  |
| --- | --- | --- |

How should you handle a customer complaint?

| Answer | Guide to resolving complaints Deal with the complaint immediately. Get to the heart of the matter quickly, and you're more likely to satisfy the customer. ... Stay calm. ... Identify the problem. ... Decide what can be done. ... Arrange a second opinion to confirm your view. ... Keep records. ... Fix the problem. |  |
| --- | --- | --- |

How do you reduce the risk of dispute?

| Answer | Communicate. Probably the most important ingredient of a successful project is good communication. ... Don't forget the details. Make sure you keep accurate records. ... Learn about building basics. Become familiar with the building process and practices. ... Read your contract. |  |
| --- | --- | --- |

What is the process for dispute resolution?

| Answer | If you have an issue with someone who you hired to do building work for you (such as a builder, contractor or designer), follow these steps to resolve the issue. Step 1 – Tell the builder or contractor in writing When you have a problem or concern about building work completed on or for your property, the first thing you should do is tell the person who you hired to do the work about your concerns. It is best to do this in writing as well as in person or over the phone. When writing your letter: keep it short and easy to understand use facts and keep your emotions out of it explain how you would like the problem fixed make sure to date, sign, and keep a copy. Allow 2 weeks for them to fix the problem, or offer you a solution you think is fair. Hopefully, you will be able to agree on an outcome. Step 2 – Make a complaint to QBCC If you are still not happy, you can you can make a complaint to your nearest Queensland Building and Construction Commission (QBCC) office. The QBCC may be able to assist with: effective work complaints complaints against certifiers building design complaints non-completion of work complaints about pre-purchase and termite inspections unlicensed contractor complaints. |  |
| --- | --- | --- |

- During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

| Answer | Good evening Barbra, I appreciate your concern. I have checked the contract and the white goods and chattels list selected by you and cross checked this with the specifications and my materials order and the receivable order sheets. I have established that the bath, as per these details, is correct and there has been no mistake on my part. As your aware the bathtub has now been installed and if a replacement is required, that can be arranged, however both the new bath tub and removal/re-installation will be an additional cost. Please advise of how you would like to proceed and details of the replacement bathtub if so required. Kind Regards Paul the Builder |  |
| --- | --- | --- |

Where would you find any possible penalties associated with a build?

| Answer | Penalties could apply if -you don’t comply with the contract -Liquidation damages -Work not been finished on time |  |
| --- | --- | --- |

Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

| Answer | A final certificate must be obtained after the final inspection has been completed. This certificate ,and all other inspection certificates, forms and accompanying documents must be given to the certifier so they can be lodged with the BCC who holds these records. |  |
| --- | --- | --- |

- Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:

  - The land has been secured and paid for by the Clients.

  - Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.

  - Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured.

  - Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list.

  - The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.

  - The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.

  - Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build.

  - The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.

  - The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.

  - The construction period excluding inclement weather and possible delays is 23 weeks

  - Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).

  - Prime costs are required for the solar hot water system and ducted air conditioning

  - Provide fictitious details for all other sections of the contract.

  - 18 solar panels are to be installed on the roof

| Answer |  |  |
| --- | --- | --- |

CPCCBC4003A Select and prepare a construction contract

CPCCBC4016A Administer a construction contract

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - Copy of a contract issued to sub-contractor for your project with relevant AS code on the front - Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails) - Copy of HSE minimum requirements sent as contract condition - Construction contracts that have been developed, signed off, or contributed to by the candidate - Proof of correspondence with client regarding construction contract. Redact sensitive information as required. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment. |  |  |  |
| Resources required: Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Explain to the client: - Essential terms and elements of a valid contract - Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements) - The range of documents that collectively make up a contract (including construction schedules, reports, specifications) - The importance of the contract to sales process - Implications of legislation, regulations and codes of practice (including Australian Consumer Law) |  |  |  |
| - Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit. |  |  |  |
| - Ensure the pre-contract agreement is signed and processed according to organisational requirements. |  |  |  |
| - Select appropriate contract and seek expert advice in the preparation of the contract, considering: - Contract rise and fall amounts - Schedule of progress payments - Processes for applying of extensions of time |  |  |  |
| - Break down contract clauses/terms/conditions with the client, including: - Rights, liabilities and potential penalties of parties under the contract - Definitions of building work, common contract terms and procedures, considering – - Practical completion and issuing a final certificate - Defects liability and completion at the cost of the contractor - Effect of ousting the contractor from the building or site - Cooling off periods - Provisional sum and prime cost allowances - Measures to be taken in the event of an anomaly in the rendering of the contract, considering – - Variations - Circumstances that bring about a breach and termination of contract, considering – - Unreasonable/vexatious notice - Abandonment of a contract - Methods for resolving contractual disputes |  |  |  |
| - Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication - Using technology (including telephone, facsimile, email) - In writing (including drafting responses to queries about contracts) |  |  |  |
| The participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments