## Monthly ECI Report
21033 - Rockpool Pelican Waters - Construction Phase D&C Monthly Design Report 25 July 2022
ECI Details
ECI commencement | 2021-03-24
ECI Completion Date | 2022-03-01
ECI Value | 444427
ECI invoiced to date | 143685.3
ECI Resources budget | TBC | Requires further confirmation internally
ECI cost to date | 2022-03-01
| CURRENT CLIENT REPORT COST DATE |  | D&C CONTRACT (18/7/22) |  | ECI PATHWAY |  | MONTH SUMMARY
CLIENT TOTAL |  |  |  | 34267400
Preliminaries |  |  |  | 4315553
Provisional & PC items (DM Fee) |  |  |  | 2307907
Subcontractors |  |  |  | 24535540
Design Management |  |  | 139640 | INCL
Margin |  |  | 9.071% | 3108400
Design Status & Program
Consultant | Agreement Status | Signed Date | Design Status | Who? | Comments
Architect & Interior Design & Town Planner | N/A |  | Developed Design | GJG | Drawings are in coordination with Services.
Structural, Civil & Hydraulic Engineer | Executed | 2021-06-18 | Schematic design | Acor | Structural - issued IFC, however have multiple comments to be addressed and updated. Civil - OPW issued, drawings at IFC. Hydraulics - Acor took the design to DD. Dyfa (PDD) are completing the design.
Hydraulic Engineer | Executed | 2022-05-30 | Submitted for Plumbing Approval | PDD | Drawings submitted for SCC PA 18.7.22.
Landscape Architect | Executed | 2021-06-02 | Developed Design | BUTLER | DD Stage - OPW Landscape and have responded to RFI 25.7.22.
Mechanical, Elect, VT & Fire Engineer | Executed | 2021-05-31 | Developed Design | STP | STP were engaged and took design up to DD.
Mechanical | Executed | 2022-05-30 | Developed Design | AAS | AAS not issued design yet
Electrical | Executed | 2022-05-30 | Developed Design | MONTEUR | Not issued design yet
Certifier | Executed | 2021-08-23 | Developed Design | FORMIGA1 | BA Stage 1 submitted, should be approved 28/7/22
Fire Engineering | Executed | 2022-05-30 | FEB | WalkerBai | FEB and FER created. QFES meeting held. Once services drawings near IFC, will submit with FER.
Food Service & Waste Consultant | Executed | 2021-06-04 | Developed Design | UFD | No action
Acoustic Engineer | Executed | 2021-05-31 | Developed Design | ACOUSTICWORKS | Revised Acoustic report based on feedback from C&P
Section J Reporting | Executed | 2021-06-22 | Developed Design | CUNDALL | JV3 modelling completed since ECI.
Traffic Engineer | Executed | 2021-06-07 | Developed Design | TTM | No action
Approvals Status
Approval |  | Approving Body | Target Lodgement | Actual lodgement | Target Approval Date | Actual Approval Date
DA Approval |  | SCRC | 2021-06-16 | 2021-06-30 | 2021-10-13 | Complete
Energex (design approval) |  | Energex | 2021-09-06 | 2021-06-30 | 2021-11-16 | Paid, offer accepted 18/7/22
Unity Water |  | Unity Water | 2021-09-13 | 2022-05-01 | 2022-08-15 | 8-10 week leadtime
Building Approval (Structure) |  | Certifier | 2021-12-09 | 2022-07-18 | 2021-12-17 | 2022-07-28
Building Approval (Full Building) |  | Certifier | 2022-04-11 | 2022-09-15 | 2022-09-20
Plumbing & Drainage Approval |  | SCCC | 2021-11-22 | 2022-07-18 | 2022-09-10
Operational Works Approval(s) |  | SCCC | 2021-09-27 | 2022-04-30 | 2021-12-15 | Complete
QFES Approval |  | QFES | 2021-11-30 |  | 2022-08-20
McNab Internal Team Review |  | McNab |  |  |  | Carseldine lessons learnt completed
Design Development (DD) Phase - Client Approval |  | Client | 2022-08-30 |  |  | Will do once services drawings issued
Issue for Construction (IFC) Phase - Client Approval |  | Client | 2022-09-30
Early Works Stages:
Pre-construction Ops team input/planning |  | McNab |  |  |  | Complete
Earliest construction commncement |  | McNab | 2022-07-15 | 2022-07-15 |  | Started earthworks.
Design Management Dashboard
|  |  | Status |  | Progress / Status | Complete
Design Management Plan |  |  | Complete
ECI Program (refer attached) |  |  | Complete
Procore Protocols |  |  | Complete
DA Matrix |  |  | NYS |  | CB to update. Responsibilities agreed.
Value Management Checklist |  |  | NYS |  | Ongoing.
Design Change Register |  |  | NYS |  | Brief Compliance Register to be used as tracking
Brief Compliance Register |  |  | NYS |  | CB to update, will use as live document with client.
Safety in Design Register |  |  | NYS |  | Compiling 25/7/22
Cost Plan Review |  |  | Progressing |  | Complete
Critical Discussion Items
Item |  | Discussion Commentary
Rockpool Oxley |  | Meeting on 26/7/22 with RPL to discuss Rockpool kickoff and the next steps of the ECI.
Unity water |  | Approval is putting the Plumbing approval at risk.
Report Annexures:

## Margin Pathway
MARGIN PATHWAY
No | Item | description | Est Value | Pending / Adopted / Rejected | Adopted Not on plan | Escalation Cost
1 |  | TBC after discussion between McNab and Rockpool regarding margin application and preliminaries
2
3
4
5
6
7
8 | [5 empty] | 0
9
10
11
12
13
14
15 |  |  | 0
|  | TOTAL | 0
0
Prelims as margin summary
| Declared prelims | 4315553 | As per client facing costplan
| ECI recovery (e/o to Carseldine) | -23086 | As per TM forecast
| forecast prelims (as per Carseldine June forecast) | -3775185 | TBC in SD by ops team
| TOTAL | 517282
Note on D15: Author:

## Client VE Target
21033 Rockpool Pelican Waters
2021-08-04
Rev: 1
Value Management
Item | Description | Value Management $ | Status | Comments | Adopted Value | Adopted; Not on Plan | Adopted; on Plan | Margin Enhancement
1 | Reduce floor to floor height by 200mm (Levels 1-4 only). Total 800mm vertical reduction. | -80000
2 | Remove Concrete Slab Extensions to Unscreened area L2-L5 (Target) | -37930.62
3 | Remove Concrete Slab Extensions to Screened area L2-L5 (Target) | -52146.42
4 | Remove Concrete Slab Extensions to Deck Area L2-L5 (Target) | -31859.55
5 | Change Glazed Operable Cafe doors to Sliding Glass doors | -21192
6 | Piling Rationalisation (Target) | -250000
7 | Reduce Extent of Northern and Western Facade Screening to Half (Target) | -168000
8 | Remove Gas Service and Enclosure | -101000
9 | Remove Foyer Batten Feature Ceiling Inset | -43199
10 | Remove Feature Batten Room Dividers to L1-L5 Lounge room | -43636
11 | Reduce GF Floor Height by 200mm | -20000
12 | Reduce Water saving storage tanks by 50KL | 0 |  | part of item 18
13 | Reduction of glazed façade to match Carseldine Extent and replace with Structural block work | -46526.4
14 | Replace double serveries with single serveries to L2-5 (to Match Carseldine) | -65000
15 | Remove 600h seated wall to Landscape | -28164
16 | Remove Raised Planters to ground level landscaping | -14000
17 | Target 30% reduction in blade walls | -80000
18 | ESD initiatives (as per Carseldine green star) | -245500
| Subtotal | -1328153.99
Subtotal |  |  |  |  | 0
Scope increase
Item | Description | Scope Increase $ | Status | Comments | Adopted Value | Adopted; Not on Plan | Adopted; on Plan
Subtotal |  |  |  |  | 0
| OVERALL ADDTIONS INCLUDING ALL OF ABOVE |  |  |  | 0
| McNab Tender Costs (as reported) | [6 empty] | 0
| VE Adjustment costs |  |  |  | 0
| Revised Total Construction Cost |  |  |  | 0