# Electronic Call Forward Sheet

| Site address | 123 ABC Residential street, QLD | Project name | 123 ABC Residential street, QLD |
| --- | --- | --- | --- |
| Client | Big Boss | Surveyor | Mr Sur |

|  | Provider details *Names have been removed due to confidentiality reasons * |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Date required | Supplier | Contractor | Contact info |
| Stage |
| Demolish existing kitchen and make good Dismantling the existing storage, slab platform including supporting walls, wall tiles, flooring, sink etc. at all levels as required carefully and disposing off and clearing away the debrisSlabs to be chased to allow for new plumbing | 5/3/23 |  | Demolition labour | 3399 |
| Plumbing rough in | 7/3/23 |  | Plumber | 0456 |
| Electrical rough in | 7/3/23 |  | Electrician | 0789 |
| Kitchen Elevation Bench Drawers Spice rack Brushed stainless steel laminate Ducting Overheads Shelves Caesarstone bench top Island Sink cupboard Paint Cabinetry - Blum Tandembox antaro h. Fronted pull-out C - DQC5JY, D - DQC69A, DQCB6M Urbane Castella 192mmCTC handle | 5/3/23 | Kitchen supplier |  | 2216 |
| Butlers Pantry Door sink cupbard Bins Dishwasher Drawers Shelves Overheads Paint | 5/3/23 | Kitchen supplier |  | 2216 |
| L shaped laundry 2450x2520x2550mm or expressed as 2.45m x 2.52m x 2.55m with 4 door laundry tub unit with 1 adj shelf with bench at 1000mm H 40mm Caesarstone organic white top running wall to wall below laundry shute cupboard and 20mm thick splashback 150mm height 4 door overhead cupboard with 2 adj shelves and dorrs hanging down as finger pull above dryer and washing machine openings with flat pull out shelves and 1 of blum soft close drawer below 2 door Tall broom storage cupboard to right side with 1 of blum soft close drawer below 1 0f internal adj shelf Brushed stainless steel laminate kick face Single door cupboard 600x600mm on opposite wall 1000mm height bench top. All internals 16mm white HMR with 1mm ABS PVCedge. All fronts in 18mm white sating with 2 pac satin finish Dryer and washing machine panels, bottoms in 32mm MDF with 2pac finish | 6/3/23 | Laundry supplier |  | 2219 |
| Island & laundry - franke ancona single bowl undermount sink – anx 110-48 Pantry - franke ancona double bowl undermount sink - anx 120 Island & pantry - mizu drift mk2 gooseneck sink mixer pull-out Laundry - mizu soothe square gooseneck sink mixer | 8/3/23 | Plumbing supplier |  | 2218 |
| Building works – wet areas, walls, ceiling, doors/windows | 10/3/23 |  | Carpenter | 1456 |
| Plaster works and finish | 17/3/23 |  | Plasterer | 1457 |
| Waterproofing | 19/3/23 |  | Waterproofer | 1234 |
| Cabinets installation, skirting/architraves installation, benchtop , kitchen, laundry, pantry installation | 28/3/23 |  | Carpenter | 1456 |
| New timber look tile flooring Kitchen – timber look tiles to match floors 1200x x230mm Laundry and kitchen - ceramic tile splashback - Snow Brillo Tile Sc19 A7615, Amber Tiles To Match Cabinets. 130mmx130mm Brushed stainless steel laminate kick face 130 sqm | 20/4/23 | Tile supplier |  | 2214 |
| Tiling | 28/4/23 |  | Tiler | 1234 |
| Beacon Herman 1 light pendant 14 watt led tape and recess led profile under overhead cupboards Single phase underground power connection from existing supply point. Led light strip under island bench Cooktop isolation switch | 28/4/23 | Electrical supplier |  | 2212 |
| Electrical fit off | 1/5/23 |  | Electrician | 0789 |
| Plumbing fit off | 1/5/23 |  | Plumber | 0456 |
| New fixed glass window to suit existing opening width frame 1800x600mm Colour to match exiting and tinted to client requirement (customized) New Triple Slider With Screens To Match Existing Profile & Colour 2710x2100mm Slider with reversed opening with screen to match existing profile and colour 1810mmx2100mm | 2/5/23 | Window supplier |  | 2222 |
| Accessories fit off | 3/5/23 |  | Carpenter | 1456 |
| Caulking | 3/5/23 |  | Carpenter | 1456 |
| Screen installation | 4/5/23 |  | Carpenter | 1456 |