## Timeline
Task Name | Start | End | Duration (days)
Start date / site survey / liaison with neighbours | 2018-09-21 | 2018-09-30 | 9
liaise with council and service providors | 2018-09-29 | 2018-10-05 | 6
Dial before you dig | 2018-10-04 | 2018-10-05 | 1
Temporary services and site accommodation | 2018-10-05 | 2018-10-16 | 11
Demolition | 2018-10-16 | 2018-10-23 | 7
Excavation including mob and demob excavator | 2018-10-22 | 2018-10-30 | 8
Concrete | 2018-11-01 | 2018-11-13 | 12
Pre backfill | 2018-11-13 | 2018-11-15 | 2
Framing including offsite construction & delivery | 2018-10-25 | 2018-12-05 | 41
Roof | 2018-11-19 | 2018-12-10 | 21
Plumbing | 2018-10-29 | 2018-12-09 | 41
Windows | 2018-11-22 | 2018-12-15 | 23
HVAC | 2018-11-29 | 2018-12-20 | 21
Electrical | 2018-12-10 | 2018-12-22 | 12
A/V | 2018-12-10 | 2018-12-15 | 5
Insulation | 2018-12-27 | 2018-12-30 | 3
Insulation | 2018-12-03 | 2018-12-21 | 18
Plasterboard | 2019-01-03 | 2019-01-23 | 20
Exterior cladding | 2019-01-03 | 2019-01-17 | 14
Exterior case work | 2019-01-04 | 2019-01-13 | 9
Laundry | 2019-02-16 | 2019-03-11 | 23
Hardwoods | 2019-01-19 | 2019-03-10 | 50
Tile | 2019-02-03 | 2019-02-14 | 11
Cabinets | 2019-01-18 | 2019-03-06 | 47
Plumbing - fixtures | 2019-02-16 | 2019-02-23 | 7
Interior doors | 2019-02-25 | 2019-03-09 | 12
Millwork | 2019-02-15 | 2019-02-17 | 2
Interior painting | 2019-02-28 | 2019-04-14 | 45
kitchen Counters | 2019-03-21 | 2019-03-31 | 10
Schedule Buffer | 2019-02-28 | 2019-03-10 | 10
roofed alfresco (loggia) | 2019-02-28 | 2019-03-18 | 18
Interior doors- hang & hardware | 2019-05-03 | 2019-05-13 | 10
Appliances | 2019-05-02 | 2019-05-03 | 1
Plumbing | 2019-05-02 | 2019-05-05 | 3
Electrical | 2019-05-03 | 2019-05-11 | 8
Bathroom Glass | 2019-05-09 | 2019-05-13 | 4
Garage Door dress up | 2019-05-13 | 2019-05-18 | 5
FINAL Inspections | 2019-05-02 | 2019-05-02 | 0
Wrap up | 2019-05-09 | 2019-06-05 | 27
House Cleaning | 2019-05-29 | 2019-06-10 | 12
Complete | 2019-06-01 | 2019-06-01 | 0