## Construction Project Timeline
SCAFFOLD CONSTRUCT/DISMANTLE PROJECT TIMELINE
PROJECT TITLE |  |  | START
8 Rees Court Palm Beach |  |  | 2021-10-04 |  | PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
John Doe |  |  | 2021-10-22 |  | 19
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
Scaffold Erection | Not Started |  | 2021-10-04 | 2021-10-04 | 1 |  | In Progress
Brickwork above 3m | Not Started |  | 2021-10-05 | 2021-10-18 | 14 |  | Complete
Fascia & Guttering | Not Started |  | 2021-10-15 | 2021-10-20 | 6 |  | On Hold
Install soffit & quad beading | Not Started |  | 2021-10-19 | 2021-10-21 | 3
Painting of soffit | Not Started |  | 2021-10-20 | 2021-10-21 | 2
Dismantle Scaffold | Not Started |  | 2021-10-22 | 2021-10-22 | 1