RIICWM401E

Supervise civil works

ASSESSMENT SUMMARY

The assessment activities for RIICWM401E Supervise civil works cover all aspects of the unit of competency. For Apprentices/Trainees, this includes supervisor completion of the Apprentice/Trainee Record (ATR).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be fair, flexible, valid and reliable. If a Participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a Participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the Participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a Participant does not answer all questions or perform all tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency.

The Trainer/Assessor can provide the Participant with additional information on interpreting the assessment outcomes and guide the Participant’s options. If a Participant is still deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result as per the process in the Student Handbook.

By signing below, the Participant acknowledges:

- They understand the assessment instructions and requirements, and consent to being assessed.

- The work submitted is to be their own work – with the work of/with others needing to be clearly acknowledged and documented.

- They consent to any photo/video recording of their work that occurs during assessment.

| Participant name | Chris Gwilliams |
| --- | --- |
| Participant signature |  |

Pre-requisite unit(s) to be achieved and authenticated prior to undertaking assessment

Not applicable

| Task | Date completed | Assessment Results |  |
| --- | --- | --- | --- |
| Theory Exam | Select Date. | Satisfactory | Not Satisfactory |
| Practical Assessment | Select Date. | Satisfactory | Not Satisfactory |
| Outcome for RIICWM401E | Select Date. | Competent | Not Yet Competent |

| Evidence requirements checklist (ticked by assessor and evidence supplied to RTO) |  |
| --- | --- |
| Theory Exam | Practical Assessment Completed Job Plan |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |

RIICWM401E

Supervise civil works

THEORY EXAM

| Participant name | Chris Gwilliams |
| --- | --- |

FOR THE PARTICIPANT

Instructions

- You will complete written questions as outlined on the following pages. You must attempt all questions and provide enough detail in your responses to demonstrate your knowledge. - It is anticipated that you should complete this assessment within two (2) hours, but additional time may be allowed upon negotiation with the Assessor. - You must complete all questions unassisted by the Assessor or other personnel but may refer to reference material as needed. All questions must be answered correctly for a ‘Satisfactory’ assessment outcome to be awarded. - An oral examination may be allowed under certain circumstances, whereby your answers will be documented by another party. - Any written questions that are incomplete, or not answered satisfactorily will need to be completed again after further training support. - If you answer a question incorrectly but modify your response, put your initials next to the written change (or the Assessor must initial a verbal change).

Resources required

Pen

FOR THE ASSESSOR

Instructions

- Where oral examination has occurred, ensure that this is acknowledged in writing (e.g. FT001 and Assessor Comments) - All questions must be satisfactorily demonstrated by the Participant for a Satisfactory determination (indicated by an Assessor tick to the right of the question). - Assessors are to complete marking in pen of a different colour to the Participant. - If the Participant verbally modifies their response, write in the modified response verbatim and put your initials next to the written change.

ASSESSOR COMMENTS

As necessary, outline: - Details on reattempts, alternative arrangements or reasonable adjustments made. - Where a Participant is deemed ‘Not Satisfactory’, provide recommendations for future training.

Which on-going risk management procedures and documentation do you access when supervising civil work and how do these link to legislative requirements?

| Answer | When supervising civil works, you access ongoing risk management procedures like the Site-Specific Safety Management Plan, Job Hazard Analyses, Safe Work Method Statements, daily toolbox talks, and the Risk Register, all of which are linked to legislative requirements. |  |
| --- | --- | --- |

What important emergency response information must be shared with workers prior to work beginning?

| Answer | Before starting work, workers must be informed of key emergency response information, including emergency contact details for internal personnel and external services, evacuation procedures, the location of emergency equipment, workplace maps highlighting exits and assembly points, and a clear description of the alarm systems |  |
| --- | --- | --- |

What are (1) the objectives of the Environmental Management Plan and (2) why you should read this as part of planning the job.

| Answer 1. 2. | It provides the key environmental, cultural and heritage responsibilities for the project. Used to satisfy the requirements of the EMP act. This act may have requirements that force you to approach certain tasks in specific manners. These include: - Waterways that may be impacted - Fauna and Flora that may be impacted - Personal companies responsible - Erosion and sediment controls |  |
| --- | --- | --- |

What is (1) the ‘scope’ of work, (2) why is this important when developing a job plan and (3) where can you sources relevant information.

| Answer 1. 2. 3. | ‘Scope’ means the parts or components of a project that a person or persons are responsible for at their level. They must create a baseline, outline all the work needed in a specific order to complete the task. It is important to have in a job plan to predict the timeline in which various tasks can be achieved to keep the project on track. The job plan should include: -Timeline -Budget -Milestone -Scheduling You can source the scope of works for an on-site construction project from the formal contract between the client and contractor. Other sources could include: -Team lists -Lessons learnt -Suppliers -Subcontractors |  |
| --- | --- | --- |

In the general principles of surveying, what is the importance of ‘working from the whole to the part’ (1) when surveying and (2) how this is achieved?

| Answer 1. 2. | This is a fundamental principle that emphasizes establishing a broad, accurate framework before focusing on detailed measurements. This approach is crucial for minimizing error accumulation and ensuring overall survey accuracy By first establishing a precise control network, any errors introduced during the subsequent detailed measurements can be easily detected and corrected by referencing the established control points |  |
| --- | --- | --- |

Why can consulting the team enhance team practices? Include one (1) example.

| Answer | Consulting the team can enhance team practices by promoting open communication, supporting shared understanding of goals, and building trust and accountability, which in turn leads to better collaboration, innovative solutions, higher quality work, and greater motivation among team members An example would be before doing a lift of material, ask the team members involved what the best method would be. Gathering multiple ideas can make the job easier and help create positive team work. |  |
| --- | --- | --- |

How do you communicate site safety requirements to ensure workers wear PPE suited to the site?

| Answer | This information should be shared at the site induction and toolbox meeting before starting the job This information should be clearly signed at the front access to the site. Constantly refer to compliance records to make sure tasks and operations are being carried our correctly and safely. When undertaking tasks leading by example can be a good way at demonstrating how to preform duties safely and correctly. |  |
| --- | --- | --- |

Why is it important to coordinate tasks with other work supervisors and schedule team activities?

| Answer | Supervisors must agree and organise strategies to best address tasks to meet the schedule. They must: -Inform them of work progress -Relay any problems -Clarify expectations and goals -Give feedback on worker performance and attitudes -Get information on company news and activities -Discuss their own needs and desires -Forward recommended improvements -Avoid Clashes -Create appropriate priorities -Create a work breakdown structure. |  |
| --- | --- | --- |

What inclusions must be considered when preparing a job plan?

| Answer | -Labour -Safety -Environmental issues -Plant and equipment -Materials -Weather -Sub Contractor work -Utility -Site access -Work Flow |  |
| --- | --- | --- |

What processes must you follow to acquire and confirm the acquisition of required resources at your workplace?

| Answer | When tasked with the purchase of resources or services needed for the job you must follow organisational guidelines which govern and prescribe requirements and procedures for the acquirement of resources. Preferred suppliers should be considered. This can have an effect on job costs. What materials are needed within certain time frames. Process required when making large purchases. If the cost of material is high sometime the purchase process can be lengthy. This can influence purchase and delivery times. |  |
| --- | --- | --- |

What is discussed during the daily pre-start meeting?

| Answer | A daily pre-start meeting discusses the day's work, associated tasks, identified hazards, and necessary safety measures to ensure a productive and safe work environment. Key topics include reviewing safety procedures, conveying important information, and providing a forum for communication and feedback between the crew and leaders to align the team on goals and risks for the day. |  |
| --- | --- | --- |

What is the ‘rule of thumb’ basis for matching a machine to a job?

| Answer | A zone, zone description, distance and machine required type table is used to determine the best machine suited for the job. The size vs speed ratio should be considered when picking a machine. The size of the machine will be picked to suit the site access and conditions while the machine type will be picked for the task being undertaken. Some tasks only need to be done in a small area while some need to be done over great distances. |  |
| --- | --- | --- |

Supervisors must have knowledge of factors affecting plant performance. What are four (4) factors that can affect plant performance and output and why must supervisors monitor these?

| Answer 1. 2. 3. 4. | Experience of operator. Different skill levels can effect worker output and timeframes Suitability of task. Materials being used. Different material types can cause jabs to last longer Pre and post operational checks. If as machine is not preforming well it can cause issues in production Safety guidelines. Standard Operating Procedures (SOPs). Not following these measures can effect timelines. |  |
| --- | --- | --- |

What methods do you use to ensure team members adhere to safety requirements such as PPE during the work tasks?

| Answer | Methods include consulting with workers on PPE selection, providing information and training on proper usage, conducting regular inspections and safety audits, implementing safety checklists, fostering open communication about safety, and demonstrating a strong personal commitment to safety protocol. SWMS should have a guideline on site specific PPE needed. Inductions should induction PPE required for site access and works. Lead by example |  |
| --- | --- | --- |

What is the supervisor’s role during site set out?

| Answer | A supervisor ensures the physical location of the project is accurately established and maintained by verifying survey markers, inspecting the area for potential hazards, and coordinating with the survey team to confirm correct placement of all boundary and setting-out points. Protecting the survey points is important. One measure that can be done is putting larger markers close to survey pins to create awareness while working around them. Offset marks and also a good idea to keep reference points out of work zones. |  |
| --- | --- | --- |

What are two (2) things you would tell the workers when explaining what the pegs mean during road set out? (30 words)

| Answer | - They dictate the extremities lines and levels of various parts of the job. - They are reference to shapes, lines and lives in accordance with the plans. These references include: -Finished road height or Finished Subgrade height (FSL) -Offsets -Changes -Levels and Grades |  |
| --- | --- | --- |

What methods do you apply when monitoring civil works to ensure the required outcomes or met on a daily basis?

| Answer | -Toolbox and prestart meetings -Performance scheduling regular -Site entry diaries -Gannt charts or bar charts -Activity scheduling -Risk assessment -Environmental analysis |  |
| --- | --- | --- |

Name and explain the purpose for three (3) of the different test results the supervisor must be able to read and understand at different hold or witness points of a project?

| Answer 1. 2. 3. | Soil tests – has information about the soil type and how it can be used in different styles and applications. This can create a timing estimate on the earthworks required. Compaction tests – has the information about the percentage of compaction and how it can be improved. This makes sure standards are met and can assist in improvements needed. Water quality tests – has the information about the waters feature and whether its goof to use in various applications. Dewatering is also important. |  |
| --- | --- | --- |

What is the purpose of road surface drainage and what are four (4) elements used to achieve this effectively?

| Answer Purpose Element 1. 2. 3. 4. | To create runoff for road surface stormwater to areas required, control water runoff, avoid flooding and prevent damage. Kerbing and channels Table drains and blocks Batter drains Pipe network. |  |
| --- | --- | --- |

What are the effects of inappropriate road drainage infrastructure?

| Answer | -Flooding -Peak water levels -Inundation -Erosion -Water velocity -Damage to road, bridge and infrastructure -Impact on surrounding property values -Damage to Fauna and flora -Personal and public liability |  |
| --- | --- | --- |

What are the three (3) main parts of roadway design and the importance of these features?

| Answer 1. 2. 3. | Alignment - creating a three-dimensional path for a road, considering both horizontal (left/right) and vertical (up/down) aspects. Profile - represents the vertical alignment of a road, showing changes in elevation along a specific path Cross Section – Degree design scaled drawing indicating road pitches Safety is important in all of these features. Level gradients must be considered for driver comfort, behaviour and potential hazards. |  |
| --- | --- | --- |

How can you support sub-contractors to achieve their responsibilities?

| Answer | Ensure clear and comprehensive contracts defining scope and expectations, maintain open lines of communication for updates and feedback, provide thorough inductions and access to project information, monitor performance closely, offer timely payments, and manage risks by building a strong, trustworthy relationship |  |
| --- | --- | --- |

How do supervisors determine human resources and sub-contractors needed for the job plan?

| Answer | -Training and skill level -Availability -Past project experience A capability matrix can be used in assistance for considering workers. The job size must be considered to allowing the job plan timing to be met. Different roles will require different resources at certain intervals throughout the job. |  |
| --- | --- | --- |

How do you, as the supervisor, (1) determine and (2) share the communication systems to be used during site tasks with others? Include in your response (3) the communication systems generally used.

| Answer 1. 2. 3. | Depends on the task being undertaken. Different tasks require different forms of communication. The can be shared through various forms. Electronic email, phone, at prestart meeting, inductions, signage while entering site, UHF. The best way to relay the communication system is verbally because you can get a quick answer that the team members understand which communication system to use. Using constant reinforcement will aid in this. Prestart and toolboxes can be used to communicate expectations. Having assigned UHF channels for tasks can aid in communication and safety. |  |
| --- | --- | --- |

What methods do you apply when monitoring worker performance for safety and compliance?

| Answer | To monitor worker safety and compliance, apply a mix of Behavioural Observation, Formal Audits and Inspections, Incident and Hazard Reporting, and Employee Feedback Mechanisms like surveys and consultation |  |
| --- | --- | --- |

How is quality assessed and confirmed?

| Answer | Quality in civil construction is assessed and confirmed through a comprehensive system of quality assurance and quality control, which includes developing a quality plan, using checklists and Inspection and Test Plans, conducting site inspections and material testing, documenting all activities, and implementing corrective actions for any deviations. Only using accredited/Licenced subcontractors in vital. |  |
| --- | --- | --- |

What are four (4) events that might occur on a normal working day that may significantly affect progress of civil works tasks and force the use of contingency plans.

| Answer 1. 2. 3. 4. | Sickness Weather Unavailability of materials Industrial disputes |  |
| --- | --- | --- |

What are four (4) contingency plans that may be in place to support a civil construction operational plan?

| Answer 1. 2. 3. 4. | Equipment Downtime. Preferred suppliers should be considered. Having back up support is also a good idea. Contracting or Outsourcing. Workers on leave. Having replacement personal or rentals. Cost Reduction Strategies (Reusing or recycling) |  |
| --- | --- | --- |

What is the relationship between various areas of civil work and how are these relationships relevant when developing job plans and work schedules?

| Answer | Various areas of civil work, are inherently interdependent, with the output of one often forming the input or foundation for another. This interdependence is crucial for developing job plans and schedules because it establishes a logical order of tasks, allowing for efficient resource allocation and risk management, ensuring that the project is completed on time |  |
| --- | --- | --- |

Elaborate on four (4) different types of estimates used when developing job plans.

| Answer 1. 2. 3. 4. | Quantity Estimate - An estimate that uses approximate quantities of major work items, based on historical data and project knowledge, to arrive at a rough cost Labour Estimate – Amount of labour to be used at each stage of the job to arrive a rough cost. Demolition Estimate – FI the need to demolition is need a quote can often be obtained for sub-contractor or an estimate can be made for rough cost. Safety Estimate – Cost of safety gear and equipment need for job. |  |
| --- | --- | --- |

What is the relationship between waste management and environmental protection?

| Answer | Waste has an impact on the environment and it is important that there is a waste management plan in place to ensure the environment around us is kept healthy and safe. Referencing the Waste and Recycling Act and EMP are good sources. These help stop Pollution and Cross contamination. |  |
| --- | --- | --- |

RIICWM401E

Supervise civil works

PRACTICAL ASSESSMENT

| Participant name | Chris Gwilliams |
| --- | --- |

FOR THE PARTICIPANT

Instructions

- The tasks outlined on the following pages will require performance of normal workplace activities, as a result of a structured activity set by an Observer in the workplace or a simulated activity set by your Assessor/Observer. - The timeframe for these tasks will be established by your Assessor/Observer, in consideration of location conditions and industry requirements. - You must complete all tasks unassisted by the Assessor or other personnel, unless the steps note this assistance. - You must attempt all tasks (and itemised steps) for a ‘Satisfactory’ assessment outcome to be awarded. - For any observation conducted that is incomplete, or without satisfactory performance, the observation will need to be completed again after further training support.

FOR THE ASSESSOR/OBSERVER

Instructions

- The following observation record should be used to judge and record your observations of the Participant as they complete the task(s) set. You must record your observations of the Participant’s performance. - For each occasion, indicate the task performed and whether it was a simulation or workplace-based task. - Any simulated assessment must ensure the Participant still performs under workplace conditions which reflect industry standards. - In the comments, provide clear detail regarding the task that the Participant was required to do (e.g. PPE used, materials handled, attachments connected, plant types). - All steps must be satisfactorily demonstrated by the Participant for a ‘Satisfactory’ determination (indicated by an Assessor tick to the right of each itemised step, or an Observer tick to the right of each itemised step, and confirmation by an Assessor in the Assessor Comments). - Where you have determined that one or more task steps have not been satisfactorily demonstrated, provide the Participant with additional support and outline details of such assistance in the Assessor/Observer Comments. Allow the Participant two (2) further opportunities to demonstrate the task again to allow an opportunity for a ‘Satisfactory’ assessment outcome to be achieved. - If after three (3) attempts the Assessor determines that the Participant cannot demonstrate the required steps, a ‘Not Satisfactory’ outcome is to be determined.

| TASK OUTCOME |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Date | Task Type (Tick) | Location | Task outcome (Tick) |  |
|  |  |  |  | Satisfactory | Not Satisfactory |
| Task 1 | Select Date. | Workplace Simulation |  |  |  |
| Task 2 (Occasion 1) | Select Date. | Workplace Simulation |  |  |  |
| Task 2 (Occasion 2) | Select Date. | Workplace Simulation |  |  |  |

ASSESSOR COMMENTS

As necessary, outline: - Details on reattempts, alternative arrangements or reasonable adjustments made. - Where a Participant is deemed ‘Not Satisfactory’, provide recommendations for future training.

| ASSESSOR COMMENTS: PRACTICAL TASK 2: OCCASION 1 |  |
| --- | --- |
| Individual student (as named on cover page) Multiple students [ All from Attendance Report, Specific students involved – identify students] |  |
| Task | Details |
| 2.1B. | Specify task to be completed: |
| 2.1C. | Identify tool used to analyse risks and determine controls: |
| 2.1D. | PPE worn/applied (tick or specify): Hi-viz Helmet Gloves Safety boots Eye protection Ear protection Other (please specify): |
| 2.3G. | Specify adjustments made: |
| 2.4D. | Outline recommendations made: |

| ASSESSOR COMMENTS: PRACTICAL TASK 2: OCCASION 2 |  |
| --- | --- |
| Individual student (as named on cover page) Multiple students [ All from Attendance Report, Specific students involved – identify students] |  |
| Task | Details |
| 2.1B. | Specify task to be completed: |
| 2.1C. | Identify tool used to analyse risks and determine controls: |
| 2.1D. | PPE worn/applied (tick or specify): Hi-viz Helmet Gloves Safety boots Eye protection Ear protection Other (please specify): |
| 2.3G. | Specify adjustments made: |
| 2.4D. | Outline recommendations made: |

RIICWM401E

Supervise civil works

Practical Task 1

Description of task: The participant must demonstrate undertaking the role of a civil construction supervisor and prepare a job plan which is to be carried out as part of Practical Task 2. The participant must include documentation demonstrating collating of information. If they do not have adequate existing documentation, they will be required to develop a new template for use or one from another job which illustrates the type of information they require. As part of this task, the participant is required to demonstrate the skills and knowledge to: - access, reading and correctly interpreting work documentation to ensure all work to be completed is compliant - identify and address potential risks, hazards and environmental issues, and implement control measures including selecting and wearing site appropriate PPE - consult with team members to confirm the task requirements - organise for the acquisition and availability of required resources - implement a job plan that meets task requirements Tasks are at the Assessor’s Discretion, but detail of tasks undertaken must be recorded in the Assessor’s Comments (on the back of the Practical Assessment cover page).

Resources required: Work team, work site, organisational policies, standard operating procedures and plans, safety processes, hazard and risk assessment documents relevant to the area of work, Project plans and specifications, EMP, TMP, Engineering survey, Testing schedule requirements, relevant SDS for any chemicals used as part of the work task being assessed.

| When completing the task, did the Participant: | Tick if satisfactorily completed. Provide comments if left unticked. |
| --- | --- |
| 1 Human resource requirements |  |
| A clear and accurate overall number of workers required to undertake the construction task. |  |
| Identify appropriate types of workers required for the task (e.g. skilled or unskilled labour, concreters, carpenters, road crews). |  |
| 2 Plant and machinery requirements |  |
| Identify appropriate types of plant and machinery required to complete the task, and justification their selection. |  |
| Identify the plant and machinery requiring a trained or licensed operator and any legislative document or note providing this information. |  |
| Identify how plant and equipment will be procured for the job and what procedures will be followed to undertake this (e.g. hire company, plant hired after requisition form submitted to the site engineer and accounts officer). |  |
| 3 Construction materials requirements |  |
| Interpret site plans and specifications to identify the types of construction materials to be used. |  |
| Apply accurate calculations of material quantities to be used during the task showing areas, volume or tonnage and wastage factors from plan requirements and engineer requirements. |  |
| Identify the total value of materials to be used. |  |
| Document contingency planning in place regarding ordering materials from alternate suppliers. |  |
| 4 Sub-contractor support requirements |  |
| Describe the requirement for all sub-contractor to undergo induction training prior to entering site. |  |
| Identify key personnel that sub-contractors will refer to. |  |
| Provide documentation from site including schedules or charts identifying: - The use of sub-contractors over a given period of time - Plans of drawing of work to be completed by sub-contractors - Sub-contractor induction records - Organisational chart indicating who sub-contractors will report to |  |
| 5 Waste disposal requirements |  |
| Identify relevant state authority acts, regulations, codes of practice and standards relating to waste removal (e.g. Environmental Protection Act). |  |
| Identify and explain how materials will be removed from site (e.g. Will they be taken to landfill, decontaminated). |  |
| Describe any specific organisational requirements for waste disposal.(as applicable). |  |
| 6 Coordination requirements |  |
| Identify and describe tasks that occur simultaneously on the job plan. |  |
| Accurately identify the time required to undertake the main construction steps. |  |
| Identify the persons required to monitor to different aspects of the project. |  |
| 7 Activity scheduling |  |
| - Clearly identify the overall length of time assigned to the project and significant milestones from production schedules, construction sequence drawings, Gannt charts or similar. |  |
| - Sequence steps effectively with an efficient use of time. |  |
| 8 Materials delivery scheduling |  |
| Clearly identify the key delivery dates for materials to be used. |  |
| Identify the locations for site deliveries. |  |
| Clearly explain the types of trucks, plant and machinery used during the materials delivery process. |  |
| 9 Risk assessment and management requirements |  |
| - Describe methods for prioritising risks onsite (e.g. using risks calculators, incident reports). |  |
| - Describe the processes involved with respect to deciding upon control measures. |  |
| 10 Occupational health and safety requirements |  |
| - Identify appropriate safety personnel for the site and their roles in the safety system. |  |
| - Provide examples of how hazards may be identified on site through inspections, conducting on going risk assessments, checking reports. |  |
| - Explain the reporting requirements for hazards and incidents on site. |  |
| - Identify the requirements for all workers on site to undergo site specific inductions. |  |
| - Explain procedures for identifying non-hazardous and hazardous materials. |  |
| - Explain procedures for handling substances/ materials onsite (e.g. SDS). |  |
| - Explain the site evacuation procedure including meeting points using the site evacuation plans. |  |
| - Identify and explain the location of firefighting and first aid equipment. |  |
| - Identify and explain the roles of emergency personnel on site (e.g. Fire warden, Chief fire warden). |  |
| 11 Quality management requirements, including testing scheduling requirements |  |
| - Identify the tolerances applicable to the civil construction task from plans and specifications. |  |
| - Determine from specifications and schedule testing milestones, the types of testing required. |  |
| - Identify the personnel required to monitor and confirm testing. |  |
| 12 Traffic management requirements |  |
| - Identify exclusion zones, signage and barriers required for the project from the traffic management plan. |  |
| - Document the personnel required to implement and monitor the traffic management plan. |  |
| 13 Environmental requirements |  |
| - Identify and document how noise, erosion, water quality, waste disposal, flora and fauna and cultural heritage artefacts/ sites were intended to be controlled on site. |  |
| 14 Task monitoring requirements |  |
| - Identify the persons required to monitor to different aspects of the project. |  |
| - Provide production charts, toolbox meeting schedule, briefing note, emails, charts diagrams or work instruction requirements for addressing issues with safety/performance. |  |
| 15 Task performance monitoring requirements |  |
| - Provide example documents including production charts, briefing note, emails, charts diagrams or work instruction indicating milestones or timeframes for the construction, organisation charts/diagrams or notes. |  |
| 16 Communication requirements |  |
| - Identify how regularly toolbox meetings occur on site. |  |
| - Explain the procedures for recording attendance and topics during toolbox meeting (agenda, sign on sheets). |  |
| - Identify communication technology which may be used onsite. |  |
| 17 Reporting requirements |  |
| - Document milestones and reporting requirements including reporting to who. |  |

RIICWM401E

Supervise civil works

Practical Task 2 (2X)

Description of task: The participant must demonstrate undertaking the role of a civil construction supervisor on two (2) occasions. Occasion 1 of this task will relate to the plan prepared in Practical Task 1. During this task, the participant the participant must display the skills and knowledge to effectively, safely and efficiently: - prepare to supervise civil works - prepare team members to execute task - facilitate a pre-start meeting to issue clear and timely instructions to team members and others involved - set out tasks as required for the effective completion of the civil works - while overseeing the execution of tasks: - monitor task performance for safety effectiveness and efficiency - initiate adjustments to civil works practice and job plan and ensure safe execution of work and achievement of required outcomes - oversee plant equipment and tools maintenance and confirm maintenance requirements are carried out and recorded according to manufacturer and site requirements - oversee work area clean up and approved waste disposal including recycling - report on the execution of tasks - complete and submit written and verbal reports - recommend required changes to conform task execution meets job requirements Tasks are at the Assessor’s Discretion, but detail of tasks undertaken must be recorded in the Assessor’s Comments (on the back of the Practical Assessment cover page).

Resources required: Work team, work site, organisational policies, standard operating procedures and plans, safety processes, hazard and risk assessment documents relevant to the area of work, Project plans and specifications, EMP, TMP, Engineering survey, Testing schedule requirements, relevant SDS for any chemicals used as part of the work task being assessed, all materials, tools, plant or equipment required to complete the task, required PPE and relevant safety equipment.

| When completing the task, did the Participant: | Tick if satisfactorily completed. Provide comments if left unticked. |  |
| --- | --- | --- |
|  | 1st Occasion | 2nd Occasion |
| 1 Prepare to supervise civil works |  |  |
| - Identify the location of the site using appropriate project plans. |  |  |
| - Determine the scope of the work task from plans and specifications. |  |  |
| - Determine and address potential risks, hazards and environmental issues and implement control measures. |  |  |
| - Select and wear PPE suited to site and tasks. |  |  |
| - Consult team members regarding resource requirements for task. |  |  |
| - Communicate with other supervisors/ team leaders to resolve coordination requirements. |  |  |
| 2 Prepare team to execute task |  |  |
| - Facilitate a pre-start meeting with team and others involved. |  |  |
| - Confirm resources required for task are acquired and available for task execution. |  |  |
| - Communicate clearly and concisely when sharing work instructions. |  |  |
| - Include sub-contractors in pre-start meeting and treat sub-contractors as part of the team. |  |  |
| - Discuss site safety, emergency and risk management procedures. |  |  |
| - Read project plans, specifications, site operational requirements such as those relating to location, or special types of construction. |  |  |
| - Explain any specific organisational, client and site requirements from site plans, specifications, geological, geotechnical data. |  |  |
| - Identify specific council, state or federal requirements for the site including those relating to finishes, quality, reporting and safety. |  |  |
| - Consider and explain any possible construction problems (or lack of), regarding the type of rock found onsite. |  |  |
| - Consider and explain any possible construction problems (or lack of), regarding the type of soil types found onsite. |  |  |
| - Identify and explain any possible above or sub-soil drainage required from relevant site plans. |  |  |
| - Clearly explain the meteorological data available for the site (rainfall, humidity, temperature and wind), and identify any issues in production (e.g. If a possibility of rain was evident), quality or safe work practices arising from the forecast. |  |  |
| - Identify key aspects of the contract for work and describe what personnel will be responsible for the work and how they will achieve this. |  |  |
| - Explain the log book, or scheduled servicing procedure for plant and machinery used on the site. |  |  |
| - Concisely explain how faulty or defective equipment will be reported and recorded onsite using example hazard identification forms. |  |  |
| - Interpret site plans or environmental plans to clearly indicate the location of site wash down facilities. |  |  |
| - Explain any environmental hazards posed from the use of plant and machinery including control measures which could be used to control these environmental hazards. |  |  |
| - Listen to and respond effectively to questions and queries. |  |  |
| - Ensure all workers understand the SWMS for the task and have signed their understanding. |  |  |
| - Ensure signs and barriers have been installed to protect work area as required. |  |  |
| - Set out task correctly from engineers’ survey pegs using plans and specifications. |  |  |
| 3 Oversee execution of tasks |  |  |
| - Watch workers undertake tasks, checking that tolerances are met as required. |  |  |
| - Monitor workers for safety concerns, making sure manual handling procedures are followed and work activities are conducted safely. |  |  |
| - Watch plant and equipment use to confirm machinery is used safely and within machine capabilities and limitations. |  |  |
| - Clearly communicates with workers regarding task execution using approved and understood communication methods. |  |  |
| - Write notes in diary if safety or compliance issues arise. |  |  |
| - Write notes of measurements made, material quality, deliveries and docket checks. |  |  |
| - Organise and make adjustments to civil works practice and job plan as required and confirm required outcomes are achieved. |  |  |
| - Confirm personnel allocated has checked that log books have been filled out and scheduled servicing has been undertaken on plant and equipment. |  |  |
| - Confirm that faulty or defective equipment is reported and recorded according to site requirements. |  |  |
| - Check that plant clean down is conducted in site wash down facilities. |  |  |
| - Oversee work area clearing and waste disposal to confirm site recycling and waste management is adhered to. |  |  |
| 4 Report on the execution of tasks |  |  |
| - Make verbal reports to relevant personnel regarding completion of stages, reaching milestones, testing required. |  |  |
| - Complete all diary entries clearly and legibly. |  |  |
| - Ensure all test results and checks are documented and stored according to site requirements. |  |  |
| - Make verbal or written recommendations regarding changes to task execution. |  |  |