## Sheet1
Element | Monday 22/1 | Tuesday 23/1 | Wedensday 24/1 | Thursday 25/1 | Friday 26/1 | Saturday 27/1 | Sunday 28/1 | Monday 29/1 | Tuesday 30/1 | Wednesday 31/1 | Thursday 1/2 | Friday 2/2
EWSS | 1x Vac truck vac out excavations & FRP | FRP | Pour | FRP bunds | Pour | Strip | Backfill around and place topsoil | Backfill around and place topsoil
Spel | 2x Labour and Duck Install Cabinet on pad | 2x Labour Install Cabinet on pad | Install Remaining grates | Grout remaining grates
RPZD slab | 2x Labour and Duck Vac out excavation and complete install of HDPE lines/Backfill | Duck and 1x Labourer Complete Backfill and trim out for Slab | FRP | Inspect and pour | Strip | locally Place top soil around
Bat cave | Loader with forks Move pieces on base and remove remaing rubbish
E-stop bollards | 1x Vac truck Excavate footings | 1x Vac truck Excavate footings | 1x Vac truck Excavate footings & Install 6 | 1x Vac truck Excavate footings & Install 6 | Install remaining bollards | Install remaining bollards
B-road | Duck & 1x Labour Excavate Service Crossing for protection Slab | 2x Labour Service Crossing Protection Slab | Duck and 2x Labour Excavate and install Drainage pipe | 1x Smooth Drum, 1x Multi tyre, Duck & 24T Ex & 3x Side tipper Backroll Existing pavement Backfill Drainage pipe Excavate Unsuitable | 1x Smooth Drum, 1x Multi tyre, 1x padfoot, 1x Water cart, 1x Grader, 24T Ex & 5x Side tipper Backroll existing pavement Excavate Unsuitable. Import Select fill Place & Compact select Fill | 1x Smooth Drum, 1x Multi tyre, 1x padfoot, 1x Water cart, 1x Grader, 24T Ex & 5x Side tipper Backroll existing pavement Excavate Unsuitable. Import Select fill Place & Compact select Fill | 1x padfoot, 1x Water cart, 1x Grader, 24T Ex & 5x Side tipper Excavate Unsuitable. Import Select fill Place & Compact select Fill | 1x Smooth Drum, 1x Multi tyre, 1x padfoot, 1x Water cart, 1x Grader, 3x Side tipper Import Select fill Place and Compact Select fill | 1x Smooth Drum, 1x Multi tyre, 1x padfoot, 1x Water cart, 1x Grader, 3x Side tipper Import Select fill Place and Compact Select fill Trim and Proof Roll Subgrade | 1x Grader, 1x watercart, 1x smooth drum,1x multi & 3x Side tippers Trim and Proof Roll Subgrade Import Base | 1x Grader, 1x watercart, 1x smooth drum,1x multi & 3x Side tippers Place and compact base layer Import base | 1x Grader, 1x watercart, 1x smooth drum,1x multi & 3x Side tippers Place and compact base layer Import base
Compound 3 | 1x Grader, 1x Padfoot Rework classified fill | 1x Grader, 1x Padfoot Rework classified fill | 1x Grader, 1x Padfoot Rework classified fill | 1x Grader, 1x padfoot & 2x Side tippers Import Classified fill Place and Compact Fill | 1x Grader, 1x padfoot & 2x Side tippers Import Classified fill Place and Compact Fill | 1x Grader,and 1x padfoot Place and Compact Fill | 1x Grader, 1x padfoot & 2x Side tippers Verge and Drain build Import classified | 1x Grader, 1x padfoot & 2x Side tippers Verge and Drain build Import classified | 1x Grader, 1x padfoot & 2x Side tippers Verge and Drain build Import classified