Project Schedule Template

Stage: Ground works

| Milestones to be completed | Piling completed read for structure to commence |
| --- | --- |
| Estimated project progress | 70% through Piling |
| Start date | 08/01/2024 |
| End date | 24/02/2024 |
| Labour start date | 08/01/2024 |
| Delivery date for materials | 08/01/2024 |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Drill holes | 10/01/2024 | 24/02/2024 | Drill Rig | 3 man |
| Install Reo cages | 11/01/2024 | 24/02/2024 | Reo | 5 man |
| Pour Piles | 11/01/2024 | 24/02/2024 | Concrete | 3 man and pump |
| Test Piles | 16/01/2024 | 23/02/2024 | Ute with computer machine | 1 man |

Contingency

| Summary of contingency | We have allowed an extra week in time for piling to be completed and have no allowance for extra piles |
| --- | --- |
| Materials needed | Reinforcement made up into cages. Concrete. |
| Labour needed | A team of 12 man onsite. |

Contingency

| Summary of contingency | Currently works are 2 days behind program due to rain. With our contingency of a week extra we are still on track. |
| --- | --- |
| Materials needed |  |
| Labour needed |  |

Stage: Structure

| Milestones to be completed | Top out to level 10. 2 pours per level with ground floor and transfer slab to be poured in 3. |
| --- | --- |
| Estimated project progress | 0% has not started yet |
| Start date | 25/02/2024 |
| End date | 25/02/2025 |
| Labour start date | 25/02/2024 |
| Delivery date for materials | 25/02/2024 |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Form Slabs | 27/02/2024 | 25/02/2025 | Ply, timber bearers, jacks ect | 15 man |
| Reo place | 27/02/2024 | 25/02/2025 | Reinforcement, ancillary | 5 man |
| Services install | 27/02/2024 | 25/02/2025 | Conduits and ancillary | 6 man |
| Pour concrete | 27/02/2024 | 25/02/2025 | Concrete | 12 man |
| Strip formwork | 27/02/2024 | 25/02/2025 | Labour | 6 man |

Contingency

| Summary of contingency | Time, we have allowed 3 days extra per cycle/level. |
| --- | --- |
| Materials needed | As noted above |
| Labour needed | As noted above |

Contingency

| Summary of contingency | Cost, we have 2% in each trade package for structure trades |
| --- | --- |
| Materials needed | As noted above |
| Labour needed | As noted above |

Stage:

| Milestones to be completed |  |
| --- | --- |
| Estimated project progress |  |
| Start date |  |
| End date |  |
| Labour start date |  |
| Delivery date for materials |  |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |

Contingency

| Summary of contingency |  |
| --- | --- |
| Materials needed |  |
| Labour needed |  |

Contingency

| Summary of contingency |  |
| --- | --- |
| Materials needed |  |
| Labour needed |  |