CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Daphne Chan |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | Click here to enter a date. |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 51 |  | Yes | No |

Assessor Comments

Order the following elements of an agreement from 1 to 4.

| Answer | Element Number | Element |  |
| --- | --- | --- | --- |
|  | 2 | Acceptance |  |
|  | 4 | Consideration |  |
|  | 3 | Intention of legal consequences |  |
|  | 1 | Offer |  |

When would an offer be considered to have lapsed?

| Answer | An offer will lapse: when the time for acceptance expires; if the offer is withdrawn before it is accepted; or after a reasonable time in the circumstances (generally the greater the value of the contract, the longer the life of the offer) |  |
| --- | --- | --- |

What happens to the offer if new terms are suggested?

| Answer | They are regarded as a counter offer which can be accepted or rejected. Once a final offer is accepted, the negotiation ends and therefore establishes the terms and conditions of the contract; and acceptance of the contract must confirm with the method prescribed by the offerer for it to be effective |  |
| --- | --- | --- |

What does it mean when a contract is supported by ‘valuable consideration’?

| Answer | One party promises to do something in return for a promise from another party Consideration is what each party gives to the other as the agreed price for the other’s promises Usually the consideration is the payment of money |  |
| --- | --- | --- |

Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

| Answer | persons suffering from a mental disability, intoxicated individuals, senile persons |  |
| --- | --- | --- |

- Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

| Answer | Parties must mutually assent to the proposed objectives and terms of a contract in order for it to be enforceable. The manifestation of the common intent of the parties is discerned from their conduct or verbal exchanges. What one party secretly intended is irrelevant if his or her conduct appears to demonstrate agreement. In a few limited cases, however, where there is no stated expression of the parties’ intent, their subjective intentions may establish an enforceable contract if both believe in the same terms of the contract. |  |
| --- | --- | --- |

Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

| Answer | Building Professionals Board |  |
| --- | --- | --- |

Under what laws are domestic building contracts regulated?

| Answer | Home Building Regulation 2014 (NSW) Section 8 Requirements for contracts to do residential building works |  |
| --- | --- | --- |

Domestic building contracts must be put in writing once the work exceeds what value?

| Answer | Section 5 Home Building Act 1989 (NSW) Thresholds for contract requirements (1)For the purposes of section 7 (1A) of the Act, the prescribed amount is: (a) For contracts entered into before 1 March 2015 - $5,000, and (b) for contracts entered into on or after 1 March 2015 - $20,000 |  |
| --- | --- | --- |

A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

| Answer | The Home Building Act 1989 no longer requires contract for work valued under $5,000 (including labour and materials), although it is recommended to have a written agreement. |  |
| --- | --- | --- |

Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

| Answer | 5 Business days |  |
| --- | --- | --- |

What are the benefits of having a written contract in place between parties?

| Answer | - Provides protection to all parties - Having the agreement fully documented provides protection to all parties. - Ensuring that owners receive the finished product they envisioned and builders get paid and paid on time |  |
| --- | --- | --- |

Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Clauses |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Acceptances | 1 - F | A | Provide specific reasons that allow the contract period to be adjusted |  |
|  | 2 | Cost adjustments | 2 - E | B | A provision for which remedies can be sought if breached |  |
|  | 3 | Extensions of time | 3 - A | C | Specifically outlines the tasks to be completed as part of the construction work |  |
|  | 4 | Payments | 4 - D | D | Outlines the requirements for deposits |  |
|  | 5 | Scope of work | 5 - C | E | Address the risk of rise/fall of expenses |  |
|  | 6 | Term | 6 - B | F | Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding |  |

Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Contract estimate |  |
|  |  | Contract request |  |
|  |  | Preliminary agreement |  |

True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

| Answer | Contract name | Description |  |
| --- | --- | --- | --- |
|  | Commercial building contracts | A lump sum contract to be used for the construction only of commercial building work with or without a Principal’s agent. |  |
|  | Commercial Cost Plus contract | A cost plus contract for use on commercial building projects, where a lump sum price cannot be established, however a fair and reasonable estimate is given. |  |
|  | New Homes Construction Contract | This plain language contract for new homes has been tailored to conform with state legislation and has a fair and balanced risk allocation. It includes both the general conditions and relevant schedules. |  |
|  | Kitchen Bathroom & Laundry Supply Install | This supply and install contract is tailored specifically for the kitchen bathroom and laundry industry |  |

Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

| Answer | Commercial Minor Works Contract for work up to $100,000 |  |
| --- | --- | --- |

Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

| Answer | Small Build $5,000 - $20,000 Large Build >$20,000 |  |
| --- | --- | --- |

Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Builder’s Licence | A licence is required for : - Residential building work valued at more than $5000 (Incl. GST) in labour and materials - All specialist work regardless of its cost. |  |
|  | Contract price | Small build: $5000 - $20000 Big build: >$20000 |  |
|  | Building approvals and inspections | Building inspections and approvals are the responsibility of a building certifier. Mandatory building inspections may be required at certain stages of construction. You can check the certifier’s licence via QBCC’s Online Licence Search |  |
|  | Practical completion and handover | You are not required to pay the final contract payment until all of the contracted work has been completed in accordance with the contract, all legal requirements, and either without any defects or omissions, or with only minor defects or minor omissions that will not unreasonably affect occupation. If you believe there are any minor defects or minor omissions, the contractor must give you a ‘defects document’ (listing agreed and non-agreed matters). This document should be compiled by you and the contractor during a handover inspection. Check your contract to see if it imposes any extra requirements on the contractor for practical completion. |  |
|  | Implied warranties | Building contracts typically contain a defect liability period in respect of building works that is usually between 12 to 24 months from practical completion of the building works. |  |

- Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Engineer specifications |  |
|  |  | Plans, drawings and specifications |  |
|  |  | Prime Cost Items Schedule |  |
|  |  | Processes for applying for extensions of time |  |
|  |  | Product catalogues |  |
|  |  | Project timelines and schedules |  |
|  |  | Provisional Sums Schedule |  |
|  |  | Rise and fall calculations |  |
|  |  | Site conditions report |  |
|  |  | Soil and sedimentation report |  |

What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

| Answer | “Prime Cost Item” means any item noted in the Prime Cost Items Schedule being an item such as a fixture or fitting (e.g. tiles or tap fittings) – (i) that has not been selected, or the price of which is not reasonably able to be ascertained, when the Contract is entered into; and (ii) for the cost of supply and delivery of which a reasonable allowance is made in the Contract by the Contractor. “Provisional Sum” means any item noted in the Provisional Sums Schedule being an amount that is an estimate of the cost of providing particular contracted services (including labour and materials) for which the Contractor, after making all reasonable enquiries, cannot provide a definite price when the Contract is entered into (e.g. the removal of asbestos materials the extent of which is uncertain). |  |
| --- | --- | --- |

Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

| Answer | apply to long-term costs and some specific costs (e.g. labour and materials, currency exchange rates for overseas-purchased goods, duties, taxes, shipping). Labour and materials. Currency exchange rates for goods purchased in foreign currency |  |
| --- | --- | --- |

True or False (Tick your response): Variations can be requested by both the client and the builder.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

| Answer | A variation in writing The contractor should issue an ‘extension of time’ form – essentially asking the client to grant you an extension of the contract period to allow for delays caused by the variations The specific reasons for an extension of time are set out in the general conditions of the building contract and include reasons such as: inclement weather and delays caused by the owner, such as changes in the scope of works You should be familiar with the General contract conditions to you know what time extensions you are entitled to over the contract period |  |
| --- | --- | --- |

Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

| Answer | Fair Trading Act NSW |  |
| --- | --- | --- |

Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

| Answer | Make reasonable inquiries about why you want to borrow the money. Make reasonable inquiries about your financial situation Take reasonable steps to verify your financial situation |  |
| --- | --- | --- |

What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

| Answer | When you buy a residential property in NSW, you have a five business day cooling off period after you exchange contracts. The cooling off periods starts as soon as you exchange contracts. The cooling off period starts as soon as you exchange and ends at 5pm on the fifth business day after exchange. You can waive the cooling off period by giving the vendor a ‘66W certificate’. |  |
| --- | --- | --- |

What are the maximum deposits recommended for a residential building project?

| Answer | For bigger jobs over $20k, where a large component of the costs is in the materials, the builder or tradesperson may ask for a deposit. Under NSW home building law, the maximum deposit you can be asked to pay is 10% |  |
| --- | --- | --- |

Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

| Answer | Deposit 5% of contract sum Base Stage 15% of contract sum Frame Stage 20% of contract sum Enclosed Stage 25% of contract sum Fixing Stage 20% of contract sum Practical Completion Balance |  |
| --- | --- | --- |

- You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

| Answer | No. For bigger jobs, where a large component of the cost is in the materials, the builder or tradesperson may ask for a deposit. Under NSW home building law, the maximum deposit you can be asked to pay is 10% |  |
| --- | --- | --- |

- Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

| Answer | Breach | Explanation |  |
| --- | --- | --- | --- |
|  | Breach of condition under contract | Breach of an essential part of the contract, which makes performance of the ret of the contract totally different from what was agreed. Consequence: can elect to discharge the contract and sue for damages |  |
|  | Breach of warranty under contract | Breach of a term of the contract which, if not carried out the basic nature of the contract is not changed Consequence: cannot elect to discharge the contract. Damages are the only remedy. |  |

What does repudiation of a contract mean?

| Answer | Repudiation occurs when a party to a contract is unwilling to perform their contractual obligations – through acknowledgement or their actions are totally inconsistent with their obligations under the contract |  |
| --- | --- | --- |

True or False (Tick your response): In the event of repudiation, the injured party has two options:

- Continue with the contract

- Accept the repudiation and move to terminate the contract

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

| Answer | A party could move to terminate a contract based on their own belief that the other party has repudiated the contract. However, if they have no legal right to terminate the contract, they may themselves have repudiated the contract and could be liable to pay damages |  |
| --- | --- | --- |

What does ‘abandonment of contract’ mean?

| Answer | contract abandonment means the parties both have conducted themselves in such a way that the original contract is no longer valid. Both parties may mutually agree to do this, or it can become part of a claim. Or a contractor fails to perform the work on a project by either not starting the project in a reasonable amount of time, or not completing the work, or failing to resume work in a reasonable amount of time. Abandonment of a construction project without legal excuse is a cause for disciplinary action. |  |
| --- | --- | --- |

A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

| Answer | A termination for cause occurs when one party stops work because of a deficiency in performance by the other party. Because the contract is terminated as a result of a party's own poor performance, the law typically provides the terminated party with little recourse in the event of a termination for cause. A termination for convenience, occurs when the owner stops work for reasons other than a deficiency in performance by the contractor. Because a termination for convenience is not the result of poor performance, the law may provide the aggrieved contractor with significant rights against the breaching owner. |  |
| --- | --- | --- |

Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

| Answer |  | Yes |  |  |
| --- | --- | --- | --- | --- |
|  |  | No |  |  |

If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

| Answer | The notice is not required to be ain nay particular form, but should contain the following details: - What must occur to perform the contract - A reasonable time in which the contract must be completed - A statement of the consequences of not performing in accordance with the notice |  |
| --- | --- | --- |

True or False (Tick your response): Where the notice given (as per Q39. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

| Answer | The client is not required to pay the final contract payment until all of the contract work has been completed in accordance with the contract, all legal requirements, and either without any defects or omissions, or with only minor defects or minor omissions that will not unreasonably affect occupation. If the client believes there are any minor defects or minor omissions, the contractor must give them a ‘defects document’ (listing agreed and non-agreed matters). This document should be complied by the client and the contractor during a handover inspection. |  |
| --- | --- | --- |

Explain the concept ‘conditions for completion at the cost of the contractor’.

| Answer | Defects after completion The Contractor must make good defects or omissions in the work under this Contract which become apparent within 6 months of the Date of Practical Completion. If there are any such defects or omissions, the Owner must give the Contractor written notice to make good such defects or omissions within the 6 month period and must give the Contractor reasonable access to the Site for that purpose. Subject to reasonable access being provided, the Contractor must within 28 calendar days of the notice being given rectify any defects notified to the Contractor during usual business hours. |  |
| --- | --- | --- |

Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

| Answer | The person’s name and contact details (i.e. business address, phone number, email address, if any) |  |
| --- | --- | --- |

Name one (1) person you should consult if you are considering ousting a contractor from a building site.

| Answer | A legal advisor |  |
| --- | --- | --- |

What document should you refer to if you are considering ousting a contractor from a building site?

| Answer | You should apply the dismissal procedure outlined in the contract |  |
| --- | --- | --- |

How should you handle a customer complaint?

| Answer | - Deal with the complaint immediately - Stay calm - Identify the problem - Decide what can be done - Arrange a second opinion to confirm your view - Keep records - Fix the problem BPB, Fair Trading NSW |  |
| --- | --- | --- |

How do you reduce the risk of dispute?

| Answer | Both the contractor and owner should: Carefully read and understand the contract Check any associated plans and specifications before signing Discuss questions with contractor and seek legal advice if needed |  |
| --- | --- | --- |

What is the process for dispute resolution?

| Answer | Firstly the client should advise their contractor in writing giving them a reasonable time to respond. If this doesn’t resolve the problem the home owner can contact the regulator (Fair Trading NSW) to explore their legal options. Its critical that the home owner engages a practising solicitor before terminating the contract. Incorrect termination may have serious legal and financial consequences and reduce the Home Owner’s Home warranty protection. |  |
| --- | --- | --- |

- During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

| Answer | Hi Client, Thanks for your email. Referring to the white goods and chattels list we agreed in the contract and the materials order and the receivable order sheets, the bath we installed complies with what is in the contract. Could you please have a look of the pertinent parts of the contract and specification and let me know if there is anything is mistaken? Thanks. Regards, Builder |  |
| --- | --- | --- |

Where would you find any possible penalties associated with a build?

| Answer | Liquidated Damage Clauses |  |
| --- | --- | --- |

Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

| Answer | It is obtained once the final inspection has been inspected and passed. Arrange an on-site inspection with the client perhaps a week before the date nominated for handover. This gives you a final opportunity to address any remaining issues prior to handover One item you will receive prior to practical completion, is the Building Code Assessment Summary (which is similar to a Certificate of Classification) from the Building Certifier which grants the right of occupancy to the building owners/users. The project sponsor and building owner(s) receive a copy of this document, which must be kept available for inspection. Approvals for building work must be obtained from a building certifier (formerly known as a ‘building surveyor/inspector’), who can be either a local government building certifier or a private certifier. |  |
| --- | --- | --- |

- Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:

  - The land has been secured and paid for by the Clients.

  - Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.

  - Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured.

  - Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list.

  - The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.

  - The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.

  - Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build.

  - The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.

  - The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.

  - The construction period excluding inclement weather and possible delays is 23 weeks

  - Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).

  - Prime costs are required for the solar hot water system and ducted air conditioning

  - Provide fictitious details for all other sections of the contract.

  - 18 solar panels are to be installed on the roof

| Answer |  |  |
| --- | --- | --- |