## Version history
DATE | VERSION
04 March 2024 | V01
15 July 2024 | V02
05 May 2025 | V03

## Discrepancies
PROJECT | 1990 Gold Coast Highway, Miami QLD
DATE COMPLETED | 2025-05-05
COMPLETED BY | Alder Constructions
| DISCREPANCY | REASONS FOR DISCREPANCY | HOW TO GET BACK ON TRACK
LABOUR COSTS
Superannuation | 862.5 | Increased labour due to site delays | Improve scheduling and allocate resources effectively.
Payroll | 7500 | Increased labour due to site delays | Improve scheduling and allocate resources effectively.
Leaves | 2700 | Unplanned leave during peak construction. | Develop a leave management plan to mitigate impact.
Training | 2000 | Additional training sessions required. | Schedule training during non-peak hours and in advance to avoid delays.
Development | 2800 | Upskilling needed to specialised tasks. | Regularly evaluate traning needs and adjust as necessary.
TOTAL | 15862.5
MATERIAL COSTS
Purchasing | 272000 | Over-budget due to market flucatuations. | Conduct market research and negotiate fixed pricing with suppliers.
Transportation | 1500 | Delays in transportation impacting schedule. | Optimise logistics and establish clear timelines with suppliers.
Storage | 900 | Extended storage needs from project delays. | Streamline project timelines to minimise storage duration.
Plant rental | 3200 | Higher demand for equipment rentals. | Book equipment in advance and evaluate rental agreements.
Equipment rental | 2400 | Unexpected breakdowns leading to extended rentals. | Implement a maintenance schedule to prevent equipment failures.
TOTAL | 280000

## Actual
| MONTH 1 | MONTH 3 | MONTH 3 | MONTH 4 | MONTH 5 | MONTH 6 | MONTH 7 | MONTH 8 | MONTH 9 | MONTH 10 | MONTH 11 | TOTAL
LABOUR COSTS
Superannuation | 11953.8613 | 15703.6088 | 14018.3977 | 14446.3954 | 14446.3954 | 11953.8613 | 14018.3977 | 14018.3977 | 14446.3 | 14018.3977 | 16942.6671 | 155966.68
Payroll | 103946.62 | 136553.12 | 121899.11 | 125620.83 | 125620.83 | 103946.62 | 121899.11 | 121899.11 | 125620 | 121899.11 | 147327.54 | 1356232
Leaves | 0 | 0 | 14615.3846 | 3846.1538 | 34615.3846 | 8092.3 | 0 | 36280 | 7569.369 | 11975.26 | 3846.15 | 120840.002
Training | 0 | 3500 | 0 | 0 | 900 | 1800 | 0 | 3300 | 0 | 0 | 0 | 9500
Development | 0 | 6250 | 950 |  | 3800 | 1500 | 0 | 0 | 2300 | 0 | 0 | 14800
TOTAL | 115900.4813 | 162006.7288 | 151482.8923 | 143913.3793 | 179382.6101 | 127292.7813 | 135917.5077 | 175497.5077 | 149935.6689 | 147892.7677 | 168116.3571 | 1657338.682
MATERIAL COSTS
Purchasing | 64848.36 | 594764.48 | 961852.08 | 1138008.5 | 800224.5454 | 1486222.38 | 612000.78 | 1377600.58 | 412260 | 899635.45 | 455052.84 | 8802469.9954
Transportation | 600 | 1500 | 5000 | 2350 | 2800 | 3150 | 2670 | 4400 | 1500 | 2100 | 1430 | 27500
Storage | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 609.0909 | 6700
Plant rental | 82940.3636 | 82940.3636 | 91568 | 97300.65 | 96522.98 | 98698.31 | 104765.57 | 112654.32 | 108971.2 | 82940.36 | 15741.88 | 975043.9973
Equipment rental | 1980 | 2989.36 | 4785.23 | 3005.96 | 2645 | 2645 | 2645 | 1985.78 | 2065.45 | 1985.78 | 1182.44 | 27915
TOTAL | 150977.8145 | 682803.2945 | 1063814.4009 | 1241274.2009 | 902801.6163 | [6 empty] | 9839628.9927

## Estimated
ESTIMATED
LABOUR COSTS
Superannuation | 155104.18
Payroll | 1348732
Leaves | 118140
Training | 7500
Development | 12000
TOTAL | 1641476.18
MATERIAL COSTS
Purchasing | 8530470
Transportation | 26000
Storage | 5800
Plant rental | 971844
Equipment rental | 25515
TOTAL | 9559629