Revised WHSMS Implementation Plan

1. Policy and Commitment

- Objective: Ensure clear communication and commitment to WHS at all levels of the organization.

- Action Steps:

  - Involve employees in developing the WHS policy to foster ownership.

  - Communicate the policy through multiple channels (meetings, intranet, posters).

  - Align the WHS policy with Kent’s strategic goals to maintain relevance and engagement.

- Timeline: 1 month

- Responsibility: Senior management, HR, WHS team

- Key Performance Indicator (KPI): 90% of employees acknowledge understanding the WHS policy.

2. Planning and Objectives

- Objective: Develop achievable, SMART safety goals based on risk assessments.

- Action Steps:

  - Conduct risk assessments to identify workplace hazards.

  - Break down large, broad objectives into smaller, manageable milestones.

  - Establish action plans for each milestone with clear timelines and resources.

- Timeline: 1-2 months

- Responsibility: WHS team, Department heads

- KPI: Achieve 75% of identified milestones within the first quarter.

3. Implementation and Operation

- Objective: Ensure roles, responsibilities, and resources are effectively assigned and operational controls are in place.

- Action Steps:

  - Define and communicate WHS responsibilities for all levels.

  - Assess resource needs regularly to ensure adequacy (staff, equipment, budget).

  - Implement a continuous training program with refresher courses.

  - Prepare emergency response procedures and conduct regular drills.

- Timeline: 3 months, with ongoing training

- Responsibility: WHS team, Operations, HR

- KPI: 100% staff trained in emergency procedures within the first 3 months.

4. Monitoring and Evaluation

- Objective: Continuously track WHS performance and adapt based on findings.

- Action Steps:

  - Set up automated reporting systems for incidents, hazards, and near-misses.

  - Perform regular workplace audits and inspections.

  - Track WHS performance using specific KPIs (incident rates, training completion).

  - Investigate all incidents and near misses promptly, with corrective actions.

- Timeline: Ongoing

- Responsibility: WHS team, Safety officers

- KPI: 100% of incidents investigated within 48 hours.

5. Management Review and Continuous Improvement

- Objective: Regularly review WHS performance and ensure continual improvement.

- Action Steps:

  - Hold quarterly management review meetings to discuss WHS data and performance.

  - Use data-driven insights to make adjustments to WHS policies and processes.

  - Set strict deadlines for implementing review outcomes and track progress.

- Timeline: Quarterly reviews

- Responsibility: Senior management, WHS team

- KPI: 100% of action items from reviews implemented within specified deadlines.