| Project # | 912-1 |  |  |
| --- | --- | --- | --- |
| Project | Vantage Yatala |  |  |
| Project Address | 60 Stapylton Jacobs Well Road, Stapylton 4207 QLD |  |  |
| Customer |  |  |  |
| Reporting Period | November |  |  |
| Project Manager | Malcolm Johnson |  |  |
| Contracts Administrator | Kelly Chen |  |  |
| Date | 22/11/2021 | Time | 8:30am – 10:00am |
| Site Meeting # | 4 |  |  |

Attendance List

| Name | Initials | Role | Attendees | Apologies |
| --- | --- | --- | --- | --- |
| Malcolm Johnson | MJ | Project Manager | ☒ | ☐ |
| Kelly Chen | KC | Contracts Administrator | ☒ | ☐ |
| Greg Donaghey | GD | Construction Manager | ☒ | ☐ |
| Troy Whalan | TW | General Manager | ☒ | ☐ |
| Alan Kelly (GDP) | AK | Civil Engineer Gassman | ☒ | ☐ |
| Mitchel Gassman | MG | Civil Engineer Gassman | ☐ | ☒ |
| Jacques Swanepoel | JS | Landscape Architect Gassman | ☐ | ☒ |
| Kris Bovenis | KB | PECE | ☐ | ☒ |
| Leanne Shea (SEE) | LS | Civil Project Manager | ☒ | ☐ |
| Stuart Yaxley (SEE) | SY | Operations Manager | ☒ | ☐ |
| Peter Hesaie (SEE) | LS | Civil Project Manager | ☒ | ☐ |
| Craig Williams | CW | Senior Site Supervisor | ☐ | ☒ |
| Emily Conlon | EC | Project Administrator | ☒ | ☐ |

Distribution List

| Name | Company | Role |
| --- | --- | --- |
| Leanne Shea | SEE Civil | Project Manager |
| Peter Hesaie | SEE Civil | Project Engineer |
| Malcolm Johnson | FPG | Project Manager |
| Kelly Chen | FPG | Contracts Administrator |
| Alan Kelly | GDP | Civil Engineer |
| Finn Rowe | SEE Civil | Construction Manager |

| - PROGRAM OVERVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Description | Status | Action By | Due Date |
| - HEALTH, SAFETY & ENVIRONMENT |  |  |  |  |
| Item | Description | Status | Action By | Due Date |
| 2.1.1 | Current Status - Health & Safety |  |  |  |
|  | - No Incidents to date in November | Note |  |  |
| 2.1.2 | Current Status – Environment |  |  |  |
|  | - X1 CPESC Inspection - Two Council Inspections Complete – SEE closed out report to GDP. | Note | SEE SEE |  |
| 2.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
| 2.2.2 | Key Issues to be Addressed – New Action Items |  |  |  |
| - Legal and Statutory Building Approvals |  |  |  |  |
| Item | Description | Status | Date Required | Comments |
| 3.1.1 | Current Status - Schedule of Statutory Building Approvals |  |  |  |
| 3.1.2 | Current Status - Authorities/Utilities |  |  |  |
|  | CoGC – Watermain relocation | Approved | 1st Dec 2021 | Live Connection Application has been submitted. |
|  | CoGC – Sewer Rising Main changes | Not approved | 1st Dec 2021 | Sewer to be put in 25/11. Drawings not IFC yet – Council RFI responded. New rising main required for northern side. GDP pushing GCWW to approve on both design and pricing. |
|  | Energex – Road Corridor Permit approval required by TMR | Approved |  | Complete. |
|  | NBN – Road crossing alteration approval. Scope is now clear. Ventia pricing works for PECE were on site. SEE Civil to check if cable has enough slack to move onto replacement pole prior HV switch. | Not approved | 1st Dec 2021 | Service has been removed. |
|  | Telstra – Relocation | Approved | 1st Dec 2021 | SEE to contact Skyring Civil. |
|  | Telstra and APA – Lowering and working around main (Telstra 1.5 weeks – cables to be moved to allow welding of gas main) | In progress | 1st Dec 2021 | APA to Manage |
|  | APA – 10 days programme TB. | Not approved | 01/12/2021 | RCP submitted. SEE to accelerate programme by commencing stage 2 earlier in order to meet the 01/12 date. Services locating and topsoil stripping started. Traffic management requirements not yet received from APA. MJ to discuss on any delay due to recent weather event. |
| 3.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
| 3.2.2 | Key Issues to be Addressed – New Action Items |  |  |  |
|  | Water Meter – 13 Emeri Street along SJW Rd – survey with GDP. |  | GDP |  |

| - Design |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Description | Status | Action By | Due Date |
| 4.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
|  | Zebra crossing at external intersection as per DTMR requirements – TMR have requested larger island – design in progress. DTMR comments received 27/04. | In progress | GDP | 01/12/2021 |
|  | Topsoil stockpile on site currently at 23,000m3. Treatment of lots confirmed – no topsoil. Polymer to be sprayed. Excess discussed leave as is in stockpile. Look at placing additional thickness. Started pulling batters on big lots. Need permanent design for clean water drain. Discussed topsoil and hydromulch on upper part of drain and topsoil and turf on lower part of drain. | Approved | FPI |  |
|  | Western Boundary Acoustic fence complete. Issue with gap behind fence, SEE to close 2x gaps. | Works in progress | SEE |  |
|  | REHAU (Awshaft) option approved by Council as a trial. SEE to propose two concrete pits to be substituted for Awshaft pits for approval by Council, to be installed as trial. | In progress | SEE |  |
| 4.2.2 | Key Issues to be Addressed – New Action Items |  |  |  |
|  | Totem Poles at SJW Road Entry – colour has been approved. | In progress | SEE/JS |  |
|  | GDP reviewing design of batter next to concrete columns on eastern boundary lot 114. No changes required from Structural Engineer perspective. Proceed as per design. | Approved | GDP | ASAP |
|  | Signage – FPI to provide shop drawings to suppliers. Letter sign on gabion wall/boulder wall with rock face. No illumination required for the estate sign. SEE to provide a quote for building the wall (excl. rock face) and footing design and sign off by structural engineer. MJ to send through details for stone facing. | FPI | FPI |  |
|  | Fairway Street Redesign to be sent to SEE - Change application with Council – should have redesign in 2 weeks |  | GDP/FPI |  |
| - FINANCIALS |  |  |  |  |
| Item | Description | Status | Action By | Due Date |
| 5.1.1 | Current Status - Current and Outstanding Progress Claims |  | Description |  |
| PC-001 | Dec 01 | Approved |  |  |
| PC-002 | Jan 02 | Approved |  |  |
| PC-003 | Feb 03 | Approved |  |  |
| PC-004 | April 04 | Submitted |  |  |
| 5.1.2 | Current Status - Current and Outstanding Variation Claims |  |  |  |
| VAR-001 | Pot size change to 140mm on Philodendeon Xanadu | Approved |  |  |
| VAR-002 | Western Boundary Fencing Works | Submitted | FPI |  |
| VAR-003 | Sewer Changes (Internal/Pump Station) | TBC | SEE |  |
| VAR-004 | Pump Station & Lower rising main (GCWW) | Submitted | GDP |  |
| VAR-005 | Pedestrian Crossing | TBC | GDP/FPI |  |
| VAR-006 | Electrical Road Crossing | TBC | SEE |  |
| VAR-007 | Hester Boundary Fence | Option 2 Approved | SEE |  |
| VAR-008 | Balance Fill Stage 1 to Stage 2 | Submitted | GDP |  |
| VAR-009 | Redesign Lot 120, 121 and 122 | TBC | SEE |  |
| VAR-010 | Delimb Tree for Overhead Powerlines | Approved |  |  |
| VAR-011 | Changes to earthworks | TBC | SEE |  |
| VAR-012 | Unsuitable Materials Replacement | TBC | SEE |  |
| 5.1.3 | Current Status - Current and Outstanding Provisional Sum Claims |  |  |  |
| PC-001 – ($5,000) | GCWW Supervision – water connection Emiri Street |  |  |  |
| PC-002 – ($5,000) | GCWW Supervision – sewer connection | No longer applicable. Works incl in variation |  |  |
| PC-003 – ($7,500) | GCWW Supervision – water connection SJW Road |  |  |  |
| PC-004 – ($18,200) | Seeding | 140,000m2 (13c) |  |  |
| PC-004 – ($42,750) | Hydromulch | 75,000m2 (57c) |  |  |
| 5.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
| 5.2.2 | Key Issues to be Addressed – New Action Items |  |  |  |
|  | Level 1 testing PEER review. Morrison said no. Waiting on construction science response. If not, need to go back to Douglas Partners. SEE to speak to ASCT if they have someone who can do an independent review. Construction sciences sending someone to site, waiting from confirmation from lawyer. |  |  |  |
| - PROGRAMME |  |  |  |  |
| Item | Description | Status | Action By | Due Date |
| 6.1.1 | Current Status - Programme Summary |  |  |  |
|  | Topsoil was 95% complete at EOM and BEW was 51% at EOM Feb. |  |  |  |
|  | Updated status programme |  |  |  |
| 6.1.2 | Current Status - Current and Outstanding EOT Claims |  |  |  |
|  | EOT-001 3 days wet weather (19/01, 20/01 & 21/01) | Approved |  |  |
|  | EOT-002 2 days wet weather | Approved |  |  |
|  | EOT-003 2 days wet weather | Approved |  |  |
|  | EOT-004 1 day wet weather | Approved |  |  |
|  | EOT-005 31 days delay HV switching | Submitted – Resubmit as Rev 1 with revised switching date of 26/11. | SEE |  |
|  | EOT-006 1 day wet weather | Approved |  |  |
|  | EOT-007 9 days wet weather | Approved |  |  |
|  | EOT-008 4 days wet weather | Submitted |  |  |
| 6.1.3 | Current Status - Risk and Opportunities |  |  |  |
| 6.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
|  | Further delays to overhead powerline relocation due to Covid | HV switch date 26/11 | SEE |  |
| 6.2.2 | Key Issues to be Addressed – New Action Items DTMR bonding to be submitted by end of July. APA works should be finished by then. APA – 6 week period seems length. Risk on not obtaining RCP on time. Invoice/ Agreement not yet received. Council uncompleted bonds – Internal Civil UCW bonds approved. AK to forward, only raise the bonds in July. LS to send through Rev 10 |  |  |  |
| - PROGRAMME |  |  |  |  |
| Item | Description | Status | Action By | Due Date |
| 7.1.1 | Current Status - Subcontractor Letting Status |  |  |  |
| Trade | Subcontractor | Status |  |  |
| Landscape | Interface Landscapes | Awarded |  |  |
| Electrical | SAE Group | Awarded |  |  |
| Shotcrete | Marine Civil | Awarded |  |  |
| FRP | Onyx | Awarded |  |  |
| RCP Supply | Humes | Awarded |  |  |
| Fencing | Ford Brothers Fencing | Awarded |  |  |
| Quarry Materials | Hanson | Awarded |  |  |
| Concrete Supply | Nielsen’s | Awarded |  |  |
| PVC and DICL Supply | Clover | Awarded |  |  |
| 7.1.2 | Current Status - Upcoming Major Lettings |  |  |  |
|  | Boulder Walls Asphalt |  |  |  |
| 7.2.1 | Key Issues to be Addressed – Action Items from Previous Meeting |  |  |  |
| 7.2.2 | Key Issues to be Addressed – New Action Items |  |  |  |