Assessment Workbook 5

BSB51415 Diploma

of Project Management

Integration Management

Version 1.01 Produced 18 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following assessment validation. | 1.0 |
| 18 October 2018 | Version 1.01 Change to Practical Assessment | 1.01 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Case Study	5

Instructions to Student	5

Introduction	6

Workbook Checklist	17

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 5 |  |  |
| --- | --- | --- | --- |
| TITLE: | Integration Management |  |  |
| FIRST AND SURNAME: | Todd Seymour |  |  |
| PHONE: | 0424263664 |  |  |
| EMAIL: | Todd.Seymour@hotmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Todd Seymour |  | Signature: | Date: 13/08/20 |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant advisor to the project team at Awesome Landscapes Pty Ltd. Specifically you are required to provide independent advice on seeing their current project through the entire life cycle. You have already provided advice to them in the previous four workbooks. The project manager has advised the project is now complete, and is about to archive all the project documentation. Your task is to evaluate the supplied project documentation and to ensure all due diligence has been completed. You will need to compare the project plan with the previous version to ensure it is ready for closure. Project Charter version 4 (.pdf) Project Plan version 4 (.pdf) Project Gantt Chart version 4 (.mpp) Project Gantt Chart version 4 (.pdf) Project Network Diagram version 4 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- Sam has asked to you check the Project Plan for anything that is missing. He has been very busy but appears to have done all the necessary finalisation of the plan ready for sign off. He has mentioned the final report or lessons learnt documentation has not been included, and the project archiving checklist have not been completed either. You will be assigned to complete these later. Examine the Project Charter (version 4) and Project Plan (version 4) and identify four (4) things that are missing. Guidance: - Assume the Project Gantt Chart and the financial figures in the summary/detailed costing tables are up to date as these have already been audited. Also remember this final project plan is in draft, and will not be signed off until the final acceptance meeting in a few days’ time. - Take note of the following: - Version control. - The updates from the project in the other workbooks you have completed in previous workbooks. - Check the project archiving checklist for everything that should be included

- Appendix 30 - Workaround planning worksheet - Appendix 31 - Project risk review matrix - Appendix 35 - Work authorisation form - Appendix 36 - Quality audit

- Sam is in the process of developing a set of Lessons Learnt Documentation for the project. - Access and review the four (4) previous workbooks you have completed and derive three (3) different lessons learnt throughout the project. - Document each lessons learnt using the Lessons Learnt Documentation Template provided. Use one template for each lessons learnt.

| Lessons Learnt Documentation Template 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Todd Seymour |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 12/05/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 002 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Upfront costs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | To ensure contracts are in place |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | No upfront deposit was written into the contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Potential cash flow problem resulting in a change request |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Upfront deposit prior to work commencing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Contract negotiations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure Awesome Landscapes request a deposit prior to a project starting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Calculate the upfront costs of pipeline projects. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure contracts clearly define deposit requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Todd Seymour |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 12/05/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 003 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Project conflict |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | To ensure contractors are aware of who they will be working with |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | When Massive folded, the new project sponsor had a poor relationship with one of the contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Wasted time having to source new contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | To have a reputable contractor already in place |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Having a reputable contractor already in place |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To ensure everyone is aware of the other companies/contractors involved with a project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Background checks on all contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To carry out background checks on all contractors prior to commencment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure any contractors involved in the later stages of a project have no conflicts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Todd Seymour |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 12/05/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 004 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Employee resignations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | To ensure morale is high and work is plentful |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | After Massive folded employees were uncertain of their future with Awesome. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | 2 employees resigned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | It would have been preferred that the former employees did not resign |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Reassuring the employees their roles were secure. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure team morale is high and the company has pipeline projects to fall back on. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor employee morale and pipeline projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To ensure multiple projects are on the books. Communicate with all staff. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communicating with staff and chasing further projects. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Sam has asked you to write the final report for the project. Complete the final report using the template below, assuming the things missing from the project plan in the question above have been included. Guidance: - Access and carefully review the project documentation you were provided with along with the case study scenario and populate all the fields with the required information. - Provide a date that is later than the last date in the Project Gantt Chart version 4. - Assume that this report will be submitted to Terrence Mackay, Stephen Lyons, Kate Chan, and Kim Nguyen. - Provide a brief summary of the project in terms of the four project constraints (Scope, Cost, Time, and Quality). - Provide a detailed summary of the project covering the functions of project management listed below. Further guidance is provided for you within the template.

| Project Name: | Cascade Peak Chalets Landscaping Project |  |  |
| --- | --- | --- | --- |
| Prepared by: | Todd Seymour |  |  |
| Date: | 12/05/2017 |  |  |
| Project Summary |  |  |  |
| Scope (What was included and excluded) |  |  |  |
| Inclusions: Remove the vegetation from site, Construct the gravel access roads, Build the retaining walls including the 3 additional walls, Maintain road, monitor erosion and existing trees, excavate for utilities and septic system, Maintain removed plants, divert the stream and construct drainage, convert roads to paths, erect signage, general landscaping including boulders, soil prep and weed eradication, Planting works, Oversee and manage the project through its lifecycle. |  |  |  |
| Exclusions Planting of new trees and removal of existing trees, Sealing of roads and construction of footpaths, bridges and culverts, Supplying any electrical services, Planting around retaining walls, Erosion around buildings in construction, maintaining the main road, additional retaining walls, Onsite security, Decorating of the chalets, Installation of utilities, Pipework or infrastructure for the septic system, Replacing plants from stage 1 that have perished, Resort road construction, hand rail construction, Signage design, Chalet pot plants, Ongoing maintenance, Purchase and planting of exotic planting, Planting maintenance plan. |  |  |  |
| Cost (Budget vs. actual) |  |  |  |
| $650,000/$514,892 |  |  |  |
| Time (Estimate vs. Actual) |  |  |  |
| 12-04-2017/ 12-04-2017 |  |  |  |
| Project Report Submitted to: |  |  |  |
| Name: Terrance Mackay |  | Title: General Manager, Cascade peak hotel | Date: 12/05/2017 |
| Name: Stephen Lyons |  | Title: Planning Manager, Cascade peaks shire council | Date: 12/05/2017 |
| Name: Kim Nguyen |  | Title: Director, Awesome Landscapes | Date: 12/05/2017 |
| Name: Kate Chan |  | Title: Project Manager, Timber home construction Ltd | Date: 12/05/2017 |
| Analysis of Project Guidance: - Process Review - Describe all of the processes used during the planning, implementation and closure stages. - Lessons Learnt - Describe what went right and or what went wrong and how effective were the management and the processes you used. If necessary, state how you overcame any problems. - Recommendations – Make recommendations as a result of the lessons learned. |  |  |  |
| Scope |  |  |  |
| Process Review - Collect requirements - Define scope - WBS - Verify scope - Control scope |  |  |  |
| Lessons Learnt Scope inclusions and exclusions must be well defined at the beginning of the project but must also adapt to the project as variations occur. I believe these were presented well within the project plan and adapted well when required. |  |  |  |
| Recommendations Continue to ensure the client clearly understands what the project entails. |  |  |  |
| Time |  |  |  |
| Process Review - Develop schedule - Control schedule |  |  |  |
| Lessons Learnt Developing the intial schedule and on going monitoring of how a project is tracking must be as accurate as possible. I believe this was done as well as it could have been given the issues regarding the project sponsor. |  |  |  |
| Recommendations During future projects, continue to monitor schedules and communicate with the project team. |  |  |  |
| Cost |  |  |  |
| Process Review - Estimate cost - Determine budget - Control cost |  |  |  |
| Lessons Learnt Costs must be estimated, determined and monitored as accuratly as possible but also adapt as project scope does and as variations occur. Given the project delivered a healthy profit, i believe this was done well and adapted when required. |  |  |  |
| Recommendations Continue to price as accuratly and competitively as possible. Ensure future projects request a deposit prior to work comencing. |  |  |  |
| Quality |  |  |  |
| Process Review - Quality assurance - Quality control |  |  |  |
| Lessons Learnt QA and QC must be performed to help ensure the product is up to the required standard. I believe the client had no problems with the product that Awesome delivered therefore this appears to have been done well. |  |  |  |
| Recommendations Continue to ensure the products Awesome deliver are of the highest quality. |  |  |  |
| Human Resources |  |  |  |
| Process Review - HR planning - Performance management - Employee relations |  |  |  |
| Lessons Learnt Awesome landscape need to ensure employees are happy in their role and team morale remains high. Awesome also needs to ensure planning is always taking place on pipeline projects. This was done reasonably well despite 2 employees resigning due mainly to events out of Awesomes control. The employees on hand were able to perform as required. |  |  |  |
| Recommendations Work on having pipeline projects in place. |  |  |  |
| Communications |  |  |  |
| Process Review - Plan communications management - Manage communications - Control communications |  |  |  |
| Lessons Learnt Clear lines of communication need to be maintained between project sponsors, steering committees and project team members. These processes were carried out well due to Awesome employing an external consultant to assist the project manager. |  |  |  |
| Recommendations Consider employing 3rd party consultants for large future projects |  |  |  |
| Procurement |  |  |  |
| Process Review - Plan procurement - Conduct procurements - Administer procurements - Close procurements |  |  |  |
| Lessons Learnt Ensure appropriate contracts are in place and sub contractors are paid when due. Ensure contractors deliver what was promised. |  |  |  |
| Recommendations Contract administration are to double check sub contractors have been paid on time. |  |  |  |
| Risk |  |  |  |
| Process Review - Risk management framework |  |  |  |
| Lessons Learnt Risk management must be of high importance. Associated plans must be implemented and evolve as the project does. This appears to have been done well and as a result, no incidents occurred during this project. |  |  |  |
| Recommendations Continue to identify and control risks as appropriate on future projects. Ensure applicable documents are kept current. |  |  |  |
| Project Integration |  |  |  |
| Process Review - Scope management - Time management - Cost management - Quality management - HR management |  |  |  |
| Lessons Learnt Ensure scope, time, cost, quality and HR all intergrate nicely. This was done well despite the problems with Massive. |  |  |  |
| Recommendations Review lesson learnt reports |  |  |  |

- Sam has approved the report in the above question to be distributed. He has also updated the project plan following your advice. Now he is ready for the project closure meeting. He has assigned you the task of organising this meeting. Answer the questions that follow.

- Who will attend this meeting? Guidance: List the attendees by name, job title, and organisation).

Terrence Mackay - General Manager - Cascade Peak Hotel Pty Ltd Stephen Lyons - Planning Manager - Cascade Peak Shire Council Kate Chan - Project Manager - Timber Home Construction Ltd Kim Nguyen - Director – Awesome Landscapes Pty Ltd Sam Ng - Project Manager – Awesome Landscapes Pty Ltd

- What information will each person need before the meeting?

A time and place for the meeting to take place as well as up to date project documentation.

- Which documents (and which version number of each document) will need to be printed off for the meeting?

- Project completion report - Project plan - Project archives checklist - Formal acceptance and closure All documents are to indicate final version.

- Which of these documents will require signatures?

The completion report, project plan, formal acceptance and closure

- Who will need to sign off on these documents?

Each member of the steering commitee

- Do you believe the project objectives aligned with the objectives of Awesome Landscapes throughout the entire project life cycle? Explain your answer.

Though the outcome and finished product is something that aligns with the objectives of Awesome Landscapes, I am quite sure the colapse of massive and the ensuing problems that caused would not be inline with Awesomes objective.

- What needs to be done after the meeting to complete the closure of the project?

Archiving of applicable documents.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document