## SUB-CONCTRACTOR RECORD
#35742 - FERRY RD GAMING REFURB
QUOTING SUB-CONTRACTOR RECORD
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
ELECTRICAL
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE $ | NOTES | ASSIGNED TO
| KTM Solutions | Ken McCoombes - 0412 884 671 ken@ktmsolutions.com.au | 2022-07-15 | 2022-08-01 | 17,280 exl GST | 15/7- Ken called wanting to put through a quote for Rockingham and I advised Megan was looking after that project (emailed Megan to let her know). I let Ken know that I was sourceing quotes for Ferry Rd, which he was interested in quoting for too. 18/7- Called and he hasn't read scope yet but can meet on site 19/7 @ 11:30am 22/7 - Spoke to Ken, is on track to send back quote by end of next week. 27/7-Sent follow-up email 28/7- Ken asked if he could get quote back on Monday (1/8) 23/10 - BC issued WO. Still need to email Ken updated plans and Electrical Schedule | BC
PLUMBING
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| Paradise Plumbing | Brad 0422 302 191 admin@plumbergc.com.au | 2022-11-08 |  |  | 07/11 waiting for Quote to come through 09/11 sent quote variation 11/11 Quote approved and confirmed by Ed | SR
JOINERY - Mark - Core4 making vaiety bases
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| Realhome | Dustin | 2022-11-07 |  |  | 07/11 quote received and WO sent
JOINERY - GAMING BASE COMPANIES
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| DESIGN GROUP PTY LTD | Bill - 0449 804 991 bill@designgroup.net.au Adam- 0420 982 122 akrdesigngroup@gmail.com https://www.designgroup.net.au/ | 2022-08-03 | 2022-08-04 |  | 3/8 - Spoke to Bill, sounded very interested. Seemed professional. Currently 4-6 weeks to manufacture. He mentioned that there is a big gaming event in sydney that. Will email him scope. (Actually have a base in GC as of a few months ago). 3/8 - Replied to my email about colour recommendations 4/8 - Received quote and example images of bases . Clarified some details over phone. 4/8- Emailed Tom's Tavern Quote Req. 4/8 - Bill and David spoke (Bill was enthusiastic and eager to do works) 5/8 - I emailed Bill full joinery scope agian for both Ferry Rd and Tom's Tavern including extra details for both works' vanities. (5/8 - Bill sent Gaming base quote for Tom's Tavern) 10/8- Bill emailed revised quote for Ferry Rd. 19/8 - Received final Quote (David Happy with). 20/8 - Issued Work order. 13/10- called left vm to revise quote - send email 15/10- I emailed requesting a revised quote and advised of gaming rm works dates. 21/10- called and reissued quote request. 22/10 - BC Issued WO via ServiceM8. (BC confirmed with Adam and Bill that it was received)
PAINTING
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| Babis & Painters | 07 5537 5470 Dimitri - 0415 847 959/ (0459 927 991) babisthepainter@gmail.com | 2022-07-13 | 2022-07-30 | 16,000 exl GST | 13/7- Spoke to Dimitri and they are still taking on work and should be able to meet on site Tues (need to confirm). 15/7- I called to confim site visit time. Arranged to meet at midday on 19/7. 22/7 - Called to follow-up and is hoping to put together a quote this weekend. 27/7-Emailed follow-up email 29/7- Asked Mirko to call Dimitri to Follow-up. 19/10 Called to follow-up on revised SOW emailed to them on 17/10. No answer, left message 20/10- BC spoke to Dimitri and he said he would go out on Saturday 22/10 and provide extra Quote for Bistro. He said he could still do work. 25/10-BC- Called left v/m. Re-isssued Quote request to include extra Bistro & External works. 26/10- BC Spoke to Dimitri and he will email Quote tonight. 27/10- DW called, and Dimiti will provide today.
TILING - Completed by Alfred Core4
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| City Coast Tiling | 07 5529 0049 cct@citycoasttiling.com.au | 2022-07-13 | 2022-07-18 | 2469 | Did Runaway Bay works 15/7- I called and spoke to Kylie. Email hasn't been looked at yet but it should be something they can do. Will likely not visit site but will email a quote. Asked to email quote by 15/7. 18/7- Received Quote. 21/10 Phoned and they advised to send a email to estimator@citycoasttiling.com.au. Will follow up Monday
| Gold Coast Tiling | 0400 836 453 alan@goldcoasttiling.com.au | 2022-07-13 |  |  | 15/7 - Called & left VM 18/7- Called again.
| Heazlewood Tiling and Cladding Service | 0412 886 684 murray@seqtilers.com.au | 2022-07-13 |  |  | 15/7- Called & Left VM. Murray called back and isn't interested in quoting.
| Fix a tile | 07) 5564 9229 |  |  |  | 15/7- Called but they are Not interested
| Square Tiling | Chris Padua - 0422 227 985 chris@squaretiling.com.au | 2022-07-15 | 2022-07-19 | 1902.3 | 15/7- He said we would sms me his email and would call on Monday arvo to schedule in to a time to meet Tues. 15/7 - sms'd me and said he will look over the scope on the weekend. He would like to visit Site but would like to confirm a time closer to the day. 18/7 - Is aiming to make it to site around 11am 19/10 Emailed to confirm details and send through revised SOW 20/10 Phoned and he is no longer available. May be available the first week of December
SAIL - Advised by Ed - David is looking after this
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| Sailmaker Shade Sail Designs | Brendon - 0447 023 791 brendon@sailmaker.com.au | 2022-07-13 |  |  | 13/7- Spoke to Brendon & he gave email. Does not visit sites to give quotes! 15/7 - I called to follow-up, left VM
| Ryan's Shade Sails (Formally: Shade Sails Gold Coast) | 07 5606 6778 Nic - 0479 110 322 ryansshadesails@gmail.com | 2022-07-13 | 2022-08-02 | 19170.91 | 13/7- Spoke to Karla & she gave email 14/7 - Nik can meet on site 19/7 @midday - will bring swatches. 22/7 - Called to follow-up, left v/m. 26/7- Called left v/m 27/7- Sent follow-up email 29/7-Called and finally got through (they have been away) and will send quote by Monday. 1/8- called again, spoke to Nic asked to send through by EOD 13/10 - called left vm 12/10- Spoke to Karla, lead time 6wks, will speak to Nic about price. will get back to me by tomorrow. 20/10 - UNABLE TO DO WORK
| Coastwide Shade Sails | 07) 5563 1124 / Tony-0412 404 410 | 2022-07-13 | 2022-07-19 | 11636.36 | 13/7 - I left VM. Tony sms's back and said he would look forward to seeing my email. 15/7- I Called to follow-up, Left VM 15/7- called office, no aswer 18/7- Tony called and can meet on site 19/7 around 11:30am 26/10/ - BC called to check they're availability is 6-8 wks. and they could potentially be without a sail for 3wks.
| Versatile Structures | Zach - 07 3271 4519 / 0407 633 188 estimating@versatilestructures.com Dave - 0478 095 970 dave@versatilestructures.com | 2022-07-15 | 2022-07-29 | 45023 | 15/7 - Spoke to Zach and should be able to quote but is unable to meet on Tues but could go Wed. (I said he could always faceTime me while he is on site - just needs to tell me a time so I can let VM know). He said he would need 2-3 weeks to manufacture! 26/7- Dave visited site this morning and I spoke with him while he was there. He said he could provide a quote for the privacy screen as well. He also said he would need 8 weeks to manufacture now! 27/7-Sent follow-up email. He emailed quote but had no pricing. (He will re-send). 29/7- Received Cataloges for shade colour and structure colour. TOO EXPENSIVE
Versatile Structure - Shade Colour options: Prefer at lease a dark grey (Concrete colour), dirt won't be as obvious.
| Amanzing Shade Pty Ltd | 1300 123 742 |  |  |  | 13/7- Spoke to reception & left details but wasn’t given any contact details to send Quote request to! Poor Customer Service - Prefer not to use
| Absolute Shade | 0419 641 851 sales@outdoorshadesails.com.au |  |  |  | 1/8- Called, Doesn’t specialise in commercial. Suggested Add Shade in Nerang.
| Add Shade | Dan -0423 749 486 dan@addshade.com.au |  |  |  | 1/8-Called spoke to Dan - he actually makes the shades for other people but he said he might be able to help find someone that could do the work & to send the scope through to him. 21/10- BC, Spoke to Dan and he may be able to help. Emailed Quote request 22/10- Texted Dan to check he received email 24/10 Called but no answer, will try later today 26/10- BC-spoke to Dan and he said he can still potentially do works and will send collate quote (based on aluminium posts).
| Urban Play | Ben (Director) - 0403 340 415 ben@urbanplay.com.au |  |  |  | 21/10- BC, Called and emailed Quote Request to see if he could do the work. 24/10 Left VM to return call 26/10-BC called, Ben Said he wouldn't be able to work with these timings. but will let me know when he could do this. Ben called back - rough price 36K, won't be able to do sail till Jan.
| M & M Tarp | 07 3245 3660 0411 753 542 |  |  |  | 21/10- BC called left vv/m
CLEANER
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| QCS Clean | Jazz Salaria - 0415 310 777 Service@qcsclean.com.au | 2022-07-14 | 2022-07-22 | 2850 | 14/7 - Jazz replied and said he could quote and can meet on 19/7 @10:30am 09/11 WO sent through
CARPET
STATUS | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE QUOTE REC. | QUOTED PRICE | NOTES | ASSIGNED TO
| FLOORING XTRA | Colin Morley: 0412 208 808 colin.morley@flooringxtra.com.au Steven Thomson: 0456 624 194 steven.thomson@fxaus.com.au Mike Matthews: 0419 732 243 |  | 2022-10-14 | 80900 | 15/10-WO issued
LEGEND
Emailed Scope but have not heard back yet
Emailed Scope and Sub-contractor would like to Quote
Emailed Scope and have received Sub-contractor's Quote
Emailed Scope and Sub-contractor unable to Quote
Emailed Scope and Sub-contractor potentially could Quote
Scope / QR not sent
Quote Accepted & WO Issued

## WO'S iSSUED
35742 - FERRY RD WORK ORDERS ISSUED
ISSUED | TRADE | AWARDED TO | DATE WO ISSUED | NOTES | ASSIGNED TO
| ELECTRICAL | KTM Ken - 0412 884 671 ken@ktmsolutions.com.au | 2022-10-23 | BC issued via Service M8 Still need to email updated plans & Electrical Schedule | BC
| JOINERY - GAMING BASES & SCREENS | DESIGN GROUP Bill - 0449 804 991 bill@designgroup.net.au | 2022-10-22 | BC issued via Service M8 | BC
| JOINERY - GENERAL | Realhome - Dustin - male amenities partition | 2022-11-09 | Mark Boxall will be manufacturing the joinery, laminate is ordered | SR
| TILING | Core4 - Alfred |  | Alfred will be doing the tiling | SR
| PLUMBING |  |  | Sourcing alternate quote from Paradise plumbing | SR
| PAINTING | BABIS Dimitris - 0415 847 959 babisthepainter@gmail.com |  | SR has emailed WO to Babis | SR
| CARPET | Flooring Xtra- Yatala Colin - 0412 208 808 colin.morley@flooringxtra.com.au | 2022-10-15 | BC issued via Service M8 Bistro Carpet Choice - Interstellar put on hold | BC
| DOSA SAIL |  |  | WE will demo existing framework, then send to True Metal Solutions to make a new frame. Once reinstalled, Dan from ADD Shade will measure and manufacture new sale shade | SR
| CLEANING | QCS Jazz | 2022-11-09 |  | SR
| SKIP BINS | Skip Bins Gold Coast |  |  | SR
| STORAGE CONTAINER | Royal Wolf |  |  | SR

## SUPPLIERS RECORD
#35742 - FERRY RD GAMING REFURB
QUOTING SUPPLIERS RECORD
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE $ | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
GAMING BAR
FEATURE LIGHTS
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE $ | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
| Astrid / Cal Beacon Lighting - Windsor 07 3861 1644 | Mayfair Luella LED - 1500mm Pendant in Black with Alabaster Shade SKU 039279 | 2 | $3742.50 $1871.25/ pendant | 5 bus days to get to store |  | 21/7 - Currently 100 in stock Trade price honoured but need to sign up. 19/10 phoned and in stock 21/10 Ordered and paid for by CC. 7/11/22 PICKED UP | SR
SPLASHBACK TILES
| National Tiles | Masia Navy Blue Gloss | 12.8sqm | $99.95sqm | 14 days |  | 8/11 Ordered. 14 Day turnaround as they are in VIC and it will take 10 days to come to the warehouse then 4 to be sent to Virginia shop. We will pick up
BAR APRON FLOOR TILE
| Unica- 07 3831 6611 | Select- Lead - R10 (310x620mm) | 10.8 sqm | $60sqm | 2-3 days |  | 22/7- in stock. R10 19/10- updated to 10.8sqm of tiles 19/10 - phoned and currently in stock. 08/11 Ordered.
BARTOP
Now using cement look top - Mark installing
WATER DISPENSER
| ALL SO COOL Shaun Ossowski so@allsocool.com.au 0418 719 604 | 75044365 | 1 |  |  |  | Supply & Install new ‘Beer-look’ Ambient Water Dispenser & font to Gaming Bar- (see plans for location) 24/10 Sent email to provide quote. 31/10 - Confirm with Ed height of tap. 300mm? | SR
BOTTLE SHELVING
Timber cladded alcohol bottle stand (2 tiers in total on benchtop). 28/7-Asked Ed who they ended up using for Walrus. Was done in-house by Mark.
BAR FAÇADE SKIRTING
| DMK Forest Products Ashmore | Metal/laminate bar strip - gold | 150mm H x 8m L | $740 for 2400mm x 1200mm sheet | 1-2 days |  |  | Ready for pick up
GAMING AMENITIES
BASINS
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | Luna Inset Basin (without tap landing) Code: 153100 | 2 | 335.43/ each | 2 week lead |  | 25/7- Emailed Tradelink about availability and lead time. 26/7- Received Quote. Pick-up from Enoggera 21/10 Ordered - put on our account | SR
PLUG & WASTE
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | PLUG & WASTE POP UP URBANE II BSH/BR Code: 195972 | 2 | 40.16/ each | 2 week lead |  | 21/10 Ordered - put on our account 24/10 Paid for with Credit Card | SR
MIXER
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | Urbane II Mid Tower Basin Mixer - Brass (Code: 196095) | 2 | 411.94/ each | 2 week lead | 2 week lead | 25/7- Emailed Tradelink about availability and lead time. 21/10 Ordered - put on our account 24/10 Paid for with Credit Card | SR
VANITY BENCHTOP | [8 empty] | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed
| Core4 | Caesarstone, Pure White 1141 (or Intense White 6011). | 2 |  |  |  | 02/11 Ed sorting out with Mark - doing laminate
TOILET PARTITION - MALE GAMING AMENITIES ONLY | [8 empty] | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed | WALL TILES- potentially needed
| REALHOME Terry - 0422 136 745 terry@realhome.net.au Dustin@realhome.net.au | Male toilet door and partition | 1 |  |  |  | NEED TO CONTACT Waiting for final measurement of male toilet. Ed to provide when he attends 2/11 02/11 Sent email to Dustin to provide quote and timeframe 03/11 Dustin will send through quote on Monday 7/11 | SR
WALL TILES- potentially needed
LOUNGE AREA / POKIE ROOM
PENDANT LIGHTS
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE $ | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
| Living Styles | Bonura Ribbed Glass Pendant Light, Large, Smoke SKU: LSPR-ID7481463 | 14 | Total= 1981.82 | 3 days dispatch + 10 days del |  | 21/7 - Currently 20+ Available- Quote emailed 28/10 Ordered lights and they said 2 week delivery via Australia Post 09/11 Being delivered by Australia Post 1-2 days 14/11 Arrived | SR
WALL PANELLING
| VJ Panel | [5 empty] | Provided from AVC PowerPOint Finishes Confirm colours 14/11 Arroved at Ferry Rd 15/11 Arrived and sent invoice to Erika to process
Wallpaper
| Murray Interiors -Mitchelton Roie/ Andrea 07 3355 7888 showroom@murraysinteriors.com.au | (Natty & Polly) Celebration - Blue/ Silver Code: 388182 | 16 rolls | 2,480 incl GST | 2-3 wks |  | 30/9- emailed for quote Wall 1 – 16m L x 3.4m Ht Wall 2 – 11m L x 2.65m Ht 1/10- Roie received email and will find out and get back to me in a few days. 17/10 - Received quote but wallpaper area amount has reduced. 19/10- Emailed Andrea with revised wallpaper areas required: Wall 1 – New Gaming Rm Wall (above Dado): 16m L x 2.2m Ht Wall 2 - Keno Lounge wall (Full-Ht): 5.5m L x 2.65m Ht Wall 3 – Amenities Corridor wall (above Dado): 6mL x 1.45mHt 19/10- Received revised quote. Asked Andrea to send through invoice so we can place order. 20/10 Wallpaper ordered and paid for in full with CC. Inv attached to Service M8 | BC/ SR
DADO
| Bunnings | 58 x28mm 3.6m Moulding White Pine Primed Flat Dado Rail
DOWELL CLADDING FOR BAR FAÇADE, ISLAND COLUMNS & FEATURE WALLS IN GAMING ROOM
| EXAMPLE IMAGE PROVIDED BY AVC | Metal/laminate bar strip - gold | 150mm H x 8m L
| Modinex 1800 156 455 Charlton - 0466 016 773 zachary@modinex.com.au | Hemlock 81 x 26 30LM x 2.9 length |  | 24275.5 |  |  | 26/7- Spoke to Logan and emailed him some detials. We would still need to install. 27/7- Charlton called and will email me - he needs the ht and wall lengths required. 27/7 - Emailed details but asked if he could measure the straight and curved North walls off the plans. 28/7- Called, left v/m - asked to send quote back by EOD Mon 1/8. 1/8- Emailed Charlton, asking for quote by EOD 1/11 Emailed Zachary to provide quote 02/11 Received invoice. Approved by Ed for payment and sent to Susan. Will once once paid 02/11 Paid for and ordered
OR
| Bunnings?? | Half Dowell trim |  |  |  |  | 29/7- Emailed Mark to see how long this would take to construct/ cost to do this in house. 1/8 - Mark Suggested contacting Lachlan, VSH Timbers - 0431 535 460
CARPET - Gaming
| Colin Morley Flooring Xtra Commercial 19 Computer Road Yatala Qld 4217 07 3382 7571 0412 208 808 colin.morley@flooringxtra.com.au | Brintons: The Collective - Stocked range- BLOOM |  |  |  |  | 12/10 - Spoked to Colin. (14weeks for Brintons -Indian Waterlily, custom carpet). Emailed to check availability. 13/10- Lucy agreed to BLOOM carpet pattern. 14/10 - Steven from Flooring Xtra called and I verbally told of carpet selection and dates and would send through WO soon. 15/10- WO issued (still waiting for Bistro Carpet selection from Lucy) | BC
DOSA
WALL LIGHTS
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE $ | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
OR
| Enlightened-living brisbane@enlightened-living.com.au https://enlightened-living.com.au/product/thurso-oval/ Shafli - 07 3607 7858 | Astro - Thurso Oval Outdoor Wall Light Code: 1376006 | 4 | 349/each incl. GST | 2-5 weeks |  | 29/7- Lead time of 2-4 weeks (can be up to 5 wks) This includes delivery. Curently Astro has 1000 units in stock. 21/10 Called and no answer will try again Ordered and paid for 15/11 Phoned to check on delivery. Will arrive at warehouse on 22/11 in Sydney plus 5-7 days to be delivered to us | SR
HEATER
| Bromic Matt - 0410 329 267 02 9426 5222 mattk@bromic.com bretts@bromic.com Brett Stewart - 0474 035 914 | Tungsten Electric 3000W wall mounted heater in Black (1410mmL x 214mm Ht) | 1 | 3000W $961.20 ex GST 6000W $1102.50 ex GST |  |  | 27/7- Called, no answer-left v.m / called office to check Matt still best contact (Yes). 27/7-Emailed quote request. (He called back but hasn't checked email- he will email me). 28/7- Brett called and suggested a 6000w or I suggested potentially x2 3000w. Sent plans through. 21/10 Called in stock. Updated prices extra $50 for freight. 28/10 Ordered and paid for | SR
CUSHION MATERIAL OPTIONS
| Parry & Williams Ray - 07 3269 3234 ray@parrywilliams.com.au sales@parrywilliams.com.au | [5 empty] | See attached collage for options. Fabricoptions from: 1. Profile Fabrics - Ash 2. Profile Fabrics – Crop 3. Warwick- Lawaki Indigo 4. Warwick – Barossa -Denim 5. Warwick – Barossa -Lead BC- emailed Lucy possible selection. Still pending Lucy's decsion. 26/10- Josie @AVC picked Option 3. Warwick - Lawaki Indigo 31/10 SR TO order 01/11 - Megan has placed order, P& W checking stock and will confirm but they have 33m in stock, should be ok 08/11 SR rang and they hadn't heard back from Ed. They will ring Ed today to confirm details
NEW PRIVACY SCREEN
[7 empty] | MEGAN TO SOURCE We have left over slat panels at the office, True Metal Solutions have provided a quote but will adjust according to what we have in stock, waiting for ED to confirm dimensions then will place order | MS
BISTRO AMENITIES
BASINS
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | Luna Inset Basin (without tap landing) Code: 153100 | 5 | with 20% |  |  | 1/11 phoned Tradelink who will ring back today to see what price they can do for us 02/11 Paid and Ordered 14/11 Picked up
PLUG & WASTE
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | PLUG & WASTE POP UP URBANE II BSH/BR Code: 195972 | 5 | 35.33 inc gst |  |  | 1/11 phoned Tradelink who will ring back today to see what price they can do for us 02/11 Paid and Ordered 14/11 picked up
MIXER
| Tradelink - Enoggera 07) 3513 5000 john.rushe@tradelink.com.au | Urbane II Mid Tower Basin Mixer - Brass (Code: 196095) | 5 |  |  |  | 1/11 phoned Tradelink who will ring back today to see what price they can do for us 02/11 Paid and Ordered 14/11 Picked up
SKIRTING TILE
BISTRO
CARPET
STATUS | COMPANY | PRODUCT DESCRIPTION | QTY | PRICE | LEAD TIME | IMAGE | NOTES | ASSIGNED TO
ORDERED on hold | Colin Morley Flooring Xtra Commercial 19 Computer Road Yatala Qld 4217 07 3382 7571 0412 208 808 colin.morley@flooringxtra.com.au | Brintons, Centauri-Interstellar |  |  |  |  | WO sent 26/10- Josie from AVC decided on Brintons, Centauri-Interstellar. 27/10- (BC) Colin confirmed selection is available and has put capet on hold. Gave install date of Early morning 29/11. | BC
LEGEND
AVAILABLE
QUOTE RECEIVED
ORDERED
READY TO COLLECT FROM SUPPLIER
READY AT OFFICE
PENDING APPROVAL
NEEDS TO BE ORDERED

## ORDERED STOCK REGISTER
35742 - REGISTER OF ORDERED SUPPLIES (Items purchased by Core 4)
Location | Item Ordered | Qty Order | Company | Date ordered | Delivery Due Date | Expected place of Delivery / pick-up location | Arrived
Mitchelton | Wallpaper Celebration 388182 Blue/Silver | 16 | Murrays Interiors | 2022-10-20 | They will ring | 4 Osborne St Mitchelton | Picked up
Enoggera | Luna Inset Basin Code 153100 | 2 | Tradelink | 2022-10-21 | They will ring | Pickering St | Arrived
Enoggera | Plug & Waste Pop Up | 2 | Tradelink | 2022-10-21 | They will ring | Pickering St | Arrived
Enoggera | Urbane11Mid Tower Basin Mixer | 2 | Tradelink | 2022-10-21 | They will ring | Pickering St | Arrived
Windsor | Mayfair Luella LED Pendant in black | 2 | Beacon | 2022-10-21 | They will ring | Across the road | Arrived
Heater | Bromic 3000W Heater | 1 | Bromic |  |  | Delivered 02/11 | Delivered
Received
PROBLEM

## PAINTING SCHEDULE
Job #35742- FERRY RD REFURB PAINTING SCHEDULE
GAMING ROOM
AREA | COLOUR | PRODUCT DESCRIPTION | COLOUR SWATCH | NOTES
*Wall & Ceiling Colour *VJ Panelling | Dulux, Rimaldo - SG5C8 |  |  | Provided from AVC PowerPoint Finshes
Feature wall colour | Dulux, Blue Steel S39 |  |  | Final Colour provided by Lucy
Bulkhead | Dulux, Fossil Grey SN3 |  |  | Final Colour provided by Lucy
*Bulkhead *Bar Blade *Accent - Where? | Dulux, Simone Weil - GR20 |  |  | Provided from AVC PowerPoint Finshes
*Skirting & Trim | Dulux, Tranquil Retreat - GR24 | ?? |  | Provided from AVC PowerPoint Finshes Dark skirting to match monument
GAMING ROOM - MALE & FEMALE AMENITIES
AREA | COLOUR | PRODUCT DESCRIPTION | COLOUR SWATCH | NOTES
WALLS | Dulux - Natural White (SW1F4)
CEILINGS | Dulux - Ceiling White
BISTRO AREA & BISTRO BAR
AREA | COLOUR | PRODUCT DESCRIPTION | IMAGE | NOTES
WALLS | Dulux - Dieskau (SN4H1) |  |  | 26/10- Josie from AVC provided colour choice.
CEILINGS | Dulux - Lexicon Half (SW1G2)
EXTERNAL WALLS - 'CREAM' COLOUR WALLS ONLY
AREA | COLOUR | PRODUCT DESCRIPTION | IMAGE | NOTES
WALLS | Colour Match existing

## LIGHTING SCHEDULE
35742- Ferry Rd Gaming Refurb LIGHTING SCHEDULE
GAMING ROOM
LOCATION | PRODUCT | QTY | IMAGE | NOTES
Bar feature pendants | Mayfair Luella LED - 1500mm Pendant in Black with Alabaster Shade From Beacon Lighting | 2 |  | Ordered and paid for
Lounge & Gaming area Pendants | Bonura Ribbed Glass Pendant Light, Large, Smoke SKU: LSPR-ID7481463 | 14
Ceiling Downlights | Recessed ceiling Downlights | 37 |  | Replace existing
Bar - underside of benchtop? | LED Strip lighting?
DOSA - GAMING ROOM
LOCATION | PRODUCT | QTY | IMAGE | NOTES
Wall-mounted | Astro - Thurso Oval Outdoor Wall Light Code: 1376006 | 4
Wall-mounted | Tungsten Electric 3000W wall mounted heater in Black (1410mmL x 214mm Ht) | 1

## SUMMARY OF QUOTING SUBBIES
#35742 - FERRY RD GAMING REFURB
SCHEDULE OF TRADES MEETING ON SITE - Tues 19/7/22
ELECTRICAL
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Electrik Avenue | Warren Limbach, Director- 0447 747 444 | 10:30 | Will be attending with Terry
2 | KTM | Ken - 0412 884 671 | 11:30
3 | Oceanside Services | Andrew Hall 0412 285 302 andrew@oceansideservices.com.au | 14:00 | Plumbing division arriving at same time.
PLUMBING
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Electrik Avenue | Terry - 0456 785 762 | 10:30 | Will be arriving with Warren
2 | Oceanside Services | Mike Bartle 0435 931 464 mike@oceansideservices.com.au | 14:00 | Electrical division arriving at same time.
3 | Capital Plumbing | Lincoln (Office # 07 5619 2305 ) | 12 - 2pm
PAINTING
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Babis & Painters | Dimitri - 0415 847 959 | 12:00
Platinum Painting & Decorating interested but can't make to site today. Will email initial quote by end of week.
Spuce it up Painting can't make it to site today but may be able to quote off plans.
TILING
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Square Tiling | Christopher - 0422 227 985 | 11am | Not available now
2 | City Coast Tiling- Already Received Quote |  |  | Provided quote
SAIL
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Ryan's Shade Sails | Nik- 07 5606 6778 / 0479 110 322 | 12:00 | Not available now
2 | Coastwide Shade Sails | Tony - 0412 404 410 | around 11:30
Versatile Structures can't make it to site but may be able to go in Wed 20/7 and facetime while there.
CLEANERS
# | COMPANY | CONTACT DETAILS | TIME MEETING | NOTES
1 | Cleaning Solutions | Kate - 1300 610 099 | 11:30am
2 | QCS Clean | Jazz Salaria - 0415 310 777 | 10:30am
RUNNING SCHEDULE
10:30 | Electric Ave - Warren and Terry
QCS - Jazz
11am | Square Tiling - Chris
11:30 | Cleaning Solutions Brisbane - Kate
KTM - Ken
around 11:30 | Coastwide Shade Sails - Tony
12:00 | Ryan's Shade Sails - Nik
Babis Painters - Dimitri
12- 2pm | Capital Plumbing - Lincoln
14:00 | Oceanside - Andrew (Elec) & Mike (Plumb)

## PAINTING FINISHES
Job #35742- FERRY RD REFURB PAINTING SCHEDULE
GAMING ROOM
AREA | COLOUR | COLOUR SWATCH | NOTES
*Wall & Ceiling Colour *VJ Panelling | Dulux, Rimaldo - SG5C8 |  | No response from Lucy to go ahead with this colour
*Bulkhead *Bar Blade *Accent - Where? | Dulux, Simone Weil - GR20 |  | No response from Lucy to go ahead with this colour
Feature wall colour | Dulux, Blue Steel S39 |  | Colour chosen my Lucy
*Skirting & Trim | Dulux, Tranquil Retreat - GR24 |  | No response from Lucy to go ahead with this colour
GAMING ROOM - MALE & FEMALE AMENITIES
AREA | COLOUR | COLOUR SWATCH
WALLS | Dulux - Natural White (SW1F4) |  | Colour chosen my Lucy
CEILINGS | Dulux - Ceiling White |  | No response from Lucy to go ahead with this colour
BISTRO AREA & BISTRO BAR
AREA | COLOUR | IMAGE
WALLS | Dulux - Dieskau (SN4H1) |  | Colour chosen my Lucy
CEILINGS | Dulux - Lexicon Half (SW1G2) |  | Colour chosen my Lucy
EXTERNAL WALLS - 'CREAM' COLOUR WALLS ONLY
AREA | COLOUR | IMAGE
WALLS | Colour Match existing

## TILE FINAL FINISHES
Job #35742- FERRY RD REFURB TILING SCHEDULE
GAMING ROOM BAR
PRODUCT DESCRIPTION | QTY | TILE PATTERN | IMAGE | Notes
Customer mood board
Splashback tiles Masia Navy Blue Gloss National Tiles | 12.8sqm |  |  | These were Lucy's choice, they are $99.95 sqm with two week turn around 14/11 estimated time to the warehouse is 24/25/11. Advised we want to pick up from warehouse
Bar Apron Floor Tile Select- Lead - R10 (310x620mm) dark grey grout | 10.8 sqm | Running lay |  | Unica Phoned and they are available to pick up
Skirting tile Simplicity dark grey natural tile 300 x 600 |  |  |  | Lucy suggested dark grey - monument possible choice is $39.95/sqm Arrival at Virginia to be picked up 16/11