CPCCBC4005A

Produce labour and material schedules for ordering

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4005A Produce labour and material schedules for ordering cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Lauren McKew |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Lauren McKew |
| --- | --- |
| Participant signature |  |
| Date | 19/04/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 30 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Concrete Suppliers | Civil Contractor |  |
|  | Steel Manufacturers | Plumber |  |
|  | Sanitary Fixture Suppliers | Electrician |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | Contractors may not always be available as they don’t only work for your company like your employees do. It is easier to schedule employees in your business as you always know what their workload/commitments are at any time (when you have scheduled properly) however if you do not provide your subcontractor with a schedule or required time for their works you risk them not being available to perform the works which will result in subsequent delays to the project. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Local Council may have specific requirements, such as allowable working hours, which will influence a constriction schedule…… INSERT. |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | So that there is no confusion as to how a certain element is to be finished and so that allowances can be made if a particular selection is a special order and may have a longer lead time than a standard selection. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | Cairns Regional Council allow for works to occur between 7am and 6pm on weekdays and 7am and 1pm on Saturdays. No work is to be undertaken on Sundays or Public Holidays. Schedules need to be made around these working hours and taken into consideration when developing a plan and program for the works. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Plans | Detail the layout and plan of the project from a birds eye view. The plans will determine the size, measurements and materials for the job which will ultimately affect how long its going to take to build which has a direct impact on the schedule. |  |
|  | Material Specifications | Indicate the type, size and strength requirements for the material to be used in construction. These specifications will determine what needs to be ordered and will affect the project schedule in regards to lead times and specific ordering constraints which may arise from specified materials ie. a particular grade of timber for an acoustic fence may have a longer lead time than timber for a standard fence. |  |
|  | Product Specifications | Product specifications will provide information on a particular fixture to be used in the build. Similar to material specifications, if a product that is specified for the job has special requirements as per the product specifications then this will have an impact on the schedule. For instance, a fixture may have a longer lead time than a standard fixture or may require extra time to install which must be factored in to the schedule. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | If a variation arises to the contract and the client has agreed to proceed with the variation, a builder must ensure the schedule is adjusted accordingly to ensure the works required for the variation are captured and allowed for, they must advise their suppliers and also must adjust their call forward sheet or similar documentation to reflect those changes. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Redesign of a bathroom layout | As a redesign of a bathroom will have an impact on the rough in stage (depending on what has been moved), this could delay all other items which follow the rough in if its going to take longer to install the new layout. Also, if the redesign incorporates changes to the products being used in the bathroom, there could be a longer lead times for the revised products. |  |
|  | Changes/enhancements to external features | Changes or additions of features will increase the scope of works and therefore will generally mean that item will take longer to complete due to additional construction/installation time or extended lead times for feature items. |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | The builder has discovered poor ground conditions where a foundation for the building is located | The poor ground conditions may need to be improved by bringing in additional material and reworking the area. This will add costs and additional time to the site preparation item of the contract. |  |
|  | An authority requires a particular application be lodged for the type of work being undertaken which was unforeseen during the estimating stage. | Having to make an application, and perhaps pay application fees and then await the outcome of the application or approval of same could have the potential to delay the works on site thus affecting the schedule of the job. Eg. Alteration to an existing sewer main which was not shown on the site plans and must be altered in order for the build to progress and Council require an approval to be granted to carry out the works on their asset. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | Overlay drawings show further detail over the top of existing plans and are designed to provide further information and clarity on the building process and can also provide information where changes may need to be made by a draftsperson, engineer or architect. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | A work order issued to a subcontractor should include information about the scope/extent of works, the address/location for the project and agreed rates for the works to be undertaken. |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | - Date of order and date of require delivery; - Purchase order number for the purchase; - The supplier’s details; - Delivery details including address and specific delivery instructions; - Contact information for the supplier; - Project manager/project contacts’ details incase there are any questions regarding the purchase order; - Description of the product that is being ordered and the quantity; - Terms and conditions for the supplier to adhere to; and - Total cost of the order. |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet tracks when materials should be ordered based on when they are required on site. They allow for scheduling of activities that are to be undertaken on site and ensure the right plant/equipment/labour is available to receive goods for the project. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Approved, ‘For Construction’ architectural plans and service location plans should be included with site documentation. |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | +250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | +400 |  |
|  | Shower bases | 250 | 265 | +15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | +300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Concrete | 1 Day | 28/04/21 | 27/04/21 | - Ensure site supervisor is contacted prior to delivery - Ensure correct mix including required QA is supplied - Multiple deliveries required to complete base slab including garage Site entrance via “Deck Drive” |  |
|  | Brick | 7 Days | 10/05/21 | 30/04/21 | - Ensure supervisor is contacted prior to delivery to ensure unloading equipment available - Site entrance via “Deck Drive” |  |
|  | Framing Timber | 3 Days | 18/05/21 | 13/05/2021 | - Ensure supervisor is contacted prior to delivery to ensure unloading equipment available - Site entrance via “Deck Drive” - Ensure timber cut to correct lengths as per order form prior to delivery |  |
|  | Cement Roof Tiles | 2 Weeks | 07/06/2021 | 24/05/21 | - Ensure supervisor is contacted prior to delivery to ensure unloading equipment available - Site entrance via “Deck Drive” |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | - Tender for pricing for the materials - Confirm most competitive and reliable supplier - Confirm lead times - Issue purchase order when required according to supplier’s lead time and job schedule | - Consider additional lead times for custom external cladding - Ensure cladding isn’t ordered too early as there are other tasks required to be completed prior to cladding being required – this is importance for cashflow reasons |  |
|  | Wall frame | - Confirm quantities /sizes/types of timber required - Obtain pricing and availability/lead times to determine supplier - Issue purchase order in relation to schedule | - Ensure goods are ordered and will be delivered on time as any delays with wall framing will have a large impact on many other subsequent activities/trades - Ensure correct timber type, sizes and lengths are quoted and ordered to ensure uninterrupted installation by the carpenter/s |  |
|  | Windows | - Obtain pricing from suppliers ensuring they allow for powder coating as required - Confirm lead times and issue purchase order with regard to any extended lead times | - Powder coated aluminium windows may have a longer lead-time due to the powder coating, therefore consideration needs to be given to a longer lead time and earlier ordering - Confirm whether the supplier is only supplying the window frames/glass and if a separate glazier subcontractor is require for installation or if the supplier is able to supply and install the windows. |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | See attached. |  |
| --- | --- | --- |

CPCCBC4005A

Produce labour and material schedules for ordering

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Lauren McKew |
| --- | --- |
| Participant signature |  |
| Date | 19/04/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4005A

Produce labour and material schedules for ordering

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to produce schedules of resource requirements so that orders can be placed for materials and labour for projects, and costs can be recorded and tracked as they are incurred. - Occasion 1: Residential project - Occasion 2: Commercial project The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A copy of a material/labour schedule or supplier list for a project - A copy of a purchase order for purchasing materials or other resources - A cost report - Site condition reports or dilapidation reports - Contract documents - Call forward sheets - Variations The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Contract documentation (including plans and specifications), computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | Lauren McKew |  |  |
| Name of observer: | Jarryd Londino |  |  |
| Role of observer (Confirm suitability to sign) | Project Engineer |  |  |
| Email address of observer | jarryd@fgf.com.au |  |  |
| Signature of observer: |  |  |  |
| Date: | 19/04/2021 |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Consider all contract conditions in the schedules, including: - All contractual requirements - Local government and regulatory bodies’ conditions of approval - Colour selections - Variations to contracts, raised by the client or builder |  |  |  |
| - Produce material and labour schedules, including: - Details of nominated suppliers and contractors in work schedules - Application of contract rates |  |  |  |
| - Produce relevant overlay drawings. |  |  |  |
| - Include contract details and instructions on orders. |  |  |  |
| - Prepare site files, including: - All necessary site documents, including plans and specifications - Preparation of call forward sheets, detailing all orders |  |  |  |
| - Analyse project costs against estimates during construction. |  |  |  |
| - Analyse approved variation costs. |  |  |  |
| - Provide a final project cost analysis. |  |  |  |
| - Maintain data files of standard costs, including: - Approved variation cost increases - Changes to standard plans, specifications, and cost files |  |  |  |
| - Effectively communicate using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments

As part of our project commencement process, procurement and project planning is one of the first and most important tasks we undertake. Our CAs typically undertake the procurement process with input from the project manager or project engineer. In my experience working with Lauren she is very capable of procuring required materials for our jobs as per our scheduling and project requirements. Often, we will approach multiple suppliers or subcontractors to obtain the most competitive rate and this generally requires a supplier or subcontractor reconciliation to be drafted and signed off by the operations manager or project manager. Lauren is also responsible for creating our site folders/construction manuals prior to our crew commencing on site which she is able to do unassisted. She is also able to manage the site file throughout the project including providing updates to drawings, variations, extensions of time, additional information, delivery schedules and any other relevant documentation required for the project. Finally, following submission of our monthly progress claims we are required to undertake a profitability analysis on our projects for presenting to the company’s senior management team. Lauren is capable of preparing profitability analysis’ for our projects and analysing monthly costs both from a procurement and labour perspective to ensure we are on track with our initial forecasts. Overall, I believe Lauren to be completely capable of managing our procurement and costs management process for our projects.