## Project Data
Minc Project Manager
Project Name | Lana Place
Job Number | 37246 | Grey fields must be completed
Site Address
Site Contact
Client
Client Name | The Community Co
Client Contact
Work Phone
Mobile Phone
Email
Address - Line 1 | 296 Vulture Street
Address - Line 2 | Kangaroo Point QLD 4169
Cilent Project Manager (insert client details if Not Applicable)
Project Manager Name
Work Phone
Mobile Phone
Email
Adress

## Tender
PROJECT TENDER AND TRACKING SHEET
Project:
TENDER | [10 empty] | TRACKING
[20 empty] | PROFIT PERCENTAGE | -551.8%
[7 empty] | TOTAL INC GST |  | 0 | [10 empty] | PROFIT | -79289.23
[7 empty] | GST | 10% | 0 | [10 empty] | REVISED CONTRACT AMOUNT | 14370
[7 empty] | TOTAL EX GST |  | 0 | [10 empty] | APPROVED VARIATIONS | 14370
[7 empty] | CONTINGENCY | 0% | 0 | [10 empty] | QUOTED AMOUNT | 0
[7 empty] | MARK UP | 25% | 0 |  |  | Total Let | 251359.23 | [6 empty] | TOTAL BILLS | 93659.23
Do not change these figures after quote has been approved | [9 empty] | Totals incl Mark Up | Contract details |  |  | Sub-Contractor Progress Claims and Invoicing
Item | TRADE | Company Name | Contact Name | Phone | Email | Quote Number | TOTAL COST |  | 0 | 0 | Order number | Company Name | Contract $ | Claim Number (if applicable) | Invoice Number | Date of claim | Payment Terms | Payment Due | This Claim | Total Claimed | Balance Owed | Comments
1 | PRELIMINARIES | [7 empty] | 0 | 0
| Refer Prelims | [5 empty] | 0
[15 empty] | 4209 | 2018-11-26 | COD | 2018-11-26
[15 empty] | 4211 | 2018-11-26 | COD | 2018-11-26
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
2 | Carpentry | [7 empty] | 0 | 0 |  | Finlaysons Timber | 347.32 | 0002-01945247 |  |  |  |  | 347.32
[12 empty] | Revised contract amount | 347.32 | [6 empty] | 347.32 | 0
3 | Electrical | [7 empty] | 0 | 0 |  | Electrik Avenue Electrical | 150 | 8867 |  |  |  |  | 150
[12 empty] | Electrik Avenue Plumbing | 118.38 | 8924 |  |  |  |  | 118.38
[12 empty] | Goanna Plumbing | 1121.23 | 25460 |  |  |  |  | 1121.23
[12 empty] | Revised contract amount | 1389.61 | [6 empty] | 1389.61 | 0
4 | Hydraulic | [7 empty] | 0 | 0 |  | Reece Plumbing | 18 | 400879538 |  |  |  |  | 18
[12 empty] | Reece Plumbing | 30.06 | 400879561 |  |  |  |  | 30.06
[12 empty] | Reece Plumbing | 158.6 | 591277868 | 1291 | 2018-12-12 | 30 days | 42025 | 158.6
[12 empty] | Reece Plumbing | 21.38 | 591797232 |  |  |  |  | 21.38
[12 empty] | Reece Plumbing | -91.08 | 805432440 |  |  |  |  | -91.08
[12 empty] | Reece Plumbing | 6.03 | 402962144 |  |  |  |  | 6.03
[12 empty] | Big Rhino Cranes | 500 | 4958SM |  |  |  |  | 500
[12 empty] | Big Rhino Cranes | 500 | 4986SM |  |  |  |  | 500
[12 empty] | Big Rhino Cranes | 500 | 5019SM |  |  |  |  | 500
[12 empty] | City Hire | 707.7 | 254739 |  |  |  |  | 707.7
[12 empty] | City Hire | 271.7 | 255204 |  |  |  |  | 271.7
[12 empty] | City Hire | 395.55 | 256634 |  |  |  |  | 395.55
[12 empty] | City Hire | -413.78 | 262456 |  |  |  |  | -413.78
[12 empty] | City Hire | 203.75 | 262849 |  |  |  |  | 203.75
[12 empty] | Kennards Hire | 3430.9 | 24127100 |  |  |  |  | 3430.9
[12 empty] | Kennards Hire | 418.19 | 24148870 |  |  |  |  | 418.19
[12 empty] | Kennards Hire | 209.08 | 24165262 |  |  |  |  | 209.08
[12 empty] | Sydney Tools | 270.91 | 9273903 |  |  |  |  | 270.91
[12 empty] | Revised contract amount | 7136.99 | [6 empty] | 7136.99 | 0
5 | Joinery | [7 empty] | 0 | 0
[12 empty] | Lyndons | -197.43 | WINT06000018118 |  |  |  |  | -197.43
[12 empty] | Lyndons | 59.59 | WINT06000019352 |  |  |  |  | 59.59
[12 empty] | Revised contract amount | -137.84 | [6 empty] | -137.84 | 0
6 | Painting | [7 empty] | 0 | 0
[12 empty] | The Waterproofing Warehouse | 14048.05 | 1009 |  |  |  |  | 14048.05
[12 empty] | The Waterproofing Warehouse | 270 | 1018 |  |  |  |  | 270
[12 empty] | The Waterproofing Warehouse | 479.6 | 1026 |  |  |  |  | 479.6
[12 empty] | Envirotech | 1060 | 38319 |  |  |  |  | 1060
[12 empty] | Revised contract amount | 15857.65 | [6 empty] | 15857.65 | 0
7 | Flooring | [7 empty] | 0 | 0 |  | SVC Tiling Services | 55000 | INV - 82096A |  |  |  |  | 227.27
[12 empty] | SVC Tiling Services | 55000 | INV - 82096B |  |  |  |  | 30922.73
[12 empty] | SVC Tiling Services | 55000 | INV - 82096C |  |  |  |  | 15575
[12 empty] | SVC Tiling Services | 55000 | INV - 80296D |  |  |  |  | 15575
[15 empty] | 44700 | 2018-12-05 | COD | 2018-12-05
[12 empty] | Revised contract amount | 220000 | [6 empty] | 62300 | 157700
8 | Air Con | [7 empty] | 0 | 0 |  | Northside Air Conditioning | 1750 | 664 |  |  |  |  | 1750
[15 empty] | 5978 | 2018-12-13 | 7 Days | 2018-12-20
[12 empty] | Revised contract amount | 1750 | [6 empty] | 1750 | 0
9 | CLEANING | [7 empty] | 0 | 0 |  | Speedy Bins | 618.5 | 238985 |  |  |  |  | 618.5
[12 empty] | Speedy Bins | 618.5 | 239065 |  |  |  |  | 618.5
[12 empty] | Speedy Bins | 618.5 | 239166 |  |  |  |  | 618.5
[12 empty] | Speedy Bins | 618.5 | 239279 |  |  |  |  | 618.5
[12 empty] | Speedy Bins | 618.5 | 239417 |  |  |  |  | 618.5
[12 empty] | Speedy Bins | 619.7 | 34107 |  |  |  |  | 619.7
[12 empty] | Speedy Bins | 100 | 34499 |  |  |  |  | 100
[12 empty] | Nudgee Road Tip | 115.83 | SINR003020 | 1675A | 2018-12-18 | 30 days | 42021 | 115.83
[12 empty] | Nudgee Road Tip | 80 | SINR003131 |  |  |  |  | 80
[12 empty] | Revised contract amount | 4008.03 | [6 empty] | 4008.03 | 0
10 | MATERIALS | [7 empty] | 0 | 0 |  | Brisbane House Stump and Steel | 127.27 | 1898 |  |  |  |  | 127.27
[12 empty] | All Preparation Equipment | 330 | 52045 |  |  |  |  | 330
[12 empty] | National Tiles | 63.64 | 4610671 | 285415 | 2018-11-28 | COD | 2018-11-28 | 63.64
[12 empty] | National Tiles | 318.18 | 4610549 |  |  |  |  | 318.18
[12 empty] | Fasteners Direct | 168.38 | 168848 |  |  |  |  | 168.38
[12 empty] | Revised contract amount | 1007.47 | [6 empty] | 1007.47 | 0
11 | LIGHTING | [7 empty] | 0 | 0
|  |  |  | 1300 601 931 | astika@aglosystems.com.au | [9 empty] | 23796-1 | 2018-12-04 | 30 Days | 2019-01-04
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
12 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
13 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
14 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
15 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
16 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
17 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
18 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
19 | [8 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
20 | Sundries | [7 empty] | 0 | 0
[12 empty] | Revised contract amount | 0 | [6 empty] | 0 | 0
The following allowance or Assumptions have been made:-
1
2
3
4
5
6
7
8
9
10
No Allowance for:-
a
b
c
d
e
f
g
h
i
j
PC Sums included in this tender
(Typical PC Allowances)
1 |  | 0
2 |  | 0
3 |  | 0
4 |  | 0
5 |  | 0
6
7
8
9
10

## Quoting Sub-Contractor Record
Press (ALT + ENTER) to go down line but stay in same cell.
STATUS | TRADE | TASK | COMPANY | CONTACT DETAILS | DATE QR SENT | DATE Q REC. | $ EX GST QUOTE | NOTES AND RECORD OF INTERACTIONS WITH SUB CONTRACTOR
RECEIVED | EG. Plumbing | EG. All plumbing on job | EG. John's Plumbing | EG. 07 8888 9999 johnsplumbing@gmail.com | EG. 18/08/2022 | EG. 19/08/2022 | EG. $4,234.00 | EG. 18.08.2022 Called reception to confirm email, send email with quote request. 19.08.2022 Met plumber on site on 19th of August morning. 19.08.2022 Received quote in afternoon.
| Refrigeration | Move AC's up 300mm | 5th Star Air Conditioning | info@5thstar.com.au | 2022-07-25 |  |  | 25/07/2022 Called 5th star, got email, then sent through quote request.
RECEIVED | Refrigeration | Move AC's up 300mm | Northside Air Conditioning | Brayden 0423 045 563 northsideairconservices@gmail.com | 2022-07-25 | 2022-08-16 | 1750.22 | 25/07/2022 Called Northside and spoke to Brayden, got email address and sent quote request through. 26/07/2022 Brayden sent through first quote. 28/07/2022 Bruce accepted this quote, cheapest. I have told Brayden. 10/08/2022 Called Brayden and booked 16th Aug as day of job. 16/08/2022 Brayden started job and found out change to scope, additional work, he resent quote, Approved by Bruce. He then completed job.
RECEIVED | Refrigeration | Move AC's up 300mm | Sun City Air Conditioning | suncityair@suncityair.com.au | 2022-07-25 | 2022-07-26 | 2198 | 25/07/2022 Called Sun City, got email address and sent quote request through. 25/07/2022 Received call from Steve Wiseman, saying he will quote, wanted to know other technical questions. 26/07/2022 Received a quote via email.

## Trade quote
| Name and Job #: | 0
[10 empty] | Contract details | Sub-Contractor Progress Claims and Invoicing
Item | Trade | Contact/ Phone Number | Contact Name | Phone | Email | Cost Ex GST | GST | Winning Tender | NOTES | Order number | Claim Number (if applicable) | Invoice Number | Date of claim | Payment Terms | Payment Due | This Claim | Total Claimed | Balance Owed | Comments
1 | PRELIMINARIES | [5 empty] | 0
[17 empty] | 0 | #REF!
2 | CARPENTER
[17 empty] | 0 | #REF!
3 | PLASTERER
[17 empty] | 0 | #REF!
4 | ROOFER
[17 empty] | 0 | #REF!
5 | JOINER
[17 empty] | 0 | #REF!
6 | MECHANICAL
[17 empty] | 0 | #REF!
7 | WINDOWS & DOORS
[17 empty] | 0 | #REF!
8 | FLOOR FINISHES
[17 empty] | 0 | #REF!
9 | GLASS BALUSTRADE
[17 empty] | 0 | #REF!
10 | PAINTER
[17 empty] | 0 | #REF!
11 | SIGNAGE
[17 empty] | 0 | #REF!
12 | COLDROOM PANELING
[17 empty] | 0 | #REF!
13 | GLASS PARTITIONS
14 | PLUMBER
15 | STRUCTURAL ENGINNER

## PS1
Pricing Schedule
Work Order #: |  | Date:
Site: | Contact:
Description of Work | Company | Quantity | Cost | Mark Up | M/U Value | Price | Part No/ size
CONTRACTORS |  |  |  | %
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  | Contractors Total |  |  | 0
MATERIALS
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  |  | 20% | 0 | 0
|  |  | Materials Total |  |  | 0
|  | Total Mark Up |  |  |  | 0
|  | Contingency |  | 0% |  | 0
|  | Total Price |  |  |  | 0
|  | Total Price Including GST |  |  |  | 0

## Take Offs
TAKE OFF - Description | [7 empty] | 0
| Description | Unit | Days | Hours | $ | Item |  | COMMENTS
0
Ceilings
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Walls
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Floors
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
After Hours
| Labour | [5 empty] | 0
TAKE OFF - Description
| Description | Unit | Days | Hours | $ | Item |  | COMMENTS
0
Ceiling
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Walls
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Misc
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
TAKE OFF - Description
| Description | Unit | Days | Hours | $ | Item |  | COMMENTS
0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
TAKE OFF - XXXXXX
| Description | Unit | Days | Hours | $ | Item |  | COMMENTS
0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
TAKE OFF - XXXXXX
| Description | Unit | Days | Hours | $ | Item |  | COMMENTS
0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0
Description of Task
| Labour | [5 empty] | 0
| Materials | [5 empty] | 0
| Hire | [5 empty] | 0
| Bins | [5 empty] | 0

## Prelims
1 | PRELIMINARIES FOR :- | 0 |  |  |  | TOTAL | 0
| CONTRACT DURATION |  | WEEKS | 0 | WORKING DAYS
| LIQUIDATED DAMAGES |  | ................. | PER DAY
| PROJECT MANAGEMENT | $ per hr | hrs per week | weeks
| Project Manager | 80 |  |  |  | 0
| Estimater | 50 |  |  |  | 0
| Contracts administrator | 50 |  |  |  | 0
| Administration Assistant | 35 |  |  |  | 0
0
SITE STAFF
|  | Rate | Men | Days | Hours
| Site manager #- | 55 |  |  |  | 0
| Carpenter # |  |  |  |  | 0
| OH&S Labourer # Additional $1.49 Per Hour |  |  |  |  | 0
| Labourer # |  |  |  |  | 0
| Trafic Controls |  |  |  |  | 0
| Site Meetings |  |  |  |  | 0
| Security |  |  |  |  | 0
| Saturdays for Labourer |  |  |  |  | 0
| Flights | 400 |  |  |  | 0
| Accommodation | 150 |  |  |  | 0
| Meals |  |  |  |  | 0
| Hire Car | 65 |  |  |  | 0
| Car Parking |  |  |  |  | 0
Site allowance of ?? has been added to above rates as shown #
0
PERMITS and FEES
| Demolition Permit |  |  |  |  | 0
| Building Permit (BA) or (CC) |  |  |  |  | 0
| Council |  |  |  |  | 0
| Engineers certification |  |  |  |  | 0
| Hoarding Permit |  |  |  |  | 0
| M.B.A. membership |  |  |  |  | 0
| Authority Fees - Power / Phone / Fire Brigade |  |  |  |  | 0
0
INSURANCES
0
| Defects Liability / Bank Guarantee | Weeks | retention | interest | Contract
0
TEMPORARY SERVICES
| Power |  | weeks @ | 40 | per week | 0
|  | Connect |  | 300 | each | 0
| Telephone | Quarter |  | 150 | /quarter | 0
|  | Calls |  | 120 | /week | 0
| Floodlights /Power Pole /Hazard /Warning Lights |  |  | 750 | /week | 0
| Delivery and connection to power |  |  |  |  | 0
| Accom | No. | Cost /week | weeks | Delivery
| Lunch rooms 6x3 |  | 120 |  |  | 0
| Storage 6x2.4 |  | 80 |  |  | 0
| Chemical toilet |  | 60 |  |  | 0
| Pump outs |  | 50 |  |  | 0
| Temp fencing |  |  |  |  | 0
| Connection to sewer |  |  |  |  | 0
| Site Office | 0 | 175 | 0 | 0 | 0
| Hoardings and handrails | 0 | @ | 0 | 0 | 0
| Safety |  |  |  |  | 0
0
| TIME SCHEDULE | Establish chart and monitor |  |  |  | 0
| SETTING OUT WORKS | Survey / Set out fees
|  | Existing conditions |  | 0
|  | "As built drawings |  | 0
0
0
| ACCESS TO SITE | Temporary road, crossover and/or planked track
| 30/40 scalpings | m3 | 0 | @ | 10.85 | 0
| Timber planking | m | 0 | @ | 0 | 0
0
PLANT & EQUIPMENT
| Vacumn cleaner | Hrs |  | @ | 500 | 0
| Barrow hoist erection | No. |  | @ | 1000 | 0
| Cherry picker 18.0m | Days |  | @ | 450 | 0
| Scissor lift 7.6m | Weeks |  | @ | 150 | 0
| Delivery |  |  |  | 100 | 0
| Mobile scafold (light) | Days |  | @ | 105 | 0
Other fixed scafold
| Access tower | Weeks |  | @ | 250 | 0
| Delivery |  |  |  | 180 | 0
| Labour (hrs attendance) | Hrs |  | @ | 0 | 0
0
| Rubbish Removal | Loads |  | @ | 430 | 0
| Ongoing Cleaning To Building | Ongoing cleaning / protection |  |  | 1hrs per day
| Builders Clean On completion | General Sweep |  |  | 0 | 0
0
| SUNDRIES | Purchased
0

## Labourer (hidden)
Builders Labourer Rate
COST PER HOUR | 45 | USE THIS RATE FOR COMPETITIVE ESTIMATING PURPOSES (LABOURER)
PROFIT, OVERHEAD and RISK | 9 | USE THIS RATE FOR ESTIMATING PURPOSES (LABOURER)
CHARGE OUT RATE | 54 | USE THIS RATE FOR DO and CHARGE or VARIATION PURPOSES (CARPENTER)

## Carpenter (hidden)
Carpenter / Plaster / Painter / Tiler Rate
COST TO COMPANY PER HOUR | 55 | USE THIS RATE FOR COMPETITIVE ESTIMATING PURPOSES (CARPENTER)
PROFIT, OVERHEAD and RISK | 11
CHARGE OUT RATE | 66 | USE THIS RATE FOR DO and CHARGE or VARIATION PURPOSES (CARPENTER)

## Electritian (hidden)
Electritian / Plumber / Specialised Trade Rates
COST TO COMPANY PER HOUR | 70 | USE THIS RATE FOR COMPETITIVE ESTIMATING PURPOSES (CARPENTER)
PROFIT, OVERHEAD and RISK | 14
CHARGE OUT RATE | 84 | USE THIS RATE FOR DO and CHARGE or VARIATION PURPOSES (CARPENTER)
Based on Metropolition Melbourne / Sydney / Adelaide

## Manager (hidden)
Site Manager / Foreman Rate
COST TO COMPANY PER HOUR | 65 | USE THIS RATE FOR COMPETITIVE ESTIMATING PURPOSES (CARPENTER)
PROFIT, OVERHEAD and RISK | 13
CHARGE OUT RATE | 78 | USE THIS RATE FOR DO and CHARGE or VARIATION PURPOSES (CARPENTER)

## Materials Req
| Job Name & Address |  | =Tender!C2
Material Order
| Description | Comments | No | Budget ea | Budget Total | Quoted ea | Total Price | Supplier | Order Number
[5 empty] | 0 |  | 0
| Toilets | P Trap plastic cistern | 8 | 220 | 1760 |  | 0
| Basins | One Hole, Wall mount | 6 | 180 | 1080 |  | 0
| Basin Mixers |  | 6 | 80 | 480 |  | 0
| toilet roll holder |  | 8 | 25 | 200 |  | 0
| Urinal | Wall mount, w/ wwall mount autoflush cistern | 1 | 550 | 550 |  | 0
| Gatic Drains | Vinyl, 100mm? | 1 | 200 | 200 |  | 0
| Kitchen Sink | 2xfull RH drain plus 1 holes | 1 | 350 | 350 |  | 0
| Kitchen mixer | Swivel | 1 | 100 | 100 |  | 0
| Zip Hydroboil | Commercial Compact 2 plus Alum vent grill kit plus filter? | 1 | 1 | 3000 |  | 0
| Male Toilet signs | Male sign plus hand plate | 2 | 30 | 60 |  | 0
| Female Tiolet signs | Female sign plus hand plate | 2 | 30 | 60 |  | 0
| Female Mirror | 3060x800 frameless polished edge | 1 | 900 | 900 |  | 0
| Male Mirror | 1400x1000 frameless with shelf to match | 1 | 900 | 900 |  | 0
| Hand Driers | JD McDonald | 3 | 550 | 1650 |  | 0
| Fluros | Twin 56Watt with Difuser | 3 | 60 | 180 |  | 0
| Tiles | 200x200 Glossy White | 65 | 15 | 975 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 12445 |  | 0
[5 empty] | Difference | 12445

## Invoice Schedule
Core4 AUS
T 1300 64 64 62
ABN 34 118 244 965 Lic 1096827
WORKSAU@CORE4SERVICE.COM
WWW.CORE4SERVICE.COM.AU
PO BOX 3082 NEWMARKET QLD 4051
Date - | 2022-11-18
Claim Summary
The Community Co
296 Vulture Street
Kangaroo Point QLD 4169
ATTN: | 0
RE: | Lana Place
Job No: | 37246
Final Claim
This is a payment claim under the 'Building Industry Fairness (Security of Payment) Act 2017'
Item | Description | Contract SUM | % Claimed | Date Invoiced | Date Due | Amount Claimed
1 | Deposit invoice of 50% | 8106.5 | 100% |  |  | 8106.5
2 | Supply of Tiles & Demolition | 56745.5 | 100% |  | 0 | 56745.5
3 | Tiling | 32426 | 100% |  | 0 | 32426
4 | Balustrade | 16213 | 100% |  | 0 | 16213
5 | Practical Completion | 48639 | 100% |  | 0 | 48639
6 |  |  |  |  | 0 | 0
7 |  |  |  |  | 0 | 0
8 |  |  |  |  | 0 | 0
VARIATIONS
V01 | Concrete Spalling investigation | 3020 | 100% |  | 0 | 3020
V02 | Block Wall Repairs | 11350 | 100% |  |  | 11350
V03 | [5 empty] | 0
0
Total claimed | [5 empty] | 176500
Less previously claimed | [5 empty] | 64852 | This amount to be manually entered each claim
Retention held this claim (if applicable) |  |  |  | Enter Rentention amount here if applicable >>> |  | 0
This Claim - Ex GST | [5 empty] | 111648
This Claim - GST Amount | [5 empty] | 11164.8
This Claim - Total | [5 empty] | 122812.8
TOTAL RETENTION HELD TO DATE | [5 empty] | 0
TOTAL RETENTION ON CONTRACT AMOUNT | [5 empty] | 0
TOTAL CONTRACT AMOUNT - Ex GST | [5 empty] | 165150
TOTAL - GST | [5 empty] | 16515
TOTAL CONTRACT AMOUNT | [5 empty] | 181665
Formulas:
Date Due = WORKDAY([Date Invoiced],F55)

## VO Summary
Core4 AUS
T 1300 64 64 62
ABN 34 118 244 965 Lic 1096827
WORKSAU@CORE4SERVICE.COM
WWW.CORE4SERVICE.COM.AU
PO BOX 3082 NEWMARKET QLD 4051
Date - | 2022-11-18
Variation Summary
The Community Co
296 Vulture Street
Kangaroo Point QLD 4169
ATTN: | 0
RE: | Lana Place
Job No: | 37246
This is a payment claim under the 'Building and Construction Industry Security of Payment Act 2002'
VO | Description | Approved Y/N | Addition | Deduction | Amount Claimed
V01 | Concrete Spalling investigation |  | 3020 |  | 3020
V02 | Block Wall Repairs |  | 11350 |  | 11350
0
0
0
0
0
0
0
0
|  |  |  | VARIATIONS APPROVED TO DATE excluding GST | 14370
Variations approved to date |  |  |  |  | 14370
Less previously paid |  |  |  |  | 0
Sub Total |  |  |  |  | 14370
Add GST |  |  |  |  | 1437
15807
Electronic Payment:- As per attached
Payment Terms as per contract
Regards,
Christian Seymour

## V01
Core4 AUS
T 1300 64 64 62
ABN 34 118 244 965 Lic 1096827
WORKSAU@CORE4SERVICE.COM
WWW.CORE4SERVICE.COM.AU
PO BOX 3082 NEWMARKET QLD 4051
VARIATION
JOB:- | 37246 | DATE: | 06.10.22
JOB No:- | 37246 | VARIATION QUOTATION No: | V.01
CLIENT:- | Lana Place CTS 15046 | SITE INSTRUCTION No:
ATTENTION:-
QUOTATION
DESCRIPTION OF VARIATION
|  | Addition | Deduction
V.01 | Concrete Spalling investigation | 3020
| Sub Total | 3020 | 0
| GST | 302
| Net Variation including GST | 3322
* The above Variation-Quotation is submitted for - YOUR APPROVAL / YOUR INFORMATION
* The above Variation - DOES / DOES NOT constitute a time variation
* Once approved, please sign |  | Date Approved
NOTES, EXCLUSIONS, QUALIFICATIONS ETC:

## V02
Core4 AUS
T 1300 64 64 62
ABN 34 118 244 965 Lic 1096827
WORKSAU@CORE4SERVICE.COM
WWW.CORE4SERVICE.COM.AU
PO BOX 3082 NEWMARKET QLD 4051
VARIATION
JOB:- | Lana Place | DATE: | 2022-10-14
JOB No:- | 37246 | VARIATION QUOTATION No: | V.02
CLIENT:- | The Community Co | SITE INSTRUCTION No:
ATTENTION:- | 0
QUOTATION
DESCRIPTION OF VARIATION (Including Breakdown of costs)
|  | Addition | Deduction
V.02 | Block Wall Repairs | 11350
| Sub Total | 11350 | 0
| GST | 1135
| Net Variation including GST | 12485
* The above Variation-Quotation is submitted for - YOUR APPROVAL / YOUR INFORMATION
* The above Variation - DOES / DOES NOT constitute a time variation
* Once approved, please sign |  | Date Approved
NOTES, EXCLUSIONS, QUALIFICATIONS ETC:

## RFI
Core4 AUS
T 1300 64 64 62
ABN 34 118 244 965 Lic 1096827
WORKSAU@CORE4SERVICE.COM
WWW.CORE4SERVICE.COM.AU
PO BOX 3082 NEWMARKET QLD 4051
RFI
To-
Attention-
Date-
| From- | 0
RFI No -
Re :
Please find below details of our Request For Information
Item | Information Requested |  | Date | Action / Response | Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19