## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Clear and Prep site | 1 | 1 | 0 | 0 | 0%
Arrange Temp Services | 1 | 2 | 0 | 0 | 0%
Arrange Contractors with Aprox dates | 1 | 2 | 0 | 0 | 0%
Arrange Materials with aprox date | 1 | 3 | 0 | 0 | 0%
Site set out | 3 | 1 | 0 | 0 | 0%
Site excavation and Footings | 3 | 1 | 0 | 0 | 0%
Plumbing Drainage | 4 | 1 | 0 | 0 | 0%
Formwork for Slab | 5 | 1 | 0 | 0 | 0%
Moisture Barrier- Termite Barrier | 5 | 1 | 0 | 0 | 0%
Inspections | 6 | 1 | 0 | 0 | 0%
Fix Reinforcement | 6 | 1 | 0 | 0 | 0%
Pour and Finish Slab | 7 | 1 | 0 | 0 | 0%
Cure Slab | 7 | 2 | 0 | 0 | 0%
Erect Wall Frames | 9 | 1 | 0 | 0 | 0%
Inspections | 9 | 1 | 0 | 0 | 0%
Erect Roof Trusses | 10 | 1 | 0 | 0 | 0%
Install Windows And Ext Door Frames | 10 | 1 | 0 | 0 | 0%
Roof Plumbing | 10 | 1 | 0 | 0 | 0%
Install Roofing | 11 | 1 | 0 | 0 | 0%
Install Cladding | 11 | 1 | 0 | 0 | 0%
Lockup | 12 | 1 | 0 | 0 | 0%
Electrical rough-in | 12 | 1 | 0 | 0 | 0%
Plumbing Rough-in | 12 | 1 | 0 | 0 | 0%
Brick Clean | 12 | 1 | 0 | 0 | 0%
Wet Area Waterproofing | 13 | 1 | 0 | 0 | 0%
Install Wall Insulation | 13 | 1 | 0 | 0 | 0%
Inspections | 13 | 1 | 0 | 0 | 0%
Internal Linings | 14 | 1 | 0 | 0 | 0%
Internal Fitout and Joinery | 14 | 2 | 0 | 0 | 0%
wall and floor Tiling | 15 | 1 | 0 | 0 | 0%
Painting | 15 | 1 | 0 | 0 | 0%
Plumbing Final Fit | 16 | 1 | 0 | 0 | 0%
Electrical Final Fit | 16 | 1 | 0 | 0 | 0%
Carpentry Final Fit | 16 | 1 | 0 | 0 | 0%
Install Ceiling Insulation | 17 | 1 | 0 | 0 | 0%
Landscaping and Fencing | 16 | 2 | 0 | 0 | 0%
Defects and Clean | 18 | 1
Time allowance for delays | 19 | 3 | 0 | 0 | 0%