## FF&E
[28 empty] | PENDING | NOT RECEIVED
| PROJECT FF&E PROCUREMENT SPREADSHEET |  | PROJECT: | # 45376: EVERTON PARK HOTEL ACCOMODATION REFURBISHMENT | [23 empty] | ORDERED | IN PROGRESS
|  |  | SITE LOCATION: | 101 FLOCKTON STREET, EVERTON PARK QLD 4053 | [23 empty] | IN TRANSIT | PARTIALLY PAID
|  |  | PROJECT COMMENCEMENT: | 27.11.23 - 22.12.23 | [23 empty] | AWAITING COLLECTION | PAID
|  |  | STAGED WORKS: | N/A | [23 empty] | DELIVERED | OVERDUE
DELIVERY SCHEDULED
CATEGORY | ITEM / DESCRIPTION | IMAGE | QTY/UOM | SUPPLIER DETAILS | ACTUAL COSTINGS |  |  |  |  | BUDGET ALLOCATION |  |  | QUOTE DETAILS |  |  |  | PURCHASE DETAILS |  | PAYMENT DETAILS |  |  | DELIVERY DETAILS |  |  |  |  | NOTES
[5 empty] | UNIT COST (ex GST) | SUBTOTAL (ex GST) | DELIVERY (ex GST) | GST | TOTAL COST (incl GST) | EST. QTY | EST. UNIT | EST. TOTAL | DATE SENT | DATE RECEIVED | VALID UNTIL | QUOTE # | DATE SENT | PO / WO # | INV # | DATE RECEIVED | STATUS | LEAD TIME | REQUIRED | EXPECTED | ACTUAL | STATUS
FLOOR FINISHES
CARPET
CARPET - FF.1 Accommodation Room Carpet | Optic Reset' Field of View Dark, 282 Fresco Dark - 304.8mm x 914.4mm. https://www.ghcommercial.com/products/field-of-view-dark?colour=fresco-dark |  | 220.0m2 | Kam Kasaei Ausflooring Warehouse 0466 058 402 / sales@ausflooringwarehouse.com.au | $35.80m2 | 7876 | N/A | 787.6 | 8663.6 | 220.0m2 | N/A | 17120 | 26.10.23 | 27.10.23 | 30.10.23 | N/A | 27.10.23 | # 1128 | # 21869 | 27.10.23 | PAID | 1 - 2 Weeks | 27.11.23 | 10.11.23 | 13.11.23 (TO SITE) | DELIVERED | Carpet Requirements: Carpet-able area, 3300mm x 4460mm (approximately 15.0m2). 12 'Standard Rooms', 1 'Family Room'. Assumed (until final site measure) that the family room is double the standard room in size. Budget Allocation: Supply and Installation. *URGENT PAYMENT* required to secure stock - Invoice paid 27.10.23. *Order to be collected from suppliers warehouse by CORE 4 tradesmen - Ready for collection 13.11.23.
TILES
TILES - FF.2 Accommodation Room Threshold / Entry Tiles | BAUHAUS Modular Mosaic Tile, Unglazed - 3-Colour 'Checkerboard'. https://glennontiles.com.au/bauhaus/ |  | 5.20m2 | Glennon Tiles (02) 9698 2799 / sales@glennontiles.com.au | $67.57 - $129.73m2 | 295.72 | 165 | 45.324 | 506.044 | N/A | N/A | 11180 | 26.10.23 | 01.11.23 | 29.11.23 | # 18106 | 03.11.23 | # 1161 | # 139542 | 06.11.23 | PAID | 1 Week | 27.11.23 | 17.11.23 | 08.11.23 (CORE 4 OFFICE) | DELIVERED | Tile Requirements: 'Cobalt': 0.08m2 / 1.04m2* 'Marina': 0.10m2 / 1.30m2* 'Ash': 0.18m2 / 2.34m2* Budget Allocation: Supply and Installation. *Per entrance step / total. 'Copper Oxide' specification changed (due to supply / stock levels) to 'Marina'. *Assumed (until final site measure) that entrance set is 900mm x 250mm x 150mm (0.36m2 / 4.68m2 totable area, excludes wastage). *Processed using D.W Credit Card 06.11.23 - $7.48 Mastercard surcharge. *Additional tile supply / order required - RFQ issued 30.11.23.
JOINERY
BED HEADBOARDS AND BENCHTOPS
JOINERY Substrate Materials (Bed Headboards, Shelves and Vanity In-Fill Panels) - MDF | Laminex |  | 30 / Sheets | Bunnings Warehouse builderserviceqld@bunnings.com.au | 33.57 | 1007.1 | 181.8 | 118.89 | 1307.79 | N/A | N/A | 26190 | 09.11.23 | 09.11.23 | 07.12.23 | # 317243563 | 14.11.23 | # 1216 |  | ON ACCOUNT | PAID | 1 Week | 27.11.23 | 16.11.23 | 20.11.23 (C.S SHED) | DELIVERED | *Material requirements confirmed by / with Christopher Street 09.11.23. Reference: "# 45376_Everton Park Accommodation Refurbishment_Joinery Combined". Order to be collected from suppliers warehouse by CORE 4 tradesmen. Budget Allocation: Materials, Manufacturing and Installation (ALL Joinery Items).
JOINERY - LAM.1 Finishing Materials - Laminate | Otway Natural (Colour Code: 1035). SKU: 400993, Laminate (HPL), Postforming, Single Sided, 3600mm x 1200mm x 0.700mm. https://www.laminex.com.au/products/otway/Natural/p/AU1006937 |  | 20 / Sheets | Laminex 132 136 / sales@laminex.com.au | 393.11 | 7862.2 | N/A | 786.22 | 8648.42 | N/A | N/A | 26190 | N/A | N/A | N/A | N/A | 14.11.23 | # 1217 |  | ON ACCOUNT | PAID | 1 Week | 27.11.23 | 22.11.23 | 20.11.23 (C.S SHED) | DELIVERED | *Material requirements confirmed by / with Christopher Street 09.11.23. Reference: "# 45376_Everton Park Accommodation Refurbishment_Joinery Combined". Order placed verbally, telephone 14.11.23, order to be collected from suppliers warehouse by CORE 4 tradesmen - Ready for collection 22.11.23. Laminex Order Number: 5704891. Accommodation Room Bed Breakdown: 6 'Standard Rooms': 1 Queen Bed, 1 King Single Bed, 6 'Standard Room' Suites: 1 Queen Bed, 1 'Family Room': 2 Queen Beds, 2 King Single Beds. Additional Laminex Order: # 5721589 - Delivered CORE 4 Office 27.11.23, delivered (C.S house by R.C 27.11.23).
JOINERY Materials - Adhesive | Anchorweld Adhesive 2701 Spray Contact Super Clear, 20 Litre (SKU: 1135500) https://www.lincolnsentry.com.au/anchorweld-adhesive-2701-spray-contact-super-clear-20-litre/p/7100175 |  | 1 / Total | Lincoln Sentry 1300 551 919 / online@lincolnsentry.com.au | 182.49 | 182.49 | N/A | 18.249 | 200.739 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15.11.23 | # 1218 |  | ON ACCOUNT | PAID | 1 Week | 22.11.23 | 15.11.23 | 20.11.23 (C.S SHED) | DELIVERED | Online Purchase (LS Order Number: 0001408392) - Order on account. Order to be collected from suppliers warehouse by CORE 4 tradesmen - Collection date T.B.C.
JOINERY Materials - ABS Cleaner | Anchorweld 802 Plastic Cleaner ABS PVC & Melamine, 20 litre (SKU: 1170094) https://www.lincolnsentry.com.au/anchorweld-802-plastic-cleaner-abs-pvc-melamine-20-litre/p/7100217 |  | 1 / Total | Lincoln Sentry 1300 551 919 / online@lincolnsentry.com.au | 215.58 | 215.58 | N/A | 21.558 | 237.138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15.11.23 | # 1218 |  | ON ACCOUNT | PAID | 1 Week | 22.11.23 | 15.11.23 | 20.11.23 (C.S SHED) | DELIVERED | Online Purchase (LS Order Number: 0001408392) - Order on account. Order to be collected from suppliers warehouse by CORE 4 tradesmen - Collection date T.B.C.
JOINERY - LAM.1 Headboards, Bedside Tables and Vanity In-Fill (Pre-Fabricated) | Otway Natural (Colour Code: 1035). |  | 29 / Items | Aussie Cut Cabinets & Board 07 3889 9577 / sales@aussiecut.com.au | N/A | 11700 | N/A | 1170 | 12870 | N/A | N/A | 26190 | 08.11.23 | 10.11.23 | 10.12.23 | # 13169 | [5 empty] | 4 Weeks |  |  |  |  | *Individual headboard panels only (no shadow gap). *Flat pack pigeon hole shelves, bedside tables and vanity in-full panels. *No delivery available, pick-up (Brendale warehouse) only.
BENCHTOPS - LAM.1 Benchtops (Pre-Fabricated) | 1. 1200mm x 600mm x 33mm, Otway Natural (Colour Code: 1035), Full Bullnose Edge. 2. 600mm x 600mm x 33mm, Otway Natural (Colour Code: 1035), Full Bullnose Edge. |  | 24 / Total | MULTIForm Joinery | 177.1167 | 4250.8 | 46 | 429.68 | 4726.48 | 24 | 225 | 5400 | 26.10.23 | 26.10.23 | 23.11.23 | # 22616 | 03.11.23 | # 1145 | # 00207346 | 07.11.23 | PAID | 1 - 2 Weeks | 27.11.23 | 29.11.23 | 29.11.23 (TO SITE) | DELIVERED | 1, 1200mm x 600mm benchtop and 1, 600mm x 600mm benchtop (separate) per 'Standard Room', 12 SR's total - 6 Left-Hand-Return (LHR) laminate edge 'sets', 6 Right-Hand-Return laminate edge 'sets'. All benchtops to have full bullnose front edge. Reference: "# 45376_Everton Park Accommodation Refurbishment_Benchtops". Cost Breakdown: $177.12 / benchtop (1200mm x 600mm and 600mm x 600mm). Payment Terms: C.O.D - Invoice to be paid prior to delivery to site, 29.11.23. Manufactured and ready for delivery 13.11.23.
JOINERY Substrate Materials (Microwave Cupboards) - MDF | 2400mm x 1200mm x 16mm MDF Panel Standard (I/N: 0590129) https://www.bunnings.com.au/2400-x-1200mm-16mm-mdf-panel-standard_p0590129 |  | 7 / Sheets | Bunnings Warehouse builderserviceqld@bunnings.com.au | 33.57 | 234.99 | 0 | 23.499 | 258.489 | N/A | N/A | N/A | 18.01.24 | 18.01.24 | 18.02.24 | # 317939187 |  |  |  | ON ACCOUNT | IN PROGRESS |  |  |  |  | PENDING | *Material requirements confirmed by / with Christopher Street 18.01.24. Reference: "# 45376_Everton Park Accommodation Refurbishment_Joinery Combined". Order to be collected from suppliers warehouse by CORE 4 tradesmen.
JOINERY - LAM.1 Finishing Materials (Microwave Cupboards) - Laminate | Otway Natural (Colour Code: 1035). SKU: 400993, Laminate (HPL), Postforming, Single Sided, 3600mm x 1200mm x 0.700mm. https://www.laminex.com.au/products/otway/Natural/p/AU1006937 |  | 9 / Sheets | Laminex 132 136 / sales@laminex.com.au | 393.11 | 3537.99 | N/A | 353.799 | 3891.789 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18.01.24 | # 1386 |  | ON ACCOUNT | IN PROGRESS | 1 Week | N/A | 24.01.24 |  | PENDING | *Material requirements confirmed by / with Christopher Street 18.01.24. Reference: "# 45376_Everton Park Accommodation Refurbishment_Joinery Combined". Order placed verbally, telephone 18.01.24, order to be delivered to CORE 4 office. Laminex Order Number: 5774880
ELECTRICAL FIXTURES & FITTINGS
LIGHTING
LIGHTING - WL.1 Headboard-Mounted Reading Light | Modern Minimalist Style Reading Wall Light - 220V-240V Black Rectangle USB Port Included (SKU: 222198860). https://www.litfad.com/modern-minimalist-style-reading-wall-light-metal-1-light-reading-wall-lamp-for-bedroom-s-770825.html?currency=AUD&gclid=EAIaIQobChMIpoLr05S9gQMV_R-DAx3_Mw8DEAQYBCABEgK4NvD_BwE |  | 34 / Total | Litfad www.litfad.com | 98.2 | 3338.8 | 0 | 333.88 | 3672.68 | 34 | 280 | 9520 | N/A | N/A | N/A | N/A | 30.10.23 | # 1143 | N/A | N/A | PAID | 2 - 4 Weeks | 27.11.23 | 24.11.23 | 13.11.23 (TO SITE) | DELIVERED | Online Purchase (LF Order Number: 615679) - Processed using D.W Credit Card 30.10.23. 1 light per bed headboard shelf / draw. Budget Allocation: Supply and Installation.
LIGHTING - WL.2 Wall-Mounted (Bathroom) Vanity Light | Nordic Style Aluminium Vanity Light LED Strip Shade Vanity Lamp for Shower Room, Black (SKU: 21385001). https://www.litfad.com/nordic-style-aluminum-vanity-light-led-strip-shape-vanity-lamp-for-shower-room-p-249914.html |  | 13 / Total | Litfad www.litfad.com | 143.281 | 1862.653 | 0 | 186.2653 | 2048.9183 | 13 | 300 | 3900 | N/A | N/A | N/A | N/A | 30.10.23 | # 1143 | N/A | N/A | PAID | 2 - 4 Weeks | 27.11.23 | 24.11.23 | 13.11.23 (TO SITE) | DELIVERED | Online Purchase - (LF Order Number: 615679) - Processed using D.W Credit Card 30.10.23. 1 light per vanity / mirror. 12 'Standard Rooms', 1 'Family Room'. Budget Allocation: Supply and Installation.
*ALTERNATIVE / REPLACEMENT* LIGHTING - WL.1 Headboard-Mounted Reading Light | Panorama 1 Light Wall Bracket in Black with USB Port https://www.beaconlighting.com.au/panorama-1-light-wall-bracket-in-black-with-usb-port |  | 34 / Total | Beacon Lighting www.beaconlighting.com.au | 180.9 | 6150.6 | 0 | 615.06 | 6765.66 | 34 | 280 | 9520 | N/A | N/A | N/A | N/A | 05.12.23 | # 1305 | N/A | N/A | PAID | 1 - 2 Weeks | 20.12.23 | 20.12.23 |  | DELIVERED | Online Purchase (BL Order Number: 110783345) - Processed using D.W Credit Card 05.12.23. 1 light per bed headboard shelf / draw. Budget Allocation: Supply and Installation.
*ALTERNATIVE / REPLACEMENT* LIGHTING - WL.2 Wall-Mounted (Bathroom) Vanity Light | Jones 2 Light LED Wall Sconce in Black https://www.beaconlighting.com.au/jones-2-light-led-wall-sconce-in-black |  | 13 / Total | Beacon Lighting www.beaconlighting.com.au | 262.72 | 3415.36 | 0 | 341.536 | 3756.896 | 13 | 300 | 3900 | N/A | N/A | N/A | N/A | 05.12.23 | # 1305 | N/A | N/A | PAID | 1 - 2 weeks | 20.12.23 | 20.12.23 |  | DELIVERED | Online Purchase (BL Order Number: 110783345) - Processed using D.W Credit Card 05.12.23. 1 light per bed headboard shelf / draw. Budget Allocation: Supply and Installation.
LIGHTING - WL.3 Wall-Mounted (External) Light | Astro Mast Light Wall Lamp https://lamptwist.com/products/astro-mast-light-wall-lamp?variant=44320811909366#shopify-section-product-specs |  | 10 / Total | LAMPTWIST www.lamptwist.com | 126 | 1260 | 250 | 126 | 1386 | 10 | 340 | 3400 | N/A | N/A | N/A | N/A | 03.11.23 | # 1174 | N/A | N/A | PAID | 2 - 3 Weeks | 27.11.23 | 01.12.23 | 29.11.23 (CORE 4 OFFICE) | DELIVERED | Online Purchase - (LT Order Number: 31205) - Processed using D.W Credit Card 03.11.23.* 4 lights per corridor / 2 lights for 'Family Room' entrance. Budget Allocation: Supply and Installation. *Order processed in EURO, currency converted (EURO - AUD) 03.11.23.
SOFT FURNISHING
CURTAINS
CURTAINS - CUR.1 Double Curtains - Sheer and Blockout | Astra & Simplicity Double Curtains - Neutral Linen-Like Sheer Paired with Plain Blockout, 'Cargo' and 'Moonlight'. https://curtainandblindco.com.au/product/astra-and-simplicity-double-curtains/ | https://www.bunnings.com.au/bastion-1-x-50m-orange-barrier-mesh_p0332625 | 17 / Total | Curtain & Blind Co. 1300 301 368 / info@curtainandblindco.com.au | $763.00 - $959.00 | 12148.1818 | 0 | 1214.8182 | 13363 | 13 | 950 | 12350 | 06.11.23 | 07.11.23 | 05.02.24 | # 439 | 08.11.23 | # 1192 | # CBC77671 | 08.11.23 | PAID | 3 - 5 Weeks* | 27.11.23 | 15.12.23 | 29.11.23 (TO SITE) | DELIVERED | Curtain Requirements - Double curtains (Blockout and Sheer): Family Room* 2 (Sliding Doors): 2200mmW x 2585mmH, approximately 200mm L/RHS overhang, centre opening. 2 (Windows): 1410mmW x 2585mmH, approximately 150mm L/RHS overhang, centre opening. 1 (Window): 1260mmW x 2585mmH, approximately 150mm LHS overhand,centre opening. Standard Rooms* 5 (Windows): 1410mmW x 2135mmH, approximately 150mm L/RHS overhang, centre opening. 7 (Windows): 1410mmW x 2490mmH, approximately 150mm L/RHS overhang, centre opening. Budget Allocation: Supply and Installation. Family Room curtain quantity under-estimated (2 instead of 5). Lead-Time: 3- 5 Weeks Production, 1 Week Freight. *Blockout Pleat Style: Triple-Pinch. Sheer Pleat Style: S-fold. Double track (white, face fix), hand wand draw type, centre opening. *40mm reduction to above-noted heights to account for variation/s on-site - Confirmed D.W 06.11.23. *URGENT PAYMENT* required to commence production - Invoice paid 08.11.23.
BATHROOM FIXTURES AND FITTINGS
SHOWER SCREEN
SHOWER SCREEN - SCR.1 Accommodation Room Shower Screen | Mondella 10 x 2000 x 875mm Glass Frameless Shower Panel (I/N: 489074). https://www.bunnings.com.au/mondella-10-x-2000-x-875mm-glass-frameless-shower-panel_p4890734 |  | 13 / Total | Bunnings Warehouse builderserviceqld@bunnings.com.au | 171.72 | 2232.36 | N/A | 223.236 | 2455.596 | 13 | 300 | 3900 | 27.10.23 | 27.10.23 | 24.11.23 | # 317118416 | 31.10.23 | # 1141 |  | ON ACCOUNT | PAID | 1 - 2 Weeks | 27.10.23 | 15.12.23 | 28.11.23 (TO SITE) | DELIVERED | Shower Screen Requirements: 800mm x 2000mm. *Order to be collected from suppliers Stafford warehouse by CORE 4 tradesmen - Ready for collection 23.11.23.
SHOWER HEAD
SHOWER HEAD Accommodation Room Shower Head | Revolution WELS 3 Star 8L/min Chrome Self Cleaning Rain Shower and Arm (I/N: 0108912). https://www.bunnings.com.au/revolution-wels-3-star-8l-min-chrome-self-cleaning-rain-shower-and-arm_p0108912 |  | 13 / Total | Bunnings Warehouse builderserviceqld@bunnings.com.au | 159.51 | 2073.63 | N/A | 207.363 | 2280.993 | 13 | 200 | 2600 | 27.10.23 | 27.10.23 | 24.11.23 | # 317118416 | 31.10.23 | # 1141 |  | ON ACCOUNT | PAID | 1 - 4 Weeks* | 27.10.23 | 15.12.23 | 28.11.23 (TO SITE) | DELIVERED | *Shower Head is currently out of stock with the supplier until the end of November, supply lead-time is 10 - 14 working days following stock replenishment - Supplier based in Western Australia. *Order to be collected from suppliers Stafford warehouse by CORE 4 tradesmen - Ready for collection 23.11.23.
BASIN
BATHROOM BASIN Accommodation Room Bathroom Basin | Mondella White Gloss Concerto Wall Hung or Above Counter Basin (I/N: 0351131). https://www.bunnings.com.au/mondella-white-gloss-concerto-wall-hung-or-above-counter-basin_p0351131 |  | 13 / Total | Bunnings Warehouse builderserviceqld@bunnings.com.au | 115.82 | 1505.66 | N/A | 150.566 | 1656.226 | 13 | 437.6923 | 5690 | 07.12.23 | 07.12.23 | 07.01.24 | # 317508188 | 08.12.23 | # 1318 |  | ON ACCOUNT | PAID | 1 Week | 20.12.23 | 15.12.23 |  | DELIVERED | *Product specifications to be checked against existing vanity and tapware (to be retained) on-site - Basin specification / suitability confirmed by Site Supervisor (M.P) 08.12.23 (verbally, telephone).
TOWEL RAIL
BATHROOM TOWEL RAIL Accommodation Room Bathroom Towel Rail | Mondella 900mm Chrome Prelude Double Towel Rail (I/N:012136). https://www.bunnings.com.au/mondella-900mm-chrome-prelude-double-towel-rail_p0125136 |  | 5 / Total | Bunnings Warehouse builderserviceqld@bunnings.com.au | 34.51 | 172.55 | N/A | 17.255 | 189.805 | 5 | 144 | 720 | 08.12.23 | 08.12.23 | 08.01.24 | # 317508188 | 08.12.23 | # 1318 |  | ON ACCOUNT | PAID | 1 Week | 20.12.23 | 15.12.23 |  | DELIVERED
MIRROR
MIRROR Accommodation Room Mirrors | Frameless Mirror, 1480mm x 1000mm |  | 13 / Total | CORE Glass and Aluminium dave@coreglassandaluminium.com.au / 0447 58 466 | 447.3077 | 5815 | N/A | 581.5 | 6396.5 | 13 | 400 | 5200 | 29.11.23 | 29.11.23 | 27.12.23 | # 23DL11020 | 30.11.23 | # 1289 |  |  | PAID | 1 Week | 20.12.23 | 15.12.23 |  | DELIVERED | Quotation: Supply and Installation. Lead-Times: 5-Days from site measure - Works schedule (pre-Christmas) filling up, lead-times current at time of quoting, subject to change.
MIRROR
MIRROR Accommodation Room Mirrors | Frameless Mirror, 1480mm x 1000mm |  | 13 / Total | True Blue Glass office@trueblueglass.com.au / (07) 3209 8774 | 654.5455 | 8509.0909 | N/A | 850.9091 | 9360 | 13 | 400 | 5200 | 29.11.23 | 29.11.23 | 27.12.23 | # 118666 | [5 empty] | 1 Week | 18.12.23 |  |  |  | Quotation: Supply and Installation. Lead-Times: 5-Days from site measure - Works schedule (pre-Christmas) filling up, lead-times current at time of quoting, subject to change.
MISCELLANEOUS FIXTURES, FITTINGS AND EQUIPMENT
ACCOMODATION ROOM NUMBERS
ROOM NUMBERS - RN.1 Accommodation Room Door Numbers | Sandleford 50mm Stainless Steel House Number/s https://www.bunnings.com.au/sandleford-50mm-stainless-steel-house-number-0_p3290934 |  | 17 / Total | Bunnings Warehouse builderserviceqld@bunnings.com.au | 4.42 | 75.14 | N/A | 7.514 | 82.654 |  |  |  | 27.10.23 | 27.10.23 | [12 empty] | Accommodation Room Number Requirements: 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13. *Price: Supply Only.
ROOM NUMBERS - RN.1 Accommodation Room Door Numbers | Motel Room Numbers - 10mm Acrylic Plaque, 2-Pack Paint (to match brand colour), White Vinyl Lettering. |  | 13 / Total | Roy Zhu 0430 075 198 / roy@rzprojects.com.au | 88.384 | 1149 | N/A | 114.9 | 1263.9 |  |  |  | 27.10.23 | 30.10.23 | [12 empty] | Accommodation Room Number Requirements: 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13. *Price: Supply and Installation.
PAINT SPECIFICATIONS - INTERNAL
INTERNAL PAINT - P.1 Accommodation Room Wall Paint | Dulux 'Moorland', S20A3 https://www.dulux.com.au/colour/greens/moorland/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
INTERNAL PAINT - P.2 Accommodation Room Bathroom Wall Paint | Dulux 'Narrow Neck', NZ9E7 https://www.dulux.com.au/specifier/colour/colours-of-nz-nz9/narrow-neck/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
INTERNAL PAINT - P.3 Accommodation Room Skirting, Door and Window Frames | Dulux 'Armada', S26A7 https://www.dulux.com.au/colour/greens/armada/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
INTERNAL PAINT - P.4 Accommodation Room Ceiling Paint | Dulux 'Vivid White', SW1G1 https://www.dulux.com.au/colour/whites-and-neutrals/vivid-white/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
PAINT SPECIFICATIONS - EXTERNAL
EXTERNAL PAINT - P.2 External Brickwork, Two-Tone Wall Paint Lower. | Dulux 'Narrow Neck', NZ9E7 https://www.dulux.com.au/specifier/colour/colours-of-nz-nz9/narrow-neck/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
EXTERNAL PAINT - P.3 External Brickwork, Two-Tone Wall Paint Upper | Dulux 'Moorland', S20A3 https://www.dulux.com.au/colour/greens/moorland/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
EXTERNAL PAINT - P.4 External Door Frame / Door Paint | Dulux 'Armada', S26A7 https://www.dulux.com.au/colour/greens/armada/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
EXTERNAL PAINT - P.5 Eaves (Accommodation Block and Carport) | Dulux 'Vivid White', SW1G1 https://www.dulux.com.au/colour/whites-and-neutrals/vivid-white/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.
EXTERNAL PAINT - P.6 Fascia and Trim (Accommodation Block and Carport) | Dulux 'Armada', S26A7 https://www.dulux.com.au/colour/greens/armada/ | [18 empty] | ON ACCOUNT | IN PROGRESS |  |  |  |  | DELIVERED | Purchased / collected by CORE 4 tradesmen / labourers as / when required.

## SUB-CONTRACTORS
[22 empty] | PENDING | NOT RECEIVED
| PROJECT SUB-CONTRACTOR PROCUREMENT SPREADSHEET |  | PROJECT: | # 45376: EVERTON PARK HOTEL ACCOMODATION REFURBISHMENT | [17 empty] | SCHEDULED | IN PROGRESS
|  |  | SITE LOCATION: | 101 FLOCKTON STREET, EVERTON PARK QLD 4053 | [17 empty] | ACTIVE | PARTIALLY PAID
|  |  | PROJECT COMMENCEMENT: | 27.11.23 - 22.12.23 | [17 empty] | ON-HOLD | PAID
|  |  | STAGED WORKS: | N/A | [17 empty] | COMPLETED | OVERDUE
TERMINATED
CATEGORY | SUB-CONTRACTOR | QTY/UOM | CONTACT DETAILS | TOTAL COST (incl GST) | BUDGET ALLOCATION |  |  | QUOTE DETAILS |  |  |  | PURCHASE DETAILS |  | PAYMENT DETAILS |  |  | ATTENDANCE DETAILS |  |  |  | NOTES
[5 empty] | EST. QTY | EST. UNIT | EST. TOTAL | DATE SENT | DATE RECEIVED | VALID UNTIL | QUOTE # | DATE SENT | PO # | INV # | DATE RECEIVED | STATUS | REQUIRED | EXPECTED | ACTUAL | STATUS
ELECTRICAL AND PLUMBING
ELECTRICAL
ELECTRICAL Internal and External Works | KTM Solutions | N/A | KTM Solutions (07) 3813 0067 / service@ktmsolutions.com.au | 23202 | N/A | N/A | 37650 | 03.11.23 | 06.11.23 | 04.12.23 | # 134563 | 15.11.23 | # 1220 |  |  | NOT RECEIVED | 27.11.23 | 27.11.23 |  | SCHEDULED | Scope of Works - Remove existing pendant lights, 15 total - 1 per 'Standard Room', 3 in the 'Family Room'. - Supply and install LED Downlights to accommodation rooms, 58 downlights total - 4 per 'Standard Room', 10 in the 'Family Room'. - Install wall lights to bed headboards, 36 lights total - 1 per shelf (CORE 4 to manufacture and install new laminate headboards). - Supply and install Double GPOs, include charging ports, Black, to bed headboards 36 GPOs total - 1 per shelf (CORE 4 to manufacture and install new laminate headboards). - Remove existing vanity wall lights to bathrooms. - Install vanity wall lights to bathrooms, 13 lights total - 1 per mirror. - Supply and install LED downlights (on timer switch) above accommodation room doors, 14 lights total. - Supply and install LED weatherproof batten lights to carport, 13 lights total. - Supply and install LED Downlights (on sensor) to corridors, 12 lights total - 6 per corridor. - Terminate / remove ALL existing (external) wall lights. - Install new wall-mounted lights to corridor and 'Family Room' entrance, 10 lights total - 4 per corridor, 2 'FR'. Budget Allocation: Subcontractor costs, and cost of CORE 4 supplied electrical fixtures and fittings.* *CORE 4 Supplied Fixtures and Fittings (Total): $6461.45
ELECTRICAL Internal and External Works | All Kind Air & Electrical | N/A | All Kind Air and Electrical (07) 3053 3405 / works@akgp.com.au | 32545.37 | N/A | N/A | 37650 | 03.11.23 | 15.11.23 | 13.12.23 | # 15884 | [9 empty] | Scope of Works - Remove existing pendant lights, 15 total - 1 per 'Standard Room', 3 in the 'Family Room'. - Supply and install LED Downlights to accommodation rooms, 58 downlights total - 4 per 'Standard Room', 10 in the 'Family Room'. - Install wall lights to bed headboards, 36 lights total - 1 per shelf (CORE 4 to manufacture and install new laminate headboards). - Supply and install Double GPOs, include charging ports, Black, to bed headboards 36 GPOs total - 1 per shelf (CORE 4 to manufacture and install new laminate headboards). - Remove existing vanity wall lights to bathrooms. - Install vanity wall lights to bathrooms, 13 lights total - 1 per mirror. - Supply and install LED downlights (on timer switch) above accommodation room doors, 14 lights total. - Supply and install LED weatherproof batten lights to carport, 13 lights total. - Supply and install LED Downlights (on sensor) to corridors, 12 lights total - 6 per corridor. - Terminate / remove ALL existing (external) wall lights. - Install new wall-mounted lights to corridor and 'Family Room' entrance, 10 lights total - 4 per corridor, 2 'FR'. Budget Allocation: Subcontractor costs, and cost of CORE 4 supplied electrical fixtures and fittings.* *CORE 4 Supplied Fixtures and Fittings (Total): $6461.45 Site Visit: 10.11.23, 10:00am
PLUMBING
Plumbing Internal Works | AK Gas & Plumbing | N/A | AK Gas & Plumbing (07) 3053 3405 / works@akgp.com.au |  | N/A | N/A | 5450 | 29.11.23 | [7 empty] | NOT RECEIVED |  |  |  | PENDING | Scope of Works - Isolation, disconnection, and removal of existing bathroom basins (13, Total). Tapware to be retained for re-installation. - Isolation and installation of new bathroom basins (13, Total). Includes re-installation of existing tapware.

## HIRE SCHEDULE
[22 empty] | PENDING | NOT RECEIVED
| PROJECT HIRE SCHEDULE SPREADSHEET | PROJECT: | # 44861 INALA HOTEL VENUE REFURBISHMENT | [18 empty] | ORDERED | IN PROGRESS
|  | SITE LOCATION: | 189 FREEMAN ROAD, INALA QLD 4077 | [18 empty] | IN TRANSIT | PARTIALLY PAID
|  | PROJECT COMMENCEMENT: | 2023-10-08 | [18 empty] | DELIVERED | PAID
|  | STAGED WORKS: | 1. PRELIMINARIES, 2. DECK CONSTRUCTION / PATIO REMEDIATION / KITCHEN CONTAINER, 3. SPORTS BAR / COOL ROOM CONDENSERS, 4. GAMING ROOM, 5. FINALISING | [19 empty] | OVERDUE
CATEGORY | ITEM / DESCRIPTION | QTY/UOM | SUPPLIER DETAILS | TOTAL COST (incl GST) | BUDGET ALLOCATION |  |  | QUOTE DETAILS |  |  |  | PURCHASE DETAILS |  | PAYMENT DETAILS |  |  | DELIVERY/HIRE DETAILS |  |  |  | NOTES
[5 empty] | EST. QTY | EST. UNIT | EST. TOTAL | DATE SENT | DATE RECEIVED | VALID UNTIL | QUOTE # | DATE SENT | PO # | INV # | DATE RECEIVED | STATUS | LEAD TIME | START | END | STATUS
TEMP FENCING FIRE
SITE SETUP Temp Fencing Hire | Tempoary Fencing Hire |  | Kennards Hire Bowen Hills (07) 3648 9300 | [12 empty] | NOT RECEIVED |  |  |  | ORDERED | 6 x 2400mm x 1800mm mesh fence panels, feet and clips - 27.11.23.
SKIP BIN HIRE
SITE SETUP Skip Bin Hire | Skip Bin Hire |  | Speedy Bins www.speedybins.com.au / 1300 550 442 | [12 empty] | NOT RECEIVED |  |  |  | ORDERED | Skip Bin Delivery: 2 x 8.0m3 Skip Bins - 24.11.23. Skip Bin Changover 1: 1 x 8.0m3 Skip Bin collected, 1 x 6.0m3 Skip Bin delivered - 28.11.23. Skip Bin Collection: 1 x 8.0m3 Skip Bin collected 29.11.23.
EQUIPMENT HIRE
EXTERNAL PAINTING WORKS Trailer Mounted Jnuckle Boom | Trailer Mounted Knuckle Boom 34' Nifty https://brisbanescissorlifthire.com.au/product/trailer-mounted-knuckle-boom-34%E2%80%B2-nifty/ | 1 / Unit | Brisbane Scissor Lift Hire (07) 3869 2322 | [12 empty] | NOT RECEIVED |  |  |  | PENDING