PRACTICAL ASSESSMENT

Residential

Wardrobes – 17 Burke Street, Coorparoo

Hi Matt, sending through an email as we have changed our mind about bedroom 2 and would now like a built-in robe to be installed exactly the same as the one in bedroom 1 will be. Please let me know if any issues.

Thanks

Jim Jones

Re: Wardrobes – 17 Burke Street, Coorparoo

Hi Jim, I have been in contact with the cabinet maker and that is absolutely something we can do for you. Because you want it exactly like the one in bedroom 1 the cost will also be exactly the same as the first wardrobe. That is an extra $2,100  and will push the supply back by 1 week. It will mean a change to the schedule but I’ve shuffled it so that it will not impact our final completion date in any way. If that suits you please confirm that you are happy to pay the extra amount and we will get it organised for you.

Thanks

Matt Cumiskey

Construction Schedule – 17 Burke Street, Coorparoo

| TASK | DATE STARTED | DATE COMPLETED | LABOUR | NOTES |
| --- | --- | --- | --- | --- |
| Excavating site | 8/6/2020 | 10/6/2020 | Subcontracted to Dans Digging |  |
| Pouring ground slab | 17/6/2020 | 17/6/2020 | Subcontracted to Cams Concrete | Pour was pushed back 1 day due to rain |
| Erection of wall frames | 20/7/2020 | 24/7/2020 | Done by myself with another carpenter |  |
| Installation of roof trusses | 27/7/2020 | 30/7/2020 | Done by myself with another carpenter |  |
| External cladding | 3/8/2020 | 7/8/2020 | Myself and 2 carpenters |  |
| Roof tiling | 10/8/2020 | 14/8/2020 | Subcontracted to Tim’s Tiles |  |
| Gyprock | 17/8/2020 | 21/8/2020 | Done by myself and another carpenter |  |
| Painting | 24/8/2020 | 28/8/2020 | Subcontracted to Pete’s Painting | Deposit due 1 week prior. Pete to supply paint |
| Cabinetry install | 1/9/2020 4/9/2020 | 1/9/2020 4/9/2020 | ABC Cabinetry | Change of order, install date. |

Commercial

Change to purchase order 36594 – Re Charlotte Street

Hey John,

I have just placed my second order of timber for Charlotte Street but the supplier hasn’t been able to supply the timbers at the original order price so the new price is $2.99/m. This will change the purchase order you raised (number 36594). Can you please amend and also update the material schedule and the Phase 2 budget?

This new price should apply to any future orders we have provisioned for as well so can you please update that in the projected costs budget and material schedules?

Thanks,

Matt