CPCCBC4005A

Produce labour and material schedules for ordering

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4005A Produce labour and material schedules for ordering cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Danielle Henderson |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Danielle Henderson |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 30 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Lighting wholesaler | Electrician |  |
|  | Landscaping supplier | Builder |  |
|  | Bathroom fixtures wholesaler | Tiler |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | Because employees are required to follow the builders request, or risk losing their employment, it is easy to know that they will carry out the work as directed. As a contractor is not employed and may have other projects to support them financially, they are able to decide when and how they complete works. An employee would be available as per project programming and would be more adaptable to a chance, provided they are only employed on the one project by the builder. Contractors can have multiple projects committed and may not be able to meet changes should they be unreasonable or sudden. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Your local council will provide approval and timeframes for these approvals, which will influence the commencement date, certain stages before construction can commence and relevant stages for sign off and certification scheduling. Your selected power authority will also have approvals and timeframes applicable for connections, which should be arranged through the approved electrician on the project to ensure their works are complete well before “power on” dates. |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | Certain colours may be under special order and require longer lead times. It is important to nominate these colours before producing a schedule so that dates can be realistic based on the colour selection and product availability/delivery. It can also help having this detailed within the schedule document so there is less risk when it comes time to that stage of the project where the relevant material/paint/etc is being sourced. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | Brisbane City Council allows building works that create an audible noise between the hours of 6.30am – 6.30pm Monday to Saturday. No works are to be carried out on a Sunday or a public holiday. If a public holiday falls on a Saturday, works can be carried out in the usual times above. Taking this into account for your schedule will affect many trades, and if exemptions are sought, this again will affect timeframes for council approval (especially if information is not accurate or submitted in full). The council has specific criteria to be met to grant the exemption. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Fire Engineering Report | This details the specifications for fire rating installations and will affect service trades, including the passive fire rating contractors, that will need to install the appropriate measures to meet the report findings. This will also provide the standard to which the Form 16 will be reviewed against and will affect the labour schedule when organising all works to meet the final fire department inspection. |  |
|  | Fixtures, Fittings & Equipment (FFE) Schedule | This specifies all installations to the construction, including doors, door handles, shower roses, joinery, whitegoods, specialist equipment, lighting and decorative materials. It is paramount to review and contact the supplier/manufacturer of each item as these timeframes will affect the materials delivery to site, which could affect the labour requirements of the schedule, in order to meet the completion date. |  |
|  | Structural drawing | This will show details to populate all required materials for the structural contractors and will show how the materials are required to be installed to develop the labour requirements. This can also plan for dates for local council attendances for appropriate sign off. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | Ensure that the variation is submitted by the client in writing before commencing works, making sure that the client and the subcontractors (if necessary) agree to the work. Any changes to the cost, including labour and materials increasing or decreasing should be dated and signed by all parties to the contract. The builder will need to make any adjustments to the schedule, notify the major suppliers of the changes and make the necessary changes to the call forward sheet. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Changes to wall colour schemes with new choice of special-order paint | This would affect the supply timeframe and in turn the painter’s commencement date, pushing back all trades to start or work in with the painters. |  |
|  | Change of a vanity selection | This could affect multiple trades in several ways. If the vanity is a different size, joinery would be affected. If pipe connections differ, plumbers rough in would need relocation or resizing. If the vanity is special order, it could affect fit off for both of these trades and in turn all other following trades. |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Additional materials and labour to accommodate room size change, after the framing stage | This would affect the builders labour schedules, and require return visits from multiple subcontractors, while creating additional sourcing of materials which would place delays on the next stage of works for this area. As subcontractors would likely schedule their works in successive days, this may create a labour delay for a whole trade if they need to wait for one area before their works commence to the construction. |  |
|  | Additional materials due to the client wanting more coats of paint after viewing internal and external walls | This would need to be ordered and painters arranged to return. If finishing trades had been in (plumbers, electricians, carpet layers & tilers) there is a risk that their installations could be damaged by the painters, adding extra materials and labour to complete. This would also give the builder an acceptable reason for an Extension of Time so that they were not penalised for delayed practical completion. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | An overlay drawing can be sketched by the builder, engineer, architect, or draftsman and shows further details to an existing plan to clarify a building process through visual communication or provide advice about changes to an engineering redesign. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | The work is to be listed to include all task details, the timelines to complete these and the rate agreed for the works. |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | Order date & delivery date Purchase Order number Supplier Details Supplier Contact information Project Manager details Delivery address Product description Terms and conditions Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is developed for materials required to complete the works and details the dates required for materials to be ordered and to schedule delivery dates to site in line with the labour schedule. This will also reference all purchase order numbers for easy reference with suppliers. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Stamped permit plans and service location plans. |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Concrete | 2 days | Dates may change throughout the build and would depend on clear weather for each “pour”. Concrete would be require in the initial stages, as well as the driveway pour. | Once the excavation team are finalising the site clear, the concrete supplier could be contacted. | Clear access to the area for concrete to be poured must be available, labour booked for day of delivery and to be on site after pour to ensure no cracks. |  |
|  | Carpet | 3 weeks | 13/08/2020 | 16/07/2020 | One-week allowance for final site measure to be carried out to incorporate any changes. Carpet should be one of the final trades as return to these areas may cause damage/defects. |  |
|  | Electrical fixtures & fittings | Varies | In conjunction with electrical labour and other trades | A full itemised quote would be locked in with the nominated electrician, or the chosen wholesaler at commencement of the job. This would be “draw down” through the building stage. | As there may not be storage on site, and the builder can only submit certain claim values per stage, consideration surrounding what areas are ready and progressed for particular materials needs to be monitored. |  |
|  | Garage door | 4 weeks | 30/07/2020 | 29/06/2020 | Ensure the colour (if not explicitly specified in contract stage) is signed by both parties prior to confirmation with the manufacturer. Door will be fitted upon delivery so area must be complete and ready for installation. Shop drawings would be locked in based on building plans, therefore this must be done to the plans. |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | The builder would determine full site measurements based on construction plans and have this locked in for the manufacturer to commence the project. Delivery dates would be scheduled throughout so that cladding is not stored on site while installation occurs. | Colour selection to match the agreed finishes schedule, or any changes/acceptance must be in writing from the client. Inspection of the building sarking prior to delivery. Appropriate unloading methods would need to be arranged for the delivery and clear access/area to be designated. Fixings for the cladding would need to be sourced and readily available for installation. |  |
|  | Wall frame | The builder will confirm measurements and quantities for wall framing to be cut off site and delivered for assembly on site. All items need to be ordered to plan to ensure structural sign off is achieved, including bracing and accessories. | Ensure services (electrical, plumbing, mechanical) are completed in conjunction with framing. |  |
|  | Windows | Plans would be sent to the supplier to review measurements and finishes to ensure the original quote is valid. Shop drawings would be produced for the builder to cross check and provide any changes to the measurements prior to manufacture. Once frames are ready, the supplier may conduct an on site measure if included within their price. All revised shop drawings would need to be signed/approved by the builder. | Measurements must be checked on site before manufacture starts, therefore if the frames are delayed, the window supply may not meet the original date. |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | Refer attachment – “Q30 – Variation Request.pdf” |  |
| --- | --- | --- |

CPCCBC4005A

Produce labour and material schedules for ordering

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4005A

Produce labour and material schedules for ordering

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to produce schedules of resource requirements so that orders can be placed for materials and labour for projects, and costs can be recorded and tracked as they are incurred. - Occasion 1: Residential project - Occasion 2: Commercial project The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A copy of a material/labour schedule or supplier list for a project - A copy of a purchase order for purchasing materials or other resources - A cost report - Site condition reports or dilapidation reports - Contract documents - Call forward sheets - Variations The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Contract documentation (including plans and specifications), computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Consider all contract conditions in the schedules, including: - All contractual requirements - Local government and regulatory bodies’ conditions of approval - Colour selections - Variations to contracts, raised by the client or builder |  |  |  |
| - Produce material and labour schedules, including: - Details of nominated suppliers and contractors in work schedules - Application of contract rates |  |  |  |
| - Produce relevant overlay drawings. |  |  |  |
| - Include contract details and instructions on orders. |  |  |  |
| - Prepare site files, including: - All necessary site documents, including plans and specifications - Preparation of call forward sheets, detailing all orders |  |  |  |
| - Analyse project costs against estimates during construction. |  |  |  |
| - Analyse approved variation costs. |  |  |  |
| - Provide a final project cost analysis. |  |  |  |
| - Maintain data files of standard costs, including: - Approved variation cost increases - Changes to standard plans, specifications, and cost files |  |  |  |
| - Effectively communicate using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments