Electronic Call Forward Sheet

| Site address | Lavarack Barracks, Townsville | Project name | EST09310 Lavarack Barracks New Locker Storage Building for 1st Military Police Battalion |
| --- | --- | --- | --- |
| Client | Augility | Surveyor | BMW Surveying Services |

|  |  | Dates |  |  | Provider details |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Task | Ref # | Notice date | Date required | Supplier | Contractor | Contact info | Instructions |
|  | Stage |  |  |  |  |  |  |  |
|  | Bulk Earthworks – Site Cut | 1 | 03/05/2024 | 23/05/2024 | Civil Contractor | Mites Constructions | Address: 7-9 Truscott St, Garbutt QLD 4814 Phone: (07) 4775 6044 | To commence works. |
|  | Civil Works – Stormwater Drainage | 2 | 09/05/2024 | 29/05/2024 | Civil Contractor Hydraulics Contractor | Mites Constructions Plumbwell | Mites Constructions: Address: 7-9 Truscott St, Garbutt QLD 4814 Phone: (07) 4775 6044 Plumbwell: Address: Hyde Park QLD 4812 Phone: 07 47 242 400 | To commence works. |
|  | Inground Services (Hydraulics) | 3 | 09/05/2024 | 29/05/2024 | Hydraulics Contractor | Plumbwell | Address: Hyde Park QLD 4812 Phone: 07 47 242 400 | To continue with works. |
|  | Foundations – Bored Piers | 4 | 21/05/2024 | 10/06/2024 | Civil Contractor | Mites Constructions | Address: 7-9 Truscott St, Garbutt QLD 4814 Phone: (07) 4775 6044 | To continue on with work required. |
|  | Slab on Ground & Footings | 5 | N/A- completed by us. | 17/06/2024 | Concrete Works – completed by us | A. Gabrielli Constructions | Address: 336 Woolcock Street, Garbutt QLD 4814 Phone: 07 4725 1100 | To complete concrete works. |
|  | Blockwork & Engaged Piers | 6 | 12/06/2024 | 02/07/2024 | Blockwork Contractor | Mascrete | Address: Hermit Park 4812 Phone: 0418 779 497 | To commence works. |
|  | Structural Steel & Roof Framing | 7 | 20/06/2024 | 10/07/2024 | Structural Steel Contractor Roofing Contractor | Norfab VP Roofing & Home improvements | Norfab- Address: 1/61-67 Enterprise St, Bohle QLD 4818 Phone: (07) 4725 7750 VP Roofing: Address: 45 Pilkington St, Garbutt QLD 4814 Phone: 07 4779 1102 | To commence Structural steel and roofing works. |
|  | External Façade & Doors | 8 | 05/07/2024 | 25/07/2024 | Carpentry Contractor | MST Constructions | Address: 137 Crocodile Cres, Mount St John QLD 4818 Phone: 07 4774 8750 | To commence works External façade and doors. |
|  | Hydraulic Rough-in / Fit Off | 9 | 05/07/2024 | 25/07/2024 | Plumbing Contractor | Plumbwell | Address: Hyde Park QLD 4812 Phone: 07 47 242 400 | To complete Hydraulic rough-in / fit off. |
|  | Electrical rough-in / fit off | 10 | 05/07/2024 | 25/07/2024 | Electrical Contractor | Waltlec Industries | Address: 22 Hugh Ryan Dr, Garbutt QLD 4814 Phone: 07 4725 5621 | To commence works for Electrical rough-in / fit off. |
|  | Lockers Installation | 11 | N/A – Completed by us | 20/08/2024 | Locker’s installation- completed by us. | A. Gabrielli Constructions Pty Ltd | Address: 336 Woolcock Street, Garbutt QLD 4814 Phone: 07 4725 1100 | To install Lockers. |
|  | Civil works and Landscaping | 12 | 15/07/2024 | 01/08/2024 | Civil Contractor Landscaping Contractor | Mites Constructions Landscaping and Irrigation Specialists | Mites: Address: 7-9 Truscott St, Garbutt QLD 4814 Phone: (07) 4775 6044 LIS: Adress: 75 Northern Link Ct, Shaw QLD 4818 Phone: 0419 029 739 | To commence Civil and Landscaping works. |