CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Mohamed Elbagoury |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | Click here to enter a date. |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 30 |  | Yes | No |

Assessor Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Wall factory | Builder |  |
|  | Roof tiles | Plummer |  |
|  | Door and window | Electrician |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | A contractor is someone who runs their own business and provides Services to other businesses or individuals. An employee works in and is part of a business. Both employee and contractor are working according to the schedule but contractor decide what work they do, how it is to be carried out and the hours when the work is to be completed while employee is directed by the builder. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Local council and the national construction code |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | Because some colours requests may require a special order to be made. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | City of Charles Sturt Monday to Saturday 7 am to 7 pm no Sunday at all Special permits could be issued on special circumstances Top of Form Any equipment with an internal combustion engine not in group 2. - Electric power tools, chainsaws or circular saws. . - Pneumatic power tools, hammers or other impacting tools or grinding equipment. - Any equipment with an internal combustion engine not in group 2. Are prohibited Monday to Friday before 7 am or after 8 pm. Weekends and public holidays before 9 am or after 8 pm. Bottom of Form |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Material specifications | Include details of the type, strength and size material to be used the material specifications influences the kind Of skilled labour who will do the job, as example for flooring if it will be tiles will require a different skill from if it ceramic tiles, in addition to that the time takes to do the tiles is different from the time needed for the timber (barque) floor. |  |
|  | Product specifications | Include items such as whitegoods, electrical goods, lights and switch types If we took the electricity as an example will find that, if a home owner wants to have chandelier is a complete different requirements from if wants spot lights, this will affect the design and the material needed which will accordingly affect the time needed to do that choice. The quality of a light switch is a common argument if not pre-decided and recorded in the schedule. |  |
|  | Elevations drawing | L Drawings of the building showing what it looks like from north, south, east and west This drawing also helps scheduling the order of materials needed for not overflowing of material and having a storage problems. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | 1. put it in writing and client must agree to before commencement of work 2. only exception for not putting it in writing is if it is not practical to produce a document before work commences (but it then must be done within 24 hours) 3. All subsequent documentation must be completed by the client within 5 business days of when the variation was agreed to |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Style of doors and windows | This variation would have the schedule interrupted as new calculation for new style and whether it needs a new design or no but normally in planning schedule a buffer is calculated and with a good project manager it will not delay the Completion date |  |
|  | Changes to room sizes | Depends on when this variation had occurred, if it is after drawing before commencing the building so all calculations will be revised and then rescheduled, but if it is after the building it is a different problem and more likely to be considered a change of scope not variation . |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Changes to brickwork or external features | It depends on the type of change, however as a general any changes will need recalculating and revising of all schedule from the time and onwards. |  |
|  | Changes to colour schemes using cheaper or more expensive paints | This variation will not have a great impact on the scheduling as the time for painting the expensive colour is as the cheaper one. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | It is a drawing that show further detail on top of any existing plans and specifications. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | • Work • Time period • Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | Order date and delivery date Purchase order number Supplier details Delivery details Supplier contact information Project manager details Product description Terms and conditions Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is a sheet used to track when materials are needed and when they should be ordered. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Architectural & land survey |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Wall frame | 10 days | 1/7/2018 | 1/6/18 | Fork lift to be present |  |
|  | brick veneer | 2 days | 15/7/18 | 1/6/18 | Distribute dropping amounts as planed |  |
|  | Windows | 7 days | 20/7/18 | 1/6/18 | To be stored inside |  |
|  | External cladding | 2 days | 15/7/18 | 1/6/18 | Distribute the drop as planned |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | 2nd step | How it will look like, as pattern colour … etc |  |
|  | Wall frame | 1st step | That it will be hand built wall frame |  |
|  | Windows | 3rd step | What material windows are made off, eg. aluminium or timber |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | # Variation Form Variations Approval Request Form. Project: a small residential project; Variation Summary No.: 001. Principal: Mr Y; PCG No.:; 555444. Contractor: Building SA; Date: 01/6/2018. Project Manager: Mr X. AGREED CONTINGENCY:; $ 50,000 -. VARIATIONS APPROVED TO DATE:; $ 0.0 -. REMAINING CONTINGENCY:; $ 50,000 -. Recommended Variations (For ). Variation No. (VARQT); Site Inst. No. (SI); Variation Title; Variation Description; Variation Estimate; Variation Recommended; PCG Rec. 12345; 630; Excavate; One corner of the project, found the soil below is unsuitable for supporting the foundation; $20,000; $25,000; N/A. TOTALS:; $ 20,000 -; $ 25,000 -. Capital Projects & Service Planning Approval. Project Manager: signature; Signed: signature; Date: 7/6/2018. Director, Capital Projects and Service Planning. Authorised by:; Signed:; Date: 7/6/2018. Reviewed and Recommended in; PCG Number:; PCG Date:. Note: All amounts exclude GST. |  |
| --- | --- | --- |