## Sheet1
LOT 8, Rees court, Palm beach
Area | Activity | Duration | Start date | Finish Date | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18
[5 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Site establishment | Temporary site fencing | 2 days | bar: Week 1 M to Week 1 T
| Site signage | 1 day | bar: Week 1 W
| Temporary electricity | 1 day | bar: Week 1 W
| Temporary water supply | 1 day | bar: Week 1 T
| Temporary toilet | 1 day | bar: Week 1 F
| Temporary site shed/lunch room | 4 days | bar: Week 1 F; Week 2 M to Week 2 W
Basement structure | Site clearence and levelling(cut and fill) | 3 days | bar: Week 2 M to Week 2 W
| Setting out | 1 day | bar: Week 2 T
| Excavation and earth works | 3 days | bar: Week 2 F; Week 3 M to Week 3 T
| Reinforcement, concrete for footings and pads | 5 days | bar: Week 3 M to Week 3 F
Superstructure | Brick work | 3 weeks | bar: Week 4 M to Week 4 F; Week 5 M to Week 5 T; Week 6 M to Week 6 F; Week 7 M to Week 7 W
| Stud frames | 3 weeks | bar: Week 4 T to Week 4 F; Week 5 M to Week 5 W; Week 6 T to Week 6 F; Week 7 M to Week 7 T
| First floor slab | 1.5 weeks | bar: Week 5 M to Week 5 F; Week 6 M to Week 6 T
| Roof framework | 2 weeks | bar: Week 6 T to Week 6 F; Week 7 M to Week 7 F; Week 8 M to Week 8 W
Services rough-in | Plumbing | 2.5 weeks | bar: Week 5 T to Week 5 W; Week 7 M to Week 7 F; Week 8 M to Week 8 F
| Electricity wiring | 2.5 weeks | bar: Week 5 T to Week 5 W; Week 7 M to Week 7 F; Week 8 M to Week 8 F
| Fire service lines | 1.5 weeks | bar: Week 5 T to Week 5 W; Week 8 M to Week 8 F
| Aircondition wiring/lines | 1.5 weeks | bar: Week 5 T to Week 5 W; Week 8 M to Week 8 F
| Data cables | 1.5 weeks | bar: Week 5 T to Week 5 W; Week 8 M to Week 8 F
Finishes | Gyprock and villa boards fixing | 2 weeks | bar: Week 9 M to Week 9 F; Week 10 M to Week 10 F
| Ground Floor slab concreting | 1 week | bar: Week 9 T to Week 9 F; Week 10 M to Week 10 W
| Stairs | 2 weeks | bar: Week 10 T to Week 10 F; Week 11 M to Week 11 F; Week 12 M to Week 12 W
| Colorbond roof sheet | 2 weeks | bar: Week 10 M to Week 10 F; Week 11 M to Week 11 F
| Ceiling boards and painting | 1.5 weeks | bar: Week 11 T to Week 11 F; Week 12 M to Week 12 F
| Plastering brick work | 2 weeks | bar: Week 9 M to Week 9 F; Week 10 M to Week 10 F
| Floor rendering | 3 days | bar: Week 10 T to Week 10 F; Week 11 M
| Waterproofing | 1 day | bar: Week 11 T
| Wall painting | 2.5 weeks | bar: Week 10 T to Week 10 F; Week 11 M to Week 11 F; Week 12 M to Week 12 F
| Floor finishes | 1 week | bar: Week 12 M to Week 12 F
Windows and doors | Door and window frames | 2 weeks | bar: Week 11 M to Week 11 F; Week 12 M to Week 12 F
| Doors and windows | 1.5 weeks | bar: Week 12 T to Week 12 F; Week 13 M to Week 13 F
Services fit-off | Down pipes | 1 week | bar: Week 14 T to Week 14 F; Week 15 M to Week 15 W
| Electrical lighting and sockets and other fixtures | 1.5 weeks | bar: Week 14 M to Week 14 F; Week 15 M to Week 15 W
| Fire alarms and sprinklers | 1 week | bar: Week 14 M to Week 14 F
| Air conditioning machines | 1 week | bar: Week 14 M to Week 14 F
| Bathroom fixtures and fittings | 1.5 weeks | bar: Week 14 M to Week 14 F; Week 15 M to Week 15 W
| Taps and other plumbing fixtures | 1 week | bar: Week 15 M to Week 15 F
| All other fittings and fixtures | 1 week | bar: Week 15 M to Week 15 F
| Door window accessoriries | 1 week | bar: Week 14 M to Week 14 F
Landscaping | Landscaping and finishing drive way | 2 weeks | bar: Week 15 M to Week 15 F; Week 16 M to Week 16 F
Handover | Final inspection | 1 day | bar: Week 16 M
| Repairing defects | 2.5 weeks | bar: Week 16 T to Week 16 F; Week 17 M to Week 17 F; Week 18 M to Week 18 T
| Handover | 1 day | bar: Week 18 F
Critical path