CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | R LYNETTE MALHABOUR |
| --- | --- |
| Participant signature |  |

| Assessor name | BRETT STOWARD |
| --- | --- |
| Assessor signature |  |

| Date | 17/09/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 45 |  | Yes | No |

Assessor Comments

ANSWER TO QUESTION 13 - TRUE

Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Project schedule |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Building and Construction Commission Act 1991 (QLD) | Maximum Penalty is 100 points |  |

Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Excavation | Prepares the site for building by removing vegetation and excavating footings. |  |
|  | Electricians | Arranges for electricity to be connected; places wiring for lighting and power cables; installs power points, wires and electrical systems. |  |
|  | Plumbers | Organises water supply; installs pipes and drains, roof and guttering, taps, hot water, toilets, down pipes; connecting sewers. |  |

Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

Explain the importance of determining subcontractor or plant availability for a job.

| Answer | The success of a project relies on a logically organised project schedule. The correct type of subcontractor to do the specific task and the plant / equipment that is needed is detrimental to the completion of the project. For example, don’t have your subcontractor to be on site if the plant is unavailable or have not yet been hired. |  |
| --- | --- | --- |

Identify two (2) methods you might use to find a supplier for materials.

| Answer | By tender – advertise the need for the material if in case the material is sourced overseas but distributors exist locally. Networking/phone with subcontractors and asking where materials can be sourced. |  |
| --- | --- | --- |

Name two (2) factors that may impact on the availability of materials.

| Answer | Distance - material made overseas. Season – material is only made in certain times of the year. |  |
| --- | --- | --- |

Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | Aust Standard 1680 |  |
| --- | --- | --- |

Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Excavator | Excavating site and clearing vegetation |  |
|  | Cranes | Used to transport/carry heavy or irregular shaped materials that can cause restriction in entry to the site. |  |

Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Safety harness | This is PPE used when working at heights to protect workers from falling. |  |
|  | VMS | Vehicle Message Signs-used to inform the community of new/changed traffic conditions along or close to working sites. |  |

Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Supplier Quotes and Purchase Orders |  |
| --- | --- | --- |

Name five (5) temporary services that need to be organised for a building site.

| Answer | Water Electricity Toilets Fenicng/barricades Waste bin |  |
| --- | --- | --- |

True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Excavation |  |
| --- | --- | --- |

Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Volune 2 Park 2.5 | Volume 1 section D |  |

You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Out of hours permit. Approval will depend on the state and council the work falls under. |  |
| --- | --- | --- |

In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Electricity supply permit | AGL |  |
|  | Waste disposal permit | Local Council |  |

True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What document should be developed when purchasing supplies or construction materials?

| Answer | Purchase order |  |
| --- | --- | --- |

True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Who should be contacted if items are missing from a delivery?

| Answer | Supplier |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | Work Health & Safety Act 2011 (QLD) Section 17-18 | This ACT places duties on various individuals and parties within the workplace. The section indicates that risks should be identified and eliminated so far as reasonably practicable. |  |

Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | Work and Safety Act 2011 |  |
| --- | --- | --- |

What document should be followed when disposing of hazardous materials?

| Answer | Safety data sheets (SDS) |  |
| --- | --- | --- |

An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10 |  |
| --- | --- | --- |

True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | This can save a great deal of time as it could be difficult to ensure their return for the next stage of the project. Cost effective, as training will not be required. Eg. If constructing 3 residences, a concreter or a bricklayer can start to lay the slab or brickwork of residence 1 then 2 then 3. |  |
| --- | --- | --- |

Provide one (1) example to explain why construction operations must be sequenced.

| Answer | Construction operation must be sequenced for a successful construction and is your obligation under WHS Act, Regulations and Codes of Practice under common law. In building a residential home for example, you do not start pouring your slab before steps are taken in approving your plans. The plans must be approved prior to commencing build otherwise you face penalty and fines all the more a build restriction. |  |
| --- | --- | --- |

Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| - Task ID | - Task | - Preceding event | - Nodes |
| --- | --- | --- | --- |
| - A | - Make enquiries and order all materials required | - Start | - 1 |
| - B | - Wait for bricks, sand and cement to arrive | - A | - 2 |
| - C | - Clear vegetation from the site | - A | - 2 |
| - D | - Order concrete to be delivered | - A | - 2 |
| - E | - Dig the trench | - C | - 4 |
| - F | - Pour the footings | - E | - 5 |
| - G | - Footings curing time | - F | - 6 |
| - H | - Load the bricks on the site | - B | - 3 |
| - I | - Mix the mortar and lay the bricks | - H | - 7 |
| - J | - Clean rubbish from the area | - I | - 8 |
|  | - Finish | - J | - 9 |

G

FF Construction operation must be sequenced for a successful construction and is your obligation under WHS Act, Regulations and Codes of Practice under common law.

In building a residential home for example, you do not start pouring your slab before steps are taken in approving your plans. The plans must be approFFFFFFFFfffffFfffFed prior to commencing build otherwise you face penalty and fines all the more a build restriction.

H

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | Microsoft excel, Microsoft project |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

Describe the critical path.

| Answer | The ‘critical path’ is defined as the shortest completion time possible to complete a job. Sets out the build and its stages. Details and records build timelines. Shows when subcontractors are due on site and how long. Structures the supply chain of materials. Allows for delays and other supply chain problems. |  |
| --- | --- | --- |

True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Deferred supply of materials. Inclement weather. Defferred supply of labour. |  |
| --- | --- | --- |

Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

Why should you take photographs of site boundaries with neighbouring properties?

| Answer | This way, all parties are made aware of the site status before work commences and data is accurate, and can easily identify if any damage has occurred through the construction process to avoid disputes later on. |  |
| --- | --- | --- |

When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

When might a neighbouring property owner be required to refer to a condition report?

| Answer | If work is to affect neighbouring properties |  |
| --- | --- | --- |