## Sheet1
ERUB FISHERIES SHED UPGRADE |  |  | Working Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65
Task | Duration | Start | Finish
Project awarded
Order Materials to site- allow 30 days for materials to arrive on Darnley from date of order | 30 days
Licenced electricians to site to inspect and decommision all required elctrical and refrigeration areas to allow for demolition and construction | 2 | bar: 1 to 2
Mobilise Site Supervisor from Cairns to Darnley | 1 | bar: 2
Clear Storeroom of furniture and stock | 1 | bar: 3
Demolition of existing structures | 6 | bar: 4 to 9
Install new columns and roof structure | 6 | bar: 10 to 15
Construct new storage area | 8 | bar: 16 to 23
Licenced electricians back to site to carry out electrical and mechanical repairs/installation | 2 | bar: 22 to 23
Paint store room | 2 | bar: 24 to 25
Pest Management to site for boundry termite treatment | 1 | bar: 25
Clean and up and disposal of all waste materials to approved dump site or stored for barge pick up | 1 | bar: 26; 53 to 54
This program allows for weather delays.
* Schedule may change depending on suppliers/ freight delivery to Darnley Island and/or weather*